## Sheet1
trs_id | transaction_source | project_no | project_name | project_zone | task_no | task_name | top_task_no | top_task_name | po_no | gl_date | expenditure_type | project_location | project_floor | project_area | expenditure_category | expend_org | amount | line_no | line_desc | inv_no | unit | qty | ipc_no | supplier_no | supplier_name | supplier_site | comment | inventory_item | owner | distributions_status | distributions_date | distributions_details
2507533 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-11-24 | Insurance |  |  |  | Taxes & Insurance | Alrowad Construction_OU | 51000 | 1 | والدروف كايرو جى اى جى و/382 | 382 | Currency | 51000 | 9928563 | 6025 | جى.اى.جى للتأمين - مصر | rowad | والدروف كايرو جى اى جى و/382 |  | Finacial | Received | 2021-11-24 | Accounted transaction received
2536136 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-11-29 | Other |  |  |  | Other | Alrowad Construction_OU | 4488.68 | 1 | التجارية معادى بلوتنج سنتر ف/59510 28/11/2021 | 59510 | Currency | 4488.68 | 10042415 | 8466 | معادى بولتنج سنتر | rowad | التجارية معادى بلوتنج سنتر ف/59510 28/11/2021 |  | Finacial | Received | 2021-11-29 | Accounted transaction received
2536177 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2021-11-29 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 4931.05 | 1 | تسوية ك-1199-بوفية | ST-1199 | Currency | 4931.05 | 10042415 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسوية ك-1199-بوفية |  | Finacial | Received | 2021-11-29 | Accounted transaction received
2536188 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-11-29 | Transportation |  |  |  | Indirect | Alrowad Construction_OU | 222 | 1 | تسوية ك-1185/1190/1192/1193/1194/1195/1196-متنوع | ST-1185/1190/1192/1193/1194/1195/1196 | Currency | 222 | 10042415 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسوية ك-1185/1190/1192/1193/1194/1195/1196-متنوع |  | Finacial | Received | 2021-11-29 | Accounted transaction received
2564657 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 315 | 1 | خرامة حجم كبير |  | Each | 1 | 45895319 |  |  |  | خرامة حجم كبير | 910010000148 | Administration | Received | 2021-12-01 | Accounted transaction received
2564658 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 124.5 | 1 | دباسة متوسطة |  | Each | 3 | 45895320 |  |  |  | دباسة متوسطة | 910010000174 | Administration | Received | 2021-12-01 | Accounted transaction received
2564659 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 187.5 | 1 | علبة دبابيس دباسة 23/13 |  | Each | 10 | 45895321 |  |  |  | علبة دبابيس دباسة 23/13 | 910010000176 | Administration | Received | 2021-12-01 | Accounted transaction received
2564660 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 538 | 1 | فايل ملفات ارشيف |  | Each | 20 | 45895322 |  |  |  | فايل ملفات ارشيف | 910010000188 | Administration | Received | 2021-12-01 | Accounted transaction received
2564655 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 325 | 1 | حافظة بلاستيك مستوردة |  | Each | 5 | 45895317 |  |  |  | حافظة بلاستيك مستوردة | 910010000138 | Administration | Received | 2021-12-01 | Accounted transaction received
2564647 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 35 | 1 | استيكة روترنج صغيرة |  | Each | 10 | 45895309 |  |  |  | استيكة روترنج صغيرة | 910010000067 | Administration | Received | 2021-12-01 | Accounted transaction received
2564648 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 8 | 1 | مسطرة معدن 30سم |  | Each | 2 | 45895310 |  |  |  | مسطرة معدن 30سم | 910010000094 | Administration | Received | 2021-12-01 | Accounted transaction received
2564649 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 135 | 1 | طقم قلم فيسفوري استنجر الماني |  | Each | 10 | 45895311 |  |  |  | طقم قلم فيسفوري استنجر الماني | 910010000116 | Administration | Received | 2021-12-01 | Accounted transaction received
2564650 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 30 | 1 | قلم جاف فرنساوي عادي ازرق |  | Each | 24 | 45895312 |  |  |  | قلم جاف فرنساوي عادي ازرق | 910010000118 | Administration | Received | 2021-12-01 | Accounted transaction received
2564651 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 30 | 1 | قلم جاف فرنساوي عادي اسود |  | Each | 24 | 45895313 |  |  |  | قلم جاف فرنساوي عادي اسود | 910010000119 | Administration | Received | 2021-12-01 | Accounted transaction received
2564652 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 62.5 | 1 | قلم سنون 0.7مم |  | Each | 5 | 45895314 |  |  |  | قلم سنون 0.7مم | 910010000127 | Administration | Received | 2021-12-01 | Accounted transaction received
2564653 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 48.75 | 1 | خلاعة دبابيس دايلي |  | Each | 5 | 45895315 |  |  |  | خلاعة دبابيس دايلي | 910010000132 | Administration | Received | 2021-12-01 | Accounted transaction received
2564654 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 117 | 1 | خلاعة دبابيس كبيرة |  | Each | 2 | 45895316 |  |  |  | خلاعة دبابيس كبيرة | 910010000133 | Administration | Received | 2021-12-01 | Accounted transaction received
2564656 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 80 | 1 | استيكى نوت 2 * 3 |  | Each | 20 | 45895318 |  |  |  | استيكى نوت 2 * 3 | 910010000139 | Administration | Received | 2021-12-01 | Accounted transaction received
2564661 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 20.75 | 1 | سنون 0.7مم |  | Each | 5 | 45895323 |  |  |  | سنون 0.7مم | 910010000191 | Administration | Received | 2021-12-01 | Accounted transaction received
2564662 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 1502.5 | 1 | رزمة ورق تصوير A3 |  | Each | 15 | 45895324 |  |  |  | رزمة ورق تصوير A3 | 910020000001 | Administration | Received | 2021-12-01 | Accounted transaction received
2564663 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 1627.92 | 1 | بردورة رصيف 50*30*12 / 15 |  | Meter | 21 | 45895325 |  |  |  | بردورة رصيف 50*30*12 / 15 | 140020000015 | Purchasing | Received | 2021-12-01 | Accounted transaction received
2564664 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 1884.03 | 1 | بولي ايثيلين 100 ميكرون شفاف |  | Kilogram | 53 | 45895326 |  |  |  | بولي ايثيلين 100 ميكرون شفاف | 040010000040 | Purchasing | Received | 2021-12-01 | Accounted transaction received
2564665 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 96.44 | 1 | كابل نحاس ترمو ضغط منخفض مقاس 4 × 4 مم (pvc/pvc) |  | Meter | 15 | 45895327 |  |  |  | كابل نحاس ترمو ضغط منخفض مقاس 4 × 4 مم (pvc/pvc) | 030030100001 | MEP | Received | 2021-12-01 | Accounted transaction received
2564666 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 2364.21 | 1 | كابل نحاس ترمو ضغط منخفض مقاس 4 × 10 مم (pvc/pvc) |  | Meter | 36 | 45895328 |  |  |  | كابل نحاس ترمو ضغط منخفض مقاس 4 × 10 مم (pvc/pvc) | 030030100005 | MEP | Received | 2021-12-01 | Accounted transaction received
2564667 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 432.63 | 1 | كابل نحاس ترمو ضغط منخفض مقاس 4 × 6 مم (pvc/pvc) |  | Meter | 10 | 45895329 |  |  |  | كابل نحاس ترمو ضغط منخفض مقاس 4 × 6 مم (pvc/pvc) | 030030100003 | MEP | Received | 2021-12-01 | Accounted transaction received
2564668 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 12.54 | 1 | شريط لحام اللون اسود |  | Each | 2 | 45895330 |  |  |  | شريط لحام اللون اسود | 030130400006 | MEP | Received | 2021-12-01 | Accounted transaction received
2564669 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 2055.8 | 1 | كشاف ليد 200 وات |  | Each | 4 | 45895331 |  |  |  | كشاف ليد 200 وات | 039010200004 | MEP | Received | 2021-12-01 | Accounted transaction received
2564670 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 25 | 1 | بردورة زراعة |  | Each | 1 | 45895332 |  |  |  | بردورة زراعة | 140020000049 | Purchasing | Received | 2021-12-01 | Accounted transaction received
2564671 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 649.42 | 1 | مفتاح ارث ليكودج 63 أمبير |  | Each | 1 | 45895333 |  |  |  | مفتاح ارث ليكودج 63 أمبير | 030110600058 | MEP | Received | 2021-12-01 | Accounted transaction received
2564672 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 135.37 | 1 | فوم باركية |  | Roll | 0.5 | 45895334 |  |  |  | فوم باركية | 040010000080 | Purchasing | Received | 2021-12-01 | Accounted transaction received
2564673 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 245.1 | 1 | قاطع مفتاح اوتوماتيك 32 امبير |  | Each | 1 | 45895335 |  |  |  | قاطع مفتاح اوتوماتيك 32 امبير | 030140200004 | MEP | Received | 2021-12-01 | Accounted transaction received
2564674 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 114 | 1 | كرتون مضلع - تغليف |  | Kilogram | 10 | 45895336 |  |  |  | كرتون مضلع - تغليف | 910010000387 | Administration | Received | 2021-12-01 | Accounted transaction received
2564675 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 1550 | 1 | رزمة ورق A4 400 جرام |  | Each | 25 | 45895337 |  |  |  | رزمة ورق A4 400 جرام | 910020000013 | Administration | Received | 2021-12-01 | Accounted transaction received
2564676 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 20 | 1 | فيشة ذكر كاوتش 16أمبير 220 فولت |  | Each | 2 | 45895338 |  |  |  | فيشة ذكر كاوتش 16أمبير 220 فولت | 039010000049 | MEP | Received | 2021-12-01 | Accounted transaction received
2564677 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 15 | 1 | فيشة نتاية كاوتش 16أمبير 220 فولت |  | Each | 2 | 45895339 |  |  |  | فيشة نتاية كاوتش 16أمبير 220 فولت | 039010000050 | MEP | Received | 2021-12-01 | Accounted transaction received
2564678 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 174.88 | 1 | Surgical mask كمامة طبية |  | Each | 250 | 45895340 |  |  |  | Surgical mask كمامة طبية | 010020000046 | Safety | Received | 2021-12-01 | Accounted transaction received
2564679 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 592.8 | 1 | كاتل شاى |  | Each | 2 | 45895341 |  |  |  | كاتل شاى | 700020000172 | Purchasing | Received | 2021-12-01 | Accounted transaction received
2564680 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-11-30 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 55399.42 | 1 | الواح ام دي اف MDF سمك 12 مم |  | Each | 226 | 45895342 |  |  |  | الواح ام دي اف MDF سمك 12 مم | 090040000075 | Purchasing | Received | 2021-12-01 | Accounted transaction received
2577026 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2021-11-30 | Hirings Payrool |  |  |  | Indirect | Alrowad Construction_OU | 235710.56 | 1 | قيد مرتبات شهر نوفمبر 2021 | Salary-NOV-2021 | Currency | 235710.56 | 10194389 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر نوفمبر 2021 |  | Finacial | Received | 2021-12-05 | Accounted transaction received
2577063 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2021-11-30 | Honouring of terrorism 0.0005 |  |  |  | Indirect | Alrowad Construction_OU | 99.9 | 1 | قيد مرتبات شهر نوفمبر 2021 | Salary-NOV-2021 | Currency | 99.9 | 10194389 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر نوفمبر 2021 |  | Finacial | Received | 2021-12-05 | Accounted transaction received
2577102 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.06 | Telephones | 17 | Indirect Cost |  | 2021-11-30 | Telephones |  |  |  | Indirect | Alrowad Construction_OU | -90.48 | 1 | قيد مرتبات شهر نوفمبر 2021 | Salary-NOV-2021 | Currency | -90.48 | 10194389 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر نوفمبر 2021 |  | Finacial | Received | 2021-12-05 | Accounted transaction received
2577138 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.02 | Health Care | 17 | Indirect Cost |  | 2021-11-30 | Medical Care |  |  |  | Direct Manpower | Alrowad Construction_OU | -2361.57 | 1 | قيد مرتبات شهر نوفمبر 2021 | Salary-NOV-2021 | Currency | -2361.57 | 10194389 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر نوفمبر 2021 |  | Finacial | Received | 2021-12-05 | Accounted transaction received
2577178 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2021-11-30 | Hirings Payrool |  |  |  | Indirect | Alrowad Construction_OU | -12767.73 | 1 | قيد مرتبات شهر نوفمبر 2021 | Salary-NOV-2021 | Currency | -12767.73 | 10194389 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر نوفمبر 2021 |  | Finacial | Received | 2021-12-05 | Accounted transaction received
2577940 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-11-30 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 78.17 | 1 | Distrbute Depreciation-Nov.21 | Distrbute Depreciation-Nov.21 | Currency | 78.17 | 10182241 | 2131 | Miscellaneous supplier | RME | Distrbute Depreciation-Nov.21 |  | Finacial | Received | 2021-12-05 | Accounted transaction received
2605704 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-14 | Networks and programs |  |  |  | Depreciation | Alrowad Construction_OU | 12377.15 | 1 | 29001-2902-2924-2946-2945-2977-2970 wald rofe | 29001-2902-2924-2946-2945-2977-2970 wald rofe | Currency | 12377.15 | 10268958 | 1709 | هيتس لتكنولوجيا المعلومات | Egypt | 29001-2902-2924-2946-2945-2977-2970 wald rofe |  | Finacial | Received | 2021-12-14 | Accounted transaction received
2605715 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-14 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 30000 | 1 | Nov-21 | Nov-21 | Currency | 30000 | 10268958 | 2131 | Miscellaneous supplier | RME | Nov-21 |  | Finacial | Received | 2021-12-14 | Accounted transaction received
2625083 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-20 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 44253 | 1 | والد روف الحلول المتكامله ف/201 14/12 | 201 | Currency | 44253 | 10453808 | 4932 | الحلول المتكامله | rowad | والد روف الحلول المتكامله ف/201 14/12 |  | Finacial | Received | 2021-12-20 | Accounted transaction received
2565838 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.03 | Hirings daily wages | 17 | Indirect Cost |  | 2021-11-30 | Bank Fees |  |  |  | Finance cost | Alrowad Construction_OU | 64786.45 | 1 | م بنكية بنك مصر 11/2021 helioples | م بنكية بنك مصر 11/2021 helioples | Currency | 64786.45 | 10160187 | 2131 | Miscellaneous supplier | RME | م بنكية بنك مصر 11/2021 helioples |  | Finacial | Received | 2021-12-01 | Accounted transaction received
2576968 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2021-11-30 | Furniture Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 5369.71 | 1 |  | Depreciation _Nov.21 | Currency | 5369.71 | 10194389 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2021-12-05 | Accounted transaction received
2576969 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2021-11-30 | Electrical appliance Deprectia |  |  |  | Depreciation | Alrowad Construction_OU | 1699.75 | 1 |  | Depreciation _Nov.21 | Currency | 1699.75 | 10194389 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2021-12-05 | Accounted transaction received
2576970 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2021-11-30 | Electrical appliance Deprectia |  |  |  | Depreciation | Alrowad Construction_OU | 100.9 | 1 |  | Depreciation _Nov.21 | Currency | 100.9 | 10194389 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2021-12-05 | Accounted transaction received
2576971 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2021-11-30 | Computers Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 166.21 | 1 |  | Depreciation _Nov.21 | Currency | 166.21 | 10194389 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2021-12-05 | Accounted transaction received
2576972 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2021-11-30 | Electrical appliance Deprectia |  |  |  | Depreciation | Alrowad Construction_OU | 2583.29 | 1 |  | Depreciation _Nov.21 | Currency | 2583.29 | 10194389 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2021-12-05 | Accounted transaction received
2577992 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-11-30 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 109.34 | 1 | Distrbute Depreciation-Nov.21 | Distrbute Depreciation-Nov.21 | Currency | 109.34 | 10182241 | 2131 | Miscellaneous supplier | RME | Distrbute Depreciation-Nov.21 |  | Finacial | Received | 2021-12-05 | Accounted transaction received
2578044 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-11-30 | Furniture Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 12.75 | 1 | Distrbute Depreciation-Nov.21 | Distrbute Depreciation-Nov.21 | Currency | 12.75 | 10182241 | 2131 | Miscellaneous supplier | RME | Distrbute Depreciation-Nov.21 |  | Finacial | Received | 2021-12-05 | Accounted transaction received
2578096 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-11-30 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 18.38 | 1 | Distrbute Depreciation-Nov.21 | Distrbute Depreciation-Nov.21 | Currency | 18.38 | 10182241 | 2131 | Miscellaneous supplier | RME | Distrbute Depreciation-Nov.21 |  | Finacial | Received | 2021-12-05 | Accounted transaction received
2578148 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-11-30 | Computers Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 10.56 | 1 | Distrbute Depreciation-Nov.21 | Distrbute Depreciation-Nov.21 | Currency | 10.56 | 10182241 | 2131 | Miscellaneous supplier | RME | Distrbute Depreciation-Nov.21 |  | Finacial | Received | 2021-12-05 | Accounted transaction received
2587684 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-07 | Stationary |  |  |  | Office and Site expenses | Alrowad Construction_OU | 295 | 1 | تسوية ك -1201/1223/1225/1226/1227-متنوع | ST-1201/1223/1225/1226/1227 | Currency | 295 | 10208697 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسوية ك -1201/1223/1225/1226/1227-متنوع |  | Finacial | Received | 2021-12-07 | Accounted transaction received
2587685 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2021-12-07 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 1508.2 | 1 | تسوية ك -1201/1223/1225/1226/1227-متنوع | ST-1201/1223/1225/1226/1227 | Currency | 1508.2 | 10208697 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسوية ك -1201/1223/1225/1226/1227-متنوع |  | Finacial | Received | 2021-12-07 | Accounted transaction received
2587686 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2021-12-07 | HSE |  |  |  | Indirect | Alrowad Construction_OU | 10000 | 1 | تسوية ك -1201/1223/1225/1226/1227-متنوع | ST-1201/1223/1225/1226/1227 | Currency | 10000 | 10208697 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسوية ك -1201/1223/1225/1226/1227-متنوع |  | Finacial | Received | 2021-12-07 | Accounted transaction received
2587687 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.03 | Hirings daily wages | 17 | Indirect Cost |  | 2021-12-07 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 15030 | 1 | تسوية ك -1201/1223/1225/1226/1227-متنوع | ST-1201/1223/1225/1226/1227 | Currency | 15030 | 10208697 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسوية ك -1201/1223/1225/1226/1227-متنوع |  | Finacial | Received | 2021-12-07 | Accounted transaction received
2600844 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.02 | Rented Cars | 17 | Indirect Cost |  | 2021-12-12 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4478.88 | 1 | 1 Astoria | 1 Astoria | Currency | 4478.88 | 10253734 | 9182 | مؤسسة الجينيرال لتأجير السيارات | rowad | 1 Astoria |  | Finacial | Received | 2021-12-12 | Accounted transaction received
2606147 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2021-12-15 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 18165.95 | 1 | يوميات عماله الفتره 2 ش 11 / الفعلي | يوميات عماله الفتره 2 ش 11 / الفعلي | Currency | 18165.95 | 10369569 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 2 ش 11 / الفعلي |  | Finacial | Received | 2021-12-15 | Accounted transaction received
2608780 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2021-12-16 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 200 | 1 | تسوية ك-195-ادارة المعدات-اكرامية معدات كرفانات | ST-195/21 | Currency | 200 | 10377322 | 2162 | Petty Cash | Mohamed Hassan Ibrahim Badawi | تسوية ك-195-ادارة المعدات-اكرامية معدات كرفانات |  | Finacial | Received | 2021-12-16 | Accounted transaction received
2620823 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-09 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 1895.22 | 1 | فوم باركية |  | Roll | 7 | 46184661 |  |  |  | فوم باركية | 040010000080 | Purchasing | Received | 2021-12-19 | Accounted transaction received
2620782 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 55 | 1 | سيلر |  | Can | 1 | 46486526 |  |  |  | سيلر | 050010000015 | Purchasing | Received | 2021-12-19 | Accounted transaction received
2620783 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 1669.67 | 1 | سيفتي عمال |  | Each | 7 | 46486527 |  |  |  | سيفتي عمال | 010030000002 | Safety | Received | 2021-12-19 | Accounted transaction received
2620784 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 87.55 | 1 | خوذة بيضاء JSP |  | Each | 3 | 46486528 |  |  |  | خوذة بيضاء JSP | 010040000004 | Safety | Received | 2021-12-19 | Accounted transaction received
2620785 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 10.54 | 1 | نظارة مهندسين M3 بيضاء |  | Each | 1 | 46486529 |  |  |  | نظارة مهندسين M3 بيضاء | 010060000004 | Safety | Received | 2021-12-19 | Accounted transaction received
2620786 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 188.49 | 1 | خوذة صفراء |  | Each | 6 | 46486530 |  |  |  | خوذة صفراء | 010040000010 | Safety | Received | 2021-12-19 | Accounted transaction received
2620787 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 7.04 | 1 | جوانتي محبب |  | Each | 1 | 46486531 |  |  |  | جوانتي محبب | 010010000006 | Safety | Received | 2021-12-19 | Accounted transaction received
2620788 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 357.19 | 1 | فيست برتقالي |  | Each | 16 | 46486532 |  |  |  | فيست برتقالي | 010020000008 | Safety | Received | 2021-12-19 | Accounted transaction received
2620789 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 45.29 | 1 | فيست ليموني |  | Each | 2 | 46486533 |  |  |  | فيست ليموني | 010020000009 | Safety | Received | 2021-12-19 | Accounted transaction received
2620790 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 51.98 | 1 | جوانتي باور جراب |  | Each | 4 | 46486534 |  |  |  | جوانتي باور جراب | 010010000009 | Safety | Received | 2021-12-19 | Accounted transaction received
2620791 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.08 | Electrical Expenses | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 114 | 1 | سوسته سحب مقاس M 25 |  | Each | 1 | 46486535 |  |  |  | سوسته سحب مقاس M 25 | 039020000010 | MEP | Received | 2021-12-19 | Accounted transaction received
2620792 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.08 | Electrical Expenses | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 18.81 | 1 | علبة ماجيك |  | Each | 6 | 46486536 |  |  |  | علبة ماجيك | 030990000397 | MEP | Received | 2021-12-19 | Accounted transaction received
2620793 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.08 | Electrical Expenses | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 60 | 1 | بكرة شريط لحام |  | Each | 2 | 46486537 |  |  |  | بكرة شريط لحام | 039010000003 | MEP | Received | 2021-12-19 | Accounted transaction received
2620794 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.08 | Electrical Expenses | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 54.72 | 1 | لقمة مفتاح |  | Each | 6 | 46486538 |  |  |  | لقمة مفتاح | 039010000007 | MEP | Received | 2021-12-19 | Accounted transaction received
2620795 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 25.08 | 1 | دكت 2.5 * 2.5 بالعود |  | Each | 1 | 46486539 |  |  |  | دكت 2.5 * 2.5 بالعود | 060010100762 | MEP | Received | 2021-12-19 | Accounted transaction received
2620796 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.08 | Electrical Expenses | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 102.6 | 1 | لفة خرطوم فليكسبل علاء الدين |  | Roll | 3 | 46486540 |  |  |  | لفة خرطوم فليكسبل علاء الدين | 030030500001 | MEP | Received | 2021-12-19 | Accounted transaction received
2620797 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.08 | Electrical Expenses | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 478.8 | 1 | بريزة خارج الحائط |  | Each | 15 | 46486541 |  |  |  | بريزة خارج الحائط | 039010000018 | MEP | Received | 2021-12-19 | Accounted transaction received
2620798 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.08 | Electrical Expenses | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 1925 | 1 | مشترك كهرباء ثلاثى 5 عين |  | Each | 11 | 46486542 |  |  |  | مشترك كهرباء ثلاثى 5 عين | 039010000019 | MEP | Received | 2021-12-19 | Accounted transaction received
2620799 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.08 | Electrical Expenses | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 3848.64 | 1 | سلك ترمو 2 * 3 |  | Roll | 2 | 46486543 |  |  |  | سلك ترمو 2 * 3 | 030030101008 | MEP | Received | 2021-12-19 | Accounted transaction received
2620800 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.08 | Electrical Expenses | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 28.5 | 1 | افيز بلاستيك كبير |  | Each | 1 | 46486544 |  |  |  | افيز بلاستيك كبير | 039019000006 | MEP | Received | 2021-12-19 | Accounted transaction received
2620801 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 40 | 1 | قفل عادى |  | Each | 2 | 46486545 |  |  |  | قفل عادى | 039020100060 | MEP | Received | 2021-12-19 | Accounted transaction received
2620802 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 50 | 1 | معجون دهان GLC |  | Can | 1 | 46486546 |  |  |  | معجون دهان GLC | 050010000113 | Purchasing | Received | 2021-12-19 | Accounted transaction received
2620803 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 55 | 1 | جالون دهان7047 |  | Gallon | 1 | 46486547 |  |  |  | جالون دهان7047 | 050010000115 | Purchasing | Received | 2021-12-19 | Accounted transaction received
2620804 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.08 | Electrical Expenses | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 330.6 | 1 | مفتاح قاطع 40A ثلاثى |  | Each | 1 | 46486548 |  |  |  | مفتاح قاطع 40A ثلاثى | 030140200005 | MEP | Received | 2021-12-19 | Accounted transaction received
2620805 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 2394 | 1 | بولي ايثيلين 100 ميكرون اسود |  | Kilogram | 150 | 46486549 |  |  |  | بولي ايثيلين 100 ميكرون اسود | 040010000104 | Purchasing | Received | 2021-12-19 | Accounted transaction received
2620806 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 50 | 1 | جنزير 8 مم |  | Meter | 1 | 46486550 |  |  |  | جنزير 8 مم | 010050000131 | Safety | Received | 2021-12-19 | Accounted transaction received
2620807 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.08 | Electrical Expenses | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 191.52 | 1 | مفتاح فردى 16 A |  | Each | 4 | 46486551 |  |  |  | مفتاح فردى 16 A | 030110600079 | MEP | Received | 2021-12-19 | Accounted transaction received
2620808 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2021-12-19 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 104.93 | 1 | Surgical mask كمامة طبية |  | Each | 150 | 46486552 |  |  |  | Surgical mask كمامة طبية | 010020000046 | Safety | Received | 2021-12-19 | Accounted transaction received
2620809 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2021-12-09 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 1192.62 | 1 | سيفتي عمال |  | Each | 5 | 46184647 |  |  |  | سيفتي عمال | 010030000002 | Safety | Received | 2021-12-19 | Accounted transaction received
2620810 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2021-12-09 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 87.55 | 1 | خوذة بيضاء JSP |  | Each | 3 | 46184648 |  |  |  | خوذة بيضاء JSP | 010040000004 | Safety | Received | 2021-12-19 | Accounted transaction received
2620811 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2021-12-09 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 21.09 | 1 | نظارة مهندسين M3 بيضاء |  | Each | 2 | 46184649 |  |  |  | نظارة مهندسين M3 بيضاء | 010060000004 | Safety | Received | 2021-12-19 | Accounted transaction received
2620812 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2021-12-09 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 565.46 | 1 | خوذة صفراء |  | Each | 18 | 46184650 |  |  |  | خوذة صفراء | 010040000010 | Safety | Received | 2021-12-19 | Accounted transaction received
2620813 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2021-12-09 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 126.43 | 1 | جوانتي جلد ثقيل ( خرسانة ) |  | Each | 12 | 46184651 |  |  |  | جوانتي جلد ثقيل ( خرسانة ) | 010010000003 | Safety | Received | 2021-12-19 | Accounted transaction received
2620814 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2021-12-09 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 70.37 | 1 | جوانتي محبب |  | Each | 10 | 46184652 |  |  |  | جوانتي محبب | 010010000006 | Safety | Received | 2021-12-19 | Accounted transaction received
2620815 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2021-12-09 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 158.53 | 1 | فيست ليموني |  | Each | 7 | 46184653 |  |  |  | فيست ليموني | 010020000009 | Safety | Received | 2021-12-19 | Accounted transaction received
2620816 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-09 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 2964 | 1 | مروحة استاند |  | Each | 4 | 46184654 |  |  |  | مروحة استاند | 700020000007 | Purchasing | Received | 2021-12-19 | Accounted transaction received
2620817 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2021-12-09 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 9.12 | 1 | سدادة أذن |  | Each | 2 | 46184655 |  |  |  | سدادة أذن | 010020000015 | Safety | Received | 2021-12-19 | Accounted transaction received
2620818 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-09 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 1777.39 | 1 | بولي ايثيلين 100 ميكرون شفاف |  | Kilogram | 50 | 46184656 |  |  |  | بولي ايثيلين 100 ميكرون شفاف | 040010000040 | Purchasing | Received | 2021-12-19 | Accounted transaction received
2620819 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-09 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 3554.77 | 1 | بولي ايثيلين 100 ميكرون شفاف |  | Kilogram | 100 | 46184657 |  |  |  | بولي ايثيلين 100 ميكرون شفاف | 040010000040 | Purchasing | Received | 2021-12-19 | Accounted transaction received
2620820 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-09 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 1824 | 1 | بولي ايثيلين 200 ميكرون شفاف |  | Kilogram | 50 | 46184658 |  |  |  | بولي ايثيلين 200 ميكرون شفاف | 040010000042 | Purchasing | Received | 2021-12-19 | Accounted transaction received
2620821 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-09 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 1617.89 | 1 | تيب مسلح |  | Each | 80 | 46184659 |  |  |  | تيب مسلح | 200010000382 | Purchasing | Received | 2021-12-19 | Accounted transaction received
2620822 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-09 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 376.2 | 1 | استريتش كبير |  | Kilogram | 10 | 46184660 |  |  |  | استريتش كبير | 200010000013 | Purchasing | Received | 2021-12-19 | Accounted transaction received
2620824 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-09 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 1881 | 1 | سلم خشب مزدوج 2 م |  | Each | 6 | 46184662 |  |  |  | سلم خشب مزدوج 2 م | 250010000312 | Procurement | Received | 2021-12-19 | Accounted transaction received
2620825 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.10 | Printers / Photo Cop | 17 | Indirect Cost |  | 2021-12-09 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 900.6 | 1 | Canon MF3010 Cartridge |  | Each | 2 | 46184663 |  |  |  | Canon MF3010 Cartridge | 800030000086 | IT | Received | 2021-12-19 | Accounted transaction received
2620826 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2021-12-09 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 174.88 | 1 | Surgical mask كمامة طبية |  | Each | 250 | 46184664 |  |  |  | Surgical mask كمامة طبية | 010020000046 | Safety | Received | 2021-12-19 | Accounted transaction received
2620827 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-09 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 5196 | 1 | سلم ألومنيوم 2 متر مجوز |  | Each | 6 | 46184665 |  |  |  | سلم ألومنيوم 2 متر مجوز | 200010002083 | Purchasing | Received | 2021-12-19 | Accounted transaction received
2620828 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-09 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 3847.5 | 1 | كرتون مضلع - تغليف |  | Kilogram | 300 | 46185828 |  |  |  | كرتون مضلع - تغليف | 910010000387 | Administration | Received | 2021-12-19 | Accounted transaction received
2630187 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-20 | Other |  |  |  | Other | Alrowad Construction_OU | 37059 | 1 | والد روف الحلول المتكامله ف/203 21/12 | 203 | Currency | 37059 | 10458928 | 4932 | الحلول المتكامله | rowad | والد روف الحلول المتكامله ف/203 21/12 |  | Finacial | Received | 2021-12-21 | Accounted transaction received
2683650 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-25 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 20 | 1 | سكينة معجون 5بوصة |  | Each | 1 | 46727652 |  |  |  | سكينة معجون 5بوصة | 200010000080 | Purchasing | Received | 2021-12-26 | Accounted transaction received
2683651 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-25 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 35 | 1 | منشار خشابي |  | Each | 1 | 46727653 |  |  |  | منشار خشابي | 200010000300 | Purchasing | Received | 2021-12-26 | Accounted transaction received
2683652 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-25 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 5 | 1 | ترباس حديد |  | Each | 1 | 46727654 |  |  |  | ترباس حديد | 250010000004 | Procurement | Received | 2021-12-26 | Accounted transaction received
2683653 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-25 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 50 | 1 | سلاح كتر |  | Each | 2 | 46727655 |  |  |  | سلاح كتر | 200010000411 | Purchasing | Received | 2021-12-26 | Accounted transaction received
2683654 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-25 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 130 | 1 | اسبراي فوم |  | Each | 2 | 46727656 |  |  |  | اسبراي فوم | 200010000471 | Purchasing | Received | 2021-12-26 | Accounted transaction received
2683655 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-25 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 30 | 1 | رولة دهان كبيرة |  | Each | 1 | 46727657 |  |  |  | رولة دهان كبيرة | 200010000544 | Purchasing | Received | 2021-12-26 | Accounted transaction received
2683656 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-25 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 15 | 1 | شاش شروخ |  | Each | 1 | 46727658 |  |  |  | شاش شروخ | 200010000655 | Purchasing | Received | 2021-12-26 | Accounted transaction received
2683657 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-25 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 20 | 1 | قفل وسط |  | Each | 1 | 46727659 |  |  |  | قفل وسط | 200010000681 | Purchasing | Received | 2021-12-26 | Accounted transaction received
2683658 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-25 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 570 | 1 | قلب سلندر |  | Each | 4 | 46727660 |  |  |  | قلب سلندر | 200010000682 | Purchasing | Received | 2021-12-26 | Accounted transaction received
2683659 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-25 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 160 | 1 | مفصلة 14 سم |  | Each | 8 | 46727661 |  |  |  | مفصلة 14 سم | 200010000965 | Purchasing | Received | 2021-12-26 | Accounted transaction received
2683660 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-25 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 200 | 1 | مسمار سن صاج 3 سم |  | Kilogram | 4 | 46727662 |  |  |  | مسمار سن صاج 3 سم | 200020000239 | Purchasing | Received | 2021-12-26 | Accounted transaction received
2683661 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-25 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 74.9 | 1 | بنطة رباط |  | Each | 7 | 46727663 |  |  |  | بنطة رباط | 200010001006 | Purchasing | Received | 2021-12-26 | Accounted transaction received
2683662 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-25 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 20 | 1 | سيليكون شفاف |  | Each | 1 | 46727664 |  |  |  | سيليكون شفاف | 200010000946 | Purchasing | Received | 2021-12-26 | Accounted transaction received
2683663 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-25 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 15 | 1 | مفصلة 11 سم |  | Each | 2 | 46727665 |  |  |  | مفصلة 11 سم | 200010001110 | Purchasing | Received | 2021-12-26 | Accounted transaction received
2683664 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-25 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 245 | 1 | مشترك كهرباء حائطى |  | Each | 7 | 46727666 |  |  |  | مشترك كهرباء حائطى | 200010001191 | Purchasing | Received | 2021-12-26 | Accounted transaction received
2683665 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-25 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 58 | 1 | مسمار خشابى 6 سم |  | Kilogram | 2 | 46727667 |  |  |  | مسمار خشابى 6 سم | 200020000141 | Purchasing | Received | 2021-12-26 | Accounted transaction received
2683666 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-25 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 150 | 1 | عتلة 50 سم |  | Each | 3 | 46727668 |  |  |  | عتلة 50 سم | 200010001248 | Purchasing | Received | 2021-12-26 | Accounted transaction received
2683667 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-25 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 27.5 | 1 | مسمار خشابى 10 سم |  | Kilogram | 1 | 46727669 |  |  |  | مسمار خشابى 10 سم | 200020000307 | Purchasing | Received | 2021-12-26 | Accounted transaction received
2683668 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-25 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 20 | 1 | مسمار سن صاج 7سم |  | Kilogram | 0.5 | 46727670 |  |  |  | مسمار سن صاج 7سم | 200020000325 | Purchasing | Received | 2021-12-26 | Accounted transaction received
2683669 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-25 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 25 | 1 | فرشة دهان 2.5 بوصة |  | Each | 1 | 46727671 |  |  |  | فرشة دهان 2.5 بوصة | 200010001553 | Purchasing | Received | 2021-12-26 | Accounted transaction received
2683670 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-25 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 20 | 1 | صنفرة ناعمة 120 |  | Meter | 4 | 46727672 |  |  |  | صنفرة ناعمة 120 | 200010001631 | Purchasing | Received | 2021-12-26 | Accounted transaction received
2683671 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-25 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 22 | 1 | مسمار خشابى 5 سم |  | Kilogram | 1 | 46727673 |  |  |  | مسمار خشابى 5 سم | 200020000562 | Purchasing | Received | 2021-12-26 | Accounted transaction received
2721997 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2021-12-27 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 51120.25 | 1 | يوميات عماله الفتره 1 ش 12 / الفعلي | يوميات عماله الفتره 1 ش 12 / الفعلي | Currency | 51120.25 | 12365596 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 1 ش 12 / الفعلي |  | Finacial | Received | 2021-12-28 | Accounted transaction received
2742495 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 250.8 | 1 | شريط قياس 5م |  | Each | 4 | 47344599 |  |  |  | شريط قياس 5م | 200010000105 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742496 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 172.09 | 1 | جاروف خرسانة |  | Each | 5 | 47344600 |  |  |  | جاروف خرسانة | 200010000051 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742497 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 50 | 1 | مساحة شرشوبة |  | Each | 1 | 47344601 |  |  |  | مساحة شرشوبة | 700020000026 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2755708 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2021-12-31 | Hirings Payrool |  |  |  | Indirect | Alrowad Construction_OU | 266496.11 | 1 | قيد مرتبات شهر ديسمبر 2021 | Salary-Dec-2021 | Currency | 266496.11 | 12409034 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر ديسمبر 2021 |  | Finacial | Received | 2022-01-01 | Accounted transaction received
2755745 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2021-12-31 | Honouring of terrorism 0.0005 |  |  |  | Indirect | Alrowad Construction_OU | 99.9 | 1 | قيد مرتبات شهر ديسمبر 2021 | Salary-Dec-2021 | Currency | 99.9 | 12409034 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر ديسمبر 2021 |  | Finacial | Received | 2022-01-01 | Accounted transaction received
2755784 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.06 | Telephones | 17 | Indirect Cost |  | 2021-12-31 | Telephones |  |  |  | Indirect | Alrowad Construction_OU | -87.86 | 1 | قيد مرتبات شهر ديسمبر 2021 | Salary-Dec-2021 | Currency | -87.86 | 12409034 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر ديسمبر 2021 |  | Finacial | Received | 2022-01-01 | Accounted transaction received
2755819 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.02 | Health Care | 17 | Indirect Cost |  | 2021-12-31 | Medical Care |  |  |  | Direct Manpower | Alrowad Construction_OU | -2361.57 | 1 | قيد مرتبات شهر ديسمبر 2021 | Salary-Dec-2021 | Currency | -2361.57 | 12409034 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر ديسمبر 2021 |  | Finacial | Received | 2022-01-01 | Accounted transaction received
2755858 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2021-12-31 | Hirings Payrool |  |  |  | Indirect | Alrowad Construction_OU | -24623.68 | 1 | قيد مرتبات شهر ديسمبر 2021 | Salary-Dec-2021 | Currency | -24623.68 | 12409034 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر ديسمبر 2021 |  | Finacial | Received | 2022-01-01 | Accounted transaction received
2756293 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.13 | Maintenance | 17 | Indirect Cost |  | 2021-12-31 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 146.04 | 1 |  | Depreciation_Dec.21 | Currency | 146.04 | 12409034 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2022-01-01 | Accounted transaction received
2756294 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.13 | Maintenance | 17 | Indirect Cost |  | 2021-12-31 | Electrical appliance Deprectia |  |  |  | Depreciation | Alrowad Construction_OU | 1699.75 | 1 |  | Depreciation_Dec.21 | Currency | 1699.75 | 12409034 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2022-01-01 | Accounted transaction received
2756295 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.13 | Maintenance | 17 | Indirect Cost |  | 2021-12-31 | Furniture Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 6913.59 | 1 |  | Depreciation_Dec.21 | Currency | 6913.59 | 12409034 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2022-01-01 | Accounted transaction received
2756296 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.13 | Maintenance | 17 | Indirect Cost |  | 2021-12-31 | Electrical appliance Deprectia |  |  |  | Depreciation | Alrowad Construction_OU | 551.94 | 1 |  | Depreciation_Dec.21 | Currency | 551.94 | 12409034 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2022-01-01 | Accounted transaction received
2756297 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.13 | Maintenance | 17 | Indirect Cost |  | 2021-12-31 | Computers Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 582.38 | 1 |  | Depreciation_Dec.21 | Currency | 582.38 | 12409034 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2022-01-01 | Accounted transaction received
2756298 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.13 | Maintenance | 17 | Indirect Cost |  | 2021-12-31 | Electrical appliance Deprectia |  |  |  | Depreciation | Alrowad Construction_OU | 2583.29 | 1 |  | Depreciation_Dec.21 | Currency | 2583.29 | 12409034 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2022-01-01 | Accounted transaction received
2761847 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2021-12-31 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 987.29 | 1 |  | Dist.Depreciation-Dec.21 | Currency | 987.29 | 12438137 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2022-01-02 | Accounted transaction received
2761891 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2021-12-31 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 1403.54 | 1 |  | Dist.Depreciation-Dec.21 | Currency | 1403.54 | 12438137 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2022-01-02 | Accounted transaction received
2761935 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2021-12-31 | Furniture Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 195.16 | 1 |  | Dist.Depreciation-Dec.21 | Currency | 195.16 | 12438137 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2022-01-02 | Accounted transaction received
2761979 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2021-12-31 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 229.86 | 1 |  | Dist.Depreciation-Dec.21 | Currency | 229.86 | 12438137 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2022-01-02 | Accounted transaction received
2762023 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2021-12-31 | Computers Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 168.59 | 1 |  | Dist.Depreciation-Dec.21 | Currency | 168.59 | 12438137 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2022-01-02 | Accounted transaction received
3071838 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2022-01-01 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | -51120.25 | 1 | يوميات عماله الفتره 2 ش 12 / التقديري | يوميات عماله الفتره 2 ش 12 / التقديري | Currency | -51120.25 | 17945536 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 2 ش 12 / التقديري |  | Finacial | Received | 2022-02-01 | Accounted transaction received
3726567 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2023-01-04 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 3856.2 | 1 | تسويه ك /2-3-4-5 - متنوعات | st-2-3-4-5-1-23 | Currency | 3856.2 | 21635257 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /2-3-4-5 - متنوعات |  | Finacial | Received | 2023-01-04 | Accounted transaction received
3726568 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.13 | Maintenance | 17 | Indirect Cost |  | 2023-01-04 | Maintenance |  |  |  | Indirect | Alrowad Construction_OU | 1824 | 1 | تسويه ك /2-3-4-5 - متنوعات | st-2-3-4-5-1-23 | Currency | 1824 | 21635257 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /2-3-4-5 - متنوعات |  | Finacial | Received | 2023-01-04 | Accounted transaction received
3726588 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2023-01-04 | Accomodation |  |  |  | Indirect | Alrowad Construction_OU | 5600 | 1 | ايجارات 1/2023 astoria | ايجارات 1/2023 astoria | Currency | 5600 | 21635257 | 2131 | Miscellaneous supplier | RME | ايجارات 1/2023 astoria |  | Finacial | Received | 2023-01-04 | Accounted transaction received
3726601 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.03 | Hirings daily wages | 17 | Indirect Cost |  | 2023-01-04 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 338832.7 | 1 | يوميات عماله م09-astoria cairo | يوميات عماله م09-astoria cairo | Currency | 338832.7 | 21635257 | 11283 | ضياءالدين عبدالدايم عمر داود-ذاتى | rowad | يوميات عماله م09-astoria cairo |  | Finacial | Received | 2023-01-04 | Accounted transaction received
3726602 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.03 | Hirings daily wages | 17 | Indirect Cost |  | 2023-01-04 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 17289.37 | 1 | يوميات عماله م05-astoria cairo | يوميات عماله م05-astoria cairo | Currency | 17289.37 | 21635257 | 12252 | حامد حسين احمد خالد – ذاتى | rowad | يوميات عماله م05-astoria cairo |  | Finacial | Received | 2023-01-04 | Accounted transaction received
3727313 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-01-04 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9298.6 | 1 | 1.1 74882/2 |  | Currency | 92.72 |  | 8027 | نصر ابراهيم احمد ابراهيم – ذاتى |  | 1.1 74882/2 |  | Finacial | Received | 2023-01-05 | Accounted transaction received
3727315 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-04 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | 11000 | 1 | 76627/2 |  | Currency | 11000 |  | 12356 | محمود يحى احمد محمد-ذاتى |  | 76627/2 |  | Finacial | Received | 2023-01-05 | Accounted transaction received
3727316 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-04 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2170 | 1 | 1.1 76627/2 |  | Currency | 48.75 |  | 12356 | محمود يحى احمد محمد-ذاتى |  | 1.1 76627/2 |  | Finacial | Received | 2023-01-05 | Accounted transaction received
3727317 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-04 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3255 | 1 | 1.2 76627/2 |  | Currency | 48.75 |  | 12356 | محمود يحى احمد محمد-ذاتى |  | 1.2 76627/2 |  | Finacial | Received | 2023-01-05 | Accounted transaction received
3727318 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-04 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5967.5 | 1 | 1.3 76627/2 |  | Currency | 48.75 |  | 12356 | محمود يحى احمد محمد-ذاتى |  | 1.3 76627/2 |  | Finacial | Received | 2023-01-05 | Accounted transaction received
3731323 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.03 | Hirings daily wages | 17 | Indirect Cost |  | 2023-01-09 | Hirings Payrool |  |  |  | Indirect | Alrowad Construction_OU | 6000 | 1 | تسوية 1/2/3/4/5/6/7/8-متنوعة | st-1/2/3/4/5/6/7/8-1-23 | Currency | 6000 | 21666857 | 2162 | Petty Cash | Ali Abdel Hamid Ali Abdel Hamid | تسوية 1/2/3/4/5/6/7/8-متنوعة |  | Finacial | Received | 2023-01-09 | Accounted transaction received
3731330 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-09 | Other |  |  |  | Other | Alrowad Construction_OU | 1333.33 | 1 | استوريا ليدينج 365 للتدريب ف/44 29/12/2022 | 44 استوريا | Currency | 1333.33 | 21666857 | 8129 | ليدينج 365 للتريب والاستثمارات | rowad | استوريا ليدينج 365 للتدريب ف/44 29/12/2022 |  | Finacial | Received | 2023-01-09 | Accounted transaction received
3736874 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2023-01-12 | Accomodation |  |  |  | Indirect | Alrowad Construction_OU | 41250 | 1 | تسويه ك /ايجارات شهر يناير | st-13-1-23 | Currency | 41250 | 21689311 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /ايجارات شهر يناير |  | Finacial | Received | 2023-01-12 | Accounted transaction received
3736875 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-12 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 800 | 1 | تسويه ك /6-9-10-11 - مهمات ومصنعيات | st-6-9-10-11-1-23 | Currency | 800 | 21689311 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /6-9-10-11 - مهمات ومصنعيات |  | Finacial | Received | 2023-01-12 | Accounted transaction received
3736884 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.03 | Hirings daily wages | 17 | Indirect Cost |  | 2023-01-12 | Bank Fees |  |  |  | Finance cost | Alrowad Construction_OU | 6668.97 | 1 | lg Bm 1/2023 astoria | lg Bm 1/2023 astoria | Currency | 6668.97 | 21689311 | 2131 | Miscellaneous supplier | RME | lg Bm 1/2023 astoria |  | Finacial | Received | 2023-01-12 | Accounted transaction received
3746414 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-01-17 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 218335 | 1 | يوميات عماله الفتره 2 ش 12 الفعلي | يوميات عماله الفتره 2 ش 12 الفعلي | Currency | 218335 | 21723190 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 2 ش 12 الفعلي |  | Finacial | Received | 2023-01-17 | Accounted transaction received
3746454 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-17 | Materials |  |  |  | Materials | Alrowad Construction_OU | -10 | 1 | تسويه ك /16-17-18-20-23-24-25-26-27 - مهمات | st-16-17-18-20-23-24-25-26-27-1-23 | Currency | -10 | 21723190 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /16-17-18-20-23-24-25-26-27 - مهمات |  | Finacial | Received | 2023-01-17 | Accounted transaction received
3746457 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.13 | Maintenance | 17 | Indirect Cost |  | 2023-01-17 | Maintenance |  |  |  | Indirect | Alrowad Construction_OU | 5700 | 1 | تسويه ك /7-14-15-22-29-30-31-32-33 - متنوعات | st-7-14-15-22-29-30-31-32-33--1-23 | Currency | 5700 | 21723190 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /7-14-15-22-29-30-31-32-33 - متنوعات |  | Finacial | Received | 2023-01-17 | Accounted transaction received
3746458 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-17 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 500 | 1 | تسويه ك /7-14-15-22-29-30-31-32-33 - متنوعات | st-7-14-15-22-29-30-31-32-33--1-23 | Currency | 500 | 21723190 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /7-14-15-22-29-30-31-32-33 - متنوعات |  | Finacial | Received | 2023-01-17 | Accounted transaction received
3758611 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-01-24 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 133200 | 1.1 | Walls to cover area |  | Currency | 72 |  | 10037 | ايه وان للمقاولات |  | 1.1 63247/1 |  | Finacial | Received | 2023-01-24 | Accounted transaction received
3758612 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-01-24 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 21600 | 1.1 | Walls to cover area |  | Currency | 72 |  | 10037 | ايه وان للمقاولات |  | 2.1 63247/1 |  | Finacial | Received | 2023-01-24 | Accounted transaction received
3758613 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-01-24 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -696.6 | 1.1 | Walls to cover area |  | Currency | -696.6 |  | 10037 | ايه وان للمقاولات |  | LABOUR_OFFICE 63247/1 |  | Finacial | Received | 2023-01-24 | Accounted transaction received
3758616 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-01-24 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 190550 | 1 | 1.1 63247/2 |  | Currency | 175 |  | 10037 | ايه وان للمقاولات |  | 1.1 63247/2 |  | Finacial | Received | 2023-01-24 | Accounted transaction received
3758617 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-01-24 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 30900 | 1 | 2.1 63247/2 |  | Currency | 175 |  | 10037 | ايه وان للمقاولات |  | 2.1 63247/2 |  | Finacial | Received | 2023-01-24 | Accounted transaction received
3758618 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-01-24 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 223600 | 1 | 3.1 63247/2 |  | Currency | 104 |  | 10037 | ايه وان للمقاولات |  | 3.1 63247/2 |  | Finacial | Received | 2023-01-24 | Accounted transaction received
3758619 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-01-24 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 11400 | 1 | 4.1 63247/2 |  | Currency | 11400 |  | 10037 | ايه وان للمقاولات |  | 4.1 63247/2 |  | Finacial | Received | 2023-01-24 | Accounted transaction received
3758620 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-01-24 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5700 | 1 | 4.2 63247/2 |  | Currency | 5700 |  | 10037 | ايه وان للمقاولات |  | 4.2 63247/2 |  | Finacial | Received | 2023-01-24 | Accounted transaction received
3758621 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-01-24 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5700 | 1 | 4.3 63247/2 |  | Currency | 5700 |  | 10037 | ايه وان للمقاولات |  | 4.3 63247/2 |  | Finacial | Received | 2023-01-24 | Accounted transaction received
3758622 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-01-24 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 20007 | 1 | 4.6 63247/2 |  | Currency | 9 |  | 10037 | ايه وان للمقاولات |  | 4.6 63247/2 |  | Finacial | Received | 2023-01-24 | Accounted transaction received
3758623 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-01-24 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 12226.5 | 1 | 4.7 63247/2 |  | Currency | 5.5 |  | 10037 | ايه وان للمقاولات |  | 4.7 63247/2 |  | Finacial | Received | 2023-01-24 | Accounted transaction received
3758624 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-01-24 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -2250.38 | 1 | LABOUR_OFFICE 63247/2 |  | Currency | -2250.38 |  | 10037 | ايه وان للمقاولات |  | LABOUR_OFFICE 63247/2 |  | Finacial | Received | 2023-01-24 | Accounted transaction received
3759419 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK | 63247 | 2023-01-24 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -27662.46 | 1 | 2 Astoria 63247/2 | 2 Astoria 63247/2 | Currency | -27662.46 | 21849006 | 10037 | ايه وان للمقاولات | rowad | 2 Astoria 63247/2 |  | Procurement | Received | 2023-01-24 | Accounted transaction received
3762333 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-01-25 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2850 | 1 | 1.1 78083/2 |  | Currency | 14.25 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | 1.1 78083/2 |  | Finacial | Received | 2023-01-25 | Accounted transaction received
3762334 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-01-25 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4275 | 1 | 1.2 78083/2 |  | Currency | 14.25 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | 1.2 78083/2 |  | Finacial | Received | 2023-01-25 | Accounted transaction received
3762335 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-01-25 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 8550 | 1 | 1.3 78083/2 |  | Currency | 14.25 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | 1.3 78083/2 |  | Finacial | Received | 2023-01-25 | Accounted transaction received
3762336 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-01-25 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -70.54 | 1 | LABOUR_OFFICE 78083/2 |  | Currency | -70.54 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | LABOUR_OFFICE 78083/2 |  | Finacial | Received | 2023-01-25 | Accounted transaction received
3762340 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-01-25 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 18424.45 | 1 | 1.1 74495/4 |  | Currency | 334.99 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | 1.1 74495/4 |  | Finacial | Received | 2023-01-25 | Accounted transaction received
3762341 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-01-25 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 6699.8 | 1 | 2.1 74495/4 |  | Currency | 334.99 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | 2.1 74495/4 |  | Finacial | Received | 2023-01-25 | Accounted transaction received
3762342 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-01-25 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | -3000 | 1 | 74495/4 |  | Currency | -3000 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | 74495/4 |  | Finacial | Received | 2023-01-25 | Accounted transaction received
3762343 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-01-25 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -113.06 | 1 | LABOUR_OFFICE 74495/4 |  | Currency | -113.06 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | LABOUR_OFFICE 74495/4 |  | Finacial | Received | 2023-01-25 | Accounted transaction received
3763402 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-01-25 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 10730.25 | 1 | 1.1 79068/1 |  | Currency | 143.07 |  | 12490 | محمد مسعد حسن محمد حسن-ذاتى |  | 1.1 79068/1 |  | Finacial | Received | 2023-01-25 | Accounted transaction received
3763404 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.06.01 | Mirrors | 8 | DOORS & WINDOWS WOR |  | 2023-01-25 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3277.5 | 1 | 1.1 78681/1 |  | Currency | 17.25 |  | 12465 | محمد مصطفى عطية الدسوقى-ذاتى |  | 1.1 78681/1 |  | Finacial | Received | 2023-01-25 | Accounted transaction received
3763416 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-25 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4830 | 1 | 1.1 76627/3 |  | Currency | 24.15 |  | 12356 | محمود يحى احمد محمد-ذاتى |  | 1.1 76627/3 |  | Finacial | Received | 2023-01-25 | Accounted transaction received
3763417 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-25 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7245 | 1 | 1.2 76627/3 |  | Currency | 24.15 |  | 12356 | محمود يحى احمد محمد-ذاتى |  | 1.2 76627/3 |  | Finacial | Received | 2023-01-25 | Accounted transaction received
3763418 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-25 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 13282.5 | 1 | 1.3 76627/3 |  | Currency | 24.15 |  | 12356 | محمود يحى احمد محمد-ذاتى |  | 1.3 76627/3 |  | Finacial | Received | 2023-01-25 | Accounted transaction received
3763426 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-01-25 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 14614.8 | 1 | 1.1 74882/4 |  | Currency | 38.46 |  | 8027 | نصر ابراهيم احمد ابراهيم – ذاتى |  | 1.1 74882/4 |  | Finacial | Received | 2023-01-25 | Accounted transaction received
3773224 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 364.8 | 1 | تنر |  | Each | 4 | 59364642 |  |  |  | تنر | 060019000008 | MEP | Received | 2023-01-28 | Accounted transaction received
3773145 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 85 | 1 | فلتر جاز طويل نيسان بيك اب |  | Each | 1 | 59598767 |  |  |  | فلتر جاز طويل نيسان بيك اب | 330030000097 | Equipment | Received | 2023-01-28 | Accounted transaction received
3773146 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 80 | 1 | فلتر جاز قصير نيسان بيك اب |  | Each | 1 | 59598768 |  |  |  | فلتر جاز قصير نيسان بيك اب | 330030000098 | Equipment | Received | 2023-01-28 | Accounted transaction received
3773147 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 570 | 1 | قاعده سيلكون دينامو بركنز 12 فولت |  | Each | 10 | 59598769 |  |  |  | قاعده سيلكون دينامو بركنز 12 فولت | 330040002702 | Equipment | Received | 2023-01-28 | Accounted transaction received
3773148 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 445740 | 1 | Vanity mirror; polished low iron clear GL-1; with brass frame MT-1; including all necessary accessories; preparations; Bathroom Materials: Brass special profile 10x20mm 6mm Mirror - 2cm edge chamfer 8mm Moisture proof plywood Dimensions |  | Each | 46 | 59598835 |  |  |  | Vanity mirror; polished low iron clear GL-1; with brass frame MT-1; including all necessary accessories; preparations; Bathroom Materials: Brass special profile 10x20mm 6mm Mirror - 2cm edge chamfer 8mm Moisture proof plywood Dimensions | 250010001361 | Procurement | Received | 2023-01-28 | Accounted transaction received
3773149 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 14136 | 1 | Comprising brass frame MT-1 For Bathroom vanity cabinet including all necessary accessories; preparations; Size 2690 x 600 x 1050 mm Materials: Steel frame 30x30mm Dimensions: 269x57x82 cm Finish: Galvanized steel, Antique brass look paint |  | Each | 2 | 59598836 |  |  |  | Comprising brass frame MT-1 For Bathroom vanity cabinet including all necessary accessories; preparations; Size 2690 x 600 x 1050 mm Materials: Steel frame 30x30mm Dimensions: 269x57x82 cm Finish: Galvanized steel, Antique brass look paint | 250010001365 | Procurement | Received | 2023-01-28 | Accounted transaction received
3773150 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 8208 | 1 | Robe Hook Plate 75*75*10 MT-1 |  | Each | 96 | 59598837 |  |  |  | Robe Hook Plate 75*75*10 MT-1 | 250010001671 | Procurement | Received | 2023-01-28 | Accounted transaction received
3773151 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 63612 | 1 | Metal trim MT-01 separating between ST-18 and existing marble @ Typical Suit |  | Meter | 46.5 | 59598838 |  |  |  | Metal trim MT-01 separating between ST-18 and existing marble @ Typical Suit | 250010001925 | Procurement | Received | 2023-01-28 | Accounted transaction received
3773152 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 7296 | 1 | الواح كونتر 1.22م*2.44م*18مم |  | Each | 8 | 59598846 |  |  |  | الواح كونتر 1.22م*2.44م*18مم | 090040000018 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773153 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 61156.78 | 1 | Marmox Board Cladding |  | Square Meter | 405 | 59598847 |  |  |  | Marmox Board Cladding | 140030000115 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773154 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 11580 | 1 | إطار تويو 185 / 65 / 15 يابانى |  | Each | 4 | 59598848 |  |  |  | إطار تويو 185 / 65 / 15 يابانى | 330040005217 | Equipment | Received | 2023-01-28 | Accounted transaction received
3773155 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 224500.2 | 1 | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² |  | Kilogram | 4190 | 59598861 |  |  |  | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² | 060040200001 | MEP | Received | 2023-01-28 | Accounted transaction received
3773156 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1852.5 | 1 | كورنر (TDF) |  | Each | 500 | 59598862 |  |  |  | كورنر (TDF) | 060040200002 | MEP | Received | 2023-01-28 | Accounted transaction received
3773157 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3079.99 | 1 | "عزل داخلى مجارى الهواء ماركة K-FLEX ارما فليكس بسمك 13 مم باللصق ابعاد الرول 1m x 14m" |  | Square Meter | 14 | 59598863 |  |  |  | "عزل داخلى مجارى الهواء ماركة K-FLEX ارما فليكس بسمك 13 مم باللصق ابعاد الرول 1m x 14m" | 060050300003 | MEP | Received | 2023-01-28 | Accounted transaction received
3773158 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 300 | 1 | افيز 40 مم |  | Each | 30 | 59600448 |  |  |  | افيز 40 مم | 240060000008 | MEP | Received | 2023-01-28 | Accounted transaction received
3773159 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 200 | 1 | افيز 65 مم |  | Each | 10 | 59600449 |  |  |  | افيز 65 مم | 240060000011 | MEP | Received | 2023-01-28 | Accounted transaction received
3773160 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2291.4 | 1 | Supplying of pendent concealed sprinkler , quick response , standard coverage , 68 C, 1/2", K=5.6 C/W cover plate |  | Each | 3 | 59600450 |  |  |  | Supplying of pendent concealed sprinkler , quick response , standard coverage , 68 C, 1/2", K=5.6 C/W cover plate | 060090100007 | MEP | Received | 2023-01-28 | Accounted transaction received
3773161 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1500.01 | 1 | أنبوبة سليكون |  | Each | 30 | 59600451 |  |  |  | أنبوبة سليكون | 060019000001 | MEP | Received | 2023-01-28 | Accounted transaction received
3773162 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1681.5 | 1 | Mechanical anchor (Drop in anchor) size M8 |  | Each | 500 | 59600452 |  |  |  | Mechanical anchor (Drop in anchor) size M8 | 060190100002 | MEP | Received | 2023-01-28 | Accounted transaction received
3773163 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3249 | 1 | Mechanical anchor (Drop in anchor) size M10 |  | Each | 600 | 59600453 |  |  |  | Mechanical anchor (Drop in anchor) size M10 | 060190100003 | MEP | Received | 2023-01-28 | Accounted transaction received
3773164 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 602.78 | 1 | Standard flat washers size 8M |  | Kilogram | 15 | 59600454 |  |  |  | Standard flat washers size 8M | 060190500002 | MEP | Received | 2023-01-28 | Accounted transaction received
3773165 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1295.04 | 1 | Standard hex nuts size M8 |  | Kilogram | 20 | 59600455 |  |  |  | Standard hex nuts size M8 | 060190600002 | MEP | Received | 2023-01-28 | Accounted transaction received
3773166 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 182.4 | 1 | وردة 12 مم |  | Kilogram | 2 | 59600456 |  |  |  | وردة 12 مم | 200020000186 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773167 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 10225.8 | 1 | threaded elbows f 90° size 1" UL LISTED,FM APPROVED |  | Each | 130 | 59600457 |  |  |  | threaded elbows f 90° size 1" UL LISTED,FM APPROVED | 060010140056 | MEP | Received | 2023-01-28 | Accounted transaction received
3773168 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 574.56 | 1 | threaded elbows f 90° size 1.25" UL LISTED,FM APPROVED |  | Each | 6 | 59600458 |  |  |  | threaded elbows f 90° size 1.25" UL LISTED,FM APPROVED | 060010140057 | MEP | Received | 2023-01-28 | Accounted transaction received
3773169 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 497.04 | 1 | threaded elbows f 90° size 1.5" UL LISTED,FM APPROVED |  | Each | 4 | 59600459 |  |  |  | threaded elbows f 90° size 1.5" UL LISTED,FM APPROVED | 060010140058 | MEP | Received | 2023-01-28 | Accounted transaction received
3773170 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 889.2 | 1 | threaded tees size 1" UL LISTED,FM APPROVED |  | Each | 10 | 59600460 |  |  |  | threaded tees size 1" UL LISTED,FM APPROVED | 060010140276 | MEP | Received | 2023-01-28 | Accounted transaction received
3773171 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2394 | 1 | threaded plugs size 1/2" UL LISTED,FM APPROVED |  | Each | 105 | 59600461 |  |  |  | threaded plugs size 1/2" UL LISTED,FM APPROVED | 060010140505 | MEP | Received | 2023-01-28 | Accounted transaction received
3773172 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 6498 | 1 | threaded reducing coupling size 1"*1/2" UL LISTED,FM APPROVED |  | Each | 100 | 59600462 |  |  |  | threaded reducing coupling size 1"*1/2" UL LISTED,FM APPROVED | 060010140334 | MEP | Received | 2023-01-28 | Accounted transaction received
3773173 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1111.5 | 1 | threaded reducing coupling size 1.25"*1" UL LISTED,FM APPROVED |  | Each | 15 | 59600463 |  |  |  | threaded reducing coupling size 1.25"*1" UL LISTED,FM APPROVED | 060010140339 | MEP | Received | 2023-01-28 | Accounted transaction received
3773174 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1112.4 | 1 | threaded reducing coupling size 1.5"*1" UL LISTED,FM APPROVED |  | Each | 11 | 59600464 |  |  |  | threaded reducing coupling size 1.5"*1" UL LISTED,FM APPROVED | 060010140343 | MEP | Received | 2023-01-28 | Accounted transaction received
3773175 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1244.88 | 1 | threaded reducing coupling size 1.5"*1.25" UL LISTED,FM APPROVED |  | Each | 12 | 59600465 |  |  |  | threaded reducing coupling size 1.5"*1.25" UL LISTED,FM APPROVED | 060010140344 | MEP | Received | 2023-01-28 | Accounted transaction received
3773176 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 420.66 | 1 | threaded reducing coupling size 2"*1.5" UL LISTED,FM APPROVED |  | Each | 3 | 59600466 |  |  |  | threaded reducing coupling size 2"*1.5" UL LISTED,FM APPROVED | 060010140351 | MEP | Received | 2023-01-28 | Accounted transaction received
3773177 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 260 | 1 | threaded union conical joint iron to iron f size 1" UL LISTED,FM APPROVED |  | Each | 4 | 59600467 |  |  |  | threaded union conical joint iron to iron f size 1" UL LISTED,FM APPROVED | 060010140596 | MEP | Received | 2023-01-28 | Accounted transaction received
3773178 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4955.58 | 1 | Clevis Hanger size 1'' |  | Each | 180 | 59600468 |  |  |  | Clevis Hanger size 1'' | 060191200003 | MEP | Received | 2023-01-28 | Accounted transaction received
3773179 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1153.68 | 1 | Clevis Hanger size 1.25 '' |  | Each | 40 | 59600469 |  |  |  | Clevis Hanger size 1.25 '' | 060191200004 | MEP | Received | 2023-01-28 | Accounted transaction received
3773180 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1022.58 | 1 | Clevis Hanger size 1.5'' |  | Each | 30 | 59600470 |  |  |  | Clevis Hanger size 1.5'' | 060191200005 | MEP | Received | 2023-01-28 | Accounted transaction received
3773181 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1085.85 | 1 | Clevis Hanger size 2'' |  | Each | 30 | 59600471 |  |  |  | Clevis Hanger size 2'' | 060191200006 | MEP | Received | 2023-01-28 | Accounted transaction received
3773182 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1995 | 1 | Clevis Hanger size 2.5'' |  | Each | 40 | 59600472 |  |  |  | Clevis Hanger size 2.5'' | 060191200007 | MEP | Received | 2023-01-28 | Accounted transaction received
3773183 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 934.8 | 1 | Clevis Hanger size 3'' |  | Each | 10 | 59600473 |  |  |  | Clevis Hanger size 3'' | 060191200008 | MEP | Received | 2023-01-28 | Accounted transaction received
3773184 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 690.84 | 1 | Clevis Hanger size 4'' |  | Each | 6 | 59600474 |  |  |  | Clevis Hanger size 4'' | 060191200010 | MEP | Received | 2023-01-28 | Accounted transaction received
3773185 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1607.4 | 1 | Standard hex bolt size M8 length 3 cm |  | Kilogram | 30 | 59600475 |  |  |  | Standard hex bolt size M8 length 3 cm | 061900700149 | MEP | Received | 2023-01-28 | Accounted transaction received
3773186 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 570 | 1 | جلبة تطويل تيش 8 مم |  | Each | 100 | 59600476 |  |  |  | جلبة تطويل تيش 8 مم | 060190300022 | MEP | Received | 2023-01-28 | Accounted transaction received
3773187 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 855 | 1 | جلبة تطويل تيش 10 مم |  | Each | 100 | 59600477 |  |  |  | جلبة تطويل تيش 10 مم | 060190300023 | MEP | Received | 2023-01-28 | Accounted transaction received
3773188 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 31799.98 | 1 | Flush plate for New Suites For flush actuation with Geberit Alphaconcealed cisterns - White Alpine Code : 115.060.11.1 |  | Each | 12 | 59600478 |  |  |  | Flush plate for New Suites For flush actuation with Geberit Alphaconcealed cisterns - White Alpine Code : 115.060.11.1 | 060030200050 | MEP | Received | 2023-01-28 | Accounted transaction received
3773189 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 78392.31 | 1 | Barcelona 1700 bathtub , Model No. BA2-N-SW-NO |  | Each | 1 | 59600479 |  |  |  | Barcelona 1700 bathtub , Model No. BA2-N-SW-NO | 060030300360 | MEP | Received | 2023-01-28 | Accounted transaction received
3773190 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4632.39 | 1 | Kit 36 intelli-waste, with overflow function, chrome , Model No. K-36-PC |  | Each | 1 | 59600480 |  |  |  | Kit 36 intelli-waste, with overflow function, chrome , Model No. K-36-PC | 060030300361 | MEP | Received | 2023-01-28 | Accounted transaction received
3773191 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2154.6 | 1 | Antislip coating to bathtub ( A Pattern ) |  | Each | 1 | 59600481 |  |  |  | Antislip coating to bathtub ( A Pattern ) | 060030300362 | MEP | Received | 2023-01-28 | Accounted transaction received
3773192 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1512 | 1 | رزمة ورق تصوير A3 |  | Each | 16 | 59600624 |  |  |  | رزمة ورق تصوير A3 | 910020000001 | Administration | Received | 2023-01-28 | Accounted transaction received
3773193 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 5040 | 1 | رزمة ورق تصوير باور A4 |  | Each | 35 | 59600625 |  |  |  | رزمة ورق تصوير باور A4 | 910020000002 | Administration | Received | 2023-01-28 | Accounted transaction received
3773194 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2280 | 1 | تيب دوكو |  | Each | 80 | 59600716 |  |  |  | تيب دوكو | 200010000048 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773195 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 598.5 | 1 | سكينة معجون صغيرة |  | Each | 15 | 59600717 |  |  |  | سكينة معجون صغيرة | 200010000081 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773196 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2394 | 1 | اسمنت ابيض |  | Ton | 0.7 | 59600718 |  |  |  | اسمنت ابيض | 140010000001 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773197 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 90 | 1 | بنطة هيلتي 8 مم بلس |  | Each | 2 | 59600719 |  |  |  | بنطة هيلتي 8 مم بلس | 200010000320 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773198 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 150 | 1 | بنطة هيلتي 10 مم بلس |  | Each | 2 | 59600720 |  |  |  | بنطة هيلتي 10 مم بلس | 200010000321 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773199 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 170 | 1 | بنطة هيلتي 12 مم بلس |  | Each | 2 | 59600721 |  |  |  | بنطة هيلتي 12 مم بلس | 200010000322 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773200 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 769.5 | 1 | فوطة صفراء |  | Each | 15 | 59600722 |  |  |  | فوطة صفراء | 200010000478 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773201 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3319.93 | 1 | مسمار سن صاج |  | Each | 9398 | 59600723 |  |  |  | مسمار سن صاج | 200020000237 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773202 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 300 | 1 | سلك شبك مقاس 6*6*4مم |  | Meter | 1.5 | 59600724 |  |  |  | سلك شبك مقاس 6*6*4مم | 150050000014 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773203 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2251.5 | 1 | مشمع اسود حفيف |  | Roll | 2 | 59600725 |  |  |  | مشمع اسود حفيف | 040010000055 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773204 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 150 | 1 | لمبة فلورسنت120سم |  | Each | 2 | 59600726 |  |  |  | لمبة فلورسنت120سم | 030040200004 | MEP | Received | 2023-01-28 | Accounted transaction received
3773205 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 804.66 | 1 | سيتوسيل 400 أبيض |  | Each | 6 | 59600727 |  |  |  | سيتوسيل 400 أبيض | 050010000066 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773206 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 225 | 1 | كالون الأهرام |  | Each | 1 | 59600728 |  |  |  | كالون الأهرام | 250010000172 | Procurement | Received | 2023-01-28 | Accounted transaction received
3773207 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 11.4 | 1 | معجون دهان GLC |  | Can | 1 | 59600729 |  |  |  | معجون دهان GLC | 050010000113 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773208 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-19 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 29.43 | 1 | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 |  | Each | 1 | 59603090 |  |  |  | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 | 030060100021 | MEP | Received | 2023-01-28 | Accounted transaction received
3773209 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-19 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1306.58 | 1 | HDMI PRE-CONN 1M Code 572596 |  | Each | 1 | 59603091 |  |  |  | HDMI PRE-CONN 1M Code 572596 | 030060100165 | MEP | Received | 2023-01-28 | Accounted transaction received
3773210 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-19 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 109.96 | 1 | TV - SINGLE SHIELDED "F" TYPE - 0-2400 HZ - 1 MOD Code 572163 |  | Each | 1 | 59603092 |  |  |  | TV - SINGLE SHIELDED "F" TYPE - 0-2400 HZ - 1 MOD Code 572163 | 030060100029 | MEP | Received | 2023-01-28 | Accounted transaction received
3773211 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-19 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1256.62 | 1 | 10A INTERMEDIATE SWITCH 1 MOD MAGNESIUM Code 572508 |  | Each | 6 | 59603093 |  |  |  | 10A INTERMEDIATE SWITCH 1 MOD MAGNESIUM Code 572508 | 030060100126 | MEP | Received | 2023-01-28 | Accounted transaction received
3773212 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-19 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1266.66 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 100 | 59603094 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-01-28 | Accounted transaction received
3773213 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-19 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1549.49 | 1 | PLATE 1SQ MOD SCH GRAPHITE Code 576552 |  | Each | 40 | 59603095 |  |  |  | PLATE 1SQ MOD SCH GRAPHITE Code 576552 | 030060100297 | MEP | Received | 2023-01-28 | Accounted transaction received
3773214 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-19 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4912.07 | 1 | 576562 Code وش مربع فضي |  | Each | 150 | 59603096 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-01-28 | Accounted transaction received
3773215 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-19 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 80.25 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 1 | 59603097 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-01-28 | Accounted transaction received
3773216 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-19 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2116.84 | 1 | Plate British standard Arteor - square - 3 modules - graphite - 575072 |  | Each | 36 | 59603098 |  |  |  | Plate British standard Arteor - square - 3 modules - graphite - 575072 | 030060100898 | MEP | Received | 2023-01-28 | Accounted transaction received
3773217 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-19 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 56.54 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 1 | 59603099 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-01-28 | Accounted transaction received
3773218 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-19 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 754.57 | 1 | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 |  | Each | 1 | 59603100 |  |  |  | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 | 030060100957 | MEP | Received | 2023-01-28 | Accounted transaction received
3773219 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 159.6 | 1 | كتر |  | Each | 4 | 59364637 |  |  |  | كتر | 200010000182 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773220 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 855 | 1 | لصق تيب بنى |  | Each | 30 | 59364638 |  |  |  | لصق تيب بنى | 200010000202 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773221 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 159.6 | 1 | بنطة هيلتي 6 مم بلس |  | Each | 4 | 59364639 |  |  |  | بنطة هيلتي 6 مم بلس | 200010000319 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773222 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1539 | 1 | تيب مسلح |  | Each | 30 | 59364640 |  |  |  | تيب مسلح | 200010000382 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773223 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 120 | 1 | ملمع خشب |  | Each | 5 | 59364641 |  |  |  | ملمع خشب | 200010000897 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773225 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 275 | 1 | سلك الومنيوم-مواعين |  | Roll | 5 | 59364643 |  |  |  | سلك الومنيوم-مواعين | 700020000044 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773226 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 7866 | 1 | زاوية حديد 5 * 5 * 5 مم مجلفنة |  | Meter | 30 | 59364707 |  |  |  | زاوية حديد 5 * 5 * 5 مم مجلفنة | 060190900061 | MEP | Received | 2023-01-28 | Accounted transaction received
3773227 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 29754 | 1 | زاوية حديد 4 * 4 * 4 مم مجلفنة |  | Meter | 180 | 59364708 |  |  |  | زاوية حديد 4 * 4 * 4 مم مجلفنة | 060190900060 | MEP | Received | 2023-01-28 | Accounted transaction received
3773228 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2023-01-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 378 | 1 | رزمة ورق تصوير A3 |  | Each | 4 | 59364771 |  |  |  | رزمة ورق تصوير A3 | 910020000001 | Administration | Received | 2023-01-28 | Accounted transaction received
3773229 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2023-01-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 720 | 1 | رزمة ورق تصوير باور A4 |  | Each | 5 | 59364772 |  |  |  | رزمة ورق تصوير باور A4 | 910020000002 | Administration | Received | 2023-01-28 | Accounted transaction received
3773230 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-01-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 403.85 | 1 | Shell RimR3X 20w50 - زيت شل |  | Liter | 7 | 59364833 |  |  |  | Shell RimR3X 20w50 - زيت شل | 340020000068 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773231 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-01-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 43989.4 | 1 | Wall covering WC-2 Cole & Son-Feather Fan 89/4015 |  | Roll | 20 | 59366398 |  |  |  | Wall covering WC-2 Cole & Son-Feather Fan 89/4015 | 050020000012 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773232 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-01-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 103375.09 | 1 | Wall covering WC-2 Cole & Son-Feather Fan 89/4015 |  | Roll | 47 | 59366399 |  |  |  | Wall covering WC-2 Cole & Son-Feather Fan 89/4015 | 050020000012 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773233 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1550.4 | 1 | فلكسيبل معدن المقاس ¾ " |  | Meter | 25 | 59369642 |  |  |  | فلكسيبل معدن المقاس ¾ " | 030020100091 | MEP | Received | 2023-01-28 | Accounted transaction received
3773234 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 920.66 | 1 | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) |  | Meter | 60 | 59369643 |  |  |  | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) | 030010000052 | MEP | Received | 2023-01-28 | Accounted transaction received
3773235 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 661.33 | 1 | سلك نحاس مصمت مقاس 1.5 مم اللون أحمر (cu/pvc) جهد (750/450) |  | Meter | 100 | 59369644 |  |  |  | سلك نحاس مصمت مقاس 1.5 مم اللون أحمر (cu/pvc) جهد (750/450) | 030030100247 | MEP | Received | 2023-01-28 | Accounted transaction received
3773236 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 369.29 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 25مم وقطر خارجى 31.1مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 1 | 59369645 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 25مم وقطر خارجى 31.1مم طول اللفه 30 متر(اللون رمادى) | 030010000062 | MEP | Received | 2023-01-28 | Accounted transaction received
3773237 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1175.79 | 1 | سلك نحاس مصمت مقاس 1.5 مم اللون أسود (cu/pvc) جهد (750/450) |  | Meter | 200 | 59369646 |  |  |  | سلك نحاس مصمت مقاس 1.5 مم اللون أسود (cu/pvc) جهد (750/450) | 030030100253 | MEP | Received | 2023-01-28 | Accounted transaction received
3773238 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2859.76 | 1 | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 |  | Meter | 30.5 | 59369647 |  |  |  | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 | 030020100002 | MEP | Received | 2023-01-28 | Accounted transaction received
3773239 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 8272.98 | 1 | ماسورة صلب مجلفن EMT المقاس 1 " طول الماسورة 3.05 |  | Meter | 61.5 | 59369648 |  |  |  | ماسورة صلب مجلفن EMT المقاس 1 " طول الماسورة 3.05 | 030020100003 | MEP | Received | 2023-01-28 | Accounted transaction received
3773240 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 9613.9 | 1 | ماسورة صلب مجلفن EMT المقاس 2 " طول الماسورة 3.05 |  | Meter | 21.35 | 59369649 |  |  |  | ماسورة صلب مجلفن EMT المقاس 2 " طول الماسورة 3.05 | 030020100005 | MEP | Received | 2023-01-28 | Accounted transaction received
3773241 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 747.84 | 1 | جلبة ماسورة EMT المقاس 2 " |  | Each | 10 | 59369650 |  |  |  | جلبة ماسورة EMT المقاس 2 " | 030020100025 | MEP | Received | 2023-01-28 | Accounted transaction received
3773242 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 353.26 | 1 | مسمار سن صاج |  | Each | 1000 | 59369651 |  |  |  | مسمار سن صاج | 200020000237 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773243 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 570.31 | 1 | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 |  | Each | 30 | 59369652 |  |  |  | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 | 150020000178 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773244 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 35 | 1 | كوع بباب UPVC مقاس 75 مم رمادى بجوان |  | Each | 1 | 59371028 |  |  |  | كوع بباب UPVC مقاس 75 مم رمادى بجوان | 060010100092 | MEP | Received | 2023-01-28 | Accounted transaction received
3773245 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 250 | 1 | فلانشة حديد½1'' - PN 16 |  | Each | 2 | 59371029 |  |  |  | فلانشة حديد½1'' - PN 16 | 060011800042 | MEP | Received | 2023-01-28 | Accounted transaction received
3773246 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 80 | 1 | مسمار صلب مجلفن 24 * 120 بالصامولة + الوردتين |  | Each | 8 | 59371030 |  |  |  | مسمار صلب مجلفن 24 * 120 بالصامولة + الوردتين | 061900700217 | MEP | Received | 2023-01-28 | Accounted transaction received
3773247 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 6 | 1 | جوان مبطط 1.5 |  | Each | 3 | 59371031 |  |  |  | جوان مبطط 1.5 | 060019000080 | MEP | Received | 2023-01-28 | Accounted transaction received
3773248 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 212.5 | 1 | خواشة 25 مم |  | Each | 1 | 59371111 |  |  |  | خواشة 25 مم | 200010000649 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773249 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 297.5 | 1 | خواشة تفتيح رخام 4" |  | Each | 1 | 59371112 |  |  |  | خواشة تفتيح رخام 4" | 200010001609 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773250 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 255 | 1 | خواشة 30 مم |  | Each | 1 | 59371113 |  |  |  | خواشة 30 مم | 200010002034 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773251 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 8173.23 | 1 | بولي ايثيلين 200 ميكرون شفاف |  | Kilogram | 110.3 | 59371182 |  |  |  | بولي ايثيلين 200 ميكرون شفاف | 040010000042 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773252 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1341.1 | 1 | سيتوسيل 400 أبيض |  | Each | 10 | 59371183 |  |  |  | سيتوسيل 400 أبيض | 050010000066 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773253 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 45 | 1 | قفل عادى |  | Each | 1 | 59371184 |  |  |  | قفل عادى | 039020100060 | MEP | Received | 2023-01-28 | Accounted transaction received
3773254 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-01-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 43989.4 | 1 | Wall covering WC-2 Cole & Son-Feather Fan 89/4015 |  | Roll | 20 | 59459331 |  |  |  | Wall covering WC-2 Cole & Son-Feather Fan 89/4015 | 050020000012 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773255 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-01-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 39590.46 | 1 | Wall covering WC-2 Cole & Son-Feather Fan 89/4015 |  | Roll | 18 | 59459332 |  |  |  | Wall covering WC-2 Cole & Son-Feather Fan 89/4015 | 050020000012 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773256 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-01-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 271006.87 | 1 | Ceramic Fan Shape Wall Tiles FS-026 |  | Square Meter | 201.7 | 59460325 |  |  |  | Ceramic Fan Shape Wall Tiles FS-026 | 170010000549 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773257 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 260.17 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 4 | 59460821 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-01-28 | Accounted transaction received
3773258 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 195.12 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 3 | 59460822 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-01-28 | Accounted transaction received
3773259 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 216.19 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 2 | 59460823 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-01-28 | Accounted transaction received
3773260 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 25.33 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 2 | 59460824 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-01-28 | Accounted transaction received
3773261 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 35.35 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 2 | 59460825 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-01-28 | Accounted transaction received
3773262 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 53.03 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 3 | 59460826 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-01-28 | Accounted transaction received
3773263 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 172.23 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 4 | 59460827 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-01-28 | Accounted transaction received
3773264 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 86.12 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 2 | 59460828 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-01-28 | Accounted transaction received
3773265 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 235.2 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 4 | 59460829 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-01-28 | Accounted transaction received
3773266 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 117.6 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 2 | 59460830 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-01-28 | Accounted transaction received
3773267 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 58.8 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 1 | 59460831 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-01-28 | Accounted transaction received
3773268 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 70 | 1 | COVER 4 M SQUARE 2X2 WHITE F 576000 Code 575080 |  | Each | 1 | 59460832 |  |  |  | COVER 4 M SQUARE 2X2 WHITE F 576000 Code 575080 | 030060100231 | MEP | Received | 2023-01-28 | Accounted transaction received
3773269 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1450 | 1 | FLOOR BOX 12 MOD code CB3 |  | Each | 1 | 59460833 |  |  |  | FLOOR BOX 12 MOD code CB3 | 030060100533 | MEP | Received | 2023-01-28 | Accounted transaction received
3773270 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 201.88 | 1 | CARRIER PLATE SYNERGY code 730094 |  | Each | 3 | 59460834 |  |  |  | CARRIER PLATE SYNERGY code 730094 | 030060100534 | MEP | Received | 2023-01-28 | Accounted transaction received
3773271 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 226.18 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 4 | 59460835 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-01-28 | Accounted transaction received
3773272 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 113.09 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 2 | 59460836 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-01-28 | Accounted transaction received
3773273 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 142891.88 | 1 | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² |  | Kilogram | 2625 | 59462644 |  |  |  | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² | 060040200001 | MEP | Received | 2023-01-28 | Accounted transaction received
3773274 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1852.5 | 1 | كورنر (TDF) |  | Each | 500 | 59462645 |  |  |  | كورنر (TDF) | 060040200002 | MEP | Received | 2023-01-28 | Accounted transaction received
3773275 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 591090 | 1 | Vanity mirror; polished low iron clear GL-1; with brass frame MT-1; including all necessary accessories; preparations; Bathroom Materials: Brass special profile 10x20mm 6mm Mirror - 2cm edge chamfer 8mm Moisture proof plywood Dimensions |  | Each | 61 | 59464823 |  |  |  | Vanity mirror; polished low iron clear GL-1; with brass frame MT-1; including all necessary accessories; preparations; Bathroom Materials: Brass special profile 10x20mm 6mm Mirror - 2cm edge chamfer 8mm Moisture proof plywood Dimensions | 250010001361 | Procurement | Received | 2023-01-28 | Accounted transaction received
3773276 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 61446 | 1 | Hardware accessories for doors HW-03 Towel Rail for Vanities MT-1 |  | Each | 49 | 59464824 |  |  |  | Hardware accessories for doors HW-03 Towel Rail for Vanities MT-1 | 250010001549 | Procurement | Received | 2023-01-28 | Accounted transaction received
3773277 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 18468 | 1 | Hardware accessories for doors HW-102 Knob for Minibar |  | Each | 81 | 59464825 |  |  |  | Hardware accessories for doors HW-102 Knob for Minibar | 250010001569 | Procurement | Received | 2023-01-28 | Accounted transaction received
3773278 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 68.35 | 1 | أفيز هانجر EMT المقاس 2 " |  | Each | 4 | 59465036 |  |  |  | أفيز هانجر EMT المقاس 2 " | 030020100080 | MEP | Received | 2023-01-28 | Accounted transaction received
3773279 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2876.22 | 1 | ماسورة 32مم UPVC سمك ثقيل قطر خارجي 32 قطر داخلي 26.6مم اللفة= 15×3 متر(اللون أبيض) |  | Meter | 135 | 59465037 |  |  |  | ماسورة 32مم UPVC سمك ثقيل قطر خارجي 32 قطر داخلي 26.6مم اللفة= 15×3 متر(اللون أبيض) | 030010000054 | MEP | Received | 2023-01-28 | Accounted transaction received
3773280 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 661.33 | 1 | سلك نحاس مصمت مقاس 1.5 مم اللون أحمر (cu/pvc) جهد (750/450) |  | Meter | 100 | 59465038 |  |  |  | سلك نحاس مصمت مقاس 1.5 مم اللون أحمر (cu/pvc) جهد (750/450) | 030030100247 | MEP | Received | 2023-01-28 | Accounted transaction received
3773281 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 8.14 | 1 | جلبة ماسورة 32مم UPVC (اللون أبيض) |  | Each | 2 | 59465039 |  |  |  | جلبة ماسورة 32مم UPVC (اللون أبيض) | 030010000069 | MEP | Received | 2023-01-28 | Accounted transaction received
3773282 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 277.76 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 1 | 59465040 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) | 030010000059 | MEP | Received | 2023-01-28 | Accounted transaction received
3773283 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 555.51 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 2 | 59465041 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) | 030010000059 | MEP | Received | 2023-01-28 | Accounted transaction received
3773284 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 587.89 | 1 | سلك نحاس مصمت مقاس 1.5 مم اللون أسود (cu/pvc) جهد (750/450) |  | Meter | 100 | 59465042 |  |  |  | سلك نحاس مصمت مقاس 1.5 مم اللون أسود (cu/pvc) جهد (750/450) | 030030100253 | MEP | Received | 2023-01-28 | Accounted transaction received
3773285 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 13.02 | 1 | أدابتور UPVC لماسورة 32مم(اللون أبيض) |  | Each | 1 | 59465043 |  |  |  | أدابتور UPVC لماسورة 32مم(اللون أبيض) | 030010000098 | MEP | Received | 2023-01-28 | Accounted transaction received
3773286 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 211.58 | 1 | جلاند فلكسبل مقاس 16 مم |  | Each | 32 | 59465044 |  |  |  | جلاند فلكسبل مقاس 16 مم | 030010000167 | MEP | Received | 2023-01-28 | Accounted transaction received
3773287 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 347.42 | 1 | جلاند فلكسبل مقاس 25 مم |  | Each | 25 | 59465045 |  |  |  | جلاند فلكسبل مقاس 25 مم | 030010000170 | MEP | Received | 2023-01-28 | Accounted transaction received
3773288 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 349.12 | 1 | بواط واتر بروف بفتحات مقاس 19 × 24 × 9 سم |  | Each | 2 | 59465046 |  |  |  | بواط واتر بروف بفتحات مقاس 19 × 24 × 9 سم | 030010000183 | MEP | Received | 2023-01-28 | Accounted transaction received
3773289 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 349.12 | 1 | بواط واتر بروف بفتحات مقاس 19 × 24 × 9 سم |  | Each | 2 | 59465047 |  |  |  | بواط واتر بروف بفتحات مقاس 19 × 24 × 9 سم | 030010000183 | MEP | Received | 2023-01-28 | Accounted transaction received
3773290 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5719.51 | 1 | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 |  | Meter | 61 | 59465048 |  |  |  | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 | 030020100002 | MEP | Received | 2023-01-28 | Accounted transaction received
3773291 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 8240.49 | 1 | ماسورة صلب مجلفن EMT المقاس 2 " طول الماسورة 3.05 |  | Meter | 18.3 | 59465049 |  |  |  | ماسورة صلب مجلفن EMT المقاس 2 " طول الماسورة 3.05 | 030020100005 | MEP | Received | 2023-01-28 | Accounted transaction received
3773292 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2746.83 | 1 | ماسورة صلب مجلفن EMT المقاس 2 " طول الماسورة 3.05 |  | Meter | 6.1 | 59465050 |  |  |  | ماسورة صلب مجلفن EMT المقاس 2 " طول الماسورة 3.05 | 030020100005 | MEP | Received | 2023-01-28 | Accounted transaction received
3773293 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2746.83 | 1 | ماسورة صلب مجلفن EMT المقاس 2 " طول الماسورة 3.05 |  | Meter | 6.1 | 59465051 |  |  |  | ماسورة صلب مجلفن EMT المقاس 2 " طول الماسورة 3.05 | 030020100005 | MEP | Received | 2023-01-28 | Accounted transaction received
3773294 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1495.68 | 1 | جلبة ماسورة EMT المقاس 2 " |  | Each | 20 | 59465052 |  |  |  | جلبة ماسورة EMT المقاس 2 " | 030020100025 | MEP | Received | 2023-01-28 | Accounted transaction received
3773295 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 130.08 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 2 | 59465053 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-01-28 | Accounted transaction received
3773296 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 86.12 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 2 | 59465054 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-01-28 | Accounted transaction received
3773297 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 70 | 1 | PLATE 2SQ MOD F-G WHITE Code 576560 |  | Each | 2 | 59465055 |  |  |  | PLATE 2SQ MOD F-G WHITE Code 576560 | 030060100267 | MEP | Received | 2023-01-28 | Accounted transaction received
3773298 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 70 | 1 | PLATE 2SQ MOD F-G WHITE Code 576560 |  | Each | 2 | 59465056 |  |  |  | PLATE 2SQ MOD F-G WHITE Code 576560 | 030060100267 | MEP | Received | 2023-01-28 | Accounted transaction received
3773299 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1162.12 | 1 | PLATE 1SQ MOD SCH GRAPHITE Code 576552 |  | Each | 30 | 59465057 |  |  |  | PLATE 1SQ MOD SCH GRAPHITE Code 576552 | 030060100297 | MEP | Received | 2023-01-28 | Accounted transaction received
3773300 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 6174.13 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 105 | 59465058 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-01-28 | Accounted transaction received
3773301 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 9644.71 | 1 | SHAVER SOCKET 230V/120-230V WITH EARTH CONNECTOR Code 572653 |  | Each | 14 | 59465059 |  |  |  | SHAVER SOCKET 230V/120-230V WITH EARTH CONNECTOR Code 572653 | 030060100178 | MEP | Received | 2023-01-28 | Accounted transaction received
3773302 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3929.65 | 1 | 576562 Code وش مربع فضي |  | Each | 120 | 59465060 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-01-28 | Accounted transaction received
3773303 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 401.85 | 1 | Standard flat washers size 10M |  | Kilogram | 10 | 59465061 |  |  |  | Standard flat washers size 10M | 060190500003 | MEP | Received | 2023-01-28 | Accounted transaction received
3773304 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 971.28 | 1 | Standard hex nuts size M10 |  | Kilogram | 15 | 59465062 |  |  |  | Standard hex nuts size M10 | 060190600003 | MEP | Received | 2023-01-28 | Accounted transaction received
3773305 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4286.4 | 1 | Threaded rod size M10 |  | Each | 100 | 59465063 |  |  |  | Threaded rod size M10 | 060190300003 | MEP | Received | 2023-01-28 | Accounted transaction received
3773306 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 244.53 | 1 | مسامير تك طول 1.5 سم |  | Kilogram | 2 | 59465064 |  |  |  | مسامير تك طول 1.5 سم | 060191210001 | MEP | Received | 2023-01-28 | Accounted transaction received
3773307 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 558.6 | 1 | مسامير سيلف دريل 5مم طول 2سم |  | Kilogram | 2 | 59465065 |  |  |  | مسامير سيلف دريل 5مم طول 2سم | 060191210007 | MEP | Received | 2023-01-28 | Accounted transaction received
3773308 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 304.17 | 1 | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 |  | Each | 16 | 59465066 |  |  |  | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 | 150020000178 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773309 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 661.2 | 1 | جلبة تطويل تيش 8 مم |  | Each | 200 | 59465067 |  |  |  | جلبة تطويل تيش 8 مم | 060190300022 | MEP | Received | 2023-01-28 | Accounted transaction received
3773310 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 718.2 | 1 | جلبة تطويل تيش 10 مم |  | Each | 200 | 59465068 |  |  |  | جلبة تطويل تيش 10 مم | 060190300023 | MEP | Received | 2023-01-28 | Accounted transaction received
3773311 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 16.3 | 1 | Metal Galvanized back box 5x10 cm with deep 47 mm |  | Each | 1 | 59465069 |  |  |  | Metal Galvanized back box 5x10 cm with deep 47 mm | 030069000028 | MEP | Received | 2023-01-28 | Accounted transaction received
3773312 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3175.26 | 1 | Plate British standard Arteor - square - 3 modules - graphite - 575072 |  | Each | 54 | 59465070 |  |  |  | Plate British standard Arteor - square - 3 modules - graphite - 575072 | 030060100898 | MEP | Received | 2023-01-28 | Accounted transaction received
3773313 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 21400.29 | 1 | Acolyte - ARB95SWBC203. 027 - Rapid Ribbon 95+ - LED Strip with 9.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser |  | Each | 50 | 59465071 |  |  |  | Acolyte - ARB95SWBC203. 027 - Rapid Ribbon 95+ - LED Strip with 9.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser | 030040700471 | MEP | Received | 2023-01-28 | Accounted transaction received
3773314 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 21400.29 | 1 | Acolyte - ARB95SWBC203. 027 - Rapid Ribbon 95+ - LED Strip with 9.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser |  | Each | 50 | 59465072 |  |  |  | Acolyte - ARB95SWBC203. 027 - Rapid Ribbon 95+ - LED Strip with 9.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser | 030040700471 | MEP | Received | 2023-01-28 | Accounted transaction received
3773315 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 38397.35 | 1 | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser |  | Each | 100 | 59465073 |  |  |  | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser | 030040700472 | MEP | Received | 2023-01-28 | Accounted transaction received
3773316 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 28798.01 | 1 | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser |  | Each | 75 | 59465074 |  |  |  | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser | 030040700472 | MEP | Received | 2023-01-28 | Accounted transaction received
3773317 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1080.75 | 1 | Driver Tridonic - 87500852 - Essence series - Driver LC 35W 24V SC 24 V – not dimmable (IP20) |  | Each | 3 | 59465075 |  |  |  | Driver Tridonic - 87500852 - Essence series - Driver LC 35W 24V SC 24 V – not dimmable (IP20) | 030040700475 | MEP | Received | 2023-01-28 | Accounted transaction received
3773318 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4845 | 1 | Connector for Led strip - Acolyte |  | Each | 100 | 59465076 |  |  |  | Connector for Led strip - Acolyte | 030040700476 | MEP | Received | 2023-01-28 | Accounted transaction received
3773319 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2422.5 | 1 | Connector for Led strip - Acolyte |  | Each | 50 | 59465077 |  |  |  | Connector for Led strip - Acolyte | 030040700476 | MEP | Received | 2023-01-28 | Accounted transaction received
3773320 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3323.74 | 1 | LT.02-Pendant Circular luminaire Ring connected to 220v mains using AC/DC Driver, the luminaire- made of cast Aluminum. Polycarbonate diffuser ensures the diffusivity of the light giving a smooth sensation without any hot or dark spots. |  | Each | 1 | 59465078 |  |  |  | LT.02-Pendant Circular luminaire Ring connected to 220v mains using AC/DC Driver, the luminaire- made of cast Aluminum. Polycarbonate diffuser ensures the diffusivity of the light giving a smooth sensation without any hot or dark spots. | 030040700491 | MEP | Received | 2023-01-28 | Accounted transaction received
3773321 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4268.16 | 1 | DAL - 30150 - AMBIANCE 100 - Recessed fixed down lighter with satin silver reflector and white ceiling trim. Overall diameter 100mm, cut out IP 65 diameter 90mm, with PHILIPS LED Lamp 5.5W MR16 GU5.3, 2700K |  | Each | 1 | 59465079 |  |  |  | DAL - 30150 - AMBIANCE 100 - Recessed fixed down lighter with satin silver reflector and white ceiling trim. Overall diameter 100mm, cut out IP 65 diameter 90mm, with PHILIPS LED Lamp 5.5W MR16 GU5.3, 2700K | 030040600115 | MEP | Received | 2023-01-28 | Accounted transaction received
3773322 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-01-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 8797.88 | 1 | Wall covering WC-2 Cole & Son-Feather Fan 89/4015 |  | Roll | 4 | 59466141 |  |  |  | Wall covering WC-2 Cole & Son-Feather Fan 89/4015 | 050020000012 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773323 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-15 | Materials |  |  |  | Materials | Alrowad Construction_OU | -142891.88 | 1 | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² |  | Kilogram | -2625 | 59523580 |  |  |  | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² | 060040200001 | MEP | Received | 2023-01-28 | Accounted transaction received
3773324 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-15 | Materials |  |  |  | Materials | Alrowad Construction_OU | -1852.5 | 1 | كورنر (TDF) |  | Each | -500 | 59523581 |  |  |  | كورنر (TDF) | 060040200002 | MEP | Received | 2023-01-28 | Accounted transaction received
3773325 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2023-01-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 378 | 1 | رزمة ورق تصوير A3 |  | Each | 4 | 59189823 |  |  |  | رزمة ورق تصوير A3 | 910020000001 | Administration | Received | 2023-01-28 | Accounted transaction received
3773326 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 180.31 | 1 | جردل حريق |  | Each | 8 | 59189989 |  |  |  | جردل حريق | 220010000005 | MEP | Received | 2023-01-28 | Accounted transaction received
3773327 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1607.4 | 1 | جوانتي باور جراب |  | Each | 30 | 59189990 |  |  |  | جوانتي باور جراب | 010010000009 | Safety | Received | 2023-01-28 | Accounted transaction received
3773328 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1140 | 1 | نظارة يوفكس سوداء |  | Each | 20 | 59189991 |  |  |  | نظارة يوفكس سوداء | 010060000009 | Safety | Received | 2023-01-28 | Accounted transaction received
3773329 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 759.97 | 1 | جوانتى طبى |  | Box | 4 | 59189992 |  |  |  | جوانتى طبى | 010010000011 | Safety | Received | 2023-01-28 | Accounted transaction received
3773330 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 855 | 1 | تيب دوكو |  | Each | 30 | 59190117 |  |  |  | تيب دوكو | 200010000048 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773331 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 82 | 1 | صابون سائل |  | Can | 4 | 59190118 |  |  |  | صابون سائل | 700020000013 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773332 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 120 | 1 | بنطة هيلتي 6 مم بلس |  | Each | 4 | 59190119 |  |  |  | بنطة هيلتي 6 مم بلس | 200010000319 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773333 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 769.5 | 1 | فوطة صفراء |  | Each | 15 | 59190120 |  |  |  | فوطة صفراء | 200010000478 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773334 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 748.09 | 1 | سيتوكس يو رمادي |  | Bag | 6 | 59190121 |  |  |  | سيتوكس يو رمادي | 360010000131 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773335 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 364.8 | 1 | تنر |  | Each | 4 | 59190122 |  |  |  | تنر | 060019000008 | MEP | Received | 2023-01-28 | Accounted transaction received
3773336 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 570 | 1 | سلك مواعين |  | Kilogram | 10 | 59190123 |  |  |  | سلك مواعين | 700020000122 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773337 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-01-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 105574.56 | 1 | Wall covering WC-2 Cole & Son-Feather Fan 89/4015 |  | Roll | 48 | 59190620 |  |  |  | Wall covering WC-2 Cole & Son-Feather Fan 89/4015 | 050020000012 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773338 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 550.62 | 1 | Clevis Hanger size 1'' |  | Each | 20 | 59191293 |  |  |  | Clevis Hanger size 1'' | 060191200003 | MEP | Received | 2023-01-28 | Accounted transaction received
3773339 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 288.42 | 1 | Clevis Hanger size 1.25 '' |  | Each | 10 | 59191294 |  |  |  | Clevis Hanger size 1.25 '' | 060191200004 | MEP | Received | 2023-01-28 | Accounted transaction received
3773340 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 340.86 | 1 | Clevis Hanger size 1.5'' |  | Each | 10 | 59191295 |  |  |  | Clevis Hanger size 1.5'' | 060191200005 | MEP | Received | 2023-01-28 | Accounted transaction received
3773341 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 361.95 | 1 | Clevis Hanger size 2'' |  | Each | 10 | 59191296 |  |  |  | Clevis Hanger size 2'' | 060191200006 | MEP | Received | 2023-01-28 | Accounted transaction received
3773342 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 29000 | 1 | HVAC Pump Model : TP 40-100/4 A-F-B-BAQE-EX3 - 18 GPM @ 25 ft |  | Each | 1 | 59191297 |  |  |  | HVAC Pump Model : TP 40-100/4 A-F-B-BAQE-EX3 - 18 GPM @ 25 ft | 060180000020 | MEP | Received | 2023-01-28 | Accounted transaction received
3773343 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 92.79 | 1 | فدية خرسانة 5 بوصة |  | Each | 3 | 59191664 |  |  |  | فدية خرسانة 5 بوصة | 200010000431 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773344 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 456.27 | 1 | فدية خرسانة 9 بوصة |  | Each | 5 | 59191665 |  |  |  | فدية خرسانة 9 بوصة | 200010000433 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773345 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 571.96 | 1 | نهاية بياض 10 مم |  | Each | 20 | 59191666 |  |  |  | نهاية بياض 10 مم | 200010000462 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773346 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1057.65 | 1 | Hardware Accessories for Wooden Doors Standard Floor Door Stop for BOH Side Door Stoper Size: 29x40(H)mm Material: Stainless steel 304 Finish: Satin finish Welder DDS007 S.S.S |  | Each | 8 | 59191667 |  |  |  | Hardware Accessories for Wooden Doors Standard Floor Door Stop for BOH Side Door Stoper Size: 29x40(H)mm Material: Stainless steel 304 Finish: Satin finish Welder DDS007 S.S.S | 250010001524 | Procurement | Received | 2023-01-28 | Accounted transaction received
3773347 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 6294.62 | 1 | شاسيه صاج 4 مم طول 3 متر |  | Each | 22 | 59191668 |  |  |  | شاسيه صاج 4 مم طول 3 متر | 150020000939 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773348 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 920.66 | 1 | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) |  | Meter | 60 | 59192985 |  |  |  | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) | 030010000052 | MEP | Received | 2023-01-28 | Accounted transaction received
3773349 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3362.57 | 1 | بواط 10 * 10 عالى المقاس ¾ " |  | Each | 50 | 59192986 |  |  |  | بواط 10 * 10 عالى المقاس ¾ " | 030020100105 | MEP | Received | 2023-01-28 | Accounted transaction received
3773350 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3539.7 | 1 | بواط إكستنشن 10 * 10 المقاس 1 " |  | Each | 50 | 59192987 |  |  |  | بواط إكستنشن 10 * 10 المقاس 1 " | 030020100111 | MEP | Received | 2023-01-28 | Accounted transaction received
3773351 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 661.33 | 1 | سلك نحاس مصمت مقاس 1.5 مم اللون أحمر (cu/pvc) جهد (750/450) |  | Meter | 100 | 59192988 |  |  |  | سلك نحاس مصمت مقاس 1.5 مم اللون أحمر (cu/pvc) جهد (750/450) | 030030100247 | MEP | Received | 2023-01-28 | Accounted transaction received
3773352 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 168.15 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 50 | 59192989 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-01-28 | Accounted transaction received
3773353 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 587.89 | 1 | سلك نحاس مصمت مقاس 1.5 مم اللون أسود (cu/pvc) جهد (750/450) |  | Meter | 100 | 59192990 |  |  |  | سلك نحاس مصمت مقاس 1.5 مم اللون أسود (cu/pvc) جهد (750/450) | 030030100253 | MEP | Received | 2023-01-28 | Accounted transaction received
3773354 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 390.89 | 1 | أدابتور UPVC لماسورة 25مم(اللون أبيض) |  | Each | 50 | 59192991 |  |  |  | أدابتور UPVC لماسورة 25مم(اللون أبيض) | 030010000097 | MEP | Received | 2023-01-28 | Accounted transaction received
3773355 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3437.1 | 1 | سلك نحاس مصمت مقاس 3 مم اللون أحمر (cu/pvc) جهد (750/450) |  | Meter | 300 | 59192992 |  |  |  | سلك نحاس مصمت مقاس 3 مم اللون أحمر (cu/pvc) جهد (750/450) | 030030100277 | MEP | Received | 2023-01-28 | Accounted transaction received
3773356 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 8205.72 | 1 | ماسورة صلب مجلفن EMT المقاس 1 " طول الماسورة 3.05 |  | Meter | 61 | 59192993 |  |  |  | ماسورة صلب مجلفن EMT المقاس 1 " طول الماسورة 3.05 | 030020100003 | MEP | Received | 2023-01-28 | Accounted transaction received
3773357 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 784.88 | 1 | لاكور ماسورة EMT المقاس 1 " |  | Each | 30 | 59192994 |  |  |  | لاكور ماسورة EMT المقاس 1 " | 030020100016 | MEP | Received | 2023-01-28 | Accounted transaction received
3773358 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 760.55 | 1 | جلبة ماسورة EMT المقاس 1 " |  | Each | 30 | 59192995 |  |  |  | جلبة ماسورة EMT المقاس 1 " | 030020100022 | MEP | Received | 2023-01-28 | Accounted transaction received
3773359 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 648.57 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 6 | 59192996 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-01-28 | Accounted transaction received
3773360 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 774.74 | 1 | PLATE 1SQ MOD SCH GRAPHITE Code 576552 |  | Each | 20 | 59192997 |  |  |  | PLATE 1SQ MOD SCH GRAPHITE Code 576552 | 030060100297 | MEP | Received | 2023-01-28 | Accounted transaction received
3773361 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 774.74 | 1 | PLATE 1SQ MOD SCH GRAPHITE Code 576552 |  | Each | 20 | 59192998 |  |  |  | PLATE 1SQ MOD SCH GRAPHITE Code 576552 | 030060100297 | MEP | Received | 2023-01-28 | Accounted transaction received
3773362 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 9593.1 | 1 | سلك نحاس مجدول مقاس 3 مم اللون أصفر × أخضر (cu/pvc) |  | Meter | 900 | 59192999 |  |  |  | سلك نحاس مجدول مقاس 3 مم اللون أصفر × أخضر (cu/pvc) | 030030101022 | MEP | Received | 2023-01-28 | Accounted transaction received
3773363 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3333.75 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أصفر (cu/pvc) |  | Meter | 400 | 59193000 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أصفر (cu/pvc) | 030030101024 | MEP | Received | 2023-01-28 | Accounted transaction received
3773364 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 6127.51 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) |  | Meter | 800 | 59193001 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) | 030030101026 | MEP | Received | 2023-01-28 | Accounted transaction received
3773365 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1513.43 | 1 | سلك نحاس مجدول مقاس 3 مم اللون أزرق (cu/pvc) |  | Meter | 200 | 59193002 |  |  |  | سلك نحاس مجدول مقاس 3 مم اللون أزرق (cu/pvc) | 030030101020 | MEP | Received | 2023-01-28 | Accounted transaction received
3773366 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2034.9 | 1 | 'S/M BOX GREY 2-GANG H Code : 69672 |  | Each | 10 | 59193003 |  |  |  | 'S/M BOX GREY 2-GANG H Code : 69672 | 030060100654 | MEP | Received | 2023-01-28 | Accounted transaction received
3773367 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 6416.83 | 1 | SCHUKO SKT 2P+E SCREW-TER GY Code ( 69571 ) |  | Each | 32 | 59193004 |  |  |  | SCHUKO SKT 2P+E SCREW-TER GY Code ( 69571 ) | 030060100727 | MEP | Received | 2023-01-28 | Accounted transaction received
3773368 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 238.94 | 1 | Metal Galvanized back box 7x14 cm with deep 47 mm |  | Each | 10 | 59193005 |  |  |  | Metal Galvanized back box 7x14 cm with deep 47 mm | 030069000027 | MEP | Received | 2023-01-28 | Accounted transaction received
3773369 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 26237.44 | 1 | Audio, Control & Instrumentation Cable Twisted Shield (UL) Size (1PX16 AWG) |  | Meter | 610 | 59193006 |  |  |  | Audio, Control & Instrumentation Cable Twisted Shield (UL) Size (1PX16 AWG) | 032070000042 | MEP | Received | 2023-01-28 | Accounted transaction received
3773370 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 10807.47 | 1 | Driver Tridonic - 87500852 - Essence series - Driver LC 35W 24V SC 24 V – not dimmable (IP20) |  | Each | 30 | 59193007 |  |  |  | Driver Tridonic - 87500852 - Essence series - Driver LC 35W 24V SC 24 V – not dimmable (IP20) | 030040700475 | MEP | Received | 2023-01-28 | Accounted transaction received
3773371 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 13294.95 | 1 | LT.02-Pendant Circular luminaire Ring connected to 220v mains using AC/DC Driver, the luminaire- made of cast Aluminum. Polycarbonate diffuser ensures the diffusivity of the light giving a smooth sensation without any hot or dark spots. |  | Each | 4 | 59193008 |  |  |  | LT.02-Pendant Circular luminaire Ring connected to 220v mains using AC/DC Driver, the luminaire- made of cast Aluminum. Polycarbonate diffuser ensures the diffusivity of the light giving a smooth sensation without any hot or dark spots. | 030040700491 | MEP | Received | 2023-01-28 | Accounted transaction received
3773372 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 380.2 | 1 | CEILING MOUNT SPEAKER, Model No. PC-648R |  | Each | 1 | 59193009 |  |  |  | CEILING MOUNT SPEAKER, Model No. PC-648R | 031070000015 | MEP | Received | 2023-01-28 | Accounted transaction received
3773373 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 54008.64 | 1 | FIRE RESISTANT INSTRUMENTATION CABLE CU/MICA/XLPE/LSHF 2 X 1.5 MM2 500 V |  | Meter | 1050 | 59193010 |  |  |  | FIRE RESISTANT INSTRUMENTATION CABLE CU/MICA/XLPE/LSHF 2 X 1.5 MM2 500 V | 032010000014 | MEP | Received | 2023-01-28 | Accounted transaction received
3773374 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-04 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 927.75 | 1 | Rigid Coupling3 '' UL listed, FM approved |  | Each | 9 | 59217087 |  |  |  | Rigid Coupling3 '' UL listed, FM approved | 060011500011 | MEP | Received | 2023-01-28 | Accounted transaction received
3773375 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-04 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1698.53 | 1 | Rigid Coupling 4'' UL listed, FM approved |  | Each | 11 | 59217088 |  |  |  | Rigid Coupling 4'' UL listed, FM approved | 060011500012 | MEP | Received | 2023-01-28 | Accounted transaction received
3773376 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-04 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1573.2 | 1 | threaded tees size 1" UL LISTED,FM APPROVED |  | Each | 20 | 59217089 |  |  |  | threaded tees size 1" UL LISTED,FM APPROVED | 060010140276 | MEP | Received | 2023-01-28 | Accounted transaction received
3773377 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-04 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3249 | 1 | threaded reducing coupling size 1"*1/2" UL LISTED,FM APPROVED |  | Each | 50 | 59217090 |  |  |  | threaded reducing coupling size 1"*1/2" UL LISTED,FM APPROVED | 060010140334 | MEP | Received | 2023-01-28 | Accounted transaction received
3773378 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-04 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1450.08 | 1 | threaded reducing tees size 2"*1" UL LISTED,FM APPROVED |  | Each | 6 | 59217091 |  |  |  | threaded reducing tees size 2"*1" UL LISTED,FM APPROVED | 060010140170 | MEP | Received | 2023-01-28 | Accounted transaction received
3773379 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-04 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 310.66 | 1 | threaded tees size 1.5" UL LISTED,FM APPROVED |  | Each | 5 | 59217092 |  |  |  | threaded tees size 1.5" UL LISTED,FM APPROVED | 060010140616 | MEP | Received | 2023-01-28 | Accounted transaction received
3773380 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-04 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 24396 | 1 | Bag Filter with section |  | Each | 1 | 59217093 |  |  |  | Bag Filter with section | 060080100006 | MEP | Received | 2023-01-28 | Accounted transaction received
3773381 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-04 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 7638 | 1 | Supplying of pendent concealed sprinkler , quick response , standard coverage , 68 C, 1/2", K=5.6 C/W cover plate |  | Each | 10 | 59217651 |  |  |  | Supplying of pendent concealed sprinkler , quick response , standard coverage , 68 C, 1/2", K=5.6 C/W cover plate | 060090100007 | MEP | Received | 2023-01-28 | Accounted transaction received
3773382 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-04 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 481.85 | 1 | 90° Elbow 4'' UL listed, FM approved |  | Each | 2 | 59217652 |  |  |  | 90° Elbow 4'' UL listed, FM approved | 060011500077 | MEP | Received | 2023-01-28 | Accounted transaction received
3773383 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-04 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 565.59 | 1 | Threaded Mechanical Tee 3''*2'' UL listed, FM approved |  | Each | 2 | 59217653 |  |  |  | Threaded Mechanical Tee 3''*2'' UL listed, FM approved | 060011500222 | MEP | Received | 2023-01-28 | Accounted transaction received
3773384 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-04 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 333.32 | 1 | Grooved Reducer 4''*3'' UL listed, FM approved |  | Each | 2 | 59217654 |  |  |  | Grooved Reducer 4''*3'' UL listed, FM approved | 060011500373 | MEP | Received | 2023-01-28 | Accounted transaction received
3773385 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-04 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3598.98 | 1 | Supply of 0.5" Escutcheon Recessed Two Pieces , RELIABLE , Model G/F1 ,Chrome Finished. |  | Each | 41 | 59217655 |  |  |  | Supply of 0.5" Escutcheon Recessed Two Pieces , RELIABLE , Model G/F1 ,Chrome Finished. | 060090300002 | MEP | Received | 2023-01-28 | Accounted transaction received
3773386 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-04 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3420 | 1 | Cast Iron Gate Valve D151 Crane UK 1" PN 20 |  | Each | 4 | 59217656 |  |  |  | Cast Iron Gate Valve D151 Crane UK 1" PN 20 | 060170100081 | MEP | Received | 2023-01-28 | Accounted transaction received
3773387 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-04 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1960.8 | 1 | Cast Iron Strainer Valve D298 Crane UK 1" PN 16 |  | Each | 2 | 59217657 |  |  |  | Cast Iron Strainer Valve D298 Crane UK 1" PN 16 | 060171000021 | MEP | Received | 2023-01-28 | Accounted transaction received
3773388 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-04 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4332 | 1 | Pressure Gauge 0.5" |  | Each | 4 | 59217658 |  |  |  | Pressure Gauge 0.5" | 060179000007 | MEP | Received | 2023-01-28 | Accounted transaction received
3773389 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-04 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1254 | 1 | Check valve DN 25 mm Model : Crane D138 |  | Each | 1 | 59217659 |  |  |  | Check valve DN 25 mm Model : Crane D138 | 060240000089 | MEP | Received | 2023-01-28 | Accounted transaction received
3773390 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-04 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1541.2 | 1 | 2 way control valve Size 1" C/W on/off actuator 3-position ( VVI46.25/2 - SUA21/3 ) |  | Each | 1 | 59217660 |  |  |  | 2 way control valve Size 1" C/W on/off actuator 3-position ( VVI46.25/2 - SUA21/3 ) | 060172800002 | MEP | Received | 2023-01-28 | Accounted transaction received
3773391 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-04 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 7182 | 1 | Double regulating valve model D931 Size 1" |  | Each | 3 | 59217661 |  |  |  | Double regulating valve model D931 Size 1" | 060170500023 | MEP | Received | 2023-01-28 | Accounted transaction received
3773392 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-04 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 182.51 | 1 | فدية خرسانة 9 بوصة |  | Each | 2 | 59218923 |  |  |  | فدية خرسانة 9 بوصة | 200010000433 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773393 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1841.33 | 1 | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) |  | Meter | 120 | 59219039 |  |  |  | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) | 030010000052 | MEP | Received | 2023-01-28 | Accounted transaction received
3773394 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2814.08 | 1 | بواط 10 * 10 عالى المقاس 1 " |  | Each | 40 | 59219040 |  |  |  | بواط 10 * 10 عالى المقاس 1 " | 030020100104 | MEP | Received | 2023-01-28 | Accounted transaction received
3773395 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 672.51 | 1 | بواط 10 * 10 عالى المقاس ¾ " |  | Each | 10 | 59219041 |  |  |  | بواط 10 * 10 عالى المقاس ¾ " | 030020100105 | MEP | Received | 2023-01-28 | Accounted transaction received
3773396 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 201.78 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 60 | 59219042 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-01-28 | Accounted transaction received
3773397 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 367.65 | 1 | بواط ثلاثي UPVC لماسورة 20مم(اللون أبيض) |  | Each | 43 | 59219043 |  |  |  | بواط ثلاثي UPVC لماسورة 20مم(اللون أبيض) | 030010000086 | MEP | Received | 2023-01-28 | Accounted transaction received
3773398 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3425.47 | 1 | أفيز 25مم UPVC(اللون أبيض) |  | Each | 939 | 59219044 |  |  |  | أفيز 25مم UPVC(اللون أبيض) | 030010000107 | MEP | Received | 2023-01-28 | Accounted transaction received
3773399 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 11439.02 | 1 | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 |  | Meter | 122 | 59219045 |  |  |  | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 | 030020100002 | MEP | Received | 2023-01-28 | Accounted transaction received
3773400 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 8205.72 | 1 | ماسورة صلب مجلفن EMT المقاس 1 " طول الماسورة 3.05 |  | Meter | 61 | 59219046 |  |  |  | ماسورة صلب مجلفن EMT المقاس 1 " طول الماسورة 3.05 | 030020100003 | MEP | Received | 2023-01-28 | Accounted transaction received
3773401 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 941.85 | 1 | لاكور ماسورة EMT المقاس 1 " |  | Each | 36 | 59219047 |  |  |  | لاكور ماسورة EMT المقاس 1 " | 030020100016 | MEP | Received | 2023-01-28 | Accounted transaction received
3773402 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1140.82 | 1 | جلبة ماسورة EMT المقاس 1 " |  | Each | 45 | 59219048 |  |  |  | جلبة ماسورة EMT المقاس 1 " | 030020100022 | MEP | Received | 2023-01-28 | Accounted transaction received
3773403 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 81.37 | 1 | أفيز أثنين جناح لماسورة EMT المقاس 1 " |  | Each | 25 | 59219049 |  |  |  | أفيز أثنين جناح لماسورة EMT المقاس 1 " | 030020100034 | MEP | Received | 2023-01-28 | Accounted transaction received
3773404 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1059.78 | 1 | مسمار سن صاج |  | Each | 3000 | 59219050 |  |  |  | مسمار سن صاج | 200020000237 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3773405 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 236.43 | 1 | THREADED ROD 10mm,length 2mt |  | Each | 8 | 59219051 |  |  |  | THREADED ROD 10mm,length 2mt | 030120300003 | MEP | Received | 2023-01-28 | Accounted transaction received
3773406 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-05 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 311.51 | 1 | سيفتي عمال |  | Each | 1 | 59248249 |  |  |  | سيفتي عمال | 010030000002 | Safety | Received | 2023-01-28 | Accounted transaction received
3773407 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-05 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 13.68 | 1 | نظارة مهندسين M3 بيضاء |  | Each | 1 | 59248250 |  |  |  | نظارة مهندسين M3 بيضاء | 010060000004 | Safety | Received | 2023-01-28 | Accounted transaction received
3773408 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-05 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 63.64 | 1 | جوانتي جلد ثقيل ( خرسانة ) |  | Each | 2 | 59248251 |  |  |  | جوانتي جلد ثقيل ( خرسانة ) | 010010000003 | Safety | Received | 2023-01-28 | Accounted transaction received
3773409 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-05 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 68.57 | 1 | شريط تحذير ابيض*احمر |  | Each | 1 | 59248252 |  |  |  | شريط تحذير ابيض*احمر | 010070000011 | Safety | Received | 2023-01-28 | Accounted transaction received
3773410 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-05 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3351.6 | 1 | فلكسيبل معدن المقاس 2 " |  | Meter | 30 | 59248330 |  |  |  | فلكسيبل معدن المقاس 2 " | 030020100095 | MEP | Received | 2023-01-28 | Accounted transaction received
3773411 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-05 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 168.15 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 50 | 59248331 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-01-28 | Accounted transaction received
3773412 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-05 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 833.27 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 3 | 59248332 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) | 030010000059 | MEP | Received | 2023-01-28 | Accounted transaction received
3773413 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-05 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 738.58 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 25مم وقطر خارجى 31.1مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 2 | 59248333 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 25مم وقطر خارجى 31.1مم طول اللفه 30 متر(اللون رمادى) | 030010000062 | MEP | Received | 2023-01-28 | Accounted transaction received
3773414 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-05 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 390.89 | 1 | أدابتور UPVC لماسورة 25مم(اللون أبيض) |  | Each | 50 | 59248334 |  |  |  | أدابتور UPVC لماسورة 25مم(اللون أبيض) | 030010000097 | MEP | Received | 2023-01-28 | Accounted transaction received
3773415 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-05 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 661.2 | 1 | جلاند فلكسبل مقاس 16 مم |  | Each | 100 | 59248335 |  |  |  | جلاند فلكسبل مقاس 16 مم | 030010000167 | MEP | Received | 2023-01-28 | Accounted transaction received
3773416 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-05 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 347.42 | 1 | جلاند فلكسبل مقاس 25 مم |  | Each | 25 | 59248336 |  |  |  | جلاند فلكسبل مقاس 25 مم | 030010000170 | MEP | Received | 2023-01-28 | Accounted transaction received
3773417 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-05 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 5935.11 | 1 | بواط واتر بروف بفتحات مقاس 19 × 24 × 9 سم |  | Each | 34 | 59248337 |  |  |  | بواط واتر بروف بفتحات مقاس 19 × 24 × 9 سم | 030010000183 | MEP | Received | 2023-01-28 | Accounted transaction received
3773418 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-05 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 6855.39 | 1 | EMT coupling/Flexible 2" inch ( Connector + IMC Coupling + Squeeze ) |  | Each | 30 | 59248338 |  |  |  | EMT coupling/Flexible 2" inch ( Connector + IMC Coupling + Squeeze ) | 030020100193 | MEP | Received | 2023-01-28 | Accounted transaction received
3773419 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-01-05 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 79180.92 | 1 | Wall covering WC-2 Cole & Son-Feather Fan 89/4015 |  | Roll | 36 | 59253131 |  |  |  | Wall covering WC-2 Cole & Son-Feather Fan 89/4015 | 050020000012 | Purchasing | Received | 2023-01-28 | Accounted transaction received
3778389 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.01 | Private Cars | 17 | Indirect Cost |  | 2023-01-29 | Fuel,Oil & Gas |  |  |  | Indirect | Alrowad Construction_OU | 6168 | 1 | 556314-556221-557251-557016-557169 astoria | 556314-556221-557251-557016-557169 astoria | Currency | 6168 | 21877164 | 3903 | توتال ايجيبت | rowad | 556314-556221-557251-557016-557169 astoria |  | Finacial | Received | 2023-01-29 | Accounted transaction received
3779607 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-30 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 5000 | 1 | تسويه ك /46 سلفه على مقاول باطن- استوريا | st-46-1-23 | Currency | 5000 | 21880684 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /46 سلفه على مقاول باطن- استوريا |  | Finacial | Received | 2023-01-30 | Accounted transaction received
3779611 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.08 | Trafic Permission & | 17 | Indirect Cost |  | 2023-01-30 | Trafic Perm-Station Fees |  |  |  | Indirect | Alrowad Construction_OU | 140 | 1 | تسويه ك /12-35-36-37-39-40-47-48-49-54-57- متنوعات | st-12-35-36-37-39-40-47-48-49-54-57-1-23 | Currency | 140 | 21880684 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /12-35-36-37-39-40-47-48-49-54-57- متنوعات |  | Finacial | Received | 2023-01-30 | Accounted transaction received
3779612 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-30 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 300 | 1 | تسويه ك /12-35-36-37-39-40-47-48-49-54-57- متنوعات | st-12-35-36-37-39-40-47-48-49-54-57-1-23 | Currency | 300 | 21880684 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /12-35-36-37-39-40-47-48-49-54-57- متنوعات |  | Finacial | Received | 2023-01-30 | Accounted transaction received
3779613 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-30 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 8085.41 | 1 | تسويه ك /12-35-36-37-39-40-47-48-49-54-57- متنوعات | st-12-35-36-37-39-40-47-48-49-54-57-1-23 | Currency | 8085.41 | 21880684 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /12-35-36-37-39-40-47-48-49-54-57- متنوعات |  | Finacial | Received | 2023-01-30 | Accounted transaction received
3779614 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-30 | Stationary |  |  |  | Office and Site expenses | Alrowad Construction_OU | 150 | 1 | تسويه ك /12-35-36-37-39-40-47-48-49-54-57- متنوعات | st-12-35-36-37-39-40-47-48-49-54-57-1-23 | Currency | 150 | 21880684 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /12-35-36-37-39-40-47-48-49-54-57- متنوعات |  | Finacial | Received | 2023-01-30 | Accounted transaction received
3779615 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-30 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 4100 | 1 | تسويه ك /12-35-36-37-39-40-47-48-49-54-57- متنوعات | st-12-35-36-37-39-40-47-48-49-54-57-1-23 | Currency | 4100 | 21880684 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /12-35-36-37-39-40-47-48-49-54-57- متنوعات |  | Finacial | Received | 2023-01-30 | Accounted transaction received
3779616 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.13 | Maintenance | 17 | Indirect Cost |  | 2023-01-30 | Maintenance |  |  |  | Indirect | Alrowad Construction_OU | 3999.99 | 1 | تسويه ك /12-35-36-37-39-40-47-48-49-54-57- متنوعات | st-12-35-36-37-39-40-47-48-49-54-57-1-23 | Currency | 3999.99 | 21880684 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /12-35-36-37-39-40-47-48-49-54-57- متنوعات |  | Finacial | Received | 2023-01-30 | Accounted transaction received
3779670 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.01 | Private Cars | 17 | Indirect Cost |  | 2023-01-30 | Fuel,Oil & Gas |  |  |  | Indirect | Alrowad Construction_OU | 260 | 1 | 2954304 astoria كروت | 2954304 astoria كروت | Currency | 260 | 21880684 | 3903 | توتال ايجيبت | rowad | 2954304 astoria كروت |  | Finacial | Received | 2023-01-30 | Accounted transaction received
3780517 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.03.02 | Repair | 2 | SITE WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 14400 | 1 | 1.3 74900/4 |  | Currency | 120 |  | 8108 | سامى عياد فهيم حليم |  | 1.3 74900/4 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780518 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.03.02 | Repair | 2 | SITE WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -64.8 | 1 | LABOUR_OFFICE 74900/4 |  | Currency | -64.8 |  | 8108 | سامى عياد فهيم حليم |  | LABOUR_OFFICE 74900/4 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780520 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 71962.6 | 1 | 1.1 62820/11 |  | Currency | 7.68 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 1.1 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780521 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 14757.95 | 1 | 1.2 62820/11 |  | Currency | 1.05 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 1.2 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780522 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5903.18 | 1 | 1.3 62820/11 |  | Currency | 0.36 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 1.3 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780523 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 73121.1 | 1 | 2.1 62820/11 |  | Currency | 100 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.1 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780524 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5630.32 | 1 | 2.10 62820/11 |  | Currency | 7 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.10 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780525 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4825.99 | 1 | 2.11 62820/11 |  | Currency | 6 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.11 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780526 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 8043.32 | 1 | 2.12 62820/11 |  | Currency | 10 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.12 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780527 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 777.17 | 1 | 2.13 62820/11 |  | Currency | 1 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.13 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780528 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 804.33 | 1 | 2.2 62820/11 |  | Currency | 1 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.2 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780529 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2413 | 1 | 2.3 62820/11 |  | Currency | 3 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.3 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780530 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1608.66 | 1 | 2.4 62820/11 |  | Currency | 2 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.4 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780531 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1608.66 | 1 | 2.5 62820/11 |  | Currency | 2 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.5 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780532 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2954.09 | 1 | 2.56 62820/11 |  | Currency | 4 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.56 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780533 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 6434.66 | 1 | 2.6 62820/11 |  | Currency | 8 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.6 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780534 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2215.57 | 1 | 2.57 62820/11 |  | Currency | 3 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.57 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780535 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2215.57 | 1 | 2.58 62820/11 |  | Currency | 3 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.58 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780536 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1864.59 | 1 | 2.59 62820/11 |  | Currency | 3 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.59 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780537 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 940.13 | 1 | 2.63 62820/11 |  | Currency | 100 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.63 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780538 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1357.96 | 1 | 2.64 62820/11 |  | Currency | 100 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.64 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780539 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 208.92 | 1 | 2.65 62820/11 |  | Currency | 10 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.65 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780540 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 16890.97 | 1 | 2.7 62820/11 |  | Currency | 21 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.7 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780541 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 804.33 | 1 | 2.8 62820/11 |  | Currency | 1 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.8 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780542 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2413 | 1 | 2.9 62820/11 |  | Currency | 3 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.9 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780543 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | -12095 | 1 | 62820/11 |  | Currency | -12095 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780544 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1033.9 | 1 | LABOUR_OFFICE 62820/11 |  | Currency | -1033.9 |  | 11007 | الاسراء للمقاولات والتوريدات |  | LABOUR_OFFICE 62820/11 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780568 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.07.05 | Gravel | 2 | SITE WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 960 | 1 | 3.1 64204/8 |  | Currency | 8 |  | 8108 | سامى عياد فهيم حليم |  | 3.1 64204/8 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780569 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.07.05 | Gravel | 2 | SITE WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 10860 | 1 | 3.2 64204/8 |  | Currency | 30 |  | 8108 | سامى عياد فهيم حليم |  | 3.2 64204/8 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780570 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.07.05 | Gravel | 2 | SITE WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 28560 | 1 | 4.1 64204/8 |  | Currency | 238 |  | 8108 | سامى عياد فهيم حليم |  | 4.1 64204/8 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780571 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.07.05 | Gravel | 2 | SITE WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -181.71 | 1 | LABOUR_OFFICE 64204/8 |  | Currency | -181.71 |  | 8108 | سامى عياد فهيم حليم |  | LABOUR_OFFICE 64204/8 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780625 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 27950 | 1 | 3.1 63247/3 |  | Currency | 117 |  | 10037 | ايه وان للمقاولات |  | 3.1 63247/3 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780626 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3990 | 1 | 4.4 63247/3 |  | Currency | 3990 |  | 10037 | ايه وان للمقاولات |  | 4.4 63247/3 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780627 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 14250 | 1 | 4.5 63247/3 |  | Currency | 14250 |  | 10037 | ايه وان للمقاولات |  | 4.5 63247/3 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780628 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2223 | 1 | 4.6 63247/3 |  | Currency | 9 |  | 10037 | ايه وان للمقاولات |  | 4.6 63247/3 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780629 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1358.5 | 1 | 4.7 63247/3 |  | Currency | 5.5 |  | 10037 | ايه وان للمقاولات |  | 4.7 63247/3 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780630 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 45830.4 | 1 | 4.8 63247/3 |  | Currency | 369.6 |  | 10037 | ايه وان للمقاولات |  | 4.8 63247/3 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780633 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-01-31 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | -1500 | 1 | 63247/3 |  | Currency | -1500 |  | 10037 | ايه وان للمقاولات |  | 63247/3 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780634 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -430.21 | 1 | LABOUR_OFFICE 63247/3 |  | Currency | -430.21 |  | 10037 | ايه وان للمقاولات |  | LABOUR_OFFICE 63247/3 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780643 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.01.01 | Plastering | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 13995.91 | 1 | 2.1 68492/4 |  | Currency | 184.99 |  | 11726 | خليفه محمد صالح |  | 2.1 68492/4 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780644 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.01.01 | Plastering | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 8060 | 1 | 1.1 68492/4 |  | Currency | 2600 |  | 11726 | خليفه محمد صالح |  | 1.1 68492/4 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780645 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.01.01 | Plastering | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 343.2 | 1 | 1.2 68492/4 |  | Currency | 312 |  | 11726 | خليفه محمد صالح |  | 1.2 68492/4 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780646 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.01.01 | Plastering | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -100.8 | 1 | LABOUR_OFFICE 68492/4 |  | Currency | -100.8 |  | 11726 | خليفه محمد صالح |  | LABOUR_OFFICE 68492/4 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780650 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-01-31 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | 2000 | 1 | 69398/5 |  | Currency | 2000 |  | 8108 | سامى عياد فهيم حليم |  | 69398/5 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780651 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 35433 | 1 | 1.2 69398/5 |  | Currency | 78.74 |  | 8108 | سامى عياد فهيم حليم |  | 1.2 69398/5 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780652 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -159.45 | 1 | LABOUR_OFFICE 69398/5 |  | Currency | -159.45 |  | 8108 | سامى عياد فهيم حليم |  | LABOUR_OFFICE 69398/5 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780654 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 43332.35 | 1 | 1.18 71263/3 |  | Currency | 456.13 |  | 12046 | رياض الصالحين |  | 1.18 71263/3 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780655 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 6609.1 | 1 | 1.19 71263/3 |  | Currency | 45.58 |  | 12046 | رياض الصالحين |  | 1.19 71263/3 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780656 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 14649.35 | 1 | 1.20 71263/3 |  | Currency | 101.03 |  | 12046 | رياض الصالحين |  | 1.20 71263/3 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780657 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4651.6 | 1 | 1.21 71263/3 |  | Currency | 32.08 |  | 12046 | رياض الصالحين |  | 1.21 71263/3 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780658 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 6841.95 | 1 | 2.17 71263/3 |  | Currency | 456.13 |  | 12046 | رياض الصالحين |  | 2.17 71263/3 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780659 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 683.7 | 1 | 2.18 71263/3 |  | Currency | 45.58 |  | 12046 | رياض الصالحين |  | 2.18 71263/3 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780660 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1515.45 | 1 | 2.19 71263/3 |  | Currency | 101.03 |  | 12046 | رياض الصالحين |  | 2.19 71263/3 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780661 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 481.2 | 1 | 2.20 71263/3 |  | Currency | 32.08 |  | 12046 | رياض الصالحين |  | 2.20 71263/3 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780662 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1076.85 | 1 | 3.1 71263/3 |  | Currency | 23.93 |  | 12046 | رياض الصالحين |  | 3.1 71263/3 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780663 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 920 | 1 | 3.2 71263/3 |  | Currency | 23 |  | 12046 | رياض الصالحين |  | 3.2 71263/3 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780664 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1442.75 | 1 | 3.3 71263/3 |  | Currency | 57.71 |  | 12046 | رياض الصالحين |  | 3.3 71263/3 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780665 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -369.92 | 1 | LABOUR_OFFICE 71263/3 |  | Currency | -369.92 |  | 12046 | رياض الصالحين |  | LABOUR_OFFICE 71263/3 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780677 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3512 | 1 | 1.1 74065/4 |  | Currency | 21.95 |  | 12200 | الدولية للتجارة والمقاولات |  | 1.1 74065/4 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780678 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1992 | 1 | 1.2 74065/4 |  | Currency | 12.45 |  | 12200 | الدولية للتجارة والمقاولات |  | 1.2 74065/4 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780679 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5449.6 | 1 | 1.3 74065/4 |  | Currency | 34.06 |  | 12200 | الدولية للتجارة والمقاولات |  | 1.3 74065/4 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780680 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 33332.2 | 1 | 1.4 74065/4 |  | Currency | 303.02 |  | 12200 | الدولية للتجارة والمقاولات |  | 1.4 74065/4 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780681 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1179.9 | 1 | 2.1 74065/4 |  | Currency | 26.22 |  | 12200 | الدولية للتجارة والمقاولات |  | 2.1 74065/4 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780682 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 536.4 | 1 | 2.2 74065/4 |  | Currency | 13.41 |  | 12200 | الدولية للتجارة والمقاولات |  | 2.2 74065/4 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780683 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 408.75 | 1 | 2.3 74065/4 |  | Currency | 16.35 |  | 12200 | الدولية للتجارة والمقاولات |  | 2.3 74065/4 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780684 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | -7175 | 1 | 74065/4 |  | Currency | -7175 |  | 12200 | الدولية للتجارة والمقاولات |  | 74065/4 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3780685 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -208.85 | 1 | LABOUR_OFFICE 74065/4 |  | Currency | -208.85 |  | 12200 | الدولية للتجارة والمقاولات |  | LABOUR_OFFICE 74065/4 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3781238 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-31 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 5100 | 1 | استوريا الماسه ف/2705 14/1 | 2705 | Currency | 5100 | 21884755 | 12416 | الماسه للتاجير ومعالجه المياه | rowad | استوريا الماسه ف/2705 14/1 |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3781266 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.10 | Printers / Photo Cop | 17 | Indirect Cost |  | 2023-01-31 | Printers/Photo Copiers |  |  |  | Indirect | Alrowad Construction_OU | 6945 | 1 | تسويه ك /60-70-72-80-92-94-95- متنوعات | st-60-70-72-80-92-94-95-1-23 | Currency | 6945 | 21884755 | 2162 | Petty Cash | Mohamed Ezzat Mohamed ELtieby | تسويه ك /60-70-72-80-92-94-95- متنوعات |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3781268 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-31 | Other |  |  |  | Other | Alrowad Construction_OU | 270 | 1 | تسويه ك /60-70-72-80-92-94-95- متنوعات | st-60-70-72-80-92-94-95-1-23 | Currency | 270 | 21884755 | 2162 | Petty Cash | Mohamed Ezzat Mohamed ELtieby | تسويه ك /60-70-72-80-92-94-95- متنوعات |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3781269 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-31 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 2198 | 1 | تسويه ك /60-70-72-80-92-94-95- متنوعات | st-60-70-72-80-92-94-95-1-23 | Currency | 2198 | 21884755 | 2162 | Petty Cash | Mohamed Ezzat Mohamed ELtieby | تسويه ك /60-70-72-80-92-94-95- متنوعات |  | Finacial | Received | 2023-01-31 | Accounted transaction received
3782968 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.03 | Hirings daily wages | 17 | Indirect Cost |  | 2023-01-31 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 67057.5 | 1 | يوميات عماله م06-astoria | يوميات عماله م06-astoria | Currency | 67057.5 | 21890273 | 12252 | حامد حسين احمد خالد – ذاتى | rowad | يوميات عماله م06-astoria |  | Finacial | Received | 2023-02-01 | Accounted transaction received
3782999 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2023-01-31 | Accomodation |  |  |  | Indirect | Alrowad Construction_OU | 5600 | 1 | ايجارات شقق ش2 astoria | ايجارات شقق ش2 astoria | Currency | 5600 | 21890273 | 2131 | Miscellaneous supplier | RME | ايجارات شقق ش2 astoria |  | Finacial | Received | 2023-02-01 | Accounted transaction received
3783332 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-01-01 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | -222255 | 1 | يوميات عماله الفتره 2 ش 12 التقديري | يوميات عماله الفتره 2 ش 12 التقديري | Currency | -222255 | 21895108 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 2 ش 12 التقديري |  | Finacial | Received | 2023-02-04 | Accounted transaction received
3783378 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-01-24 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 206435 | 1 | يوميات عماله الفتره 1 ش 1 الفعلي | يوميات عماله الفتره 1 ش 1 الفعلي | Currency | 206435 | 21895108 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 1 ش 1 الفعلي |  | Finacial | Received | 2023-02-04 | Accounted transaction received
3783426 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-01-25 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 206435 | 1 | يوميات عماله الفتره 2 ش 1 التقديري | يوميات عماله الفتره 2 ش 1 التقديري | Currency | 206435 | 21895108 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 2 ش 1 التقديري |  | Finacial | Received | 2023-02-04 | Accounted transaction received
3783553 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-31 | Other |  |  |  | Other | Alrowad Construction_OU | 6406.64 | 1 | 3249-3260-3268 astoria | 3249-3260-3268 astoria | Currency | 6406.64 | 21895108 | 1709 | هيتس لتكنولوجيا المعلومات | Egypt | 3249-3260-3268 astoria |  | Finacial | Received | 2023-02-04 | Accounted transaction received
3783587 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost | 78452 | 2023-01-31 | Materials |  |  |  | Materials | Alrowad Construction_OU | -9170.9 | 1 | استوريا ديكومكس ف1177000101112023000030 | 1.1770001011e+21 | Currency | -9170.9 | 21895108 | 7997 | ديكومكس لتطوير وتصنيع منتجات ومستلزمات البناء والديكور | rowad | استوريا ديكومكس ف1177000101112023000030 |  | Purchasing | Received | 2023-02-04 | Accounted transaction received
3783894 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-31 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 900 | 1 |  | FA Depreciation-Jan23 | Currency | 900 | 21895108 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-02-04 | Accounted transaction received
3783895 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.06 | Surveying Equipment | 17 | Indirect Cost |  | 2023-01-31 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 2764.5 | 1 |  | FA Depreciation-Jan23 | Currency | 2764.5 | 21895108 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-02-04 | Accounted transaction received
3783896 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.10 | Scaffolding | 17 | Indirect Cost |  | 2023-01-31 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 6681.77 | 1 |  | FA Depreciation-Jan23 | Currency | 6681.77 | 21895108 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-02-04 | Accounted transaction received
3783897 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-31 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 14.98 | 1 |  | FA Depreciation-Jan23 | Currency | 14.98 | 21895108 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-02-04 | Accounted transaction received
3783898 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-31 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 1080.93 | 1 |  | FA Depreciation-Jan23 | Currency | 1080.93 | 21895108 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-02-04 | Accounted transaction received
3783899 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-31 | Furniture Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 8324.58 | 1 |  | FA Depreciation-Jan23 | Currency | 8324.58 | 21895108 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-02-04 | Accounted transaction received
3783900 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-31 | Electrical appliance Deprectia |  |  |  | Depreciation | Alrowad Construction_OU | 1316.5 | 1 |  | FA Depreciation-Jan23 | Currency | 1316.5 | 21895108 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-02-04 | Accounted transaction received
3783901 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2023-01-31 | Electrical appliance Deprectia |  |  |  | Depreciation | Alrowad Construction_OU | 3076.19 | 1 |  | FA Depreciation-Jan23 | Currency | 3076.19 | 21895108 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-02-04 | Accounted transaction received
3783902 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.07 | Computers | 17 | Indirect Cost |  | 2023-01-31 | Computers Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 6005.04 | 1 |  | FA Depreciation-Jan23 | Currency | 6005.04 | 21895108 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-02-04 | Accounted transaction received
3783903 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.10 | Printers / Photo Cop | 17 | Indirect Cost |  | 2023-01-31 | Electrical appliance Deprectia |  |  |  | Depreciation | Alrowad Construction_OU | 2583.29 | 1 |  | FA Depreciation-Jan23 | Currency | 2583.29 | 21895108 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-02-04 | Accounted transaction received
3783904 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.01 | Private Cars | 17 | Indirect Cost |  | 2023-01-31 | Vehicles Depreciations |  |  |  | Depreciation | Alrowad Construction_OU | 5265.21 | 1 |  | FA Depreciation-Jan23 | Currency | 5265.21 | 21895108 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-02-04 | Accounted transaction received
2630002 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-20 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | -44253 | 1 | والد روف الحلول المتكامله ف/201 14/12 | 201 | Currency | -44253 | 10458928 | 4932 | الحلول المتكامله | rowad | والد روف الحلول المتكامله ف/201 14/12 |  | Finacial | Received | 2021-12-21 | Accounted transaction received
2727622 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2021-12-27 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 51120.25 | 1 | يوميات عماله الفتره 2 ش 12 / التقديري | يوميات عماله الفتره 2 ش 12 / التقديري | Currency | 51120.25 | 12361729 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 2 ش 12 / التقديري |  | Finacial | Received | 2021-12-28 | Accounted transaction received
2729851 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2021-12-29 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 3137.4 | 1 | تسوية ك-1234/1241/1249/1267-متنوع | ST-1234/1241/1249/1267 | Currency | 3137.4 | 12374974 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسوية ك-1234/1241/1249/1267-متنوع |  | Finacial | Received | 2021-12-29 | Accounted transaction received
2729852 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.03 | Hirings daily wages | 17 | Indirect Cost |  | 2021-12-29 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 3000 | 1 | تسوية ك-1234/1241/1249/1267-متنوع | ST-1234/1241/1249/1267 | Currency | 3000 | 12374974 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسوية ك-1234/1241/1249/1267-متنوع |  | Finacial | Received | 2021-12-29 | Accounted transaction received
2729853 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.10 | Printers / Photo Cop | 17 | Indirect Cost |  | 2021-12-29 | Printers/Photo Copiers |  |  |  | Indirect | Alrowad Construction_OU | 2190.39 | 1 | تسوية ك-1234/1241/1249/1267-متنوع | ST-1234/1241/1249/1267 | Currency | 2190.39 | 12374974 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسوية ك-1234/1241/1249/1267-متنوع |  | Finacial | Received | 2021-12-29 | Accounted transaction received
2730126 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.08 | Trafic Permission & | 17 | Indirect Cost |  | 2021-12-29 | Trafic Perm-Station Fees |  |  |  | Indirect | Alrowad Construction_OU | 125 | 1 | تسوية ك-1207/1248/1252-متنوع | ST-1207/1248/1252 | Currency | 125 | 12374974 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسوية ك-1207/1248/1252-متنوع |  | Finacial | Received | 2021-12-29 | Accounted transaction received
2742498 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 60 | 1 | مساحة |  | Each | 3 | 47344602 |  |  |  | مساحة | 700010000011 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742499 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 60 | 1 | مكنسة خشنة |  | Each | 3 | 47344603 |  |  |  | مكنسة خشنة | 700020000004 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742500 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 798 | 1 | مكنسة ناعمة |  | Each | 50 | 47344604 |  |  |  | مكنسة ناعمة | 200010000449 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742418 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.07 | Computers | 17 | Indirect Cost |  | 2021-12-29 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 250 | 1 | طقم سماعات |  | Each | 1 | 47384119 |  |  |  | طقم سماعات | 330040000039 | Equipment | Received | 2021-12-30 | Accounted transaction received
2742419 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 109.44 | 1 | طبة تسليك مقاس 110 مم |  | Each | 2 | 47336261 |  |  |  | طبة تسليك مقاس 110 مم | 060010100190 | MEP | Received | 2021-12-30 | Accounted transaction received
2742420 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 72.1 | 1 | كوع صرف ابيض قطر 1.5" ( 48 مم ) |  | Each | 5 | 47336262 |  |  |  | كوع صرف ابيض قطر 1.5" ( 48 مم ) | 060010100207 | MEP | Received | 2021-12-30 | Accounted transaction received
2742421 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 71.82 | 1 | كوع صرف ابيض قطر 4" ( 110 مم ) |  | Each | 2 | 47336263 |  |  |  | كوع صرف ابيض قطر 4" ( 110 مم ) | 060010100210 | MEP | Received | 2021-12-30 | Accounted transaction received
2742422 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 177.84 | 1 | كوع صرف ابيض 45 درجه قطر 1.5" ( 48 مم ) |  | Each | 12 | 47336264 |  |  |  | كوع صرف ابيض 45 درجه قطر 1.5" ( 48 مم ) | 060010100216 | MEP | Received | 2021-12-30 | Accounted transaction received
2742423 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 180.4 | 1 | كوع صرف ابيض 45 درجه قطر 4" ( 110 مم ) |  | Each | 5 | 47336265 |  |  |  | كوع صرف ابيض 45 درجه قطر 4" ( 110 مم ) | 060010100219 | MEP | Received | 2021-12-30 | Accounted transaction received
2742424 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 314.64 | 1 | كوع صرف ابيض بباب قطر 4" ( 110 مم ) |  | Each | 6 | 47336266 |  |  |  | كوع صرف ابيض بباب قطر 4" ( 110 مم ) | 060010100223 | MEP | Received | 2021-12-30 | Accounted transaction received
2742425 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 239.4 | 1 | مشترك صرف ابيض قطر 1.5" ( 48 مم ) |  | Each | 8 | 47336267 |  |  |  | مشترك صرف ابيض قطر 1.5" ( 48 مم ) | 060010100229 | MEP | Received | 2021-12-30 | Accounted transaction received
2742426 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 379.62 | 1 | مشترك صرف ابيض قطر 4" ( 110 مم ) |  | Each | 6 | 47336268 |  |  |  | مشترك صرف ابيض قطر 4" ( 110 مم ) | 060010100232 | MEP | Received | 2021-12-30 | Accounted transaction received
2742427 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 63.84 | 1 | مشترك صرف ابيض 45 درجه قطر 4" ( 110 مم ) |  | Each | 1 | 47336269 |  |  |  | مشترك صرف ابيض 45 درجه قطر 4" ( 110 مم ) | 060010100238 | MEP | Received | 2021-12-30 | Accounted transaction received
2742428 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 85.5 | 1 | مشترك صرف ابيض بباب قطر 4" ( 110 مم ) |  | Each | 1 | 47336270 |  |  |  | مشترك صرف ابيض بباب قطر 4" ( 110 مم ) | 060010100242 | MEP | Received | 2021-12-30 | Accounted transaction received
2742429 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 27.36 | 1 | مشترك صليبه 90 درجه صرف ابيض قطر 4" ( 110 مم ) |  | Each | 1 | 47336271 |  |  |  | مشترك صليبه 90 درجه صرف ابيض قطر 4" ( 110 مم ) | 060010100268 | MEP | Received | 2021-12-30 | Accounted transaction received
2742430 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 27.36 | 1 | هوايه صرف ابيض قطر 4" ( 110 مم ) |  | Each | 1 | 47336272 |  |  |  | هوايه صرف ابيض قطر 4" ( 110 مم ) | 060010100273 | MEP | Received | 2021-12-30 | Accounted transaction received
2742431 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 359.1 | 1 | جلبة تمدد صرف ابيض قطر 4" ( 110 مم ) |  | Each | 10 | 47336273 |  |  |  | جلبة تمدد صرف ابيض قطر 4" ( 110 مم ) | 060010100277 | MEP | Received | 2021-12-30 | Accounted transaction received
2742432 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 57.11 | 1 | جلبة اصلاح صرف ابيض قطر 4" ( 110 مم ) |  | Each | 1 | 47336274 |  |  |  | جلبة اصلاح صرف ابيض قطر 4" ( 110 مم ) | 060010100280 | MEP | Received | 2021-12-30 | Accounted transaction received
2742433 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 34.2 | 1 | مسلوب صرف ابيض مقاس 110/"1.5 مم |  | Each | 1 | 47336275 |  |  |  | مسلوب صرف ابيض مقاس 110/"1.5 مم | 060010100296 | MEP | Received | 2021-12-30 | Accounted transaction received
2742434 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 176.7 | 1 | جلبة صرف ابيض قطر 1.5" |  | Each | 10 | 47336276 |  |  |  | جلبة صرف ابيض قطر 1.5" | 060010100322 | MEP | Received | 2021-12-30 | Accounted transaction received
2742435 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 2623.14 | 1 | مواسير صرف ابيض قطر 4" ( 110 مم ) |  | Meter | 30 | 47336277 |  |  |  | مواسير صرف ابيض قطر 4" ( 110 مم ) | 060010100201 | MEP | Received | 2021-12-30 | Accounted transaction received
2742436 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 478.8 | 1 | مواسير صرف ابيض قطر 1.5" ( 48 مم ) |  | Meter | 12 | 47336278 |  |  |  | مواسير صرف ابيض قطر 1.5" ( 48 مم ) | 060010100198 | MEP | Received | 2021-12-30 | Accounted transaction received
2742437 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 60 | 1 | بكرة تيفلون |  | Each | 3 | 47336279 |  |  |  | بكرة تيفلون | 060019000003 | MEP | Received | 2021-12-30 | Accounted transaction received
2742438 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 320 | 1 | وصلة شطاف |  | Each | 8 | 47336280 |  |  |  | وصلة شطاف | 240050000078 | MEP | Received | 2021-12-30 | Accounted transaction received
2742439 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 152.76 | 1 | شحم نياتي |  | Kilogram | 2 | 47336281 |  |  |  | شحم نياتي | 060019000009 | MEP | Received | 2021-12-30 | Accounted transaction received
2742440 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 80 | 1 | سيلكون ضد البكتريا |  | Each | 2 | 47336282 |  |  |  | سيلكون ضد البكتريا | 060019000017 | MEP | Received | 2021-12-30 | Accounted transaction received
2742441 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 380 | 1 | شطاف خارجى |  | Each | 4 | 47336283 |  |  |  | شطاف خارجى | 240050000094 | MEP | Received | 2021-12-30 | Accounted transaction received
2742442 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 160 | 1 | نبل نيكل 1/2" * 3/8" |  | Each | 16 | 47336284 |  |  |  | نبل نيكل 1/2" * 3/8" | 060031000057 | MEP | Received | 2021-12-30 | Accounted transaction received
2742443 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 256.25 | 1 | بلوك نوت بسلك مربعات A4 |  | Each | 25 | 47340006 |  |  |  | بلوك نوت بسلك مربعات A4 | 910010000002 | Administration | Received | 2021-12-30 | Accounted transaction received
2742444 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 258.5 | 1 | الة حاسبة كاسيو FX82 |  | Each | 1 | 47340007 |  |  |  | الة حاسبة كاسيو FX82 | 910010000021 | Administration | Received | 2021-12-30 | Accounted transaction received
2742445 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 201 | 1 | قلم يوني بول اسود |  | Each | 12 | 47340008 |  |  |  | قلم يوني بول اسود | 910010000023 | Administration | Received | 2021-12-30 | Accounted transaction received
2742446 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 300 | 1 | علبة اسطوانات CD -52 |  | Each | 50 | 47340009 |  |  |  | علبة اسطوانات CD -52 | 910010000038 | Administration | Received | 2021-12-30 | Accounted transaction received
2742447 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 1080 | 1 | حافظة ديجيتال حرف L A4 |  | Each | 10 | 47340010 |  |  |  | حافظة ديجيتال حرف L A4 | 910010000056 | Administration | Received | 2021-12-30 | Accounted transaction received
2742448 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 310 | 1 | تراي 3دور |  | Each | 2 | 47340011 |  |  |  | تراي 3دور | 910010000070 | Administration | Received | 2021-12-30 | Accounted transaction received
2742449 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 65 | 1 | بول دوج 15مم |  | Each | 10 | 47340012 |  |  |  | بول دوج 15مم | 910010000110 | Administration | Received | 2021-12-30 | Accounted transaction received
2742450 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 140 | 1 | علبة بول دوج 32م |  | Each | 10 | 47340013 |  |  |  | علبة بول دوج 32م | 910010000112 | Administration | Received | 2021-12-30 | Accounted transaction received
2742451 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 247.5 | 1 | علبة بول دوج 41مم |  | Each | 10 | 47340014 |  |  |  | علبة بول دوج 41مم | 910010000113 | Administration | Received | 2021-12-30 | Accounted transaction received
2742452 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 201 | 1 | قلم يوني بول ازرق 150 |  | Each | 12 | 47340015 |  |  |  | قلم يوني بول ازرق 150 | 910010000124 | Administration | Received | 2021-12-30 | Accounted transaction received
2742453 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 201 | 1 | قلم يوني بول احمر150 |  | Each | 12 | 47340016 |  |  |  | قلم يوني بول احمر150 | 910010000126 | Administration | Received | 2021-12-30 | Accounted transaction received
2742454 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 410 | 1 | حافظة بلاستيك مستوردة |  | Each | 5 | 47340017 |  |  |  | حافظة بلاستيك مستوردة | 910010000138 | Administration | Received | 2021-12-30 | Accounted transaction received
2742455 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 240 | 1 | استيكى نوت 3*5 |  | Each | 30 | 47340018 |  |  |  | استيكى نوت 3*5 | 910010000141 | Administration | Received | 2021-12-30 | Accounted transaction received
2742456 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 99.5 | 1 | خرامة كانجارو 520 |  | Each | 2 | 47340019 |  |  |  | خرامة كانجارو 520 | 910010000149 | Administration | Received | 2021-12-30 | Accounted transaction received
2742457 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 889.5 | 1 | فواصل ياسين 20 ألوان |  | Each | 30 | 47340020 |  |  |  | فواصل ياسين 20 ألوان | 910010000167 | Administration | Received | 2021-12-30 | Accounted transaction received
2742458 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 15 | 1 | دبابيس دباسة كبيرة |  | Each | 1 | 47340021 |  |  |  | دبابيس دباسة كبيرة | 910010000173 | Administration | Received | 2021-12-30 | Accounted transaction received
2742459 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 385 | 1 | دباسة متوسطة |  | Each | 10 | 47340022 |  |  |  | دباسة متوسطة | 910010000174 | Administration | Received | 2021-12-30 | Accounted transaction received
2742460 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 58.5 | 1 | علبة دبابيس دباسة واش 24/6 |  | Each | 10 | 47340023 |  |  |  | علبة دبابيس دباسة واش 24/6 | 910010000179 | Administration | Received | 2021-12-30 | Accounted transaction received
2742461 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 7.5 | 1 | بكرة سوليتب عادي |  | Each | 5 | 47340024 |  |  |  | بكرة سوليتب عادي | 910010000181 | Administration | Received | 2021-12-30 | Accounted transaction received
2742462 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 1345 | 1 | فايل ملفات ارشيف |  | Each | 50 | 47340025 |  |  |  | فايل ملفات ارشيف | 910010000188 | Administration | Received | 2021-12-30 | Accounted transaction received
2742463 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 99.6 | 1 | سنون 0.7مم |  | Each | 24 | 47340026 |  |  |  | سنون 0.7مم | 910010000191 | Administration | Received | 2021-12-30 | Accounted transaction received
2742464 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 25 | 1 | قلم ماركر يوكن ازرق |  | Each | 5 | 47340027 |  |  |  | قلم ماركر يوكن ازرق | 910010000091 | Administration | Received | 2021-12-30 | Accounted transaction received
2742465 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 190 | 1 | فواصل كرتون مقاس 10 * 31 سم (100 قطعة) |  | Each | 5 | 47340028 |  |  |  | فواصل كرتون مقاس 10 * 31 سم (100 قطعة) | 910010000169 | Administration | Received | 2021-12-30 | Accounted transaction received
2742466 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 70 | 1 | ورق صابون |  | Each | 10 | 47340029 |  |  |  | ورق صابون | 910010000228 | Administration | Received | 2021-12-30 | Accounted transaction received
2742467 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 821 | 1 | دباسة كبيرة 150 ورقة |  | Each | 3 | 47340030 |  |  |  | دباسة كبيرة 150 ورقة | 910010000245 | Administration | Received | 2021-12-30 | Accounted transaction received
2742468 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 300 | 1 | قلم سنون روترنج 0.7 مم |  | Each | 24 | 47340031 |  |  |  | قلم سنون روترنج 0.7 مم | 910010000251 | Administration | Received | 2021-12-30 | Accounted transaction received
2742469 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 220 | 1 | دفتر Material Request |  | Each | 20 | 47340032 |  |  |  | دفتر Material Request | 910010000269 | Administration | Received | 2021-12-30 | Accounted transaction received
2742470 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 285 | 1 | قلم جاف Zebra |  | Each | 60 | 47340033 |  |  |  | قلم جاف Zebra | 910010000363 | Administration | Received | 2021-12-30 | Accounted transaction received
2742471 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2021-12-28 | Stationary |  |  |  | Office and Site expenses | Waldorf Astoria-0164 | 145 | 1 | كوريكتور شريط |  | Each | 10 | 47340034 |  |  |  | كوريكتور شريط | 910010000478 | Administration | Received | 2021-12-30 | Accounted transaction received
2742472 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 138 | 1 | أسمنت أسود |  | Ton | 0.1 | 47344529 |  |  |  | أسمنت أسود | 140010000003 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742473 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 20 | 1 | مواسير PPR قطر 20 مم للمياه البارده و الساخنه |  | Meter | 1 | 47344530 |  |  |  | مواسير PPR قطر 20 مم للمياه البارده و الساخنه | 060010300001 | MEP | Received | 2021-12-30 | Accounted transaction received
2742474 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 45 | 1 | مسلوب لحام PPR مقاس 25-20 مم |  | Each | 3 | 47344531 |  |  |  | مسلوب لحام PPR مقاس 25-20 مم | 060010300146 | MEP | Received | 2021-12-30 | Accounted transaction received
2742475 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 240 | 1 | كوع لحام PPR قطر 25 مم |  | Each | 20 | 47344532 |  |  |  | كوع لحام PPR قطر 25 مم | 060010300037 | MEP | Received | 2021-12-30 | Accounted transaction received
2742476 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 60 | 1 | كوع لحام 45 درجه PPR قطر 25 مم |  | Each | 6 | 47344533 |  |  |  | كوع لحام 45 درجه PPR قطر 25 مم | 060010300048 | MEP | Received | 2021-12-30 | Accounted transaction received
2742477 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 156 | 1 | مشترك لحام PPR قطر 20 مم |  | Each | 12 | 47344534 |  |  |  | مشترك لحام PPR قطر 20 مم | 060010300069 | MEP | Received | 2021-12-30 | Accounted transaction received
2742478 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 10 | 1 | مشترك لحام PPR قطر 25 مم |  | Each | 1 | 47344535 |  |  |  | مشترك لحام PPR قطر 25 مم | 060010300070 | MEP | Received | 2021-12-30 | Accounted transaction received
2742479 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 15039.97 | 1 | الواح كونتر 1.22م*2.44م*18مم |  | Each | 32 | 47344536 |  |  |  | الواح كونتر 1.22م*2.44م*18مم | 090040000018 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742480 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 23499.96 | 1 | الواح كونتر 1.22م*2.44م*18مم |  | Each | 50 | 47344537 |  |  |  | الواح كونتر 1.22م*2.44م*18مم | 090040000018 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742481 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 8000 | 1 | خشب موسكي 2بوصة *4بوصة* 6م |  | Cubic Meter | 1 | 47344538 |  |  |  | خشب موسكي 2بوصة *4بوصة* 6م | 090030000012 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742482 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 11999.99 | 1 | خشب موسكي 2بوصة*4بوصة*3م |  | Cubic Meter | 1.5 | 47344539 |  |  |  | خشب موسكي 2بوصة*4بوصة*3م | 090030000025 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742483 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 300 | 1 | سلة مهملات |  | Each | 5 | 47344563 |  |  |  | سلة مهملات | 200010000083 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742484 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 26.25 | 1 | جبس |  | Ton | 0.02 | 47344564 |  |  |  | جبس | 140010000004 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742485 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 62.7 | 1 | شريط لحام اللون اسود |  | Each | 10 | 47344565 |  |  |  | شريط لحام اللون اسود | 030130400006 | MEP | Received | 2021-12-30 | Accounted transaction received
2742486 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 30 | 1 | شاسية لمفتاح او بريزة |  | Each | 6 | 47344566 |  |  |  | شاسية لمفتاح او بريزة | 039010000006 | MEP | Received | 2021-12-30 | Accounted transaction received
2742487 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 160 | 1 | مشترك كهرباء ثلاثى 5 عين |  | Each | 2 | 47344567 |  |  |  | مشترك كهرباء ثلاثى 5 عين | 039010000019 | MEP | Received | 2021-12-30 | Accounted transaction received
2742488 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 50 | 1 | رزة قفل |  | Each | 2 | 47344568 |  |  |  | رزة قفل | 039020100061 | MEP | Received | 2021-12-30 | Accounted transaction received
2742489 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 180 | 1 | مشترك كهرباء 4 عين |  | Each | 2 | 47344569 |  |  |  | مشترك كهرباء 4 عين | 039010000030 | MEP | Received | 2021-12-30 | Accounted transaction received
2742490 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2021-12-28 | Other |  |  |  | Other | Waldorf Astoria-0164 | 65 | 1 | حبل سلبة |  | Meter | 50 | 47344570 |  |  |  | حبل سلبة | 010050000106 | Safety | Received | 2021-12-30 | Accounted transaction received
2742491 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 5814 | 1 | سلك ترمو 2*3 |  | Meter | 300 | 47344571 |  |  |  | سلك ترمو 2*3 | 030030101047 | MEP | Received | 2021-12-30 | Accounted transaction received
2742492 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 3065.46 | 1 | كابل ترمو بلاستيك 2*6 |  | Meter | 100 | 47344572 |  |  |  | كابل ترمو بلاستيك 2*6 | 030030101052 | MEP | Received | 2021-12-30 | Accounted transaction received
2742493 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 11602.94 | 1 | كابل داتا UTP CAT6 |  | Meter | 1300 | 47344573 |  |  |  | كابل داتا UTP CAT6 | 032030000005 | MEP | Received | 2021-12-30 | Accounted transaction received
2742494 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 319.2 | 1 | شريط قياس 10م |  | Each | 4 | 47344598 |  |  |  | شريط قياس 10م | 200010000101 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742501 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 34.2 | 1 | فوطة صفراء |  | Each | 6 | 47344605 |  |  |  | فوطة صفراء | 200010000478 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742502 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 100 | 1 | مفصلة 11 سم |  | Each | 20 | 47344606 |  |  |  | مفصلة 11 سم | 200010001110 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742503 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 90 | 1 | مشترك كهرباء حائطى |  | Each | 6 | 47344607 |  |  |  | مشترك كهرباء حائطى | 200010001191 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742504 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 130 | 1 | جرس مكتب |  | Each | 2 | 47344608 |  |  |  | جرس مكتب | 700020000103 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742505 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 286.12 | 1 | مطرقة 1.5كيلو |  | Each | 5 | 47344640 |  |  |  | مطرقة 1.5كيلو | 200010000231 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742506 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 120 | 1 | قلم دوكو |  | Each | 6 | 47344641 |  |  |  | قلم دوكو | 200010000171 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742507 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 60 | 1 | قلم فسفوري استدلر |  | Each | 2 | 47344642 |  |  |  | قلم فسفوري استدلر | 910010000117 | Administration | Received | 2021-12-30 | Accounted transaction received
2742508 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 471.62 | 1 | كوريك باليد |  | Each | 10 | 47344643 |  |  |  | كوريك باليد | 200010000443 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742509 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 76.69 | 1 | مسطرين |  | Each | 5 | 47344644 |  |  |  | مسطرين | 200010000445 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742510 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 25 | 1 | رزة |  | Each | 5 | 47344645 |  |  |  | رزة | 200010000653 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742511 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 35 | 1 | مزيل صدأW40 |  | Each | 1 | 47344646 |  |  |  | مزيل صدأW40 | 200010000665 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742512 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 75 | 1 | قلب سلندر |  | Each | 1 | 47344647 |  |  |  | قلب سلندر | 200010000682 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742513 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 240 | 1 | مفتاح بلدي مشرشر 24 |  | Each | 4 | 47344648 |  |  |  | مفتاح بلدي مشرشر 24 | 200010000882 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742514 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 120 | 1 | فلوماك |  | Each | 12 | 47344649 |  |  |  | فلوماك | 200010000917 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742515 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 115 | 1 | أجنة تكسير يدوى |  | Each | 5 | 47344650 |  |  |  | أجنة تكسير يدوى | 200010000508 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742516 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 1710 | 1 | شيكارة بلاستيك فارغة |  | Each | 1000 | 47344651 |  |  |  | شيكارة بلاستيك فارغة | 200010000115 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742517 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 171 | 1 | بنطة أجنة لهيلتي 70 |  | Each | 2 | 47344652 |  |  |  | بنطة أجنة لهيلتي 70 | 200010000998 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742518 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 171 | 1 | اسبراي الوان |  | Each | 6 | 47344653 |  |  |  | اسبراي الوان | 200010001522 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742519 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 364.8 | 1 | شريط قياس صلب 7متر |  | Each | 4 | 47344654 |  |  |  | شريط قياس صلب 7متر | 200010001715 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742520 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Other |  |  |  | Other | Waldorf Astoria-0164 | 3100.81 | 1 | سيفتي عمال |  | Each | 13 | 47345469 |  |  |  | سيفتي عمال | 010030000002 | Safety | Received | 2021-12-30 | Accounted transaction received
2742521 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Other |  |  |  | Other | Waldorf Astoria-0164 | 147.63 | 1 | نظارة مهندسين M3 بيضاء |  | Each | 14 | 47345470 |  |  |  | نظارة مهندسين M3 بيضاء | 010060000004 | Safety | Received | 2021-12-30 | Accounted transaction received
2742522 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Other |  |  |  | Other | Waldorf Astoria-0164 | 471.22 | 1 | خوذة صفراء |  | Each | 15 | 47345471 |  |  |  | خوذة صفراء | 010040000010 | Safety | Received | 2021-12-30 | Accounted transaction received
2742523 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Other |  |  |  | Other | Waldorf Astoria-0164 | 161.86 | 1 | جوانتي محبب |  | Each | 23 | 47345472 |  |  |  | جوانتي محبب | 010010000006 | Safety | Received | 2021-12-30 | Accounted transaction received
2742524 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Other |  |  |  | Other | Waldorf Astoria-0164 | 736.71 | 1 | فيست برتقالي |  | Each | 33 | 47345473 |  |  |  | فيست برتقالي | 010020000008 | Safety | Received | 2021-12-30 | Accounted transaction received
2742525 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Other |  |  |  | Other | Waldorf Astoria-0164 | 430.29 | 1 | فيست ليموني |  | Each | 19 | 47345474 |  |  |  | فيست ليموني | 010020000009 | Safety | Received | 2021-12-30 | Accounted transaction received
2742526 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 25 | 1 | بلاستيك CD ظرف |  | Each | 50 | 47345475 |  |  |  | بلاستيك CD ظرف | 910010000136 | Administration | Received | 2021-12-30 | Accounted transaction received
2742527 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Other |  |  |  | Other | Waldorf Astoria-0164 | 168.95 | 1 | جوانتي باور جراب |  | Each | 13 | 47345476 |  |  |  | جوانتي باور جراب | 010010000009 | Safety | Received | 2021-12-30 | Accounted transaction received
2742528 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 50 | 1 | تى 1/2 بوصة بسن |  | Each | 5 | 47345477 |  |  |  | تى 1/2 بوصة بسن | 240070000176 | MEP | Received | 2021-12-30 | Accounted transaction received
2742529 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 118.56 | 1 | كنكة قهوة |  | Each | 3 | 47345478 |  |  |  | كنكة قهوة | 700020000070 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742530 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 369 | 1 | سخان بلاطة عين واحدة |  | Each | 1 | 47345479 |  |  |  | سخان بلاطة عين واحدة | 200010001341 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742531 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-28 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 680 | 1 | صندوق قمامة بلاستيك (سعة 260 لتر) |  | Each | 2 | 47345480 |  |  |  | صندوق قمامة بلاستيك (سعة 260 لتر) | 700020000173 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742532 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2021-12-28 | Elec. Conduits |  |  |  | Materials | Waldorf Astoria-0164 | 29204.06 | 1 | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) |  | Meter | 2160 | 47346209 |  |  |  | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) | 030010000052 | MEP | Received | 2021-12-30 | Accounted transaction received
2742533 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2021-12-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 417.24 | 1 | جلبة ماسورة 20مم UPVC (اللون أبيض) |  | Each | 200 | 47346210 |  |  |  | جلبة ماسورة 20مم UPVC (اللون أبيض) | 030010000067 | MEP | Received | 2021-12-30 | Accounted transaction received
2742534 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2021-12-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2267.18 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 925 | 47346211 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2021-12-30 | Accounted transaction received
2742535 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2021-12-28 | Elec. Conduits |  |  |  | Materials | Waldorf Astoria-0164 | 8493.71 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 25مم وقطر خارجى 31.1مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 23 | 47346212 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 25مم وقطر خارجى 31.1مم طول اللفه 30 متر(اللون رمادى) | 030010000062 | MEP | Received | 2021-12-30 | Accounted transaction received
2742536 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2021-12-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 175.28 | 1 | بواط نهاية UPVC لماسورة 20مم(اللون أبيض) |  | Each | 25 | 47346213 |  |  |  | بواط نهاية UPVC لماسورة 20مم(اللون أبيض) | 030010000080 | MEP | Received | 2021-12-30 | Accounted transaction received
2742537 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2021-12-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 31.01 | 1 | بواط إمتداد UPVC لماسورة 20مم(اللون أبيض) |  | Each | 4 | 47346214 |  |  |  | بواط إمتداد UPVC لماسورة 20مم(اللون أبيض) | 030010000082 | MEP | Received | 2021-12-30 | Accounted transaction received
2742538 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2021-12-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 271.32 | 1 | بواط زاوية UPVC لماسورة 20مم(اللون أبيض) |  | Each | 35 | 47346215 |  |  |  | بواط زاوية UPVC لماسورة 20مم(اللون أبيض) | 030010000084 | MEP | Received | 2021-12-30 | Accounted transaction received
2742539 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2021-12-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 25 | 1 | بواط زاوية UPVC لماسورة 25مم(اللون أبيض) |  | Each | 3 | 47346216 |  |  |  | بواط زاوية UPVC لماسورة 25مم(اللون أبيض) | 030010000085 | MEP | Received | 2021-12-30 | Accounted transaction received
2742540 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2021-12-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 208.97 | 1 | بواط ثلاثي UPVC لماسورة 25مم(اللون أبيض) |  | Each | 23 | 47346217 |  |  |  | بواط ثلاثي UPVC لماسورة 25مم(اللون أبيض) | 030010000087 | MEP | Received | 2021-12-30 | Accounted transaction received
2742541 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2021-12-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2571.5 | 1 | أدابتور UPVC لماسورة 20مم(اللون أبيض) |  | Each | 618 | 47346218 |  |  |  | أدابتور UPVC لماسورة 20مم(اللون أبيض) | 030010000096 | MEP | Received | 2021-12-30 | Accounted transaction received
2742563 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.09 | Water & SewageExpens | 17 | Indirect Cost |  | 2021-12-29 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 74.1 | 1 | جلبة لحام 3/4بوصة |  | Each | 10 | 47384118 |  |  |  | جلبة لحام 3/4بوصة | 240020000041 | MEP | Received | 2021-12-30 | Accounted transaction received
2742542 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2021-12-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 10681.34 | 1 | أدابتور UPVC لماسورة 25مم(اللون أبيض) |  | Each | 1830 | 47346219 |  |  |  | أدابتور UPVC لماسورة 25مم(اللون أبيض) | 030010000097 | MEP | Received | 2021-12-30 | Accounted transaction received
2742543 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2021-12-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 160.51 | 1 | جلبة UPVC مخفضة 25/20مم (اللون أبيض) |  | Each | 55 | 47346220 |  |  |  | جلبة UPVC مخفضة 25/20مم (اللون أبيض) | 030010000101 | MEP | Received | 2021-12-30 | Accounted transaction received
2742544 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2021-12-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 832.2 | 1 | أفيز 20مم UPVC(اللون أبيض) |  | Each | 200 | 47346703 |  |  |  | أفيز 20مم UPVC(اللون أبيض) | 030010000106 | MEP | Received | 2021-12-30 | Accounted transaction received
2742545 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2021-12-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 12164.88 | 1 | أفيز 25مم UPVC(اللون أبيض) |  | Each | 2335 | 47346704 |  |  |  | أفيز 25مم UPVC(اللون أبيض) | 030010000107 | MEP | Received | 2021-12-30 | Accounted transaction received
2742546 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2021-12-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 13527.81 | 1 | جلاند فلكسبل مقاس 25 مم |  | Each | 1350 | 47346705 |  |  |  | جلاند فلكسبل مقاس 25 مم | 030010000170 | MEP | Received | 2021-12-30 | Accounted transaction received
2742547 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2021-12-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3664.19 | 1 | مسمار 8 مم + فيشر 8 مم طول 4 سم |  | Each | 4870 | 47346706 |  |  |  | مسمار 8 مم + فيشر 8 مم طول 4 سم | 030120200007 | MEP | Received | 2021-12-30 | Accounted transaction received
2742548 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2021-12-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 9846.86 | 1 | UPVC BACK BOX 10X10 |  | Each | 590 | 47346707 |  |  |  | UPVC BACK BOX 10X10 | 030069000025 | MEP | Received | 2021-12-30 | Accounted transaction received
2742549 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2021-12-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 16874.98 | 1 | Metal Galvanized back box 7x14 cm with deep 47 mm |  | Each | 252 | 47346708 |  |  |  | Metal Galvanized back box 7x14 cm with deep 47 mm | 030069000027 | MEP | Received | 2021-12-30 | Accounted transaction received
2742550 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Other |  |  |  | Other | Waldorf Astoria-0164 | 39763.2 | 1 | بولي ايثيلين 200 ميكرون شفاف |  | Kilogram | 1090 | 47347738 |  |  |  | بولي ايثيلين 200 ميكرون شفاف | 040010000042 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742551 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Other |  |  |  | Other | Waldorf Astoria-0164 | 1590.51 | 1 | تيب مسلح |  | Each | 100 | 47347739 |  |  |  | تيب مسلح | 200010000382 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742552 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Other |  |  |  | Other | Waldorf Astoria-0164 | 4326.3 | 1 | استريتش كبير |  | Kilogram | 115 | 47347740 |  |  |  | استريتش كبير | 200010000013 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742553 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Other |  |  |  | Other | Waldorf Astoria-0164 | 18410.68 | 1 | فوم باركية |  | Roll | 68 | 47347741 |  |  |  | فوم باركية | 040010000080 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742554 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Other |  |  |  | Other | Waldorf Astoria-0164 | 3306 | 1 | لفائف بلاستيكية ذات فقاعات هواء |  | Roll | 20 | 47347742 |  |  |  | لفائف بلاستيكية ذات فقاعات هواء | 040010000103 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742555 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-28 | Other |  |  |  | Other | Waldorf Astoria-0164 | 6258.6 | 1 | كرتون مضلع - تغليف |  | Kilogram | 488 | 47347743 |  |  |  | كرتون مضلع - تغليف | 910010000387 | Administration | Received | 2021-12-30 | Accounted transaction received
2742556 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 3.00. | Concrete Works | 3 | CONCRETE WORK |  | 2021-12-29 | Steel Fixer |  |  |  | Direct Manpower | Waldorf Astoria-0164 | 1965.99 | 1 | حديد تسليح قطر 10مم |  | Ton | 0.13 | 47368049 |  |  |  | حديد تسليح قطر 10مم | 150010000001 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742557 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 3.00. | Concrete Works | 3 | CONCRETE WORK |  | 2021-12-29 | Steel Fixer |  |  |  | Direct Manpower | Waldorf Astoria-0164 | 19044.59 | 1 | حديد تسليح قطر 12 مم |  | Ton | 1.26 | 47368050 |  |  |  | حديد تسليح قطر 12 مم | 150010000002 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742558 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 3.00. | Concrete Works | 3 | CONCRETE WORK |  | 2021-12-29 | Steel Fixer |  |  |  | Direct Manpower | Waldorf Astoria-0164 | 26851.57 | 1 | حديد تسليح قطر 16 مم |  | Ton | 1.78 | 47368051 |  |  |  | حديد تسليح قطر 16 مم | 150010000004 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742559 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 3.00. | Concrete Works | 3 | CONCRETE WORK |  | 2021-12-29 | Steel Fixer |  |  |  | Direct Manpower | Waldorf Astoria-0164 | 3857.48 | 1 | حديد تسليح قطر 18 مم |  | Ton | 0.26 | 47368052 |  |  |  | حديد تسليح قطر 18 مم | 150010000005 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742560 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 3.00. | Concrete Works | 3 | CONCRETE WORK |  | 2021-12-29 | Steel Fixer |  |  |  | Direct Manpower | Waldorf Astoria-0164 | 11803.26 | 1 | حديد تسليح قطر 22 مم |  | Ton | 0.78 | 47368053 |  |  |  | حديد تسليح قطر 22 مم | 150010000007 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742561 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-29 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 60 | 1 | مسمار بفيشر 8 مم سقف |  | Each | 1 | 47384116 |  |  |  | مسمار بفيشر 8 مم سقف | 200020000054 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742562 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-29 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 45 | 1 | منشار خشابي |  | Each | 1 | 47384117 |  |  |  | منشار خشابي | 200010000300 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742564 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-29 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 12.5 | 1 | ميدالية بلاستيك صغيرة |  | Each | 10 | 47384120 |  |  |  | ميدالية بلاستيك صغيرة | 910010000162 | Administration | Received | 2021-12-30 | Accounted transaction received
2742565 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-29 | Other |  |  |  | Other | Waldorf Astoria-0164 | 8 | 1 | كيس استيك نقدية 75جرام |  | Each | 1 | 47384121 |  |  |  | كيس استيك نقدية 75جرام | 910010000210 | Administration | Received | 2021-12-30 | Accounted transaction received
2742566 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-29 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 90 | 1 | فرشة سلك يدوي |  | Each | 3 | 47384122 |  |  |  | فرشة سلك يدوي | 200010000438 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742567 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.09 | Water & SewageExpens | 17 | Indirect Cost |  | 2021-12-29 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 54.72 | 1 | طبة تسليك مقاس 110 مم |  | Each | 1 | 47384123 |  |  |  | طبة تسليك مقاس 110 مم | 060010100190 | MEP | Received | 2021-12-30 | Accounted transaction received
2742568 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.09 | Water & SewageExpens | 17 | Indirect Cost |  | 2021-12-29 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 13.68 | 1 | جلبة صرف ابيض قطر 1.5" |  | Each | 2 | 47384124 |  |  |  | جلبة صرف ابيض قطر 1.5" | 060010100322 | MEP | Received | 2021-12-30 | Accounted transaction received
2742569 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.09 | Water & SewageExpens | 17 | Indirect Cost |  | 2021-12-29 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 63.84 | 1 | مشترك 90 درجه لصق UPVC مقاس 110 مم ضغط رمادى |  | Each | 1 | 47384125 |  |  |  | مشترك 90 درجه لصق UPVC مقاس 110 مم ضغط رمادى | 060010100373 | MEP | Received | 2021-12-30 | Accounted transaction received
2742570 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.09 | Water & SewageExpens | 17 | Indirect Cost |  | 2021-12-29 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 68.4 | 1 | مشترك مسلوب لصق UPVC مقاس 110-50 مم ضغط رمادى |  | Each | 2 | 47384126 |  |  |  | مشترك مسلوب لصق UPVC مقاس 110-50 مم ضغط رمادى | 060010100410 | MEP | Received | 2021-12-30 | Accounted transaction received
2742571 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.09 | Water & SewageExpens | 17 | Indirect Cost |  | 2021-12-29 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 1140 | 1 | مواسير PPR قطر 25 مم للمياه البارده و الساخنه |  | Meter | 40 | 47384127 |  |  |  | مواسير PPR قطر 25 مم للمياه البارده و الساخنه | 060010300002 | MEP | Received | 2021-12-30 | Accounted transaction received
2742572 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.09 | Water & SewageExpens | 17 | Indirect Cost |  | 2021-12-29 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 95.76 | 1 | مواسير PPR قطر 50 مم للمياه البارده و الساخنه |  | Meter | 3 | 47384128 |  |  |  | مواسير PPR قطر 50 مم للمياه البارده و الساخنه | 060010300005 | MEP | Received | 2021-12-30 | Accounted transaction received
2742573 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.09 | Water & SewageExpens | 17 | Indirect Cost |  | 2021-12-29 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 149.34 | 1 | مشترك لحام PPR قطر 110 مم |  | Each | 1 | 47384129 |  |  |  | مشترك لحام PPR قطر 110 مم | 060010300077 | MEP | Received | 2021-12-30 | Accounted transaction received
2742574 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.09 | Water & SewageExpens | 17 | Indirect Cost |  | 2021-12-29 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 137.94 | 1 | لزق حار 814 |  | Each | 2 | 47384130 |  |  |  | لزق حار 814 | 200010000609 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742575 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-29 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 25 | 1 | مسمار سن صاج 3 سم |  | Kilogram | 0.5 | 47384131 |  |  |  | مسمار سن صاج 3 سم | 200020000239 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742576 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-29 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 114 | 1 | دواية لمبة قلاووظ |  | Each | 20 | 47384132 |  |  |  | دواية لمبة قلاووظ | 039010400001 | MEP | Received | 2021-12-30 | Accounted transaction received
2742577 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-29 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 456 | 1 | لمبة موفرة |  | Each | 20 | 47384133 |  |  |  | لمبة موفرة | 039010400002 | MEP | Received | 2021-12-30 | Accounted transaction received
2742578 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-29 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 30 | 1 | مفك صليبه صغير |  | Each | 1 | 47384134 |  |  |  | مفك صليبه صغير | 039020300036 | MEP | Received | 2021-12-30 | Accounted transaction received
2742579 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.07 | Computers | 17 | Indirect Cost |  | 2021-12-29 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 630 | 1 | مشترك كهرباء 4 عين |  | Each | 6 | 47384135 |  |  |  | مشترك كهرباء 4 عين | 039010000030 | MEP | Received | 2021-12-30 | Accounted transaction received
2742580 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2021-12-29 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 165 | 1 | معجون دهان GLC |  | Can | 1 | 47384136 |  |  |  | معجون دهان GLC | 050010000113 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742581 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2021-12-29 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 1710 | 1 | Mosaic sheet tiles size 31.6*31.6 |  | Square Meter | 0.2 | 47384137 |  |  |  | Mosaic sheet tiles size 31.6*31.6 | 170010000305 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742582 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2021-12-29 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 875 | 1 | مسمار خشابى 5 سم |  | Kilogram | 50 | 47384138 |  |  |  | مسمار خشابى 5 سم | 200020000562 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742583 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-29 | Other |  |  |  | Other | Waldorf Astoria-0164 | 250 | 1 | خيش بال |  | Square Meter | 25 | 47384752 |  |  |  | خيش بال | 040010000026 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742584 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-29 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 50 | 1 | شريط قياس 5م |  | Each | 1 | 47384753 |  |  |  | شريط قياس 5م | 200010000105 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742585 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.07 | Computers | 17 | Indirect Cost |  | 2021-12-29 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 220 | 1 | VGA Converter to HDMI |  | Each | 1 | 47384754 |  |  |  | VGA Converter to HDMI | 800050000033 | IT | Received | 2021-12-30 | Accounted transaction received
2742586 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-29 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 85.5 | 1 | كتر |  | Each | 3 | 47386541 |  |  |  | كتر | 200010000182 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742587 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-29 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 467.37 | 1 | تيب مسلح |  | Each | 28 | 47386542 |  |  |  | تيب مسلح | 200010000382 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742588 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-29 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 45.6 | 1 | سلاح كتر |  | Each | 2 | 47386543 |  |  |  | سلاح كتر | 200010000411 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742589 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-29 | Other |  |  |  | Other | Waldorf Astoria-0164 | 171 | 1 | مسمار صلب 6سم |  | Kilogram | 3 | 47386544 |  |  |  | مسمار صلب 6سم | 200020000075 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742590 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2021-12-29 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 1453.5 | 1 | فوم ابيض سمك 2 سم كثافة 17 |  | Cubic Meter | 3 | 47386545 |  |  |  | فوم ابيض سمك 2 سم كثافة 17 | 040010000011 | Purchasing | Received | 2021-12-30 | Accounted transaction received
2742591 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.07 | Computers | 17 | Indirect Cost |  | 2021-12-29 | Accomodation |  |  |  | Indirect | Waldorf Astoria-0164 | 1140 | 1 | كابل داتا UTP CAT6 |  | Meter | 100 | 47386546 |  |  |  | كابل داتا UTP CAT6 | 032030000005 | MEP | Received | 2021-12-30 | Accounted transaction received
3794542 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 15732 | 1 | Resilient Seated OS&Y Flanged Gate Valve 300PSI Size 4", Model: REL-OSY-L399F (ANSI) Part No. 7U99002341 Class 150 |  | Each | 1 | 59762218 |  |  |  | Resilient Seated OS&Y Flanged Gate Valve 300PSI Size 4", Model: REL-OSY-L399F (ANSI) Part No. 7U99002341 Class 150 | 060170400033 | MEP | Received | 2023-02-05 | Accounted transaction received
3795542 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 969 | 1 | Wire Nut 4mm |  | Each | 10 | 59753713 |  |  |  | Wire Nut 4mm | 030130800016 | MEP | Received | 2023-02-05 | Accounted transaction received
3795543 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2094.74 | 1 | بواط واتر بروف بفتحات مقاس 19 × 24 × 9 سم |  | Each | 12 | 59753632 |  |  |  | بواط واتر بروف بفتحات مقاس 19 × 24 × 9 سم | 030010000183 | MEP | Received | 2023-02-05 | Accounted transaction received
3795544 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 520.33 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 8 | 59753633 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-02-05 | Accounted transaction received
3795545 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 53618.18 | 1 | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 |  | Each | 45 | 59753634 |  |  |  | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 | 030060100182 | MEP | Received | 2023-02-05 | Accounted transaction received
3795546 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 939.82 | 1 | FUSED 13A SWITCH +NEON SQ ALU Code 572651 |  | Each | 2 | 59753635 |  |  |  | FUSED 13A SWITCH +NEON SQ ALU Code 572651 | 030060100186 | MEP | Received | 2023-02-05 | Accounted transaction received
3795547 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 107251.2 | 1 | FIRE RESISTANT CABLE , 950°c 2x2.5 mm |  | Meter | 1500 | 59753636 |  |  |  | FIRE RESISTANT CABLE , 950°c 2x2.5 mm | 032010000001 | MEP | Received | 2023-02-05 | Accounted transaction received
3795548 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1065.9 | 1 | سلك نحاس مجدول مقاس 3 مم اللون أصفر × أخضر (cu/pvc) |  | Meter | 100 | 59753637 |  |  |  | سلك نحاس مجدول مقاس 3 مم اللون أصفر × أخضر (cu/pvc) | 030030101022 | MEP | Received | 2023-02-05 | Accounted transaction received
3795549 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 833.44 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أصفر (cu/pvc) |  | Meter | 100 | 59753638 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أصفر (cu/pvc) | 030030101024 | MEP | Received | 2023-02-05 | Accounted transaction received
3795550 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4595.63 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) |  | Meter | 600 | 59753639 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) | 030030101026 | MEP | Received | 2023-02-05 | Accounted transaction received
3795551 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2270.14 | 1 | سلك نحاس مجدول مقاس 3 مم اللون أزرق (cu/pvc) |  | Meter | 300 | 59753640 |  |  |  | سلك نحاس مجدول مقاس 3 مم اللون أزرق (cu/pvc) | 030030101020 | MEP | Received | 2023-02-05 | Accounted transaction received
3795552 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 95.09 | 1 | mosaic adapter code 69580 |  | Each | 1 | 59753641 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-02-05 | Accounted transaction received
3795553 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 80.25 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 1 | 59753642 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-02-05 | Accounted transaction received
3795554 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 515.09 | 1 | DS , 4 pole , 40A , 400V , abs enclosure IP 65 Code : KEM 440U Y/R ABS |  | Each | 1 | 59753643 |  |  |  | DS , 4 pole , 40A , 400V , abs enclosure IP 65 Code : KEM 440U Y/R ABS | 030060200073 | MEP | Received | 2023-02-05 | Accounted transaction received
3795555 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 23461.2 | 1 | Fire Resistance Cable FIRECEL SR114H 300/500V EN50200 BS5839,BS7629-1,BS6387 CWZ 950C LPCB 217F ( Size 2*1.5 mm ) |  | Meter | 500 | 59753644 |  |  |  | Fire Resistance Cable FIRECEL SR114H 300/500V EN50200 BS5839,BS7629-1,BS6387 CWZ 950C LPCB 217F ( Size 2*1.5 mm ) | 032010000012 | MEP | Received | 2023-02-05 | Accounted transaction received
3795556 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 18160.77 | 1 | Fire Resistance Cable FIRECEL SR114H 300/500V EN50200 BS5839,BS7629-1,BS6387 CWZ 950C LPCB 217F ( Size 2*2.5 mm ) |  | Meter | 422 | 59753645 |  |  |  | Fire Resistance Cable FIRECEL SR114H 300/500V EN50200 BS5839,BS7629-1,BS6387 CWZ 950C LPCB 217F ( Size 2*2.5 mm ) | 032010000013 | MEP | Received | 2023-02-05 | Accounted transaction received
3795557 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 130.01 | 1 | Double pole switches 32 A – 250V~ 1 gang 1?way switch + led power indicator - 617629 |  | Each | 1 | 59753646 |  |  |  | Double pole switches 32 A – 250V~ 1 gang 1?way switch + led power indicator - 617629 | 030060100943 | MEP | Received | 2023-02-05 | Accounted transaction received
3795558 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 638.97 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 190 | 59753696 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-02-05 | Accounted transaction received
3795559 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2939.47 | 1 | سلك نحاس مصمت مقاس 1.5 مم اللون أسود (cu/pvc) جهد (750/450) |  | Meter | 500 | 59753697 |  |  |  | سلك نحاس مصمت مقاس 1.5 مم اللون أسود (cu/pvc) جهد (750/450) | 030030100253 | MEP | Received | 2023-02-05 | Accounted transaction received
3795560 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4582.8 | 1 | سلك نحاس مصمت مقاس 3 مم اللون أحمر (cu/pvc) جهد (750/450) |  | Meter | 400 | 59753698 |  |  |  | سلك نحاس مصمت مقاس 3 مم اللون أحمر (cu/pvc) جهد (750/450) | 030030100277 | MEP | Received | 2023-02-05 | Accounted transaction received
3795561 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 138.97 | 1 | جلاند فلكسبل مقاس 25 مم |  | Each | 10 | 59753699 |  |  |  | جلاند فلكسبل مقاس 25 مم | 030010000170 | MEP | Received | 2023-02-05 | Accounted transaction received
3795562 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5719.51 | 1 | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 |  | Meter | 61 | 59753700 |  |  |  | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 | 030020100002 | MEP | Received | 2023-02-05 | Accounted transaction received
3795563 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 360.87 | 1 | جلبة ماسورة EMT المقاس ¾ " |  | Each | 20 | 59753701 |  |  |  | جلبة ماسورة EMT المقاس ¾ " | 030020100021 | MEP | Received | 2023-02-05 | Accounted transaction received
3795564 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 29400.6 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 500 | 59753702 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-02-05 | Accounted transaction received
3795565 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3274.71 | 1 | 576562 Code وش مربع فضي |  | Each | 100 | 59753703 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-02-05 | Accounted transaction received
3795566 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 456 | 1 | بادي اشعال 400 وات |  | Each | 2 | 59753704 |  |  |  | بادي اشعال 400 وات | 200010000603 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795567 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1368 | 1 | بكرة شريط لحام |  | Each | 80 | 59753705 |  |  |  | بكرة شريط لحام | 039010000003 | MEP | Received | 2023-02-05 | Accounted transaction received
3795568 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1482 | 1 | ترانس 400 وات |  | Each | 2 | 59753706 |  |  |  | ترانس 400 وات | 039010400005 | MEP | Received | 2023-02-05 | Accounted transaction received
3795569 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2131.8 | 1 | سلك نحاس مجدول مقاس 3 مم اللون أصفر × أخضر (cu/pvc) |  | Meter | 200 | 59753707 |  |  |  | سلك نحاس مجدول مقاس 3 مم اللون أصفر × أخضر (cu/pvc) | 030030101022 | MEP | Received | 2023-02-05 | Accounted transaction received
3795570 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2033.49 | 1 | سلك نحاس مجدول مقاس4 مم اللون أحمر (cu/pvc) |  | Meter | 200 | 59753708 |  |  |  | سلك نحاس مجدول مقاس4 مم اللون أحمر (cu/pvc) | 030030101023 | MEP | Received | 2023-02-05 | Accounted transaction received
3795571 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3333.75 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أصفر (cu/pvc) |  | Meter | 400 | 59753709 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أصفر (cu/pvc) | 030030101024 | MEP | Received | 2023-02-05 | Accounted transaction received
3795572 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1758.72 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أزرق (cu/pvc) |  | Meter | 200 | 59753710 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أزرق (cu/pvc) | 030030101025 | MEP | Received | 2023-02-05 | Accounted transaction received
3795573 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 6488.92 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أصفر × أخضر (cu/pvc) |  | Meter | 800 | 59753711 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أصفر × أخضر (cu/pvc) | 030030101027 | MEP | Received | 2023-02-05 | Accounted transaction received
3795574 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1026 | 1 | لمبة ميتالايت 400 وات |  | Each | 2 | 59753712 |  |  |  | لمبة ميتالايت 400 وات | 039010300012 | MEP | Received | 2023-02-05 | Accounted transaction received
3785542 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 37500 | 1 | 1.1 64001/2 |  | Currency | 1 |  | 10950 | دار الخبره والمشروعات الهندسيه |  | 1.1 64001/2 |  | Finacial | Received | 2023-02-04 | Accounted transaction received
3785543 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 12500 | 1 | 1.2 64001/2 |  | Currency | 1 |  | 10950 | دار الخبره والمشروعات الهندسيه |  | 1.2 64001/2 |  | Finacial | Received | 2023-02-04 | Accounted transaction received
3785544 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -225 | 1 | LABOUR_OFFICE 64001/2 |  | Currency | -225 |  | 10950 | دار الخبره والمشروعات الهندسيه |  | LABOUR_OFFICE 64001/2 |  | Finacial | Received | 2023-02-04 | Accounted transaction received
3785547 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 191520 | 1 | 1.1 72838/1 |  | Currency | 1 |  | 10847 | برونكس لتشغيل المعادن |  | 1.1 72838/1 |  | Finacial | Received | 2023-02-04 | Accounted transaction received
3785548 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -861.84 | 1 | LABOUR_OFFICE 72838/1 |  | Currency | -861.84 |  | 10847 | برونكس لتشغيل المعادن |  | LABOUR_OFFICE 72838/1 |  | Finacial | Received | 2023-02-04 | Accounted transaction received
3792027 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 750 | 1 | لمبة ليد |  | Each | 10 | 59710255 |  |  |  | لمبة ليد | 030040100001 | MEP | Received | 2023-02-05 | Accounted transaction received
3792028 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1374 | 1 | أنبوبة سليكون |  | Each | 30 | 59710256 |  |  |  | أنبوبة سليكون | 060019000001 | MEP | Received | 2023-02-05 | Accounted transaction received
3791949 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 400 | 1 | فيشر 8 مم |  | Carton | 16 | 59710099 |  |  |  | فيشر 8 مم | 200010000164 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3791950 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1841.33 | 1 | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) |  | Meter | 120 | 59710100 |  |  |  | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) | 030010000052 | MEP | Received | 2023-02-05 | Accounted transaction received
3791951 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2353.8 | 1 | بواط 10 * 10 عالى المقاس ¾ " |  | Each | 35 | 59710101 |  |  |  | بواط 10 * 10 عالى المقاس ¾ " | 030020100105 | MEP | Received | 2023-02-05 | Accounted transaction received
3791952 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 336.3 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 100 | 59710102 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-02-05 | Accounted transaction received
3791953 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2777.55 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 10 | 59710103 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) | 030010000059 | MEP | Received | 2023-02-05 | Accounted transaction received
3791954 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 738.58 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 25مم وقطر خارجى 31.1مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 2 | 59710104 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 25مم وقطر خارجى 31.1مم طول اللفه 30 متر(اللون رمادى) | 030010000062 | MEP | Received | 2023-02-05 | Accounted transaction received
3791955 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2351.58 | 1 | سلك نحاس مصمت مقاس 1.5 مم اللون أسود (cu/pvc) جهد (750/450) |  | Meter | 400 | 59710105 |  |  |  | سلك نحاس مصمت مقاس 1.5 مم اللون أسود (cu/pvc) جهد (750/450) | 030030100253 | MEP | Received | 2023-02-05 | Accounted transaction received
3791956 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 125 | 1 | بواط زاوية UPVC لماسورة 25مم(اللون أبيض) |  | Each | 15 | 59710106 |  |  |  | بواط زاوية UPVC لماسورة 25مم(اللون أبيض) | 030010000085 | MEP | Received | 2023-02-05 | Accounted transaction received
3791957 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1172.66 | 1 | أدابتور UPVC لماسورة 25مم(اللون أبيض) |  | Each | 150 | 59710107 |  |  |  | أدابتور UPVC لماسورة 25مم(اللون أبيض) | 030010000097 | MEP | Received | 2023-02-05 | Accounted transaction received
3791958 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1145.7 | 1 | سلك نحاس مصمت مقاس 3 مم اللون أحمر (cu/pvc) جهد (750/450) |  | Meter | 100 | 59710108 |  |  |  | سلك نحاس مصمت مقاس 3 مم اللون أحمر (cu/pvc) جهد (750/450) | 030030100277 | MEP | Received | 2023-02-05 | Accounted transaction received
3791959 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 125.63 | 1 | جلاند فلكسبل مقاس 16 مم |  | Each | 19 | 59710109 |  |  |  | جلاند فلكسبل مقاس 16 مم | 030010000167 | MEP | Received | 2023-02-05 | Accounted transaction received
3791960 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 486.38 | 1 | جلاند فلكسبل مقاس 25 مم |  | Each | 35 | 59710110 |  |  |  | جلاند فلكسبل مقاس 25 مم | 030010000170 | MEP | Received | 2023-02-05 | Accounted transaction received
3791961 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 523.69 | 1 | بواط واتر بروف بفتحات مقاس 19 × 24 × 9 سم |  | Each | 3 | 59710111 |  |  |  | بواط واتر بروف بفتحات مقاس 19 × 24 × 9 سم | 030010000183 | MEP | Received | 2023-02-05 | Accounted transaction received
3791962 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 11439.02 | 1 | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 |  | Meter | 122 | 59710112 |  |  |  | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 | 030020100002 | MEP | Received | 2023-02-05 | Accounted transaction received
3791963 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2746.83 | 1 | ماسورة صلب مجلفن EMT المقاس 2 " طول الماسورة 3.05 |  | Meter | 6.1 | 59710113 |  |  |  | ماسورة صلب مجلفن EMT المقاس 2 " طول الماسورة 3.05 | 030020100005 | MEP | Received | 2023-02-05 | Accounted transaction received
3791964 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 451.08 | 1 | جلبة ماسورة EMT المقاس ¾ " |  | Each | 25 | 59710114 |  |  |  | جلبة ماسورة EMT المقاس ¾ " | 030020100021 | MEP | Received | 2023-02-05 | Accounted transaction received
3791965 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 380.27 | 1 | جلبة ماسورة EMT المقاس 1 " |  | Each | 15 | 59710115 |  |  |  | جلبة ماسورة EMT المقاس 1 " | 030020100022 | MEP | Received | 2023-02-05 | Accounted transaction received
3791966 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 149.57 | 1 | جلبة ماسورة EMT المقاس 2 " |  | Each | 2 | 59710116 |  |  |  | جلبة ماسورة EMT المقاس 2 " | 030020100025 | MEP | Received | 2023-02-05 | Accounted transaction received
3791967 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2221.28 | 1 | أفيز أثنين جناح لماسورة EMT المقاس ¾ " |  | Each | 887 | 59710117 |  |  |  | أفيز أثنين جناح لماسورة EMT المقاس ¾ " | 030020100033 | MEP | Received | 2023-02-05 | Accounted transaction received
3791968 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 29.43 | 1 | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 |  | Each | 1 | 59710118 |  |  |  | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 | 030060100021 | MEP | Received | 2023-02-05 | Accounted transaction received
3791969 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2613.17 | 1 | HDMI PRE-CONN 1M Code 572596 |  | Each | 2 | 59710119 |  |  |  | HDMI PRE-CONN 1M Code 572596 | 030060100165 | MEP | Received | 2023-02-05 | Accounted transaction received
3791970 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1495.95 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 23 | 59710120 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-02-05 | Accounted transaction received
3791971 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 126.67 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 10 | 59710121 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-02-05 | Accounted transaction received
3791972 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 547.96 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 31 | 59710122 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-02-05 | Accounted transaction received
3791973 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3875.2 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 90 | 59710123 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-02-05 | Accounted transaction received
3791974 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1176.02 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 20 | 59710124 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-02-05 | Accounted transaction received
3791975 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 11711.44 | 1 | SHAVER SOCKET 230V/120-230V WITH EARTH CONNECTOR Code 572653 |  | Each | 17 | 59710125 |  |  |  | SHAVER SOCKET 230V/120-230V WITH EARTH CONNECTOR Code 572653 | 030060100178 | MEP | Received | 2023-02-05 | Accounted transaction received
3791976 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 16533.79 | 1 | SHAVER SOCKET 230V/120-230V WITH EARTH CONNECTOR Code 572653 |  | Each | 24 | 59710126 |  |  |  | SHAVER SOCKET 230V/120-230V WITH EARTH CONNECTOR Code 572653 | 030060100178 | MEP | Received | 2023-02-05 | Accounted transaction received
3791977 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 270 | 1 | لزق حار 717 (علبة ولدون |  | Each | 6 | 59710127 |  |  |  | لزق حار 717 (علبة ولدون | 200020000177 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3791978 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 350 | 1 | بنطة مسمار 24 مم |  | Each | 2 | 59710128 |  |  |  | بنطة مسمار 24 مم | 200010000843 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3791979 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 600 | 1 | مسمار 6 مم * 50 مم |  | Kilogram | 2.5 | 59710129 |  |  |  | مسمار 6 مم * 50 مم | 200020000221 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3791980 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 600 | 1 | سيليكون أبيض |  | Each | 12 | 59710130 |  |  |  | سيليكون أبيض | 200010000945 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3791981 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 150 | 1 | مسمار تجميع بالصامولة 10 سم |  | Kilogram | 1 | 59710131 |  |  |  | مسمار تجميع بالصامولة 10 سم | 200020000292 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3791982 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 100 | 1 | صامولة 17 مم |  | Kilogram | 1.5 | 59710132 |  |  |  | صامولة 17 مم | 200020000137 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3791983 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 105 | 1 | مسمار مخ طاسة 6مم |  | Kilogram | 1.5 | 59710133 |  |  |  | مسمار مخ طاسة 6مم | 200020000142 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3791984 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 200 | 1 | مسمار برشام |  | Each | 200 | 59710134 |  |  |  | مسمار برشام | 200020000312 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3791985 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 180 | 1 | مسمار سلف دريل 2.5 سم |  | Each | 90 | 59710135 |  |  |  | مسمار سلف دريل 2.5 سم | 200020000317 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3791986 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 600 | 1 | اسبراي الوان |  | Each | 12 | 59710136 |  |  |  | اسبراي الوان | 200010001522 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3791987 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 43500.01 | 1 | FLOOR BOX 12 MOD code CB3 |  | Each | 30 | 59710137 |  |  |  | FLOOR BOX 12 MOD code CB3 | 030060100533 | MEP | Received | 2023-02-05 | Accounted transaction received
3791988 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 765.94 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) |  | Meter | 100 | 59710138 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) | 030030101026 | MEP | Received | 2023-02-05 | Accounted transaction received
3791989 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2066.82 | 1 | سلك نحاس مجدول مقاس 6 مم اللون أسود (cu/pvc) |  | Meter | 100 | 59710139 |  |  |  | سلك نحاس مجدول مقاس 6 مم اللون أسود (cu/pvc) | 030030101031 | MEP | Received | 2023-02-05 | Accounted transaction received
3791990 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 100 | 1 | وردة 17 مم |  | Kilogram | 1.5 | 59710140 |  |  |  | وردة 17 مم | 200020000377 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3791991 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 295.59 | 1 | Wiring Devices (54000) METAL FLUSH-MOUNTING BOX FOR INSTALLATION IN CONCRETE FLOOR - 3 MODULES |  | Each | 3 | 59710141 |  |  |  | Wiring Devices (54000) METAL FLUSH-MOUNTING BOX FOR INSTALLATION IN CONCRETE FLOOR - 3 MODULES | 030060100618 | MEP | Received | 2023-02-05 | Accounted transaction received
3791992 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 190.1 | 1 | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 |  | Each | 10 | 59710142 |  |  |  | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 | 150020000178 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3791993 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 29048.8 | 1 | HDMI Cable 15 M |  | Each | 14 | 59710143 |  |  |  | HDMI Cable 15 M | 800040000129 | IT | Received | 2023-02-05 | Accounted transaction received
3791994 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 380.65 | 1 | Signature Detector Base ( SIGA-SB ) |  | Each | 3 | 59710144 |  |  |  | Signature Detector Base ( SIGA-SB ) | 031010000145 | MEP | Received | 2023-02-05 | Accounted transaction received
3791995 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 31920 | 1 | Master Seal NP 472 |  | Kit | 280 | 59710145 |  |  |  | Master Seal NP 472 | 360010000355 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3791996 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 6390.84 | 1 | LV Power cable CU / PVC / PVC 3 X 6 mm2 (0.6/1 KV) |  | Meter | 100 | 59710146 |  |  |  | LV Power cable CU / PVC / PVC 3 X 6 mm2 (0.6/1 KV) | 030030101179 | MEP | Received | 2023-02-05 | Accounted transaction received
3791997 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 319.36 | 1 | UPVC BACK BOX 10X10 |  | Each | 14 | 59710147 |  |  |  | UPVC BACK BOX 10X10 | 030069000025 | MEP | Received | 2023-02-05 | Accounted transaction received
3791998 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 16.3 | 1 | Metal Galvanized back box 5x10 cm with deep 47 mm |  | Each | 1 | 59710148 |  |  |  | Metal Galvanized back box 5x10 cm with deep 47 mm | 030069000028 | MEP | Received | 2023-02-05 | Accounted transaction received
3791999 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 149973.23 | 1 | Acolyte - ARB95SWBC203. 027 - Rapid Ribbon 95+ - LED Strip with 9.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser |  | Each | 350.4 | 59710149 |  |  |  | Acolyte - ARB95SWBC203. 027 - Rapid Ribbon 95+ - LED Strip with 9.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser | 030040700471 | MEP | Received | 2023-02-05 | Accounted transaction received
3792000 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 456928.46 | 1 | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser |  | Each | 1190 | 59710150 |  |  |  | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser | 030040700472 | MEP | Received | 2023-02-05 | Accounted transaction received
3792001 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2283.88 | 1 | Intelligent multi-criteria optical smoke and Heat detector - SIGA-OSHD |  | Each | 3 | 59710151 |  |  |  | Intelligent multi-criteria optical smoke and Heat detector - SIGA-OSHD | 031010000240 | MEP | Received | 2023-02-05 | Accounted transaction received
3792002 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1734.2 | 1 | 15/75 cd Speaker/Strobe, 70V - 4" Cone, Round - WHITE - 965-7A-4RW |  | Each | 1 | 59710152 |  |  |  | 15/75 cd Speaker/Strobe, 70V - 4" Cone, Round - WHITE - 965-7A-4RW | 031010000241 | MEP | Received | 2023-02-05 | Accounted transaction received
3792003 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4531.31 | 1 | 4" Cone Speaker (70VRMS), Round - WHITE - 965-1A-4RW |  | Each | 6 | 59710153 |  |  |  | 4" Cone Speaker (70VRMS), Round - WHITE - 965-1A-4RW | 031010000244 | MEP | Received | 2023-02-05 | Accounted transaction received
3792004 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 76950 | 1 | Micro Switch Hafele/ Marckophon - 820.22.110/4321 - Switches 230 VDoor contact switches - Built-in switch |  | Each | 75 | 59710154 |  |  |  | Micro Switch Hafele/ Marckophon - 820.22.110/4321 - Switches 230 VDoor contact switches - Built-in switch | 030060200070 | MEP | Received | 2023-02-05 | Accounted transaction received
3792005 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 64638 | 1 | Micro Switch Hafele/ Marckophon - 820.22.110/4321 - Switches 230 VDoor contact switches - Built-in switch |  | Each | 63 | 59710155 |  |  |  | Micro Switch Hafele/ Marckophon - 820.22.110/4321 - Switches 230 VDoor contact switches - Built-in switch | 030060200070 | MEP | Received | 2023-02-05 | Accounted transaction received
3792006 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1530.05 | 1 | Category 6A Field Terminated Plug and Boot with Black Latch Protector Clip |  | Each | 17 | 59710156 |  |  |  | Category 6A Field Terminated Plug and Boot with Black Latch Protector Clip | 031030000447 | MEP | Received | 2023-02-05 | Accounted transaction received
3792007 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 109.8 | 1 | WA PLATE - 77MM - 2X3MOD MOSA Code : 689677 |  | Each | 1 | 59710157 |  |  |  | WA PLATE - 77MM - 2X3MOD MOSA Code : 689677 | 030060100931 | MEP | Received | 2023-02-05 | Accounted transaction received
3792008 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 515.09 | 1 | DS , 4 pole , 40A , 400V , abs enclosure IP 65 Code : KEM 440U Y/R ABS |  | Each | 1 | 59710158 |  |  |  | DS , 4 pole , 40A , 400V , abs enclosure IP 65 Code : KEM 440U Y/R ABS | 030060200073 | MEP | Received | 2023-02-05 | Accounted transaction received
3792009 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 46922.4 | 1 | Fire Resistance Cable FIRECEL SR114H 300/500V EN50200 BS5839,BS7629-1,BS6387 CWZ 950C LPCB 217F ( Size 2*1.5 mm ) |  | Meter | 1000 | 59710159 |  |  |  | Fire Resistance Cable FIRECEL SR114H 300/500V EN50200 BS5839,BS7629-1,BS6387 CWZ 950C LPCB 217F ( Size 2*1.5 mm ) | 032010000012 | MEP | Received | 2023-02-05 | Accounted transaction received
3792010 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 48864.96 | 1 | FIRE RESISTANT INSTRUMENTATION CABLE CU/MICA/XLPE/LSHF 2 X 1.5 MM2 500 V |  | Meter | 950 | 59710160 |  |  |  | FIRE RESISTANT INSTRUMENTATION CABLE CU/MICA/XLPE/LSHF 2 X 1.5 MM2 500 V | 032010000014 | MEP | Received | 2023-02-05 | Accounted transaction received
3792011 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 20035.5 | 1 | LED transformer - ET-E 10 W LED 220-240V |  | Each | 185 | 59710161 |  |  |  | LED transformer - ET-E 10 W LED 220-240V | 039019000062 | MEP | Received | 2023-02-05 | Accounted transaction received
3792012 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 56.54 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 1 | 59710162 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-02-05 | Accounted transaction received
3792013 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3492 | 1 | Speaker (70V) - Cone Type, WHITE - 757-1A-S70 |  | Each | 3 | 59710163 |  |  |  | Speaker (70V) - Cone Type, WHITE - 757-1A-S70 | 031010000279 | MEP | Received | 2023-02-05 | Accounted transaction received
3792014 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 764000.64 | 1 | DAL - 30150 - AMBIANCE 100 - Recessed fixed down lighter with satin silver reflector and white ceiling trim. Overall diameter 100mm, cut out IP 65 diameter 90mm, with PHILIPS LED Lamp 5.5W MR16 GU5.3, 2700K |  | Each | 179 | 59710164 |  |  |  | DAL - 30150 - AMBIANCE 100 - Recessed fixed down lighter with satin silver reflector and white ceiling trim. Overall diameter 100mm, cut out IP 65 diameter 90mm, with PHILIPS LED Lamp 5.5W MR16 GU5.3, 2700K | 030040600115 | MEP | Received | 2023-02-05 | Accounted transaction received
3792015 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 12240.01 | 1 | Floor box 6 Module with double socket, space for 2 data socket complete with back box , IP66, Part Number GESR2 - OBO Germany |  | Each | 1 | 59710165 |  |  |  | Floor box 6 Module with double socket, space for 2 data socket complete with back box , IP66, Part Number GESR2 - OBO Germany | 030060100992 | MEP | Received | 2023-02-05 | Accounted transaction received
3792016 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2052 | 1 | تيب دوكو |  | Each | 72 | 59710244 |  |  |  | تيب دوكو | 200010000048 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3792017 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 311.51 | 1 | سيفتي عمال |  | Each | 1 | 59710245 |  |  |  | سيفتي عمال | 010030000002 | Safety | Received | 2023-02-05 | Accounted transaction received
3792018 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 13.68 | 1 | نظارة مهندسين M3 بيضاء |  | Each | 1 | 59710246 |  |  |  | نظارة مهندسين M3 بيضاء | 010060000004 | Safety | Received | 2023-02-05 | Accounted transaction received
3792019 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 10.29 | 1 | نظارة مهندسين M3 سوداء |  | Each | 1 | 59710247 |  |  |  | نظارة مهندسين M3 سوداء | 010060000005 | Safety | Received | 2023-02-05 | Accounted transaction received
3792020 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 127.68 | 1 | فيست برتقالي |  | Each | 4 | 59710248 |  |  |  | فيست برتقالي | 010020000008 | Safety | Received | 2023-02-05 | Accounted transaction received
3792021 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 30 | 1 | صابون سائل |  | Can | 2 | 59710249 |  |  |  | صابون سائل | 700020000013 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3792022 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 273.6 | 1 | جوانتي باور جراب |  | Each | 12 | 59710250 |  |  |  | جوانتي باور جراب | 010010000009 | Safety | Received | 2023-02-05 | Accounted transaction received
3792023 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 13.68 | 1 | سدادة أذن |  | Each | 3 | 59710251 |  |  |  | سدادة أذن | 010020000015 | Safety | Received | 2023-02-05 | Accounted transaction received
3792024 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3749.46 | 1 | بولي ايثيلين 300 ميكرون ابيض |  | Kilogram | 50.6 | 59710252 |  |  |  | بولي ايثيلين 300 ميكرون ابيض | 040010000037 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3792025 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 387.6 | 1 | فرشة سلك كباية حرة |  | Each | 4 | 59710253 |  |  |  | فرشة سلك كباية حرة | 200010000436 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3792026 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 199.5 | 1 | مكنسة ناعمة |  | Each | 5 | 59710254 |  |  |  | مكنسة ناعمة | 200010000449 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3792029 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 786.6 | 1 | بكرة شريط لحام |  | Each | 30 | 59710257 |  |  |  | بكرة شريط لحام | 039010000003 | MEP | Received | 2023-02-05 | Accounted transaction received
3792030 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1500 | 1 | شيكارة بلاستيك فارغة |  | Each | 500 | 59710258 |  |  |  | شيكارة بلاستيك فارغة | 200010000115 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3792031 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 253.29 | 1 | بنطة (مسمار) تكسير لهيلتي 70 |  | Each | 4 | 59710259 |  |  |  | بنطة (مسمار) تكسير لهيلتي 70 | 200010000997 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3792032 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 284.14 | 1 | بنطة أجنة لهيلتي 70 |  | Each | 4 | 59710260 |  |  |  | بنطة أجنة لهيلتي 70 | 200010000998 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3792033 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 45 | 1 | كالون وحدة أدراج |  | Each | 1 | 59710261 |  |  |  | كالون وحدة أدراج | 700010000073 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3792034 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 11400 | 1 | X Tile STA White |  | Ton | 1 | 59710262 |  |  |  | X Tile STA White | 050010000077 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3792035 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1015.74 | 1 | كرتون مضلع - تغليف |  | Kilogram | 66 | 59710263 |  |  |  | كرتون مضلع - تغليف | 910010000387 | Administration | Received | 2023-02-05 | Accounted transaction received
3792036 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 300 | 1 | فيشة نتاية كاوتش 16أمبير 220 فولت |  | Each | 15 | 59710264 |  |  |  | فيشة نتاية كاوتش 16أمبير 220 فولت | 039010000050 | MEP | Received | 2023-02-05 | Accounted transaction received
3792037 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 421.8 | 1 | quick response recesssd pendant sprinkler 68 c? , K=5.6 & nominal thread 15 mm |  | Each | 1 | 59710265 |  |  |  | quick response recesssd pendant sprinkler 68 c? , K=5.6 & nominal thread 15 mm | 060090400006 | MEP | Received | 2023-02-05 | Accounted transaction received
3792038 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3591 | 1 | Pressure Gauge 0.5" |  | Each | 12 | 59710266 |  |  |  | Pressure Gauge 0.5" | 060179000007 | MEP | Received | 2023-02-05 | Accounted transaction received
3792039 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 399 | 1 | تيب دوكو 2سم |  | Each | 35 | 59710267 |  |  |  | تيب دوكو 2سم | 200010002032 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3792040 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 513 | 1 | فوطة حمام قطن |  | Each | 10 | 59710268 |  |  |  | فوطة حمام قطن | 700020000193 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3792041 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 30 | 1 | وردة صاج |  | Kilogram | 0.5 | 59710274 |  |  |  | وردة صاج | 200020000168 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3792042 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-01-23 | Maintenance |  |  |  | Indirect | Waldorf Astoria-0164 | 18800 | 1 | إطار تيوبلس 215 / 70 R15 ميشلان تايلاندى |  | Each | 4 | 59710963 |  |  |  | إطار تيوبلس 215 / 70 R15 ميشلان تايلاندى | 330040004946 | Equipment | Received | 2023-02-05 | Accounted transaction received
3792043 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Alrowad Construction_OU | -45144 | 1 | Micro Switch Hafele/ Marckophon - 820.22.110/4321 - Switches 230 VDoor contact switches - Built-in switch |  | Each | -44 | 59711144 |  |  |  | Micro Switch Hafele/ Marckophon - 820.22.110/4321 - Switches 230 VDoor contact switches - Built-in switch | 030060200070 | MEP | Received | 2023-02-05 | Accounted transaction received
3792044 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-23 | Materials |  |  |  | Materials | Alrowad Construction_OU | -1057.65 | 1 | Hardware Accessories for Wooden Doors Standard Floor Door Stop for BOH Side Door Stoper Size: 29x40(H)mm Material: Stainless steel 304 Finish: Satin finish Welder DDS007 S.S.S |  | Each | -8 | 59711145 |  |  |  | Hardware Accessories for Wooden Doors Standard Floor Door Stop for BOH Side Door Stoper Size: 29x40(H)mm Material: Stainless steel 304 Finish: Satin finish Welder DDS007 S.S.S | 250010001524 | Procurement | Received | 2023-02-05 | Accounted transaction received
3792045 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 16536.16 | 1 | Hardware Accessories for Wooden Doors Privacy Door Latch Privacy Door Latch Welder 43702424 Silver |  | Each | 52 | 59735567 |  |  |  | Hardware Accessories for Wooden Doors Privacy Door Latch Privacy Door Latch Welder 43702424 Silver | 250010001514 | Procurement | Received | 2023-02-05 | Accounted transaction received
3792046 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 87039.82 | 1 | Hardware Accessories for Wooden Doors Concealed hinge system & Bathroom Concealed Hinges Simonswerk completely concealed hinge system with load capacity 80.0 kg two hinges per door leaf (1x2m) |  | Each | 32 | 59735568 |  |  |  | Hardware Accessories for Wooden Doors Concealed hinge system & Bathroom Concealed Hinges Simonswerk completely concealed hinge system with load capacity 80.0 kg two hinges per door leaf (1x2m) | 250010001515 | Procurement | Received | 2023-02-05 | Accounted transaction received
3792078 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 760.7 | 1 | mosaic adapter code 69580 |  | Each | 8 | 59736739 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-02-05 | Accounted transaction received
3792047 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2334 | 1 | Hardware Accessories for Wooden Doors Concealed Door closer TESA Concealed Door closer Size 3: suitable for door width up to 95cm and can be used in Fire Doors. |  | Each | 1 | 59735569 |  |  |  | Hardware Accessories for Wooden Doors Concealed Door closer TESA Concealed Door closer Size 3: suitable for door width up to 95cm and can be used in Fire Doors. | 250010001516 | Procurement | Received | 2023-02-05 | Accounted transaction received
3792048 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 684 | 1 | Hardware Accessories for Wooden Doors Mortice lock without Double Cylinder TESA Entrance Mortice Lock without Cylinder - Sash lock for timber doors. |  | Each | 2 | 59735570 |  |  |  | Hardware Accessories for Wooden Doors Mortice lock without Double Cylinder TESA Entrance Mortice Lock without Cylinder - Sash lock for timber doors. | 250010001518 | Procurement | Received | 2023-02-05 | Accounted transaction received
3792049 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1583.96 | 1 | Hardware Accessories for Wooden Doors Double Cylinder TESA Security TE-5 Double Cylinder 35x35mm. 5 Spring Loaded Anti pick Pins. Made to EN-1303 Regulation. |  | Each | 8 | 59735571 |  |  |  | Hardware Accessories for Wooden Doors Double Cylinder TESA Security TE-5 Double Cylinder 35x35mm. 5 Spring Loaded Anti pick Pins. Made to EN-1303 Regulation. | 250010001519 | Procurement | Received | 2023-02-05 | Accounted transaction received
3792050 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 18827.99 | 1 | Hardware Accessories for Wooden Doors Accessory sliding soft close - 120 kg - 3 Meter Accessory sliding soft close - 120 kg - 3 Meter TESA 73401311 Silver |  | Each | 6 | 59735572 |  |  |  | Hardware Accessories for Wooden Doors Accessory sliding soft close - 120 kg - 3 Meter Accessory sliding soft close - 120 kg - 3 Meter TESA 73401311 Silver | 250010001520 | Procurement | Received | 2023-02-05 | Accounted transaction received
3792051 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 378 | 1 | Hardware Accessories for Wooden Doors TESA TE5 Thumb turn Cylinder 35x35mm. 5 Spring Loaded Anti pick Pins + 1 SENSOR in the key. Certified according to EN1303. |  | Each | 1 | 59735573 |  |  |  | Hardware Accessories for Wooden Doors TESA TE5 Thumb turn Cylinder 35x35mm. 5 Spring Loaded Anti pick Pins + 1 SENSOR in the key. Certified according to EN1303. | 250010001522 | Procurement | Received | 2023-02-05 | Accounted transaction received
3792052 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3437.35 | 1 | Hardware Accessories for Wooden Doors Standard Floor Door Stop for BOH Side Door Stoper Size: 29x40(H)mm Material: Stainless steel 304 Finish: Satin finish Welder DDS007 S.S.S |  | Each | 26 | 59735574 |  |  |  | Hardware Accessories for Wooden Doors Standard Floor Door Stop for BOH Side Door Stoper Size: 29x40(H)mm Material: Stainless steel 304 Finish: Satin finish Welder DDS007 S.S.S | 250010001524 | Procurement | Received | 2023-02-05 | Accounted transaction received
3792053 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 155479.88 | 1 | Hardware Accessories For Wooden Doors Concealed Hinge Simonswerk completely concealed hinge system load capacity 120 kg two hinges per door leaf (1x2m) overall |  | Each | 26 | 59735575 |  |  |  | Hardware Accessories For Wooden Doors Concealed Hinge Simonswerk completely concealed hinge system load capacity 120 kg two hinges per door leaf (1x2m) overall | 250010001606 | Procurement | Received | 2023-02-05 | Accounted transaction received
3792054 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 16380.09 | 1 | Hardware Accessories For Wooden Doors Sliding Soft Close Door Sync 9820120 KG FUNICULAR SLIDING DOOR SYSTEM - HAS SOFT Closing with track 4 meter Albatur 73401211 Silver |  | Each | 3 | 59735576 |  |  |  | Hardware Accessories For Wooden Doors Sliding Soft Close Door Sync 9820120 KG FUNICULAR SLIDING DOOR SYSTEM - HAS SOFT Closing with track 4 meter Albatur 73401211 Silver | 250010001607 | Procurement | Received | 2023-02-05 | Accounted transaction received
3792055 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 57246.52 | 1 | Supply Concealed Door closer to 80KG for wooden doors, including any requirements to complete the works as per consultant's approval & submittal approval. Consort CDCC3 Silver |  | Each | 7 | 59735577 |  |  |  | Supply Concealed Door closer to 80KG for wooden doors, including any requirements to complete the works as per consultant's approval & submittal approval. Consort CDCC3 Silver | 250010001608 | Procurement | Received | 2023-02-05 | Accounted transaction received
3792056 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 12539.72 | 1 | Supply Concealed Door closer up to 120KG for wooden doors, including any requirements to complete the works as per consultant's approval & submittal approval. LCN 3133 Silver |  | Each | 1 | 59735578 |  |  |  | Supply Concealed Door closer up to 120KG for wooden doors, including any requirements to complete the works as per consultant's approval & submittal approval. LCN 3133 Silver | 250010001609 | Procurement | Received | 2023-02-05 | Accounted transaction received
3792057 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 11400 | 1 | Supply 3D Concealed Hinges up to 80KG for wooden doors from MTC brand, including any requirements to complete the works as per consultant's approval & submittal approval. |  | Each | 10 | 59735579 |  |  |  | Supply 3D Concealed Hinges up to 80KG for wooden doors from MTC brand, including any requirements to complete the works as per consultant's approval & submittal approval. | 250010001610 | Procurement | Received | 2023-02-05 | Accounted transaction received
3792058 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 37050 | 1 | Action floor spring max 180kg for Glass doors, brand Stanley |  | Each | 5 | 59735580 |  |  |  | Action floor spring max 180kg for Glass doors, brand Stanley | 310010000018 | Fleets | Received | 2023-02-05 | Accounted transaction received
3792059 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1000.92 | 1 | Patch Fitting Hinge for Frameless Glass Door STPF-S10 BOTTOM PATCH, Stanley Brand |  | Each | 2 | 59735581 |  |  |  | Patch Fitting Hinge for Frameless Glass Door STPF-S10 BOTTOM PATCH, Stanley Brand | 250010001693 | Procurement | Received | 2023-02-05 | Accounted transaction received
3792060 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 7365.31 | 1 | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) |  | Meter | 480 | 59736721 |  |  |  | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) | 030010000052 | MEP | Received | 2023-02-05 | Accounted transaction received
3792061 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 336.3 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 100 | 59736722 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-02-05 | Accounted transaction received
3792062 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3333.07 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 12 | 59736723 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) | 030010000059 | MEP | Received | 2023-02-05 | Accounted transaction received
3792063 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4115.26 | 1 | سلك نحاس مصمت مقاس 1.5 مم اللون أسود (cu/pvc) جهد (750/450) |  | Meter | 700 | 59736724 |  |  |  | سلك نحاس مصمت مقاس 1.5 مم اللون أسود (cu/pvc) جهد (750/450) | 030030100253 | MEP | Received | 2023-02-05 | Accounted transaction received
3792064 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1172.66 | 1 | أدابتور UPVC لماسورة 25مم(اللون أبيض) |  | Each | 150 | 59736725 |  |  |  | أدابتور UPVC لماسورة 25مم(اللون أبيض) | 030010000097 | MEP | Received | 2023-02-05 | Accounted transaction received
3792065 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1145.7 | 1 | سلك نحاس مصمت مقاس 3 مم اللون أحمر (cu/pvc) جهد (750/450) |  | Meter | 100 | 59736726 |  |  |  | سلك نحاس مصمت مقاس 3 مم اللون أحمر (cu/pvc) جهد (750/450) | 030030100277 | MEP | Received | 2023-02-05 | Accounted transaction received
3792066 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2644.8 | 1 | جلاند فلكسبل مقاس 16 مم |  | Each | 400 | 59736727 |  |  |  | جلاند فلكسبل مقاس 16 مم | 030010000167 | MEP | Received | 2023-02-05 | Accounted transaction received
3792067 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 698.25 | 1 | بواط واتر بروف بفتحات مقاس 19 × 24 × 9 سم |  | Each | 4 | 59736728 |  |  |  | بواط واتر بروف بفتحات مقاس 19 × 24 × 9 سم | 030010000183 | MEP | Received | 2023-02-05 | Accounted transaction received
3792068 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 195.12 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 3 | 59736729 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-02-05 | Accounted transaction received
3792069 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 77.47 | 1 | PLATE 1SQ MOD SCH GRAPHITE Code 576552 |  | Each | 2 | 59736730 |  |  |  | PLATE 1SQ MOD SCH GRAPHITE Code 576552 | 030060100297 | MEP | Received | 2023-02-05 | Accounted transaction received
3792070 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 705.61 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 12 | 59736731 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-02-05 | Accounted transaction received
3792071 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 25489.6 | 1 | SHAVER SOCKET 230V/120-230V WITH EARTH CONNECTOR Code 572653 |  | Each | 37 | 59736732 |  |  |  | SHAVER SOCKET 230V/120-230V WITH EARTH CONNECTOR Code 572653 | 030060100178 | MEP | Received | 2023-02-05 | Accounted transaction received
3792072 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 469.91 | 1 | FUSED 13A SWITCH +NEON SQ ALU Code 572651 |  | Each | 1 | 59736733 |  |  |  | FUSED 13A SWITCH +NEON SQ ALU Code 572651 | 030060100186 | MEP | Received | 2023-02-05 | Accounted transaction received
3792073 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1637.36 | 1 | 576562 Code وش مربع فضي |  | Each | 50 | 59736734 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-02-05 | Accounted transaction received
3792074 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 943.01 | 1 | Threaded rod size M10 |  | Each | 22 | 59736735 |  |  |  | Threaded rod size M10 | 060190300003 | MEP | Received | 2023-02-05 | Accounted transaction received
3792075 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1016.75 | 1 | سلك نحاس مجدول مقاس4 مم اللون أحمر (cu/pvc) |  | Meter | 100 | 59736736 |  |  |  | سلك نحاس مجدول مقاس4 مم اللون أحمر (cu/pvc) | 030030101023 | MEP | Received | 2023-02-05 | Accounted transaction received
3792076 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 811.12 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أصفر × أخضر (cu/pvc) |  | Meter | 100 | 59736737 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أصفر × أخضر (cu/pvc) | 030030101027 | MEP | Received | 2023-02-05 | Accounted transaction received
3792077 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 247.13 | 1 | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 |  | Each | 13 | 59736738 |  |  |  | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 | 150020000178 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3792079 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 80.25 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 1 | 59736740 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-02-05 | Accounted transaction received
3792080 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 15390 | 1 | Master Seal NP 472 |  | Kit | 135 | 59736741 |  |  |  | Master Seal NP 472 | 360010000355 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3792081 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 15390 | 1 | Master Seal NP 472 |  | Kit | 135 | 59736742 |  |  |  | Master Seal NP 472 | 360010000355 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3792082 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 159.68 | 1 | UPVC BACK BOX 10X10 |  | Each | 7 | 59736743 |  |  |  | UPVC BACK BOX 10X10 | 030069000025 | MEP | Received | 2023-02-05 | Accounted transaction received
3792083 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 119.47 | 1 | Metal Galvanized back box 7x14 cm with deep 47 mm |  | Each | 5 | 59736744 |  |  |  | Metal Galvanized back box 7x14 cm with deep 47 mm | 030069000027 | MEP | Received | 2023-02-05 | Accounted transaction received
3792084 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 352.81 | 1 | Plate British standard Arteor - square - 3 modules - graphite - 575072 |  | Each | 6 | 59736745 |  |  |  | Plate British standard Arteor - square - 3 modules - graphite - 575072 | 030060100898 | MEP | Received | 2023-02-05 | Accounted transaction received
3792085 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 27360 | 1 | Honeywell thermostat model (WS8B4WB/U) |  | Each | 50 | 59736746 |  |  |  | Honeywell thermostat model (WS8B4WB/U) | 060081900004 | MEP | Received | 2023-02-05 | Accounted transaction received
3792086 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 57596.02 | 1 | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser |  | Each | 150 | 59736747 |  |  |  | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser | 030040700472 | MEP | Received | 2023-02-05 | Accounted transaction received
3792087 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 23266.17 | 1 | LT.02-Pendant Circular luminaire Ring connected to 220v mains using AC/DC Driver, the luminaire- made of cast Aluminum. Polycarbonate diffuser ensures the diffusivity of the light giving a smooth sensation without any hot or dark spots. |  | Each | 7 | 59736748 |  |  |  | LT.02-Pendant Circular luminaire Ring connected to 220v mains using AC/DC Driver, the luminaire- made of cast Aluminum. Polycarbonate diffuser ensures the diffusivity of the light giving a smooth sensation without any hot or dark spots. | 030040700491 | MEP | Received | 2023-02-05 | Accounted transaction received
3792088 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 100.39 | 1 | SPLASH PROOF COVER Code : 617636 |  | Each | 1 | 59736749 |  |  |  | SPLASH PROOF COVER Code : 617636 | 030060100927 | MEP | Received | 2023-02-05 | Accounted transaction received
3792089 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 112.68 | 1 | 1G 20A DP SWT + NEON + E WH - 617671 |  | Each | 1 | 59736750 |  |  |  | 1G 20A DP SWT + NEON + E WH - 617671 | 030060100942 | MEP | Received | 2023-02-05 | Accounted transaction received
3792090 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 866.4 | 1 | LED transformer - ET-E 10 W LED 220-240V |  | Each | 8 | 59736751 |  |  |  | LED transformer - ET-E 10 W LED 220-240V | 039019000062 | MEP | Received | 2023-02-05 | Accounted transaction received
3792091 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 219.65 | 1 | PLATE BS FOR 13A FCU 1G SQ -Dark Bronze - Legrand 571340 |  | Each | 1 | 59736752 |  |  |  | PLATE BS FOR 13A FCU 1G SQ -Dark Bronze - Legrand 571340 | 030060100961 | MEP | Received | 2023-02-05 | Accounted transaction received
3792092 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.01 | HAVC Duct Works | 15 | MECHANICAL WORKS |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 63121.8 | 1 | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² |  | Kilogram | 1130 | 59736756 |  |  |  | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² | 060040200001 | MEP | Received | 2023-02-05 | Accounted transaction received
3792093 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-26 | Other |  |  |  | Other | Waldorf Astoria-0164 | 402.07 | 1 | فدية خرسانة 5 بوصة |  | Each | 13 | 59736768 |  |  |  | فدية خرسانة 5 بوصة | 200010000431 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3792094 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-26 | Other |  |  |  | Other | Waldorf Astoria-0164 | 1551.33 | 1 | فدية خرسانة 9 بوصة |  | Each | 17 | 59736769 |  |  |  | فدية خرسانة 9 بوصة | 200010000433 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3792095 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-26 | Other |  |  |  | Other | Waldorf Astoria-0164 | 524.4 | 1 | بكرة شريط لحام |  | Each | 20 | 59736770 |  |  |  | بكرة شريط لحام | 039010000003 | MEP | Received | 2023-02-05 | Accounted transaction received
3792096 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-26 | Other |  |  |  | Other | Waldorf Astoria-0164 | 751.29 | 1 | أسطوانة قطعيه 9 بوصه |  | Each | 35 | 59736771 |  |  |  | أسطوانة قطعيه 9 بوصه | 039020200001 | MEP | Received | 2023-02-05 | Accounted transaction received
3792097 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 334.73 | 1 | Ceramic Fan Shape Wall Tiles FS-026 |  | Square Meter | 0.25 | 59736772 |  |  |  | Ceramic Fan Shape Wall Tiles FS-026 | 170010000549 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3792098 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-26 | Other |  |  |  | Other | Waldorf Astoria-0164 | 916 | 1 | أنبوبة سليكون |  | Each | 20 | 59736776 |  |  |  | أنبوبة سليكون | 060019000001 | MEP | Received | 2023-02-05 | Accounted transaction received
3792099 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-26 | Penalty- Safety |  |  |  | Finance cost | Waldorf Astoria-0164 | 623.03 | 1 | سيفتي عمال |  | Each | 2 | 59736780 |  |  |  | سيفتي عمال | 010030000002 | Safety | Received | 2023-02-05 | Accounted transaction received
3792100 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-01-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 45000 | 1 | فوم ازرق 5 سم |  | Cubic Meter | 30 | 59736792 |  |  |  | فوم ازرق 5 سم | 040010000013 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3792101 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-26 | Penalty- Safety |  |  |  | Finance cost | Waldorf Astoria-0164 | 127.68 | 1 | فيست برتقالي |  | Each | 4 | 59736798 |  |  |  | فيست برتقالي | 010020000008 | Safety | Received | 2023-02-05 | Accounted transaction received
3792102 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-01-26 | Penalty- Safety |  |  |  | Finance cost | Waldorf Astoria-0164 | 91.2 | 1 | جوانتي باور جراب |  | Each | 4 | 59736799 |  |  |  | جوانتي باور جراب | 010010000009 | Safety | Received | 2023-02-05 | Accounted transaction received
3796403 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 35469 | 1 | 1.1.007 66685/6 |  | Currency | 70 |  | 10916 | الفسطاط للمقاولات |  | 1.1.007 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796404 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2495.45 | 1 | 1.1.018 66685/6 |  | Currency | 286 |  | 10916 | الفسطاط للمقاولات |  | 1.1.018 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796405 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 6458.39 | 1 | 1.1.028 66685/6 |  | Currency | 268 |  | 10916 | الفسطاط للمقاولات |  | 1.1.028 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796406 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1344 | 1 | 1.1.039 66685/6 |  | Currency | 52 |  | 10916 | الفسطاط للمقاولات |  | 1.1.039 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796407 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 284 | 1 | 1.1.044 66685/6 |  | Currency | 10 |  | 10916 | الفسطاط للمقاولات |  | 1.1.044 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796408 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 116877.6 | 1 | 1.1.045 66685/6 |  | Currency | 12 |  | 10916 | الفسطاط للمقاولات |  | 1.1.045 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796409 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 105840 | 1 | 1.1.046 66685/6 |  | Currency | 12 |  | 10916 | الفسطاط للمقاولات |  | 1.1.046 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796410 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3704.4 | 1 | 1.1.047 66685/6 |  | Currency | 2 |  | 10916 | الفسطاط للمقاولات |  | 1.1.047 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796411 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7144.2 | 1 | 1.1.05 66685/6 |  | Currency | 18 |  | 10916 | الفسطاط للمقاولات |  | 1.1.05 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796412 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4740.12 | 1 | 2.2.008 66685/6 |  | Currency | 528 |  | 10916 | الفسطاط للمقاولات |  | 2.2.008 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796413 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 936.91 | 1 | 2.2.009 66685/6 |  | Currency | 254 |  | 10916 | الفسطاط للمقاولات |  | 2.2.009 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796414 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 321.11 | 1 | 2.2.01 66685/6 |  | Currency | 108 |  | 10916 | الفسطاط للمقاولات |  | 2.2.01 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796415 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 681.6 | 1 | 2.2.031 66685/6 |  | Currency | 4 |  | 10916 | الفسطاط للمقاولات |  | 2.2.031 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796416 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1191.28 | 1 | 2.2.032 66685/6 |  | Currency | 18 |  | 10916 | الفسطاط للمقاولات |  | 2.2.032 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796417 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4018.68 | 1 | 2.2.039 66685/6 |  | Currency | 122 |  | 10916 | الفسطاط للمقاولات |  | 2.2.039 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796418 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 28595.95 | 1 | 2.2.04 66685/6 |  | Currency | 1817 |  | 10916 | الفسطاط للمقاولات |  | 2.2.04 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796419 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3740.4 | 1 | 2.2.051 66685/6 |  | Currency | 2 |  | 10916 | الفسطاط للمقاولات |  | 2.2.051 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796420 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 540 | 1 | 3.3.015 66685/6 |  | Currency | 50 |  | 10916 | الفسطاط للمقاولات |  | 3.3.015 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796421 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 49392 | 1 | 3.3.019 66685/6 |  | Currency | 16 |  | 10916 | الفسطاط للمقاولات |  | 3.3.019 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796422 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 21667.5 | 1 | 3.3.02 66685/6 |  | Currency | 9 |  | 10916 | الفسطاط للمقاولات |  | 3.3.02 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796423 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 25.8 | 1 | 4.4.005 66685/6 |  | Currency | 4 |  | 10916 | الفسطاط للمقاولات |  | 4.4.005 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796424 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 6080.4 | 1 | 4.4.016 66685/6 |  | Currency | 12 |  | 10916 | الفسطاط للمقاولات |  | 4.4.016 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796425 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 918 | 1 | 4.4.018 66685/6 |  | Currency | 85 |  | 10916 | الفسطاط للمقاولات |  | 4.4.018 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796426 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 10936.8 | 1 | 4.4.023 66685/6 |  | Currency | 4 |  | 10916 | الفسطاط للمقاولات |  | 4.4.023 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796427 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 39734.1 | 1 | 4.4.024 66685/6 |  | Currency | 17 |  | 10916 | الفسطاط للمقاولات |  | 4.4.024 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796428 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 37485 | 1 | 4.4.025 66685/6 |  | Currency | 17 |  | 10916 | الفسطاط للمقاولات |  | 4.4.025 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796429 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5940.01 | 1 | 5.5.001 66685/6 |  | Currency | 135 |  | 10916 | الفسطاط للمقاولات |  | 5.5.001 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796430 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 10534.97 | 1 | 5.5.002 66685/6 |  | Currency | 830 |  | 10916 | الفسطاط للمقاولات |  | 5.5.002 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796431 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2469.6 | 1 | 5.5.015 66685/6 |  | Currency | 1 |  | 10916 | الفسطاط للمقاولات |  | 5.5.015 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796432 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7751.7 | 1 | 5.5.018 66685/6 |  | Currency | 3 |  | 10916 | الفسطاط للمقاولات |  | 5.5.018 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796433 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | -71350 | 1 | 66685/6 |  | Currency | -71350 |  | 10916 | الفسطاط للمقاولات |  | 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796434 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -2327.94 | 1 | LABOUR_OFFICE 66685/6 |  | Currency | -2327.94 |  | 10916 | الفسطاط للمقاولات |  | LABOUR_OFFICE 66685/6 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3795575 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3528.07 | 1 | Plate British standard Arteor - square - 3 modules - graphite - 575072 |  | Each | 60 | 59753714 |  |  |  | Plate British standard Arteor - square - 3 modules - graphite - 575072 | 030060100898 | MEP | Received | 2023-02-05 | Accounted transaction received
3795576 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 47996.69 | 1 | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser |  | Each | 125 | 59753715 |  |  |  | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser | 030040700472 | MEP | Received | 2023-02-05 | Accounted transaction received
3795577 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1368 | 1 | PVC Box 110x150x70 mm ip66 |  | Each | 12 | 59753716 |  |  |  | PVC Box 110x150x70 mm ip66 | 030069000031 | MEP | Received | 2023-02-05 | Accounted transaction received
3795578 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 484.5 | 1 | مسدس سيلكون ( سيلانت ) |  | Each | 3 | 59753782 |  |  |  | مسدس سيلكون ( سيلانت ) | 200010000224 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795579 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4275 | 1 | تيب دوكو |  | Each | 150 | 59753783 |  |  |  | تيب دوكو | 200010000048 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795580 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 598.5 | 1 | سكينة معجون 5بوصة |  | Each | 15 | 59753784 |  |  |  | سكينة معجون 5بوصة | 200010000080 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795581 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 164 | 1 | صابون سائل |  | Can | 8 | 59753785 |  |  |  | صابون سائل | 700020000013 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795582 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 14044.8 | 1 | بولي ايثيلين 200 ميكرون شفاف |  | Kilogram | 176 | 59753786 |  |  |  | بولي ايثيلين 200 ميكرون شفاف | 040010000042 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795583 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 79.8 | 1 | سلاح كتر |  | Each | 2 | 59753787 |  |  |  | سلاح كتر | 200010000411 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795584 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 279.3 | 1 | فدية منشار 9.25 بوصة |  | Each | 1 | 59753788 |  |  |  | فدية منشار 9.25 بوصة | 200010000434 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795585 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 399 | 1 | مكنسة ناعمة |  | Each | 10 | 59753789 |  |  |  | مكنسة ناعمة | 200010000449 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795586 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 120 | 1 | ملمع خشب |  | Each | 5 | 59753790 |  |  |  | ملمع خشب | 200010000897 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795587 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1453.5 | 1 | تنر |  | Each | 15 | 59753791 |  |  |  | تنر | 060019000008 | MEP | Received | 2023-02-05 | Accounted transaction received
3795588 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 684 | 1 | فدية خرشوفة 4 بوصة 2 صف |  | Each | 8 | 59753792 |  |  |  | فدية خرشوفة 4 بوصة 2 صف | 200010000499 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795589 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 570 | 1 | إسطوانة بسكوتة 5 بوصة |  | Each | 20 | 59753793 |  |  |  | إسطوانة بسكوتة 5 بوصة | 140010000020 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795590 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4055.76 | 1 | سيتوسيل 400 أبيض |  | Each | 28 | 59753794 |  |  |  | سيتوسيل 400 أبيض | 050010000066 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795591 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 57 | 1 | مسمار خشابى 6 سم |  | Kilogram | 1 | 59753795 |  |  |  | مسمار خشابى 6 سم | 200020000141 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795592 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1250.01 | 1 | جاسكيت لاصق ذاتي عرض 5 سم |  | Each | 25 | 59753796 |  |  |  | جاسكيت لاصق ذاتي عرض 5 سم | 060050300004 | MEP | Received | 2023-02-05 | Accounted transaction received
3795593 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 524.4 | 1 | اسبراي الوان |  | Each | 4 | 59753797 |  |  |  | اسبراي الوان | 200010001522 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795594 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 527.25 | 1 | كرتون مضلع - تغليف |  | Kilogram | 37 | 59753798 |  |  |  | كرتون مضلع - تغليف | 910010000387 | Administration | Received | 2023-02-05 | Accounted transaction received
3795595 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 136.8 | 1 | مسمار سنارة 3.5 سم |  | Kilogram | 2 | 59753799 |  |  |  | مسمار سنارة 3.5 سم | 200020000466 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795596 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 717.9 | 1 | خواشة 22 مم |  | Each | 3 | 59753800 |  |  |  | خواشة 22 مم | 039020200041 | MEP | Received | 2023-02-05 | Accounted transaction received
3795597 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 256.5 | 1 | تيب دوكو 2سم |  | Each | 15 | 59753801 |  |  |  | تيب دوكو 2سم | 200010002032 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795598 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 13680 | 1 | Master Seal NP 472 |  | Kit | 120 | 59753802 |  |  |  | Master Seal NP 472 | 360010000355 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795599 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 299 | 1 | كاتل شاى |  | Each | 1 | 59753803 |  |  |  | كاتل شاى | 700020000172 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795600 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 35 | 1 | خرشوفة 36 مم |  | Each | 1 | 59753804 |  |  |  | خرشوفة 36 مم | 200010001441 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795601 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 855 | 1 | فوطة حمام قطن |  | Each | 25 | 59753805 |  |  |  | فوطة حمام قطن | 700020000193 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795602 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 8586.08 | 1 | Hardware Accessories for Wooden Doors Privacy Door Latch Privacy Door Latch Welder 43702424 Silver |  | Each | 27 | 59753806 |  |  |  | Hardware Accessories for Wooden Doors Privacy Door Latch Privacy Door Latch Welder 43702424 Silver | 250010001514 | Procurement | Received | 2023-02-05 | Accounted transaction received
3795603 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 16319.97 | 1 | Hardware Accessories for Wooden Doors Concealed hinge system & Bathroom Concealed Hinges Simonswerk completely concealed hinge system with load capacity 80.0 kg two hinges per door leaf (1x2m) |  | Each | 6 | 59753807 |  |  |  | Hardware Accessories for Wooden Doors Concealed hinge system & Bathroom Concealed Hinges Simonswerk completely concealed hinge system with load capacity 80.0 kg two hinges per door leaf (1x2m) | 250010001515 | Procurement | Received | 2023-02-05 | Accounted transaction received
3795604 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 36480 | 1 | Action floor spring max 300kg for Glass doors, brand Stanley |  | Each | 4 | 59753808 |  |  |  | Action floor spring max 300kg for Glass doors, brand Stanley | 310010000019 | Fleets | Received | 2023-02-05 | Accounted transaction received
3795605 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3195.31 | 1 | Bisazza glass mosaic - VTC 20.23 Color: Light Blue for jacuzzi stairs Tile Size: 2*2 cm |  | Square Meter | 0.81 | 59753809 |  |  |  | Bisazza glass mosaic - VTC 20.23 Color: Light Blue for jacuzzi stairs Tile Size: 2*2 cm | 310010000025 | Fleets | Received | 2023-02-05 | Accounted transaction received
3795606 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 311.51 | 1 | سيفتي عمال |  | Each | 1 | 59753813 |  |  |  | سيفتي عمال | 010030000002 | Safety | Received | 2023-02-05 | Accounted transaction received
3795607 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.09.04 | Fire Fighting Networ | 2 | SITE WORK |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 763.8 | 1 | Supplying of pendent concealed sprinkler , quick response , standard coverage , 68 C, 1/2", K=5.6 C/W cover plate |  | Each | 1 | 59753835 |  |  |  | Supplying of pendent concealed sprinkler , quick response , standard coverage , 68 C, 1/2", K=5.6 C/W cover plate | 060090100007 | MEP | Received | 2023-02-05 | Accounted transaction received
3795608 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 285 | 1 | فيشر 6 مم |  | Each | 200 | 59753836 |  |  |  | فيشر 6 مم | 200010000679 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795609 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1596 | 1 | كورنر (TDF) |  | Each | 400 | 59753837 |  |  |  | كورنر (TDF) | 060040200002 | MEP | Received | 2023-02-05 | Accounted transaction received
3795610 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 513 | 1 | مسمار 6 مم بالكيلو |  | Kilogram | 5 | 59753838 |  |  |  | مسمار 6 مم بالكيلو | 200020000274 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795611 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 7391.71 | 1 | "عزل داخلى مجارى الهواء ماركة K-FLEX ارما فليكس بسمك 13 مم باللصق ابعاد الرول 1m x 14m" |  | Square Meter | 28 | 59753839 |  |  |  | "عزل داخلى مجارى الهواء ماركة K-FLEX ارما فليكس بسمك 13 مم باللصق ابعاد الرول 1m x 14m" | 060050300003 | MEP | Received | 2023-02-05 | Accounted transaction received
3795612 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.01 | HAVC Duct Works | 15 | MECHANICAL WORKS |  | 2023-01-30 | Duct Works |  |  |  | Materials | Waldorf Astoria-0164 | 2579.36 | 1 | Duct sealant |  | Each | 60 | 59753840 |  |  |  | Duct sealant | 060019000096 | MEP | Received | 2023-02-05 | Accounted transaction received
3795613 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 300 | 1 | مسامير سيلف دريل 10مم طول 2سم |  | Each | 150 | 59753841 |  |  |  | مسامير سيلف دريل 10مم طول 2سم | 060191210006 | MEP | Received | 2023-02-05 | Accounted transaction received
3795614 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 360 | 1 | مسمار سن صاج 1.5 سم |  | Kilogram | 3 | 59753842 |  |  |  | مسمار سن صاج 1.5 سم | 200020000392 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795615 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2359.8 | 1 | Hot dip Galvanized after fabrication, Cable Tray Trunk Type, 200mm Width, 100mm height of Side,1.5mm thickness,10mmReturnFlange ,3000mm Length. |  | Meter | 12 | 59753843 |  |  |  | Hot dip Galvanized after fabrication, Cable Tray Trunk Type, 200mm Width, 100mm height of Side,1.5mm thickness,10mmReturnFlange ,3000mm Length. | 030101400048 | MEP | Received | 2023-02-05 | Accounted transaction received
3795616 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 90 | 1 | حنفية 2/1 خلاط بارد |  | Each | 1 | 59753844 |  |  |  | حنفية 2/1 خلاط بارد | 240070000408 | MEP | Received | 2023-02-05 | Accounted transaction received
3795617 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 24464.4 | 1 | UP10 جلد طبيعي خاص بالتنجيد ومقاوم للإحتكاك الجاف والرطب |  | Square Foot | 370 | 59762157 |  |  |  | UP10 جلد طبيعي خاص بالتنجيد ومقاوم للإحتكاك الجاف والرطب | 700020000217 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795618 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 36438.73 | 1 | جلد طبيعي خاص بالتنجيد ومقاوم للإحتكاك الجاف والرطب Approved Supplier Code: W - BR13 |  | Square Foot | 551.1 | 59762158 |  |  |  | جلد طبيعي خاص بالتنجيد ومقاوم للإحتكاك الجاف والرطب Approved Supplier Code: W - BR13 | 700020000231 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795619 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 120657.6 | 1 | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² |  | Kilogram | 2160 | 59762200 |  |  |  | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² | 060040200001 | MEP | Received | 2023-02-05 | Accounted transaction received
3795620 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1995 | 1 | Threaded Mechanical Tee 2½''*1'' UL listed, FM approved |  | Each | 5 | 59762201 |  |  |  | Threaded Mechanical Tee 2½''*1'' UL listed, FM approved | 060011500213 | MEP | Received | 2023-02-05 | Accounted transaction received
3795621 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 5004.34 | 1 | Threaded Mechanical Tee 2.5''*1.25'' UL listed, FM approved |  | Each | 7 | 59762202 |  |  |  | Threaded Mechanical Tee 2.5''*1.25'' UL listed, FM approved | 060011500214 | MEP | Received | 2023-02-05 | Accounted transaction received
3795622 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 7749.94 | 1 | Threaded Mechanical Tee 2.5''*1.5'' UL listed, FM approved |  | Each | 9 | 59762203 |  |  |  | Threaded Mechanical Tee 2.5''*1.5'' UL listed, FM approved | 060011500215 | MEP | Received | 2023-02-05 | Accounted transaction received
3795623 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3511.2 | 1 | 90° Elbow 2.50'' UL listed, FM approved |  | Each | 14 | 59762204 |  |  |  | 90° Elbow 2.50'' UL listed, FM approved | 060011500075 | MEP | Received | 2023-02-05 | Accounted transaction received
3795624 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4312.37 | 1 | 90° Elbow 3'' UL listed, FM approved |  | Each | 11 | 59762205 |  |  |  | 90° Elbow 3'' UL listed, FM approved | 060011500076 | MEP | Received | 2023-02-05 | Accounted transaction received
3795625 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2954.12 | 1 | 90° Elbow 4'' UL listed, FM approved |  | Each | 3 | 59762206 |  |  |  | 90° Elbow 4'' UL listed, FM approved | 060011500077 | MEP | Received | 2023-02-05 | Accounted transaction received
3795626 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 938.83 | 1 | Tee 2.50'' UL listed, FM approved |  | Each | 1 | 59762207 |  |  |  | Tee 2.50'' UL listed, FM approved | 060011500113 | MEP | Received | 2023-02-05 | Accounted transaction received
3795627 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1685.23 | 1 | Tee 4'' UL listed, FM approved |  | Each | 1 | 59762208 |  |  |  | Tee 4'' UL listed, FM approved | 060011500115 | MEP | Received | 2023-02-05 | Accounted transaction received
3795628 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1179.53 | 1 | Rigid Coupling 2'' UL listed, FM approved |  | Each | 5 | 59762209 |  |  |  | Rigid Coupling 2'' UL listed, FM approved | 060011500009 | MEP | Received | 2023-02-05 | Accounted transaction received
3795629 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1324.36 | 1 | Rigid Coupling3 '' UL listed, FM approved |  | Each | 4 | 59762210 |  |  |  | Rigid Coupling3 '' UL listed, FM approved | 060011500011 | MEP | Received | 2023-02-05 | Accounted transaction received
3795630 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1824 | 1 | Threaded Mechanical Tee 3''*1.25'' UL listed, FM approved |  | Each | 4 | 59762211 |  |  |  | Threaded Mechanical Tee 3''*1.25'' UL listed, FM approved | 060011500221 | MEP | Received | 2023-02-05 | Accounted transaction received
3795631 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2280 | 1 | Threaded Mechanical Tee 4''*1'' UL listed, FM approved |  | Each | 4 | 59762212 |  |  |  | Threaded Mechanical Tee 4''*1'' UL listed, FM approved | 060011500223 | MEP | Received | 2023-02-05 | Accounted transaction received
3795632 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1140 | 1 | Threaded Mechanical Tee 4''*1.25'' UL listed, FM approved |  | Each | 2 | 59762213 |  |  |  | Threaded Mechanical Tee 4''*1.25'' UL listed, FM approved | 060011500224 | MEP | Received | 2023-02-05 | Accounted transaction received
3795633 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3499.54 | 1 | Grooved Reducer 2.5*2'' UL listed, FM approved |  | Each | 3 | 59762214 |  |  |  | Grooved Reducer 2.5*2'' UL listed, FM approved | 060011500366 | MEP | Received | 2023-02-05 | Accounted transaction received
3795634 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1117.55 | 1 | Grooved Reducer 3''*2.5'' UL listed, FM approved |  | Each | 1 | 59762215 |  |  |  | Grooved Reducer 3''*2.5'' UL listed, FM approved | 060011500370 | MEP | Received | 2023-02-05 | Accounted transaction received
3795635 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1140 | 1 | Grooved Mechanical Tee 4''*2'' UL listed, FM approved |  | Each | 2 | 59762216 |  |  |  | Grooved Mechanical Tee 4''*2'' UL listed, FM approved | 060011500261 | MEP | Received | 2023-02-05 | Accounted transaction received
3795636 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 6612 | 1 | Forged Carbon Steel A105 Weld Neck Flange Class 150 Size : 4" |  | Each | 4 | 59762217 |  |  |  | Forged Carbon Steel A105 Weld Neck Flange Class 150 Size : 4" | 060011800170 | MEP | Received | 2023-02-05 | Accounted transaction received
3795637 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 14877 | 1 | Resilient Seated Flanged Swing Check Valve 300PSI Size 4", Model: REL-FCV-L501F Part No. 7U99002375 Class 150 |  | Each | 1 | 59762219 |  |  |  | Resilient Seated Flanged Swing Check Valve 300PSI Size 4", Model: REL-FCV-L501F Part No. 7U99002375 Class 150 | 060170600030 | MEP | Received | 2023-02-05 | Accounted transaction received
3795638 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 21375 | 1 | Ceramic fan shape wall tiles FS-026 Sheet Size 20*25 cm |  | Sheet | 200 | 59762223 |  |  |  | Ceramic fan shape wall tiles FS-026 Sheet Size 20*25 cm | 170010000654 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795639 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 336.26 | 1 | بواط 10 * 10 عالى المقاس ¾ " |  | Each | 5 | 59762272 |  |  |  | بواط 10 * 10 عالى المقاس ¾ " | 030020100105 | MEP | Received | 2023-02-05 | Accounted transaction received
3795640 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2394 | 1 | بواط واتر بروف بفتحات مقاس 30 × 38 × 12 سم |  | Each | 6 | 59762273 |  |  |  | بواط واتر بروف بفتحات مقاس 30 × 38 × 12 سم | 030010000185 | MEP | Received | 2023-02-05 | Accounted transaction received
3795641 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1040.66 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 16 | 59762274 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-02-05 | Accounted transaction received
3795642 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 126.67 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 10 | 59762275 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-02-05 | Accounted transaction received
3795643 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 833.44 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أصفر (cu/pvc) |  | Meter | 100 | 59762276 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أصفر (cu/pvc) | 030030101024 | MEP | Received | 2023-02-05 | Accounted transaction received
3795644 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 811.12 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أصفر × أخضر (cu/pvc) |  | Meter | 100 | 59762277 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أصفر × أخضر (cu/pvc) | 030030101027 | MEP | Received | 2023-02-05 | Accounted transaction received
3795645 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2235.79 | 1 | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS |  | Each | 10 | 59762278 |  |  |  | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS | 030060100617 | MEP | Received | 2023-02-05 | Accounted transaction received
3795646 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 985.31 | 1 | Wiring Devices (54000) METAL FLUSH-MOUNTING BOX FOR INSTALLATION IN CONCRETE FLOOR - 3 MODULES |  | Each | 10 | 59762279 |  |  |  | Wiring Devices (54000) METAL FLUSH-MOUNTING BOX FOR INSTALLATION IN CONCRETE FLOOR - 3 MODULES | 030060100618 | MEP | Received | 2023-02-05 | Accounted transaction received
3795647 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 380.21 | 1 | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 |  | Each | 20 | 59762280 |  |  |  | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 | 150020000178 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795648 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1331.22 | 1 | mosaic adapter code 69580 |  | Each | 14 | 59762281 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-02-05 | Accounted transaction received
3795649 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 793.39 | 1 | DS 2 pole , 63A, ABS Enclsosure IP 65 , PART NUMBER : kem 263u y/r abs |  | Each | 1 | 59762282 |  |  |  | DS 2 pole , 63A, ABS Enclsosure IP 65 , PART NUMBER : kem 263u y/r abs | 030060200023 | MEP | Received | 2023-02-05 | Accounted transaction received
3795650 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 902.09 | 1 | Surface mounting socket P17 Pro ? IP 66/67 ? 200/250 V~ ? 63 A ? 2P+E (Legrand 555554) |  | Each | 1 | 59762283 |  |  |  | Surface mounting socket P17 Pro ? IP 66/67 ? 200/250 V~ ? 63 A ? 2P+E (Legrand 555554) | 030060300022 | MEP | Received | 2023-02-05 | Accounted transaction received
3795651 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 507.29 | 1 | Straight plug P17 Pro ? IP 66/67 ? 200/250 V~ ? 63 A ? 2P+E (Legrand 555524) |  | Each | 1 | 59762284 |  |  |  | Straight plug P17 Pro ? IP 66/67 ? 200/250 V~ ? 63 A ? 2P+E (Legrand 555524) | 030060300023 | MEP | Received | 2023-02-05 | Accounted transaction received
3795652 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1123.47 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 14 | 59762285 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-02-05 | Accounted transaction received
3795653 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 238.94 | 1 | Metal Galvanized back box 7x14 cm with deep 47 mm |  | Each | 10 | 59762286 |  |  |  | Metal Galvanized back box 7x14 cm with deep 47 mm | 030069000027 | MEP | Received | 2023-02-05 | Accounted transaction received
3795654 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1734.2 | 1 | 15/75 cd Speaker/Strobe, 70V - 4" Cone, Round - WHITE - 965-7A-4RW |  | Each | 1 | 59762287 |  |  |  | 15/75 cd Speaker/Strobe, 70V - 4" Cone, Round - WHITE - 965-7A-4RW | 031010000241 | MEP | Received | 2023-02-05 | Accounted transaction received
3795655 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 501.94 | 1 | SPLASH PROOF COVER Code : 617636 |  | Each | 5 | 59762288 |  |  |  | SPLASH PROOF COVER Code : 617636 | 030060100927 | MEP | Received | 2023-02-05 | Accounted transaction received
3795656 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 338.03 | 1 | 1G 20A DP SWT + NEON + E WH - 617671 |  | Each | 3 | 59762289 |  |  |  | 1G 20A DP SWT + NEON + E WH - 617671 | 030060100942 | MEP | Received | 2023-02-05 | Accounted transaction received
3795657 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 260.01 | 1 | Double pole switches 32 A – 250V~ 1 gang 1?way switch + led power indicator - 617629 |  | Each | 2 | 59762290 |  |  |  | Double pole switches 32 A – 250V~ 1 gang 1?way switch + led power indicator - 617629 | 030060100943 | MEP | Received | 2023-02-05 | Accounted transaction received
3795658 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 14250 | 1 | Master Seal NP 472 |  | Kit | 125 | 59762297 |  |  |  | Master Seal NP 472 | 360010000355 | Purchasing | Received | 2023-02-05 | Accounted transaction received
3795659 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2667.6 | 1 | Hinges Mckinney Spring Hinge 1552 4.5" x 4.0" 630 |  | Each | 3 | 59762309 |  |  |  | Hinges Mckinney Spring Hinge 1552 4.5" x 4.0" 630 | 250010000662 | Procurement | Received | 2023-02-05 | Accounted transaction received
3795660 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 13680 | 1 | NFR Single Leaf Steel Door (D7), REGENT Type with Dimensions (1000*2400mm) Door Sheet Thk. (1.2mm),Frame Series CF, Frame Sheet Thk. (1.5mm),Jamb Width 150mm Powder Coated Finish |  | Each | 1 | 59762310 |  |  |  | NFR Single Leaf Steel Door (D7), REGENT Type with Dimensions (1000*2400mm) Door Sheet Thk. (1.2mm),Frame Series CF, Frame Sheet Thk. (1.5mm),Jamb Width 150mm Powder Coated Finish | 250010001025 | Procurement | Received | 2023-02-05 | Accounted transaction received
3795661 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 16319.97 | 1 | Hardware Accessories for Wooden Doors Concealed hinge system & Bathroom Concealed Hinges Simonswerk completely concealed hinge system with load capacity 80.0 kg two hinges per door leaf (1x2m) |  | Each | 6 | 59762311 |  |  |  | Hardware Accessories for Wooden Doors Concealed hinge system & Bathroom Concealed Hinges Simonswerk completely concealed hinge system with load capacity 80.0 kg two hinges per door leaf (1x2m) | 250010001515 | Procurement | Received | 2023-02-05 | Accounted transaction received
3795662 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 34200 | 1 | FR Flush Steel Access Door With Dim (60×60cm) - Regent Type - 1.2mm Leaf Sheet Thickness - CF Frame Series - 1.5mm Frame Sheet Thickness - Jamb Depth 150mm - Polyurethane Paint as per technical & material submittal approval |  | Each | 6 | 59762312 |  |  |  | FR Flush Steel Access Door With Dim (60×60cm) - Regent Type - 1.2mm Leaf Sheet Thickness - CF Frame Series - 1.5mm Frame Sheet Thickness - Jamb Depth 150mm - Polyurethane Paint as per technical & material submittal approval | 250010001838 | Procurement | Received | 2023-02-05 | Accounted transaction received
3795663 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 34200 | 1 | FR Flush Steel Access Door with Dim (810×2230mm) - Regent Type - 1.2mm Leaf Sheet Thickness - CF Frame Series - 1.5mm Frame Sheet Thickness - Jamb Depth 150mm - Polyurethane Paint as per technical & material submittal approval |  | Each | 2 | 59762313 |  |  |  | FR Flush Steel Access Door with Dim (810×2230mm) - Regent Type - 1.2mm Leaf Sheet Thickness - CF Frame Series - 1.5mm Frame Sheet Thickness - Jamb Depth 150mm - Polyurethane Paint as per technical & material submittal approval | 250010001839 | Procurement | Received | 2023-02-05 | Accounted transaction received
3795664 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 455.29 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 7 | 59762327 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-02-05 | Accounted transaction received
3795665 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 665.61 | 1 | mosaic adapter code 69580 |  | Each | 7 | 59762328 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-02-05 | Accounted transaction received
3795666 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 902.09 | 1 | Surface mounting socket P17 Pro ? IP 66/67 ? 200/250 V~ ? 63 A ? 2P+E (Legrand 555554) |  | Each | 1 | 59762329 |  |  |  | Surface mounting socket P17 Pro ? IP 66/67 ? 200/250 V~ ? 63 A ? 2P+E (Legrand 555554) | 030060300022 | MEP | Received | 2023-02-05 | Accounted transaction received
3795667 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 507.29 | 1 | Straight plug P17 Pro ? IP 66/67 ? 200/250 V~ ? 63 A ? 2P+E (Legrand 555524) |  | Each | 1 | 59762330 |  |  |  | Straight plug P17 Pro ? IP 66/67 ? 200/250 V~ ? 63 A ? 2P+E (Legrand 555524) | 030060300023 | MEP | Received | 2023-02-05 | Accounted transaction received
3795668 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 561.73 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 7 | 59762331 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-02-05 | Accounted transaction received
3795669 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-01-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 306.8 | 1 | STRAIGHT PLUG P17 - IP66/67 - 380/415 V~ - 32 A - 3P+N+E Legrand 555439 |  | Each | 1 | 59762332 |  |  |  | STRAIGHT PLUG P17 - IP66/67 - 380/415 V~ - 32 A - 3P+N+E Legrand 555439 | 030060100737 | MEP | Received | 2023-02-05 | Accounted transaction received
3798708 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-01-31 | Honouring of terrorism 0.0005 |  |  |  | Indirect | Alrowad Construction_OU | 420.07 | 1 | قيد مرتبات شهر يناير 2023 | Salary-Jan-2023 | Currency | 420.07 | 21955997 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر يناير 2023 |  | Finacial | Received | 2023-02-06 | Accounted transaction received
3798746 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.06 | Telephones | 17 | Indirect Cost |  | 2023-01-31 | Telephones |  |  |  | Indirect | Alrowad Construction_OU | -643.84 | 1 | قيد مرتبات شهر يناير 2023 | Salary-Jan-2023 | Currency | -643.84 | 21955997 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر يناير 2023 |  | Finacial | Received | 2023-02-06 | Accounted transaction received
3798783 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.02 | Health Care | 17 | Indirect Cost |  | 2023-01-31 | Medical Care |  |  |  | Direct Manpower | Alrowad Construction_OU | -3541.55 | 1 | قيد مرتبات شهر يناير 2023 | Salary-Jan-2023 | Currency | -3541.55 | 21955997 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر يناير 2023 |  | Finacial | Received | 2023-02-06 | Accounted transaction received
3798822 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-01-31 | Hirings Payrool |  |  |  | Indirect | Alrowad Construction_OU | -47001.66 | 1 | قيد مرتبات شهر يناير 2023 | Salary-Jan-2023 | Currency | -47001.66 | 21955997 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر يناير 2023 |  | Finacial | Received | 2023-02-06 | Accounted transaction received
3805623 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.02 | Rented Cars | 17 | Indirect Cost |  | 2023-02-06 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 19980 | 1 | 3 waldorf astoria | 3 waldorf astoria | Currency | 19980 | 21954562 | 3084 | محمد احمد محمد محمد | Rowad | 3 waldorf astoria |  | Finacial | Received | 2023-02-06 | Accounted transaction received
3805624 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.02 | Rented Cars | 17 | Indirect Cost |  | 2023-02-06 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -19980 | 1 | 3 waldorf astoria | 3 waldorf astoria | Currency | -19980 | 21954562 | 3084 | محمد احمد محمد محمد | Rowad | 3 waldorf astoria |  | Finacial | Received | 2023-02-06 | Accounted transaction received
3805625 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.02 | Rented Cars | 17 | Indirect Cost |  | 2023-02-06 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 19980 | 1 | 3 waldorf astoria | 3 waldorf astoria | Currency | 19980 | 21954562 | 3084 | محمد احمد محمد محمد | Rowad | 3 waldorf astoria |  | Finacial | Received | 2023-02-06 | Accounted transaction received
3805626 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.02 | Rented Cars | 17 | Indirect Cost |  | 2023-02-06 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 37500 | 1 | 3 waldorf astoria | 3 waldorf astoria | Currency | 37500 | 21954562 | 5214 | المتحدة لايجار وتوريد السيارات | rowad | 3 waldorf astoria |  | Finacial | Received | 2023-02-06 | Accounted transaction received
3805629 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.02 | Rented Cars | 17 | Indirect Cost |  | 2023-02-06 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 27996 | 1 | 3 waldorf astoria | 3 waldorf astoria | Currency | 27996 | 21954562 | 9182 | مؤسسة الجينيرال لتأجير السيارات | rowad | 3 waldorf astoria |  | Finacial | Received | 2023-02-06 | Accounted transaction received
3810984 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2308.5 |  | Conduits for lighting fixtures |  | Currency | 27 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.053 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3808082 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2023-02-07 | Stationary |  |  |  | Office and Site expenses | Alrowad Construction_OU | 50 | 1 | تسويه ك /60-61-62-63-64-65-66--71-72-73-74-75-76 - متنوعات | st-60-61-62-63-64-65-66--71-72-73-74-75-76-2-23 | Currency | 50 | 21961801 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /60-61-62-63-64-65-66--71-72-73-74-75-76 - متنوعات |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3808083 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-02-07 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 4710 | 1 | تسويه ك /60-61-62-63-64-65-66--71-72-73-74-75-76 - متنوعات | st-60-61-62-63-64-65-66--71-72-73-74-75-76-2-23 | Currency | 4710 | 21961801 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /60-61-62-63-64-65-66--71-72-73-74-75-76 - متنوعات |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3808084 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.08 | Electrical Expenses | 17 | Indirect Cost |  | 2023-02-07 | Electrical Expenses |  |  |  | Indirect | Alrowad Construction_OU | 3414.5 | 1 | تسويه ك /60-61-62-63-64-65-66--71-72-73-74-75-76 - متنوعات | st-60-61-62-63-64-65-66--71-72-73-74-75-76-2-23 | Currency | 3414.5 | 21961801 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /60-61-62-63-64-65-66--71-72-73-74-75-76 - متنوعات |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3808085 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2023-02-07 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 5449.85 | 1 | تسويه ك /60-61-62-63-64-65-66--71-72-73-74-75-76 - متنوعات | st-60-61-62-63-64-65-66--71-72-73-74-75-76-2-23 | Currency | 5449.85 | 21961801 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /60-61-62-63-64-65-66--71-72-73-74-75-76 - متنوعات |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3808096 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2023-02-07 | Accomodation |  |  |  | Indirect | Alrowad Construction_OU | 41250 | 1 | تسويه ك /70 ايجارات شهر فبراير- استوربا | st-70-2-23 | Currency | 41250 | 21961801 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /70 ايجارات شهر فبراير- استوربا |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3808172 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.03 | Hirings daily wages | 17 | Indirect Cost |  | 2023-02-07 | Bank Fees |  |  |  | Finance cost | Alrowad Construction_OU | 18415.9 | 1 | lg BM 2/2023 astoria | lg BM 2/2023 astoria | Currency | 18415.9 | 21961801 | 2131 | Miscellaneous supplier | RME | lg BM 2/2023 astoria |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3809980 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-31 | Computers Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 4375.96 | 1 | FA adj.Depreciation To projects | FA adj.Depreciation To projects | Currency | 4375.96 | 21991805 | 2131 | Miscellaneous supplier | RME | FA adj.Depreciation To projects |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810031 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-31 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 12826.36 | 1 | FA adj.Depreciation To projects | FA adj.Depreciation To projects | Currency | 12826.36 | 21991805 | 2131 | Miscellaneous supplier | RME | FA adj.Depreciation To projects |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810985 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 940.5 |  | Conduits for lighting fixtures |  | Currency | 11 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.055 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810082 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-31 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 26370.87 | 1 | FA adj.Depreciation To projects | FA adj.Depreciation To projects | Currency | 26370.87 | 21991805 | 2131 | Miscellaneous supplier | RME | FA adj.Depreciation To projects |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810986 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1296 |  | Conduits for lighting fixtures |  | Currency | 6 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.098 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810133 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-31 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 24227.16 | 1 | FA adj.Depreciation To projects | FA adj.Depreciation To projects | Currency | 24227.16 | 21991805 | 2131 | Miscellaneous supplier | RME | FA adj.Depreciation To projects |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810184 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-31 | Furniture Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 1901.4 | 1 | FA adj.Depreciation To projects | FA adj.Depreciation To projects | Currency | 1901.4 | 21991805 | 2131 | Miscellaneous supplier | RME | FA adj.Depreciation To projects |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810987 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2025 |  | Conduits for lighting fixtures |  | Currency | 15 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.093 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810235 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-01-31 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 3135.81 | 1 | FA adj.Depreciation To projects | FA adj.Depreciation To projects | Currency | 3135.81 | 21991805 | 2131 | Miscellaneous supplier | RME | FA adj.Depreciation To projects |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810988 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1881 |  | Conduits for lighting fixtures |  | Currency | 22 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.063 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810968 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | 107182 |  | Conduits for lighting fixtures |  | Currency | 107182 |  | 4820 | سيجاب للهندسه والتجاره |  | 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810969 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 27000 |  | Conduits for lighting fixtures |  | Currency | 120 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.024 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810970 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7271.97 |  | Conduits for lighting fixtures |  | Currency | 356 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.025 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810971 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2238.39 |  | Conduits for lighting fixtures |  | Currency | 11 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.038 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810972 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 730.24 |  | Conduits for lighting fixtures |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.039 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810974 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4104 |  | Conduits for lighting fixtures |  | Currency | 48 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.051 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810975 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1282.5 |  | Conduits for lighting fixtures |  | Currency | 15 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.061 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810976 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 940.5 |  | Conduits for lighting fixtures |  | Currency | 11 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.063 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810977 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 342 |  | Conduits for lighting fixtures |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.064 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810978 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 482.4 |  | Conduits for lighting fixtures |  | Currency | 8 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.083 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810979 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 456 |  | Conduits for lighting fixtures |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.085 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810983 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2250 |  | Conduits for lighting fixtures |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.049 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810989 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 598.5 |  | Conduits for lighting fixtures |  | Currency | 7 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.068 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810990 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1728 |  | Conduits for lighting fixtures |  | Currency | 8 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.097 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810991 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1539 |  | Conduits for lighting fixtures |  | Currency | 9 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.004 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810992 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 342 |  | Conduits for lighting fixtures |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.025 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810993 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4006.5 |  | Conduits for lighting fixtures |  | Currency | 29 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.026 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810994 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1090.13 |  | Conduits for lighting fixtures |  | Currency | 10 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.037 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810995 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 639.54 |  | Conduits for lighting fixtures |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.038 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810996 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1710 |  | Conduits for lighting fixtures |  | Currency | 20 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.052 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810997 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3249 |  | Conduits for lighting fixtures |  | Currency | 38 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.072 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810998 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2432 |  | Conduits for lighting fixtures |  | Currency | 32 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.064 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3810999 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2308.5 |  | Conduits for lighting fixtures |  | Currency | 27 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.077 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3811000 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4617 |  | Conduits for lighting fixtures |  | Currency | 54 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.075 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3811001 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 855 |  | Conduits for lighting fixtures |  | Currency | 10 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.081 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3811002 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1111.5 |  | Conduits for lighting fixtures |  | Currency | 13 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.083 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3811003 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 513 |  | Conduits for lighting fixtures |  | Currency | 6 |  | 4820 | سيجاب للهندسه والتجاره |  | 9.9.003 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3811004 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 513 |  | Conduits for lighting fixtures |  | Currency | 6 |  | 4820 | سيجاب للهندسه والتجاره |  | 9.9.007 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3811005 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 513 |  | Conduits for lighting fixtures |  | Currency | 6 |  | 4820 | سيجاب للهندسه والتجاره |  | 9.9.004 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3811006 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 342 |  | Conduits for lighting fixtures |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 9.9.008 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3811007 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 48 |  | Conduits for lighting fixtures |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 1.1.001 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3811009 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | -5750 |  | Conduits for lighting fixtures |  | Currency | -5750 |  | 4820 | سيجاب للهندسه والتجاره |  | 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3811010 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -348.97 |  | Conduits for lighting fixtures |  | Currency | -348.97 |  | 4820 | سيجاب للهندسه والتجاره |  | LABOUR_OFFICE 67059/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3811946 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1151.87 | 1 | 1.1.002 63967/7 |  | Currency | 272 |  | 10825 | احمد كريم جروب للتجارة والمقاولات |  | 1.1.002 63967/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3811947 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2353.99 | 1 | 1.1.003 63967/7 |  | Currency | 272 |  | 10825 | احمد كريم جروب للتجارة والمقاولات |  | 1.1.003 63967/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3811948 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2430.57 | 1 | 1.1.021 63967/7 |  | Currency | 254 |  | 10825 | احمد كريم جروب للتجارة والمقاولات |  | 1.1.021 63967/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3811949 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1107.18 | 1 | 1.1.022 63967/7 |  | Currency | 254 |  | 10825 | احمد كريم جروب للتجارة والمقاولات |  | 1.1.022 63967/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3811950 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7208.86 | 1 | 1.1.024 63967/7 |  | Currency | 254 |  | 10825 | احمد كريم جروب للتجارة والمقاولات |  | 1.1.024 63967/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3811951 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 53580 | 1 | 2.1 63967/7 |  | Currency | 235 |  | 10825 | احمد كريم جروب للتجارة والمقاولات |  | 2.1 63967/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3811952 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -305.25 | 1 | LABOUR_OFFICE 63967/7 |  | Currency | -305.25 |  | 10825 | احمد كريم جروب للتجارة والمقاولات |  | LABOUR_OFFICE 63967/7 |  | Finacial | Received | 2023-02-08 | Accounted transaction received
3813946 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.08.00 | Gypsum Board(G) | 9 | FINISHES WORK |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 43875 | 1 | 3.1 80045/3 |  | Currency | 32.5 |  | 12187 | اركاد للترميم |  | 3.1 80045/3 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813947 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.08.00 | Gypsum Board(G) | 9 | FINISHES WORK |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5250 | 1 | 4.1 80045/3 |  | Currency | 5 |  | 12187 | اركاد للترميم |  | 4.1 80045/3 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813948 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.08.00 | Gypsum Board(G) | 9 | FINISHES WORK |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -221.06 | 1 | LABOUR_OFFICE 80045/3 |  | Currency | -221.06 |  | 12187 | اركاد للترميم |  | LABOUR_OFFICE 80045/3 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813975 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 12390 | 1 | 1.1.01 60674/6 |  | Currency | 33.6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.01 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813976 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 33800 | 1 | 1.1.21 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.21 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813977 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 53006 | 1 | 1.1.24 60674/6 |  | Currency | 2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.24 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813978 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 12270 | 1 | 1.1.25 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.25 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813979 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 190800 | 1 | 1.1.3 60674/6 |  | Currency | 159 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.3 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813980 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 237248 | 1 | 1.1.08 60674/6 |  | Currency | 32 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.08 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813981 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9095 | 1 | 1.1.22 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.22 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813982 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 10850 | 1 | 1.1.23 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.23 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813983 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 104000 | 1 | 1.1.27 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.27 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813984 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3000 | 1 | 1.1.02 60674/6 |  | Currency | 8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.02 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813985 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 20000 | 1 | 1.1.15 60674/6 |  | Currency | 2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.15 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813986 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 106000 | 1 | 1.1.2 60674/6 |  | Currency | 4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.2 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813987 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 265000 | 1 | 1.1.8 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.8 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813988 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 22400 | 1 | 1.1.62 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.62 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813989 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 40000 | 1 | 1.1.65 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.65 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813990 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3800 | 1 | 1.1.73 60674/6 |  | Currency | 53 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.73 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813991 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 11050 | 1 | 1.1.71 60674/6 |  | Currency | 37 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.71 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813992 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 18800 | 1 | 1.1.81 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.81 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813993 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 29200 | 1 | 1.1.82 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.82 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813994 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 192000 | 1 | 1.1.61 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.61 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813995 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 128000 | 1 | 1.1.6 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.6 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813996 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 64000 | 1 | 1.1.64 60674/6 |  | Currency | 1.6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.64 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813997 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 17100 | 1 | 1.1.72 60674/6 |  | Currency | 36.5 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.72 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813998 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 12760 | 1 | 1.1.77 60674/6 |  | Currency | 57 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.77 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3813999 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 23750 | 1 | 1.1.86 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.86 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814000 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 23040 | 1 | 1.1.83 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.83 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814001 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 36400 | 1 | 1.1.87 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.87 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814002 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 133000 | 1 | 1.1.88 60674/6 |  | Currency | 140 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.88 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814003 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 110000 | 1 | 1.1.94 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.94 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814004 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 42180 | 1 | 1.1.103 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.103 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814005 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 107000 | 1 | 1.1.95 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.95 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814006 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 30210 | 1 | 1.1.101 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.101 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814007 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 46740 | 1 | 1.1.104 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.104 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814008 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 228000 | 1 | 1.1.106 60674/6 |  | Currency | 5 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.106 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814009 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 81600 | 1 | 1.1.91 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.91 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814010 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 49305 | 1 | 1.1.105 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.105 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814011 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 474000 | 1 | 1.1.93 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.93 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814012 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 930050 | 1 | 1.1.96 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.96 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814013 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 34200 | 1 | 1.1.102 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.102 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814014 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 11400 | 1 | 1.1.117 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.117 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814015 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 85500 | 1 | 1.1.108 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.108 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814016 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 88920 | 1 | 1.1.109 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.109 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814017 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 66120 | 1 | 1.1.114 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.114 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814018 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 76380 | 1 | 1.1.11 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.11 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814019 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 125400 | 1 | 1.1.111 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.111 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814020 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 301600 | 1 | 1.1.12 60674/6 |  | Currency | 1.6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.12 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814021 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 51300 | 1 | 1.1.107 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.107 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814022 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 35565.6 | 1 | 1.1.122 60674/6 |  | Currency | 2.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.122 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814023 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3762 | 1 | 1.1.136 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.136 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814024 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9690 | 1 | 1.1.135 60674/6 |  | Currency | 1.6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.135 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814025 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 429300 | 1 | 1.1.119 60674/6 |  | Currency | 1.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.119 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814026 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 39000 | 1 | 1.1.145 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.145 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814027 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 45320 | 1 | 1.1.152 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.152 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814028 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 14000 | 1 | 1.1.139 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.139 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814029 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 20000 | 1 | 1.1.146 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.146 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814030 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4600 | 1 | 1.1.153 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.153 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814031 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 14000 | 1 | 1.1.154 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.154 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814032 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 47808 | 1 | 1.1.162 60674/6 |  | Currency | 2.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.162 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814033 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1700 | 1 | 1.1.138 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.138 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814034 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 48960 | 1 | 1.1.166 60674/6 |  | Currency | 2.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.166 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814035 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 69120 | 1 | 1.1.167 60674/6 |  | Currency | 1.6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.167 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814036 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 57600 | 1 | 1.1.163 60674/6 |  | Currency | 2.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.163 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814037 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 93024 | 1 | 1.1.165 60674/6 |  | Currency | 2.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.165 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814038 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 57600 | 1 | 1.1.164 60674/6 |  | Currency | 2.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.164 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814039 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 65280 | 1 | 1.1.171 60674/6 |  | Currency | 1.6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.171 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814040 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 23616 | 1 | 1.1.169 60674/6 |  | Currency | 1.6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.169 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814041 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 84480 | 1 | 1.1.174 60674/6 |  | Currency | 3.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.174 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814042 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 40800 | 1 | 1.1.177 60674/6 |  | Currency | 2.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.177 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814043 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 57600 | 1 | 1.1.172 60674/6 |  | Currency | 1.6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.172 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814044 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 20000 | 1 | 1.1.178 60674/6 |  | Currency | 2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.178 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814045 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 46080 | 1 | 1.1.186 60674/6 |  | Currency | 4.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.186 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814047 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 53760 | 1 | 1.1.188 60674/6 |  | Currency | 6.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.188 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814048 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 23040 | 1 | 1.1.184 60674/6 |  | Currency | 2.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.184 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814049 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 18432 | 1 | 1.1.191 60674/6 |  | Currency | 4.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.191 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814050 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 23040 | 1 | 1.1.192 60674/6 |  | Currency | 2.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.192 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814051 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 15360 | 1 | 1.1.187 60674/6 |  | Currency | 2.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.187 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814052 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 23040 | 1 | 1.1.194 60674/6 |  | Currency | 2.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.194 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814053 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 76075 | 1 | 3.3 60674/6 |  | Currency | 8.95 |  | 10767 | النديم للصناعات المشربيه |  | 3.3 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814054 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 11400 | 1 | 3.4 60674/6 |  | Currency | 3 |  | 10767 | النديم للصناعات المشربيه |  | 3.4 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814055 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 11700 | 1 | 3.5 60674/6 |  | Currency | 13 |  | 10767 | النديم للصناعات المشربيه |  | 3.5 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814056 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3525 | 1 | 3.6 60674/6 |  | Currency | 1.5 |  | 10767 | النديم للصناعات المشربيه |  | 3.6 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814057 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 14250 | 1 | 3.7 60674/6 |  | Currency | 0.6 |  | 10767 | النديم للصناعات المشربيه |  | 3.7 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814058 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 12000 | 1 | 3.8 60674/6 |  | Currency | 1.2 |  | 10767 | النديم للصناعات المشربيه |  | 3.8 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814059 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 17280 | 1 | 3.9 60674/6 |  | Currency | 1.8 |  | 10767 | النديم للصناعات المشربيه |  | 3.9 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814060 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 57000 | 1 | 1.1.03 60674/6 |  | Currency | 2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.03 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814061 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 75600 | 1 | 3.1 60674/6 |  | Currency | 63 |  | 10767 | النديم للصناعات المشربيه |  | 3.1 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814062 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1278900 | 1 | 3.2 60674/6 |  | Currency | 121.8 |  | 10767 | النديم للصناعات المشربيه |  | 3.2 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814063 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 284000 | 1 | 2.7 60674/6 |  | Currency | 4 |  | 10767 | النديم للصناعات المشربيه |  | 2.7 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814064 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 77040 | 1 | 2.8 60674/6 |  | Currency | 4 |  | 10767 | النديم للصناعات المشربيه |  | 2.8 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814065 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 74200 | 1 | 2.9 60674/6 |  | Currency | 28 |  | 10767 | النديم للصناعات المشربيه |  | 2.9 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814066 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 30096 | 1 | 2.10 60674/6 |  | Currency | 1.6 |  | 10767 | النديم للصناعات المشربيه |  | 2.10 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814067 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 561450 | 1 | 2.3 60674/6 |  | Currency | 3.8 |  | 10767 | النديم للصناعات المشربيه |  | 2.3 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814068 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | -5750 | 1 | 60674/6 |  | Currency | -5750 |  | 10767 | النديم للصناعات المشربيه |  | 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814069 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -39702.41 | 1 | LABOUR_OFFICE 60674/6 |  | Currency | -39702.41 |  | 10767 | النديم للصناعات المشربيه |  | LABOUR_OFFICE 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814163 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 12390 | 1 | 1.1.01 60674/6 |  | Currency | 33.6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.01 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814164 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 33800 | 1 | 1.1.21 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.21 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814165 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 53006 | 1 | 1.1.24 60674/6 |  | Currency | 2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.24 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814166 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 12270 | 1 | 1.1.25 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.25 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814167 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 190800 | 1 | 1.1.3 60674/6 |  | Currency | 159 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.3 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814168 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 237248 | 1 | 1.1.08 60674/6 |  | Currency | 32 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.08 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814169 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9095 | 1 | 1.1.22 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.22 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814170 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 10850 | 1 | 1.1.23 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.23 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814171 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 104000 | 1 | 1.1.27 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.27 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814172 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3000 | 1 | 1.1.02 60674/6 |  | Currency | 8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.02 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814173 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 20000 | 1 | 1.1.15 60674/6 |  | Currency | 2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.15 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814174 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 106000 | 1 | 1.1.2 60674/6 |  | Currency | 4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.2 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814175 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 265000 | 1 | 1.1.8 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.8 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814176 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 22400 | 1 | 1.1.62 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.62 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814177 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 40000 | 1 | 1.1.65 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.65 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814178 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3800 | 1 | 1.1.73 60674/6 |  | Currency | 53 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.73 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814179 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 11050 | 1 | 1.1.71 60674/6 |  | Currency | 37 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.71 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814180 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 18800 | 1 | 1.1.81 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.81 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814181 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 29200 | 1 | 1.1.82 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.82 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814182 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 192000 | 1 | 1.1.61 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.61 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814183 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 128000 | 1 | 1.1.6 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.6 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814184 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 64000 | 1 | 1.1.64 60674/6 |  | Currency | 1.6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.64 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814185 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 17100 | 1 | 1.1.72 60674/6 |  | Currency | 36.5 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.72 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814186 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 12760 | 1 | 1.1.77 60674/6 |  | Currency | 57 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.77 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814187 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 23750 | 1 | 1.1.86 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.86 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814188 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 23040 | 1 | 1.1.83 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.83 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814189 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 36400 | 1 | 1.1.87 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.87 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814190 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 133000 | 1 | 1.1.88 60674/6 |  | Currency | 140 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.88 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814191 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 110000 | 1 | 1.1.94 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.94 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814192 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 42180 | 1 | 1.1.103 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.103 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814193 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 107000 | 1 | 1.1.95 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.95 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814194 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 30210 | 1 | 1.1.101 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.101 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814195 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 46740 | 1 | 1.1.104 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.104 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814196 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 228000 | 1 | 1.1.106 60674/6 |  | Currency | 5 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.106 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814197 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 81600 | 1 | 1.1.91 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.91 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814198 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 49305 | 1 | 1.1.105 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.105 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814199 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 474000 | 1 | 1.1.93 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.93 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814200 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 930050 | 1 | 1.1.96 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.96 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814201 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 34200 | 1 | 1.1.102 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.102 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814202 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 11400 | 1 | 1.1.117 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.117 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814203 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 85500 | 1 | 1.1.108 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.108 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814204 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 88920 | 1 | 1.1.109 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.109 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814205 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 66120 | 1 | 1.1.114 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.114 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814206 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 76380 | 1 | 1.1.11 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.11 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814207 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 125400 | 1 | 1.1.111 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.111 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814208 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 301600 | 1 | 1.1.12 60674/6 |  | Currency | 1.6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.12 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814209 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 51300 | 1 | 1.1.107 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.107 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814210 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 35565.6 | 1 | 1.1.122 60674/6 |  | Currency | 2.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.122 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814211 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3762 | 1 | 1.1.136 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.136 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814212 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9690 | 1 | 1.1.135 60674/6 |  | Currency | 1.6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.135 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814213 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 429300 | 1 | 1.1.119 60674/6 |  | Currency | 1.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.119 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814214 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 39000 | 1 | 1.1.145 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.145 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814215 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 45320 | 1 | 1.1.152 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.152 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814216 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 14000 | 1 | 1.1.139 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.139 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814217 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 20000 | 1 | 1.1.146 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.146 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814218 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4600 | 1 | 1.1.153 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.153 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814219 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 14000 | 1 | 1.1.154 60674/6 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.154 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814220 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 47808 | 1 | 1.1.162 60674/6 |  | Currency | 2.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.162 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814221 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1700 | 1 | 1.1.138 60674/6 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.138 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814222 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 48960 | 1 | 1.1.166 60674/6 |  | Currency | 2.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.166 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814223 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 69120 | 1 | 1.1.167 60674/6 |  | Currency | 1.6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.167 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814224 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 57600 | 1 | 1.1.163 60674/6 |  | Currency | 2.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.163 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814225 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 93024 | 1 | 1.1.165 60674/6 |  | Currency | 2.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.165 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814226 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 57600 | 1 | 1.1.164 60674/6 |  | Currency | 2.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.164 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814227 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 65280 | 1 | 1.1.171 60674/6 |  | Currency | 1.6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.171 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3842338 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 10.06. | Mat | 10 | SPECIALITIES | 78456 | 2023-02-21 | Materials |  |  |  | Materials | Alrowad Construction_OU | -40793.78 | 1 | استوريا مسك ف/3420 9/2 163 | 3420 c.m | Currency | -1364.34 | 22105940 | 1543 | مسك للاستشارات والخدمات الميكانيكية | Egypt | استوريا مسك ف/3420 9/2 163 |  | Mechanical | Received | 2023-02-21 | Accounted transaction received
3842340 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 10.06. | Mat | 10 | SPECIALITIES | 78456 | 2023-02-21 | Materials |  |  |  | Materials | Alrowad Construction_OU | 40793.78 | 1 | استوريا مسك ف/3420 9/2 163 | 3420 | Currency | 40793.78 | 22105940 | 1543 | مسك للاستشارات والخدمات الميكانيكية | Egypt | استوريا مسك ف/3420 9/2 163 |  | Mechanical | Received | 2023-02-21 | Accounted transaction received
3796548 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3300 | 1 | 1.1 61571/7 |  | Currency | 3 |  | 8598 | جرابل للتجارة والصناعه |  | 1.1 61571/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796549 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 94920 | 1 | 1.2 61571/7 |  | Currency | 67.8 |  | 8598 | جرابل للتجارة والصناعه |  | 1.2 61571/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796550 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 390 | 1 | 1.9 61571/7 |  | Currency | 0.6 |  | 8598 | جرابل للتجارة والصناعه |  | 1.9 61571/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796551 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7216.5 | 1 | 1.14 61571/7 |  | Currency | 12.75 |  | 8598 | جرابل للتجارة والصناعه |  | 1.14 61571/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796552 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 11448 | 1 | 1.23 61571/7 |  | Currency | 6 |  | 8598 | جرابل للتجارة والصناعه |  | 1.23 61571/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796553 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 69972 | 1 | 1.42 61571/7 |  | Currency | 20.58 |  | 8598 | جرابل للتجارة والصناعه |  | 1.42 61571/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796554 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 8520 | 1 | 2.2 61571/7 |  | Currency | 1.5 |  | 8598 | جرابل للتجارة والصناعه |  | 2.2 61571/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796555 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 70125 | 1 | 7.1 61571/7 |  | Currency | 12.75 |  | 8598 | جرابل للتجارة والصناعه |  | 7.1 61571/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796556 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -20000 | 1 | 12.2 61571/7 |  | Currency | -80 |  | 8598 | جرابل للتجارة والصناعه |  | 12.2 61571/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796557 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -125000 | 1 | 12.1 61571/7 |  | Currency | -500 |  | 8598 | جرابل للتجارة والصناعه |  | 12.1 61571/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796558 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -11970 | 1 | 1.25 61571/7 |  | Currency | -1.26 |  | 8598 | جرابل للتجارة والصناعه |  | 1.25 61571/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796559 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 243390 | 1 | 1.26 61571/7 |  | Currency | 25.62 |  | 8598 | جرابل للتجارة والصناعه |  | 1.26 61571/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796560 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 241170 | 1 | 1.28 61571/7 |  | Currency | 10 |  | 8598 | جرابل للتجارة والصناعه |  | 1.28 61571/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796561 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7200 | 1 | 1.29 61571/7 |  | Currency | 60 |  | 8598 | جرابل للتجارة والصناعه |  | 1.29 61571/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796562 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 10800 | 1 | 1.31 61571/7 |  | Currency | 36 |  | 8598 | جرابل للتجارة والصناعه |  | 1.31 61571/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796564 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 40000 | 1 | 11.1 61571/7 |  | Currency | 16 |  | 8598 | جرابل للتجارة والصناعه |  | 11.1 61571/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796565 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1980.75 | 1 | 14.2 61571/7 |  | Currency | 0.75 |  | 8598 | جرابل للتجارة والصناعه |  | 14.2 61571/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796566 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -45090 | 1 | 14.3 61571/7 |  | Currency | -5.01 |  | 8598 | جرابل للتجارة والصناعه |  | 14.3 61571/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796569 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -460 | 1 | 1.45 61571/7 |  | Currency | -0.23 |  | 8598 | جرابل للتجارة والصناعه |  | 1.45 61571/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796574 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 72165 | 1 | 1.22 61571/7 |  | Currency | 42.5 |  | 8598 | جرابل للتجارة والصناعه |  | 1.22 61571/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796575 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -3060.35 | 1 | LABOUR_OFFICE 61571/7 |  | Currency | -3060.35 |  | 8598 | جرابل للتجارة والصناعه |  | LABOUR_OFFICE 61571/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796603 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 107702.4 | 1 | 1.1 60898/7 |  | Currency | 1346.28 |  | 10796 | جلوبال بريما |  | 1.1 60898/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796604 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 11278.75 | 1 | 1.2 60898/7 |  | Currency | 90.23 |  | 10796 | جلوبال بريما |  | 1.2 60898/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796605 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 25111.25 | 1 | 1.3 60898/7 |  | Currency | 200.89 |  | 10796 | جلوبال بريما |  | 1.3 60898/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796606 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 6578.75 | 1 | 1.4 60898/7 |  | Currency | 52.63 |  | 10796 | جلوبال بريما |  | 1.4 60898/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796607 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 81840 | 1 | 1.5 60898/7 |  | Currency | 1023 |  | 10796 | جلوبال بريما |  | 1.5 60898/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796608 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5840 | 1 | 1.9 60898/7 |  | Currency | 73 |  | 10796 | جلوبال بريما |  | 1.9 60898/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796609 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 8125 | 1 | 1.10 60898/7 |  | Currency | 65 |  | 10796 | جلوبال بريما |  | 1.10 60898/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796610 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 12750 | 1 | 1.12 60898/7 |  | Currency | 102 |  | 10796 | جلوبال بريما |  | 1.12 60898/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796611 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5849.6 | 1 | 1.14 60898/7 |  | Currency | 73.12 |  | 10796 | جلوبال بريما |  | 1.14 60898/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796612 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 40388.4 | 1 | 2.1 60898/7 |  | Currency | 1346.28 |  | 10796 | جلوبال بريما |  | 2.1 60898/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796613 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3158.05 | 1 | 2.2 60898/7 |  | Currency | 90.23 |  | 10796 | جلوبال بريما |  | 2.2 60898/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796614 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7031.15 | 1 | 2.3 60898/7 |  | Currency | 200.89 |  | 10796 | جلوبال بريما |  | 2.3 60898/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796615 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1842.05 | 1 | 2.4 60898/7 |  | Currency | 52.63 |  | 10796 | جلوبال بريما |  | 2.4 60898/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796616 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 30690 | 1 | 2.5 60898/7 |  | Currency | 1023 |  | 10796 | جلوبال بريما |  | 2.5 60898/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796617 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2190 | 1 | 2.9 60898/7 |  | Currency | 73 |  | 10796 | جلوبال بريما |  | 2.9 60898/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796618 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2275 | 1 | 2.10 60898/7 |  | Currency | 65 |  | 10796 | جلوبال بريما |  | 2.10 60898/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796619 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3570 | 1 | 2.12 60898/7 |  | Currency | 102 |  | 10796 | جلوبال بريما |  | 2.12 60898/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796620 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2193.6 | 1 | 2.14 60898/7 |  | Currency | 73.12 |  | 10796 | جلوبال بريما |  | 2.14 60898/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796621 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1775.25 | 1 | 4.1 60898/7 |  | Currency | 39.45 |  | 10796 | جلوبال بريما |  | 4.1 60898/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796622 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1686 | 1 | 5.2 60898/7 |  | Currency | 42.15 |  | 10796 | جلوبال بريما |  | 5.2 60898/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796623 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2362.5 | 1 | 5.3 60898/7 |  | Currency | 94.5 |  | 10796 | جلوبال بريما |  | 5.3 60898/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796624 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -7062 | 1 | 5.7 60898/7 |  | Currency | -64.2 |  | 10796 | جلوبال بريما |  | 5.7 60898/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796625 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | -1500 | 1 | 60898/7 |  | Currency | -1500 |  | 10796 | جلوبال بريما |  | 60898/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3796626 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-01-31 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1607.29 | 1 | LABOUR_OFFICE 60898/7 |  | Currency | -1607.29 |  | 10796 | جلوبال بريما |  | LABOUR_OFFICE 60898/7 |  | Finacial | Received | 2023-02-05 | Accounted transaction received
3798667 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-01-31 | Hirings Payrool |  |  |  | Indirect | Alrowad Construction_OU | 1288485.2 | 1 | قيد مرتبات شهر يناير 2023 | Salary-Jan-2023 | Currency | 1288485.2 | 21955997 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر يناير 2023 |  | Finacial | Received | 2023-02-06 | Accounted transaction received
3814228 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 23616 | 1 | 1.1.169 60674/6 |  | Currency | 1.6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.169 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814229 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 84480 | 1 | 1.1.174 60674/6 |  | Currency | 3.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.174 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814230 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 40800 | 1 | 1.1.177 60674/6 |  | Currency | 2.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.177 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814231 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 57600 | 1 | 1.1.172 60674/6 |  | Currency | 1.6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.172 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814232 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 20000 | 1 | 1.1.178 60674/6 |  | Currency | 2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.178 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814233 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 46080 | 1 | 1.1.186 60674/6 |  | Currency | 4.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.186 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814235 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 53760 | 1 | 1.1.188 60674/6 |  | Currency | 6.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.188 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814236 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 23040 | 1 | 1.1.184 60674/6 |  | Currency | 2.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.184 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814237 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 18432 | 1 | 1.1.191 60674/6 |  | Currency | 4.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.191 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814238 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 23040 | 1 | 1.1.192 60674/6 |  | Currency | 2.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.192 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814239 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 15360 | 1 | 1.1.187 60674/6 |  | Currency | 2.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.187 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814240 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 23040 | 1 | 1.1.194 60674/6 |  | Currency | 2.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.194 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814241 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 76075 | 1 | 3.3 60674/6 |  | Currency | 8.95 |  | 10767 | النديم للصناعات المشربيه |  | 3.3 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814242 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 11400 | 1 | 3.4 60674/6 |  | Currency | 3 |  | 10767 | النديم للصناعات المشربيه |  | 3.4 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814243 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 11700 | 1 | 3.5 60674/6 |  | Currency | 13 |  | 10767 | النديم للصناعات المشربيه |  | 3.5 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814244 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3525 | 1 | 3.6 60674/6 |  | Currency | 1.5 |  | 10767 | النديم للصناعات المشربيه |  | 3.6 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814245 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 14250 | 1 | 3.7 60674/6 |  | Currency | 0.6 |  | 10767 | النديم للصناعات المشربيه |  | 3.7 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814246 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 12000 | 1 | 3.8 60674/6 |  | Currency | 1.2 |  | 10767 | النديم للصناعات المشربيه |  | 3.8 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814247 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 17280 | 1 | 3.9 60674/6 |  | Currency | 1.8 |  | 10767 | النديم للصناعات المشربيه |  | 3.9 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814248 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 57000 | 1 | 1.1.03 60674/6 |  | Currency | 2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.03 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814249 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 75600 | 1 | 3.1 60674/6 |  | Currency | 63 |  | 10767 | النديم للصناعات المشربيه |  | 3.1 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814250 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1278900 | 1 | 3.2 60674/6 |  | Currency | 121.8 |  | 10767 | النديم للصناعات المشربيه |  | 3.2 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814251 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 284000 | 1 | 2.7 60674/6 |  | Currency | 4 |  | 10767 | النديم للصناعات المشربيه |  | 2.7 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814252 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 77040 | 1 | 2.8 60674/6 |  | Currency | 4 |  | 10767 | النديم للصناعات المشربيه |  | 2.8 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814253 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 74200 | 1 | 2.9 60674/6 |  | Currency | 28 |  | 10767 | النديم للصناعات المشربيه |  | 2.9 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814254 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 30096 | 1 | 2.10 60674/6 |  | Currency | 1.6 |  | 10767 | النديم للصناعات المشربيه |  | 2.10 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814255 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 561450 | 1 | 2.3 60674/6 |  | Currency | 3.8 |  | 10767 | النديم للصناعات المشربيه |  | 2.3 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814256 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | -5750 | 1 | 60674/6 |  | Currency | -5750 |  | 10767 | النديم للصناعات المشربيه |  | 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3814257 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -39702.41 | 1 | LABOUR_OFFICE 60674/6 |  | Currency | -39702.41 |  | 10767 | النديم للصناعات المشربيه |  | LABOUR_OFFICE 60674/6 |  | Finacial | Received | 2023-02-09 | Accounted transaction received
3817969 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 32180 | 1 | 4.1 69063/5 |  | Currency | 80.45 |  | 11716 | بنه للديكورات والتشطيبات والتوريدات العموميه والتسويق العقارى |  | 4.1 69063/5 |  | Finacial | Received | 2023-02-12 | Accounted transaction received
3817970 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 990 | 1 | 4.2 69063/5 |  | Currency | 2.2 |  | 11716 | بنه للديكورات والتشطيبات والتوريدات العموميه والتسويق العقارى |  | 4.2 69063/5 |  | Finacial | Received | 2023-02-12 | Accounted transaction received
3817972 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2520 | 1 | 7.2 69063/5 |  | Currency | 84 |  | 11716 | بنه للديكورات والتشطيبات والتوريدات العموميه والتسويق العقارى |  | 7.2 69063/5 |  | Finacial | Received | 2023-02-12 | Accounted transaction received
3817973 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3325.74 | 1 | 7.3 69063/5 |  | Currency | 201.56 |  | 11716 | بنه للديكورات والتشطيبات والتوريدات العموميه والتسويق العقارى |  | 7.3 69063/5 |  | Finacial | Received | 2023-02-12 | Accounted transaction received
3817974 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -175.57 | 1 | LABOUR_OFFICE 69063/5 |  | Currency | -175.57 |  | 11716 | بنه للديكورات والتشطيبات والتوريدات العموميه والتسويق العقارى |  | LABOUR_OFFICE 69063/5 |  | Finacial | Received | 2023-02-12 | Accounted transaction received
3820206 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.06 | Telephones | 17 | Indirect Cost |  | 2023-02-11 | Telephones |  |  |  | Indirect | Alrowad Construction_OU | 6941.38 | 1 | استحقاق فاتورة اورنج عن ش اكتوبر22 | استحقاق فاتورة اورنج عن ش اكتوبر22 | Currency | 6941.38 | 22007703 | 2135 | اورنج مصر للاتصالات | Egypt | استحقاق فاتورة اورنج عن ش اكتوبر22 |  | Finacial | Received | 2023-02-14 | Accounted transaction received
3820248 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.06 | Telephones | 17 | Indirect Cost |  | 2023-02-11 | Telephones |  |  |  | Indirect | Alrowad Construction_OU | 6941.38 | 1 | استحاق فاتورة اورنج عن ش نوفمبر22 | استحاق فاتورة اورنج عن ش نوفمبر22 | Currency | 6941.38 | 22007703 | 2135 | اورنج مصر للاتصالات | Egypt | استحاق فاتورة اورنج عن ش نوفمبر22 |  | Finacial | Received | 2023-02-14 | Accounted transaction received
3820429 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.01 | Private Cars | 17 | Indirect Cost |  | 2023-02-12 | Insurance |  |  |  | Taxes & Insurance | Alrowad Construction_OU | 18008.75 | 1 | 5276-5264-5265-5275-5267-5271 astoria | 5276-5264-5265-5275-5267-5271 astoria | Currency | 18008.75 | 22007703 | 1623 | اورينت للتأمين التكافلي مصر | Egypt | 5276-5264-5265-5275-5267-5271 astoria |  | Finacial | Received | 2023-02-14 | Accounted transaction received
3820949 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.08 | Trafic Permission & | 17 | Indirect Cost |  | 2023-02-14 | Trafic Perm-Station Fees |  |  |  | Indirect | Alrowad Construction_OU | 95 | 1 | تسويه ك /67-68-69-78-79-80-84 - متنوعات | st-67-68-69-78-79-80-84-2-23 | Currency | 95 | 22009476 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /67-68-69-78-79-80-84 - متنوعات |  | Finacial | Received | 2023-02-14 | Accounted transaction received
3820950 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-02-14 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 300 | 1 | تسويه ك /67-68-69-78-79-80-84 - متنوعات | st-67-68-69-78-79-80-84-2-23 | Currency | 300 | 22009476 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /67-68-69-78-79-80-84 - متنوعات |  | Finacial | Received | 2023-02-14 | Accounted transaction received
3820953 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-02-14 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 14640 | 1 | تسويه ك /67-68-69-78-79-80-84 - متنوعات | st-67-68-69-78-79-80-84-2-23 | Currency | 14640 | 22009476 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /67-68-69-78-79-80-84 - متنوعات |  | Finacial | Received | 2023-02-14 | Accounted transaction received
3825079 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.10 | Printers / Photo Cop | 17 | Indirect Cost |  | 2023-02-15 | Printers/Photo Copiers |  |  |  | Indirect | Alrowad Construction_OU | 1900 | 1 | تصوير فيديو وصور بالمشاريع. | تصوير فيديو وصور بالمشاريع. | Currency | 1900 | 22077707 | 9821 | محمد عاطف عبدالعزيز موسي | rowad | تصوير فيديو وصور بالمشاريع. |  | Finacial | Received | 2023-02-16 | Accounted transaction received
3825106 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.08 | Trafic Permission & | 17 | Indirect Cost |  | 2023-02-15 | Trafic Perm-Station Fees |  |  |  | Indirect | Alrowad Construction_OU | 145 | 1 | تسويه ك /83 - سيارات | st-83-2-23 | Currency | 145 | 22077707 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /83 - سيارات |  | Finacial | Received | 2023-02-16 | Accounted transaction received
3840379 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 12 | FURNISHINGS | 12 | FURNISHINGS |  | 2023-02-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 53740.8 | 1 | UP17 جلد طبيعي خاص بالتنجيد ومقاوم للإحتكاك الجاف والرطب |  | Square Meter | 85.71 | 60153579 |  |  |  | UP17 جلد طبيعي خاص بالتنجيد ومقاوم للإحتكاك الجاف والرطب | 700020000216 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840380 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 958.74 | 1 | ماسورة 32مم UPVC سمك ثقيل قطر خارجي 32 قطر داخلي 26.6مم اللفة= 15×3 متر(اللون أبيض) |  | Meter | 45 | 60157464 |  |  |  | ماسورة 32مم UPVC سمك ثقيل قطر خارجي 32 قطر داخلي 26.6مم اللفة= 15×3 متر(اللون أبيض) | 030010000054 | MEP | Received | 2023-02-21 | Accounted transaction received
3840381 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 639.16 | 1 | ماسورة 32مم UPVC سمك ثقيل قطر خارجي 32 قطر داخلي 26.6مم اللفة= 15×3 متر(اللون أبيض) |  | Meter | 30 | 60157465 |  |  |  | ماسورة 32مم UPVC سمك ثقيل قطر خارجي 32 قطر داخلي 26.6مم اللفة= 15×3 متر(اللون أبيض) | 030010000054 | MEP | Received | 2023-02-21 | Accounted transaction received
3840382 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2017.54 | 1 | بواط 10 * 10 عالى المقاس ¾ " |  | Each | 30 | 60157466 |  |  |  | بواط 10 * 10 عالى المقاس ¾ " | 030020100105 | MEP | Received | 2023-02-21 | Accounted transaction received
3840383 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 168.15 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 50 | 60157467 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-02-21 | Accounted transaction received
3840384 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 101.74 | 1 | جلبة ماسورة 32مم UPVC (اللون أبيض) |  | Each | 25 | 60157468 |  |  |  | جلبة ماسورة 32مم UPVC (اللون أبيض) | 030010000069 | MEP | Received | 2023-02-21 | Accounted transaction received
3840385 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 101.74 | 1 | جلبة ماسورة 32مم UPVC (اللون أبيض) |  | Each | 25 | 60157469 |  |  |  | جلبة ماسورة 32مم UPVC (اللون أبيض) | 030010000069 | MEP | Received | 2023-02-21 | Accounted transaction received
3840386 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 555.51 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 2 | 60157470 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) | 030010000059 | MEP | Received | 2023-02-21 | Accounted transaction received
3840387 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 587.89 | 1 | سلك نحاس مصمت مقاس 1.5 مم اللون أسود (cu/pvc) جهد (750/450) |  | Meter | 100 | 60157471 |  |  |  | سلك نحاس مصمت مقاس 1.5 مم اللون أسود (cu/pvc) جهد (750/450) | 030030100253 | MEP | Received | 2023-02-21 | Accounted transaction received
3840388 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 325.47 | 1 | أدابتور UPVC لماسورة 32مم(اللون أبيض) |  | Each | 25 | 60157472 |  |  |  | أدابتور UPVC لماسورة 32مم(اللون أبيض) | 030010000098 | MEP | Received | 2023-02-21 | Accounted transaction received
3840389 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 325.47 | 1 | أدابتور UPVC لماسورة 32مم(اللون أبيض) |  | Each | 25 | 60157473 |  |  |  | أدابتور UPVC لماسورة 32مم(اللون أبيض) | 030010000098 | MEP | Received | 2023-02-21 | Accounted transaction received
3840390 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2291.4 | 1 | سلك نحاس مصمت مقاس 3 مم اللون أحمر (cu/pvc) جهد (750/450) |  | Meter | 200 | 60157474 |  |  |  | سلك نحاس مصمت مقاس 3 مم اللون أحمر (cu/pvc) جهد (750/450) | 030030100277 | MEP | Received | 2023-02-21 | Accounted transaction received
3840391 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 573.42 | 1 | سلك نحاس مصمت مقاس 3 مم اللون أصفر (cu/xlpe) جهد (750/450) |  | Meter | 100 | 60157475 |  |  |  | سلك نحاس مصمت مقاس 3 مم اللون أصفر (cu/xlpe) جهد (750/450) | 030030100280 | MEP | Received | 2023-02-21 | Accounted transaction received
3840392 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 661.2 | 1 | جلاند فلكسبل مقاس 16 مم |  | Each | 100 | 60157476 |  |  |  | جلاند فلكسبل مقاس 16 مم | 030010000167 | MEP | Received | 2023-02-21 | Accounted transaction received
3840393 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 399 | 1 | بواط واتر بروف بفتحات مقاس 30 × 38 × 12 سم |  | Each | 1 | 60157477 |  |  |  | بواط واتر بروف بفتحات مقاس 30 × 38 × 12 سم | 030010000185 | MEP | Received | 2023-02-21 | Accounted transaction received
3840394 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 8579.27 | 1 | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 |  | Meter | 91.5 | 60157478 |  |  |  | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 | 030020100002 | MEP | Received | 2023-02-21 | Accounted transaction received
3840395 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1105.8 | 1 | لاكور ماسورة EMT المقاس ¾ " |  | Each | 50 | 60157479 |  |  |  | لاكور ماسورة EMT المقاس ¾ " | 030020100015 | MEP | Received | 2023-02-21 | Accounted transaction received
3840396 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 902.16 | 1 | جلبة ماسورة EMT المقاس ¾ " |  | Each | 50 | 60157480 |  |  |  | جلبة ماسورة EMT المقاس ¾ " | 030020100021 | MEP | Received | 2023-02-21 | Accounted transaction received
3840397 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 125.21 | 1 | أفيز أثنين جناح لماسورة EMT المقاس ¾ " |  | Each | 50 | 60157481 |  |  |  | أفيز أثنين جناح لماسورة EMT المقاس ¾ " | 030020100033 | MEP | Received | 2023-02-21 | Accounted transaction received
3840398 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3838.08 | 1 | HDMI PRE-CONN 1M Code 572596 |  | Each | 3 | 60157482 |  |  |  | HDMI PRE-CONN 1M Code 572596 | 030060100165 | MEP | Received | 2023-02-21 | Accounted transaction received
3840399 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1100.15 | 1 | SWITCH 20AX 1 WAY 1 MOD Code 572509 |  | Each | 8 | 60157483 |  |  |  | SWITCH 20AX 1 WAY 1 MOD Code 572509 | 030060100048 | MEP | Received | 2023-02-21 | Accounted transaction received
3840400 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 687.59 | 1 | SWITCH 20AX 1 WAY 1 MOD Code 572509 |  | Each | 5 | 60157484 |  |  |  | SWITCH 20AX 1 WAY 1 MOD Code 572509 | 030060100048 | MEP | Received | 2023-02-21 | Accounted transaction received
3840401 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 61.74 | 1 | 10AX 2 WAY SWITCH 2 MOD Code 572535 |  | Each | 1 | 60157485 |  |  |  | 10AX 2 WAY SWITCH 2 MOD Code 572535 | 030060100125 | MEP | Received | 2023-02-21 | Accounted transaction received
3840402 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1852.27 | 1 | 10AX 2 WAY SWITCH 2 MOD Code 572535 |  | Each | 30 | 60157486 |  |  |  | 10AX 2 WAY SWITCH 2 MOD Code 572535 | 030060100125 | MEP | Received | 2023-02-21 | Accounted transaction received
3840403 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 65.04 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 1 | 60157487 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-02-21 | Accounted transaction received
3840404 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 89.42 | 1 | TV "F" TYPE 1 MOD Code 572663 |  | Each | 1 | 60157488 |  |  |  | TV "F" TYPE 1 MOD Code 572663 | 030060100134 | MEP | Received | 2023-02-21 | Accounted transaction received
3840405 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 864.76 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 7 | 60157489 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-02-21 | Accounted transaction received
3840406 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 126.67 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 10 | 60157490 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-02-21 | Accounted transaction received
3840407 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 88.38 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 5 | 60157491 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-02-21 | Accounted transaction received
3840408 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 176.76 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 10 | 60157492 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-02-21 | Accounted transaction received
3840409 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 176.76 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 10 | 60157493 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-02-21 | Accounted transaction received
3840410 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5880.12 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 100 | 60157494 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-02-21 | Accounted transaction received
3840411 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3747.64 | 1 | INTERNAL CONTROL UNIT FOR HOTEL BEDROOM Code 572554 |  | Each | 9 | 60157495 |  |  |  | INTERNAL CONTROL UNIT FOR HOTEL BEDROOM Code 572554 | 030060100175 | MEP | Received | 2023-02-21 | Accounted transaction received
3840412 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 416.4 | 1 | INTERNAL CONTROL UNIT FOR HOTEL BEDROOM Code 572554 |  | Each | 1 | 60157496 |  |  |  | INTERNAL CONTROL UNIT FOR HOTEL BEDROOM Code 572554 | 030060100175 | MEP | Received | 2023-02-21 | Accounted transaction received
3840413 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3274.71 | 1 | 576562 Code وش مربع فضي |  | Each | 100 | 60157497 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-02-21 | Accounted transaction received
3840414 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1065.9 | 1 | سلك نحاس مجدول مقاس 3 مم اللون أصفر × أخضر (cu/pvc) |  | Meter | 100 | 60157498 |  |  |  | سلك نحاس مجدول مقاس 3 مم اللون أصفر × أخضر (cu/pvc) | 030030101022 | MEP | Received | 2023-02-21 | Accounted transaction received
3840415 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 765.94 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) |  | Meter | 100 | 60157499 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) | 030030101026 | MEP | Received | 2023-02-21 | Accounted transaction received
3840416 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1513.43 | 1 | سلك نحاس مجدول مقاس 3 مم اللون أزرق (cu/pvc) |  | Meter | 200 | 60157500 |  |  |  | سلك نحاس مجدول مقاس 3 مم اللون أزرق (cu/pvc) | 030030101020 | MEP | Received | 2023-02-21 | Accounted transaction received
3840417 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 190.1 | 1 | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 |  | Each | 10 | 60157501 |  |  |  | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 | 150020000178 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840418 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 190.1 | 1 | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 |  | Each | 10 | 60157502 |  |  |  | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 | 150020000178 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840419 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 19.01 | 1 | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 |  | Each | 1 | 60157503 |  |  |  | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 | 150020000178 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840420 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 665.61 | 1 | mosaic adapter code 69580 |  | Each | 7 | 60157504 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-02-21 | Accounted transaction received
3840421 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 95.09 | 1 | mosaic adapter code 69580 |  | Each | 1 | 60157505 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-02-21 | Accounted transaction received
3840422 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 561.73 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 7 | 60157506 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-02-21 | Accounted transaction received
3840423 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 80.25 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 1 | 60157507 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-02-21 | Accounted transaction received
3840424 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 588.01 | 1 | Plate British standard Arteor - square - 3 modules - graphite - 575072 |  | Each | 10 | 60157508 |  |  |  | Plate British standard Arteor - square - 3 modules - graphite - 575072 | 030060100898 | MEP | Received | 2023-02-21 | Accounted transaction received
3840425 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1345.9 | 1 | 3.5mm Jack socket Arteor - preterminated - 1 module - magnesium - 572591 |  | Each | 2 | 60157509 |  |  |  | 3.5mm Jack socket Arteor - preterminated - 1 module - magnesium - 572591 | 030060100899 | MEP | Received | 2023-02-21 | Accounted transaction received
3840426 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1203.33 | 1 | Acolyte - ARB95SWBC653.027 - Rapid Ribbon 95+ - LED Strip with 9.8 W/M, 2700K, CRI/97 IP65, 24VDC, with aluminum profile and Opal diffuser |  | Each | 2.4 | 60157510 |  |  |  | Acolyte - ARB95SWBC653.027 - Rapid Ribbon 95+ - LED Strip with 9.8 W/M, 2700K, CRI/97 IP65, 24VDC, with aluminum profile and Opal diffuser | 030040700470 | MEP | Received | 2023-02-21 | Accounted transaction received
3840427 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5415.01 | 1 | Acolyte - ARB95SWBC653.027 - Rapid Ribbon 95+ - LED Strip with 9.8 W/M, 2700K, CRI/97 IP65, 24VDC, with aluminum profile and Opal diffuser |  | Each | 10.8 | 60157511 |  |  |  | Acolyte - ARB95SWBC653.027 - Rapid Ribbon 95+ - LED Strip with 9.8 W/M, 2700K, CRI/97 IP65, 24VDC, with aluminum profile and Opal diffuser | 030040700470 | MEP | Received | 2023-02-21 | Accounted transaction received
3840428 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 592.8 | 1 | لاكور بواط على فليكسبل EMT المقاس 3/4 " |  | Each | 20 | 60157512 |  |  |  | لاكور بواط على فليكسبل EMT المقاس 3/4 " | 030020100214 | MEP | Received | 2023-02-21 | Accounted transaction received
3840429 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 501.94 | 1 | SPLASH PROOF COVER Code : 617636 |  | Each | 5 | 60157513 |  |  |  | SPLASH PROOF COVER Code : 617636 | 030060100927 | MEP | Received | 2023-02-21 | Accounted transaction received
3840430 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 563.39 | 1 | 1G 20A DP SWT + NEON + E WH - 617671 |  | Each | 5 | 60157514 |  |  |  | 1G 20A DP SWT + NEON + E WH - 617671 | 030060100942 | MEP | Received | 2023-02-21 | Accounted transaction received
3840431 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 6452.4 | 1 | بكرة تيب فضي |  | Each | 129 | 60157524 |  |  |  | بكرة تيب فضي | 060019000005 | MEP | Received | 2023-02-21 | Accounted transaction received
3840432 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 391961.53 | 1 | Barcelona 1700 bathtub , Model No. BA2-N-SW-NO |  | Each | 5 | 60157525 |  |  |  | Barcelona 1700 bathtub , Model No. BA2-N-SW-NO | 060030300360 | MEP | Received | 2023-02-21 | Accounted transaction received
3840433 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 23161.95 | 1 | Kit 36 intelli-waste, with overflow function, chrome , Model No. K-36-PC |  | Each | 5 | 60157526 |  |  |  | Kit 36 intelli-waste, with overflow function, chrome , Model No. K-36-PC | 060030300361 | MEP | Received | 2023-02-21 | Accounted transaction received
3840434 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 10773 | 1 | Antislip coating to bathtub ( A Pattern ) |  | Each | 5 | 60157527 |  |  |  | Antislip coating to bathtub ( A Pattern ) | 060030300362 | MEP | Received | 2023-02-21 | Accounted transaction received
3840435 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-02-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 798 | 1 | لمبة ليد |  | Each | 20 | 60158157 |  |  |  | لمبة ليد | 030040100001 | MEP | Received | 2023-02-21 | Accounted transaction received
3840436 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-02-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 161.5 | 1 | بكرة شريط لحام |  | Each | 10 | 60158158 |  |  |  | بكرة شريط لحام | 039010000003 | MEP | Received | 2023-02-21 | Accounted transaction received
3840437 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-02-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 171 | 1 | دواية لمبة قلاووظ |  | Each | 15 | 60158159 |  |  |  | دواية لمبة قلاووظ | 039010400001 | MEP | Received | 2023-02-21 | Accounted transaction received
3840438 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 25 | 1 | مواسير UPVC قطر خارجى 25 مم ضغط 16 بار رمادى لصق |  | Meter | 1 | 60166589 |  |  |  | مواسير UPVC قطر خارجى 25 مم ضغط 16 بار رمادى لصق | 060010100003 | MEP | Received | 2023-02-21 | Accounted transaction received
3840439 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 40 | 1 | جلبه لصق UPVC مقاس 25 مم ضغط رمادى |  | Each | 4 | 60166590 |  |  |  | جلبه لصق UPVC مقاس 25 مم ضغط رمادى | 060010100455 | MEP | Received | 2023-02-21 | Accounted transaction received
3840440 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 35 | 1 | جلبه لصق UPVC مقاس 50 مم ضغط رمادى |  | Each | 2 | 60166591 |  |  |  | جلبه لصق UPVC مقاس 50 مم ضغط رمادى | 060010100458 | MEP | Received | 2023-02-21 | Accounted transaction received
3840441 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 60 | 1 | مشترك مسلوب لصق UPVC مقاس 32-25 مم ضغط رمادى |  | Each | 3 | 60166592 |  |  |  | مشترك مسلوب لصق UPVC مقاس 32-25 مم ضغط رمادى | 060010100416 | MEP | Received | 2023-02-21 | Accounted transaction received
3840442 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 40 | 1 | مشترك مسلوب لصق UPVC مقاس 50-32 مم ضغط رمادى |  | Each | 2 | 60166593 |  |  |  | مشترك مسلوب لصق UPVC مقاس 50-32 مم ضغط رمادى | 060010100422 | MEP | Received | 2023-02-21 | Accounted transaction received
3840443 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 999.78 | 1 | بكرة تيب شفاف عرض 5 سم |  | Each | 100 | 60166594 |  |  |  | بكرة تيب شفاف عرض 5 سم | 060019000041 | MEP | Received | 2023-02-21 | Accounted transaction received
3840444 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 410.4 | 1 | وردة 8 مم |  | Kilogram | 4.5 | 60166595 |  |  |  | وردة 8 مم | 200020000145 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840445 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 72 | 1 | كوع 25 مم UPVC درجه 90 |  | Each | 6 | 60166596 |  |  |  | كوع 25 مم UPVC درجه 90 | 060010100775 | MEP | Received | 2023-02-21 | Accounted transaction received
3840446 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 199.5 | 1 | سلاح كتر |  | Each | 5 | 60170630 |  |  |  | سلاح كتر | 200010000411 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840447 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2086.2 | 1 | تنر |  | Each | 30 | 60170631 |  |  |  | تنر | 060019000008 | MEP | Received | 2023-02-21 | Accounted transaction received
3840448 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 17100 | 1 | X Tile STA White |  | Ton | 1.5 | 60170632 |  |  |  | X Tile STA White | 050010000077 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840449 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 93339 | 1 | Wall covering – WC-3 – Cole & Son- The Ardmore Collection, Narina Linen 109/10049 |  | Roll | 30 | 60170633 |  |  |  | Wall covering – WC-3 – Cole & Son- The Ardmore Collection, Narina Linen 109/10049 | 050020000013 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840450 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1353.57 | 1 | بواط ثماني فتحات ¾ المقاس ¾ " |  | Each | 21 | 59966802 |  |  |  | بواط ثماني فتحات ¾ المقاس ¾ " | 030020100098 | MEP | Received | 2023-02-21 | Accounted transaction received
3840451 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 31.64 | 1 | بواط UPVC شكل U لماسورة 25مم(اللون أبيض) |  | Each | 3 | 59966803 |  |  |  | بواط UPVC شكل U لماسورة 25مم(اللون أبيض) | 030010000091 | MEP | Received | 2023-02-21 | Accounted transaction received
3840452 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1375.18 | 1 | SWITCH 20AX 1 WAY 1 MOD Code 572509 |  | Each | 10 | 59966804 |  |  |  | SWITCH 20AX 1 WAY 1 MOD Code 572509 | 030060100048 | MEP | Received | 2023-02-21 | Accounted transaction received
3840453 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 260.17 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 4 | 59966805 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-02-21 | Accounted transaction received
3840454 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 247.07 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 2 | 59966806 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-02-21 | Accounted transaction received
3840455 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 35.35 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 2 | 59966807 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-02-21 | Accounted transaction received
3840456 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 86.12 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 2 | 59966808 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-02-21 | Accounted transaction received
3840457 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 190.17 | 1 | mosaic adapter code 69580 |  | Each | 2 | 59966809 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-02-21 | Accounted transaction received
3840458 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 902.09 | 1 | Surface mounting socket P17 Pro ? IP 66/67 ? 200/250 V~ ? 63 A ? 2P+E (Legrand 555554) |  | Each | 1 | 59966810 |  |  |  | Surface mounting socket P17 Pro ? IP 66/67 ? 200/250 V~ ? 63 A ? 2P+E (Legrand 555554) | 030060300022 | MEP | Received | 2023-02-21 | Accounted transaction received
3840459 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 160.5 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 2 | 59966811 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-02-21 | Accounted transaction received
3840460 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 831.56 | 1 | SWITCH PLEXO IP 55 ? 2?WAY ? 10 AX ? 250 V~ ? FLUSH MOUNTING ? GREY Legrand 69811 |  | Each | 2 | 59966812 |  |  |  | SWITCH PLEXO IP 55 ? 2?WAY ? 10 AX ? 250 V~ ? FLUSH MOUNTING ? GREY Legrand 69811 | 030060100729 | MEP | Received | 2023-02-21 | Accounted transaction received
3840461 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1322.06 | 1 | LID & TRIM 3 COMPARTMENTS GREY ( Legrand 689631 ) |  | Each | 2 | 59966813 |  |  |  | LID & TRIM 3 COMPARTMENTS GREY ( Legrand 689631 ) | 030060100738 | MEP | Received | 2023-02-21 | Accounted transaction received
3840462 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 246.66 | 1 | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 |  | Each | 2 | 59966814 |  |  |  | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 | 030060100951 | MEP | Received | 2023-02-21 | Accounted transaction received
3840463 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 158.03 | 1 | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 |  | Each | 2 | 59966815 |  |  |  | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 | 030060100956 | MEP | Received | 2023-02-21 | Accounted transaction received
3840464 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1279.36 | 1 | HDMI PRE-CONN 1M Code 572596 |  | Each | 1 | 59971828 |  |  |  | HDMI PRE-CONN 1M Code 572596 | 030060100165 | MEP | Received | 2023-02-21 | Accounted transaction received
3840465 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1375.18 | 1 | SWITCH 20AX 1 WAY 1 MOD Code 572509 |  | Each | 10 | 59971829 |  |  |  | SWITCH 20AX 1 WAY 1 MOD Code 572509 | 030060100048 | MEP | Received | 2023-02-21 | Accounted transaction received
3840466 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 617.42 | 1 | 10AX 2 WAY SWITCH 2 MOD Code 572535 |  | Each | 10 | 59971830 |  |  |  | 10AX 2 WAY SWITCH 2 MOD Code 572535 | 030060100125 | MEP | Received | 2023-02-21 | Accounted transaction received
3840467 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2016.28 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 31 | 59971831 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-02-21 | Accounted transaction received
3840468 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 178.84 | 1 | TV "F" TYPE 1 MOD Code 572663 |  | Each | 2 | 59971832 |  |  |  | TV "F" TYPE 1 MOD Code 572663 | 030060100134 | MEP | Received | 2023-02-21 | Accounted transaction received
3840469 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 671.69 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 38 | 59971833 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-02-21 | Accounted transaction received
3840470 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 129.17 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 3 | 59971834 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-02-21 | Accounted transaction received
3840471 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 939.82 | 1 | FUSED 13A SWITCH +NEON SQ ALU Code 572651 |  | Each | 2 | 59971835 |  |  |  | FUSED 13A SWITCH +NEON SQ ALU Code 572651 | 030060100186 | MEP | Received | 2023-02-21 | Accounted transaction received
3840472 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 11600 | 1 | FLOOR BOX 12 MOD code CB3 |  | Each | 8 | 59971836 |  |  |  | FLOOR BOX 12 MOD code CB3 | 030060100533 | MEP | Received | 2023-02-21 | Accounted transaction received
3840473 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2377.18 | 1 | mosaic adapter code 69580 |  | Each | 25 | 59971837 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-02-21 | Accounted transaction received
3840474 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2648.17 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 33 | 59971838 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-02-21 | Accounted transaction received
3840475 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1505.83 | 1 | SPLASH PROOF COVER Code : 617636 |  | Each | 15 | 59971839 |  |  |  | SPLASH PROOF COVER Code : 617636 | 030060100927 | MEP | Received | 2023-02-21 | Accounted transaction received
3840476 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1690.16 | 1 | 1G 20A DP SWT + NEON + E WH - 617671 |  | Each | 15 | 59971840 |  |  |  | 1G 20A DP SWT + NEON + E WH - 617671 | 030060100942 | MEP | Received | 2023-02-21 | Accounted transaction received
3840477 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 369.98 | 1 | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 |  | Each | 3 | 59971841 |  |  |  | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 | 030060100951 | MEP | Received | 2023-02-21 | Accounted transaction received
3840478 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 113.09 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 2 | 59971842 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-02-21 | Accounted transaction received
3840479 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 79.02 | 1 | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 |  | Each | 1 | 59971843 |  |  |  | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 | 030060100956 | MEP | Received | 2023-02-21 | Accounted transaction received
3840480 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1509.13 | 1 | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 |  | Each | 2 | 59971844 |  |  |  | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 | 030060100957 | MEP | Received | 2023-02-21 | Accounted transaction received
3840481 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1175.79 | 1 | سلك نحاس مصمت مقاس 1.5 مم اللون أسود (cu/pvc) جهد (750/450) |  | Meter | 200 | 59971858 |  |  |  | سلك نحاس مصمت مقاس 1.5 مم اللون أسود (cu/pvc) جهد (750/450) | 030030100253 | MEP | Received | 2023-02-21 | Accounted transaction received
3840482 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5719.51 | 1 | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 |  | Meter | 61 | 59971859 |  |  |  | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 | 030020100002 | MEP | Received | 2023-02-21 | Accounted transaction received
3840483 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2593.5 | 1 | كورنر TDF |  | Each | 650 | 59986374 |  |  |  | كورنر TDF | 350010000035 | MEP | Received | 2023-02-21 | Accounted transaction received
3840484 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 946.02 | 1 | أنبوبة سليكون |  | Each | 22 | 59986375 |  |  |  | أنبوبة سليكون | 060019000001 | MEP | Received | 2023-02-21 | Accounted transaction received
3840485 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 68428.5 | 1 | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² |  | Kilogram | 1225 | 59986376 |  |  |  | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² | 060040200001 | MEP | Received | 2023-02-21 | Accounted transaction received
3840486 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 499.89 | 1 | كاوتشة صرف 32/50 |  | Each | 50 | 59986377 |  |  |  | كاوتشة صرف 32/50 | 060019000033 | MEP | Received | 2023-02-21 | Accounted transaction received
3840487 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1385.78 | 1 | وصلة مرنة 50 سم |  | Each | 20 | 59986378 |  |  |  | وصلة مرنة 50 سم | 060021000009 | MEP | Received | 2023-02-21 | Accounted transaction received
3840488 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2092.99 | 1 | بستلة فوستر |  | Each | 1 | 59986379 |  |  |  | بستلة فوستر | 060019000039 | MEP | Received | 2023-02-21 | Accounted transaction received
3840489 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 799.82 | 1 | بكرة تيب شفاف عرض 5 سم |  | Each | 80 | 59986380 |  |  |  | بكرة تيب شفاف عرض 5 سم | 060019000041 | MEP | Received | 2023-02-21 | Accounted transaction received
3840490 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1392.08 | 1 | Duct Gasket size 5 cm |  | Each | 24 | 59986381 |  |  |  | Duct Gasket size 5 cm | 060019000098 | MEP | Received | 2023-02-21 | Accounted transaction received
3840491 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3168.01 | 1 | Duct insulation (thikness 1" -density 24 kg/m3) |  | Each | 4 | 59986382 |  |  |  | Duct insulation (thikness 1" -density 24 kg/m3) | 060050300008 | MEP | Received | 2023-02-21 | Accounted transaction received
3840492 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-02-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 10879.98 | 1 | Hardware Accessories for Wooden Doors Concealed hinge system & Bathroom Concealed Hinges Simonswerk completely concealed hinge system with load capacity 80.0 kg two hinges per door leaf (1x2m) |  | Each | 4 | 59986521 |  |  |  | Hardware Accessories for Wooden Doors Concealed hinge system & Bathroom Concealed Hinges Simonswerk completely concealed hinge system with load capacity 80.0 kg two hinges per door leaf (1x2m) | 250010001515 | Procurement | Received | 2023-02-21 | Accounted transaction received
3842366 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-02-21 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 899.92 | 1 | استوريا الماسه ف/13208 7/2 | 13208 | Currency | 899.92 | 22105940 | 12416 | الماسه للتاجير ومعالجه المياه | rowad | استوريا الماسه ف/13208 7/2 |  | Finacial | Received | 2023-02-21 | Accounted transaction received
3843254 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1752.8 | 1 | 2.3 60898/8 |  | Currency | 50.08 |  | 10796 | جلوبال بريما |  | 2.3 60898/8 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843255 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 627.9 | 1 | 2.4 60898/8 |  | Currency | 17.94 |  | 10796 | جلوبال بريما |  | 2.4 60898/8 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843250 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2871.25 | 1 | 1.2 60898/8 |  | Currency | 22.97 |  | 10796 | جلوبال بريما |  | 1.2 60898/8 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843251 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 6260 | 1 | 1.3 60898/8 |  | Currency | 50.08 |  | 10796 | جلوبال بريما |  | 1.3 60898/8 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843252 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2242.5 | 1 | 1.4 60898/8 |  | Currency | 17.94 |  | 10796 | جلوبال بريما |  | 1.4 60898/8 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843253 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 803.95 | 1 | 2.2 60898/8 |  | Currency | 22.97 |  | 10796 | جلوبال بريما |  | 2.2 60898/8 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843256 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 591.75 | 1 | 4.1 60898/8 |  | Currency | 13.15 |  | 10796 | جلوبال بريما |  | 4.1 60898/8 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843257 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 43470 | 1 | 6.2 60898/8 |  | Currency | 1449 |  | 10796 | جلوبال بريما |  | 6.2 60898/8 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843258 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 43470 | 1 | 6.4 60898/8 |  | Currency | 1449 |  | 10796 | جلوبال بريما |  | 6.4 60898/8 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843259 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 30000 | 1 | 6.5 60898/8 |  | Currency | 1000 |  | 10796 | جلوبال بريما |  | 6.5 60898/8 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843260 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 78542.4 | 1 | 8.1 60898/8 |  | Currency | 981.78 |  | 10796 | جلوبال بريما |  | 8.1 60898/8 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843261 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 29453.4 | 1 | 8.2 60898/8 |  | Currency | 981.78 |  | 10796 | جلوبال بريما |  | 8.2 60898/8 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843262 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 70893 | 1 | 8.3 60898/8 |  | Currency | 2363.1 |  | 10796 | جلوبال بريما |  | 8.3 60898/8 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843263 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 60886.8 | 1 | 8.4 60898/8 |  | Currency | 2029.56 |  | 10796 | جلوبال بريما |  | 8.4 60898/8 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843264 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 15450 | 1 | 8.5 60898/8 |  | Currency | 515 |  | 10796 | جلوبال بريما |  | 8.5 60898/8 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843265 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 562 | 1 | 5.2 60898/8 |  | Currency | 14.05 |  | 10796 | جلوبال بريما |  | 5.2 60898/8 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843266 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 787.5 | 1 | 5.3 60898/8 |  | Currency | 31.5 |  | 10796 | جلوبال بريما |  | 5.3 60898/8 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843267 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1748.99 | 1 | LABOUR_OFFICE 60898/8 |  | Currency | -1748.99 |  | 10796 | جلوبال بريما |  | LABOUR_OFFICE 60898/8 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843285 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 67830 | 1 | 1.5 61155/6 |  | Currency | 0.7 |  | 10847 | برونكس لتشغيل المعادن |  | 1.5 61155/6 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843286 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 38760 | 1 | 1.21 61155/6 |  | Currency | 1 |  | 10847 | برونكس لتشغيل المعادن |  | 1.21 61155/6 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843287 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 22000 | 1 | 1.23 61155/6 |  | Currency | 0.4 |  | 10847 | برونكس لتشغيل المعادن |  | 1.23 61155/6 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843288 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 51660 | 1 | 1.28 61155/6 |  | Currency | 42 |  | 10847 | برونكس لتشغيل المعادن |  | 1.28 61155/6 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843289 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 11915.85 | 1 | 1.29 61155/6 |  | Currency | 28.25 |  | 10847 | برونكس لتشغيل المعادن |  | 1.29 61155/6 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843290 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 186276 | 1 | 1.68 61155/6 |  | Currency | 172 |  | 10847 | برونكس لتشغيل المعادن |  | 1.68 61155/6 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843291 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 21660 | 1 | 1.69 61155/6 |  | Currency | 5 |  | 10847 | برونكس لتشغيل المعادن |  | 1.69 61155/6 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843292 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 12996 | 1 | 1.70 61155/6 |  | Currency | 3 |  | 10847 | برونكس لتشغيل المعادن |  | 1.70 61155/6 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843293 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 177378.3 | 1 | 1.77 61155/6 |  | Currency | 92 |  | 10847 | برونكس لتشغيل المعادن |  | 1.77 61155/6 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843294 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5784.08 | 1 | 1.78 61155/6 |  | Currency | 3 |  | 10847 | برونكس لتشغيل المعادن |  | 1.78 61155/6 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843295 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 53352 | 1 | 1.79 61155/6 |  | Currency | 90 |  | 10847 | برونكس لتشغيل المعادن |  | 1.79 61155/6 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843296 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5928 | 1 | 1.80 61155/6 |  | Currency | 10 |  | 10847 | برونكس لتشغيل المعادن |  | 1.80 61155/6 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843297 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 8610 | 1 | 2.1 61155/6 |  | Currency | 7 |  | 10847 | برونكس لتشغيل المعادن |  | 2.1 61155/6 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843298 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 6500 | 1 | 2.3 61155/6 |  | Currency | 20 |  | 10847 | برونكس لتشغيل المعادن |  | 2.3 61155/6 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843299 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 88270.2 | 1 | 2.5 61155/6 |  | Currency | 267 |  | 10847 | برونكس لتشغيل المعادن |  | 2.5 61155/6 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843300 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5928 | 1 | 2.6 61155/6 |  | Currency | 10 |  | 10847 | برونكس لتشغيل المعادن |  | 2.6 61155/6 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843301 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1653 | 1 | 2.7 61155/6 |  | Currency | 5 |  | 10847 | برونكس لتشغيل المعادن |  | 2.7 61155/6 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843302 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -4959 | 1 | 1.55 61155/6 |  | Currency | 0 |  | 10847 | برونكس لتشغيل المعادن |  | 1.55 61155/6 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843303 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -2314.2 | 1 | 1.57 61155/6 |  | Currency | 0 |  | 10847 | برونكس لتشغيل المعادن |  | 1.57 61155/6 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843304 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 80028 | 1 | 1.50 61155/6 |  | Currency | 135 |  | 10847 | برونكس لتشغيل المعادن |  | 1.50 61155/6 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843305 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -3776.65 | 1 | LABOUR_OFFICE 61155/6 |  | Currency | -3776.65 |  | 10847 | برونكس لتشغيل المعادن |  | LABOUR_OFFICE 61155/6 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843326 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 27000 | 1 | 1.1 79995/1 |  | Currency | 30 |  | 1753 | سهمان (محمود عبد العاطي وشريكه |  | 1.1 79995/1 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843327 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 19440 | 1 | 1.2 79995/1 |  | Currency | 48.6 |  | 1753 | سهمان (محمود عبد العاطي وشريكه |  | 1.2 79995/1 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843328 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -208.98 | 1 | LABOUR_OFFICE 79995/1 |  | Currency | -208.98 |  | 1753 | سهمان (محمود عبد العاطي وشريكه |  | LABOUR_OFFICE 79995/1 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843362 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 4.02. | Glass Work | 4 | MASONRY WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 132000 | 1 | 1.5 70629/5 |  | Currency | 48 |  | 1108 | البركة للتوريدات العمومية والمقاولات-احم |  | 1.5 70629/5 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843363 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 4.02. | Glass Work | 4 | MASONRY WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 49985 | 1 | 2.1 70629/5 |  | Currency | 7.69 |  | 1108 | البركة للتوريدات العمومية والمقاولات-احم |  | 2.1 70629/5 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843364 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 4.02. | Glass Work | 4 | MASONRY WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 88200 | 1 | 3.1 70629/5 |  | Currency | 25.2 |  | 1108 | البركة للتوريدات العمومية والمقاولات-احم |  | 3.1 70629/5 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843365 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 4.02. | Glass Work | 4 | MASONRY WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 29175 | 1 | 4.1 70629/5 |  | Currency | 7.78 |  | 1108 | البركة للتوريدات العمومية والمقاولات-احم |  | 4.1 70629/5 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843366 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 4.02. | Glass Work | 4 | MASONRY WORK |  | 2023-02-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1347.12 | 1 | LABOUR_OFFICE 70629/5 |  | Currency | -1347.12 |  | 1108 | البركة للتوريدات العمومية والمقاولات-احم |  | LABOUR_OFFICE 70629/5 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843489 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.08 | Trafic Permission & | 17 | Indirect Cost |  | 2023-02-21 | Trafic Perm-Station Fees |  |  |  | Indirect | Alrowad Construction_OU | 350 | 1 | تسوية22/23/24-م.سيارات | st-22/23/24-2-23 | Currency | 350 | 22112677 | 2162 | Petty Cash | Mustafa Ahmed El Badawi Mohamed | تسوية22/23/24-م.سيارات |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3843762 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2611.61 | 1 | فلكسيبل معدن المقاس ¾ " |  | Meter | 105 | 60172379 |  |  |  | فلكسيبل معدن المقاس ¾ " | 030020100091 | MEP | Received | 2023-02-22 | Accounted transaction received
3843763 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 672.51 | 1 | بواط 10 * 10 عالى المقاس ¾ " |  | Each | 10 | 60172380 |  |  |  | بواط 10 * 10 عالى المقاس ¾ " | 030020100105 | MEP | Received | 2023-02-22 | Accounted transaction received
3843764 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1175.79 | 1 | سلك نحاس مصمت مقاس 1.5 مم اللون أسود (cu/pvc) جهد (750/450) |  | Meter | 200 | 60172381 |  |  |  | سلك نحاس مصمت مقاس 1.5 مم اللون أسود (cu/pvc) جهد (750/450) | 030030100253 | MEP | Received | 2023-02-22 | Accounted transaction received
3843765 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2394 | 1 | بواط واتر بروف بفتحات مقاس 30 × 38 × 12 سم |  | Each | 6 | 60172382 |  |  |  | بواط واتر بروف بفتحات مقاس 30 × 38 × 12 سم | 030010000185 | MEP | Received | 2023-02-22 | Accounted transaction received
3843766 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 684 | 1 | غطاء بواط معدن مقاس 4*4 |  | Each | 100 | 60172383 |  |  |  | غطاء بواط معدن مقاس 4*4 | 030020100129 | MEP | Received | 2023-02-22 | Accounted transaction received
3843767 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 12793.6 | 1 | HDMI PRE-CONN 1M Code 572596 |  | Each | 10 | 60172384 |  |  |  | HDMI PRE-CONN 1M Code 572596 | 030060100165 | MEP | Received | 2023-02-22 | Accounted transaction received
3843768 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 650.41 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 10 | 60172385 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-02-22 | Accounted transaction received
3843769 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 447.09 | 1 | TV "F" TYPE 1 MOD Code 572663 |  | Each | 5 | 60172386 |  |  |  | TV "F" TYPE 1 MOD Code 572663 | 030060100134 | MEP | Received | 2023-02-22 | Accounted transaction received
3843770 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 617.69 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 5 | 60172387 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-02-22 | Accounted transaction received
3843771 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 126.67 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 10 | 60172388 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-02-22 | Accounted transaction received
3843772 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 265.14 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 15 | 60172389 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-02-22 | Accounted transaction received
3843773 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 430.58 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 10 | 60172390 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-02-22 | Accounted transaction received
3843774 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 807.5 | 1 | بكرة شريط لحام |  | Each | 50 | 60172391 |  |  |  | بكرة شريط لحام | 039010000003 | MEP | Received | 2023-02-22 | Accounted transaction received
3843775 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 741 | 1 | روزتة معزولة 6مم |  | Each | 50 | 60172392 |  |  |  | روزتة معزولة 6مم | 030130800001 | MEP | Received | 2023-02-22 | Accounted transaction received
3843776 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1026 | 1 | روزتة معزولة 10مم |  | Each | 50 | 60172393 |  |  |  | روزتة معزولة 10مم | 030130800002 | MEP | Received | 2023-02-22 | Accounted transaction received
3843777 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 190.1 | 1 | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 |  | Each | 10 | 60172394 |  |  |  | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 | 150020000178 | Purchasing | Received | 2023-02-22 | Accounted transaction received
3843778 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 10090.63 | 1 | Reading lamp - Recessed down light LED 12W, IP 65, 2700K, CRI 90, Optics 30°, Aluminum with textured powder coat finish body |  | Each | 7 | 60172395 |  |  |  | Reading lamp - Recessed down light LED 12W, IP 65, 2700K, CRI 90, Optics 30°, Aluminum with textured powder coat finish body | 030040700461 | MEP | Received | 2023-02-22 | Accounted transaction received
3843779 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4713.06 | 1 | Acolyte - ARB95SWBC653.027 - Rapid Ribbon 95+ - LED Strip with 9.8 W/M, 2700K, CRI/97 IP65, 24VDC, with aluminum profile and Opal diffuser |  | Each | 9.4 | 60172396 |  |  |  | Acolyte - ARB95SWBC653.027 - Rapid Ribbon 95+ - LED Strip with 9.8 W/M, 2700K, CRI/97 IP65, 24VDC, with aluminum profile and Opal diffuser | 030040700470 | MEP | Received | 2023-02-22 | Accounted transaction received
3843780 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1233.28 | 1 | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 |  | Each | 10 | 60172397 |  |  |  | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 | 030060100951 | MEP | Received | 2023-02-22 | Accounted transaction received
3843781 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1185.25 | 1 | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 |  | Each | 15 | 60172398 |  |  |  | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 | 030060100956 | MEP | Received | 2023-02-22 | Accounted transaction received
3843782 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1533.77 | 1 | سيفتي عمال |  | Each | 5 | 60176078 |  |  |  | سيفتي عمال | 010030000002 | Safety | Received | 2023-02-22 | Accounted transaction received
3843783 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 118.19 | 1 | فيست برتقالي |  | Each | 3 | 60176079 |  |  |  | فيست برتقالي | 010020000008 | Safety | Received | 2023-02-22 | Accounted transaction received
3843784 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 205.2 | 1 | فيست ليموني |  | Each | 5 | 60176080 |  |  |  | فيست ليموني | 010020000009 | Safety | Received | 2023-02-22 | Accounted transaction received
3843785 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 501.6 | 1 | جوانتي باور جراب |  | Each | 22 | 60176081 |  |  |  | جوانتي باور جراب | 010010000009 | Safety | Received | 2023-02-22 | Accounted transaction received
3843786 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1044.65 | 1 | فلكسيبل معدن المقاس ¾ " |  | Meter | 42 | 60176190 |  |  |  | فلكسيبل معدن المقاس ¾ " | 030020100091 | MEP | Received | 2023-02-22 | Accounted transaction received
3843787 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 336.3 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 100 | 60176191 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-02-22 | Accounted transaction received
3843788 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 390.89 | 1 | أدابتور UPVC لماسورة 25مم(اللون أبيض) |  | Each | 50 | 60176192 |  |  |  | أدابتور UPVC لماسورة 25مم(اللون أبيض) | 030010000097 | MEP | Received | 2023-02-22 | Accounted transaction received
3843789 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 570 | 1 | اكستنشن 10*10 مقاس 3/4" |  | Each | 20 | 60176193 |  |  |  | اكستنشن 10*10 مقاس 3/4" | 030020100146 | MEP | Received | 2023-02-22 | Accounted transaction received
3843790 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5928 | 1 | لاكور بواط على فليكسبل EMT المقاس 3/4 " |  | Each | 200 | 60176194 |  |  |  | لاكور بواط على فليكسبل EMT المقاس 3/4 " | 030020100214 | MEP | Received | 2023-02-22 | Accounted transaction received
3844127 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-02-20 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | 18200 | 1 | 62756/4 |  | Currency | 18200 |  | 6250 | شيلد للانشاءات المتخصصه |  | 62756/4 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3844128 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-02-20 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -7200 | 1 | 1.2 62756/4 |  | Currency | 0 |  | 6250 | شيلد للانشاءات المتخصصه |  | 1.2 62756/4 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3844129 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-02-20 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5156.8 | 1 | 1.3 62756/4 |  | Currency | 23.44 |  | 6250 | شيلد للانشاءات المتخصصه |  | 1.3 62756/4 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3844130 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-02-20 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5541.8 | 1 | 1.4 62756/4 |  | Currency | 25.19 |  | 6250 | شيلد للانشاءات المتخصصه |  | 1.4 62756/4 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3844131 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-02-20 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2392 | 1 | 1.6 62756/4 |  | Currency | 23.92 |  | 6250 | شيلد للانشاءات المتخصصه |  | 1.6 62756/4 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3844132 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-02-20 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 17501 | 1 | 3.1 62756/4 |  | Currency | 94.6 |  | 6250 | شيلد للانشاءات المتخصصه |  | 3.1 62756/4 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3844133 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-02-20 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 255242 | 1 | 4.1 62756/4 |  | Currency | 392.68 |  | 6250 | شيلد للانشاءات المتخصصه |  | 4.1 62756/4 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3844134 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-02-20 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 19355.25 | 1 | 3.2 62756/4 |  | Currency | 258.07 |  | 6250 | شيلد للانشاءات المتخصصه |  | 3.2 62756/4 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3844137 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-02-20 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | -750 | 1 | 62756/4 |  | Currency | -750 |  | 6250 | شيلد للانشاءات المتخصصه |  | 62756/4 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3850422 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 9.10. | GRC | 9 | FINISHES WORK | 80045 | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -7560 | 1 | 4 Waldorf Astoria Cairo 80045/4 | 4 Waldorf Astoria Cairo 80045/4 | Currency | -7560 | 22139844 | 12187 | اركاد للترميم | rowad | 4 Waldorf Astoria Cairo 80045/4 |  | Operation M | Received | 2023-02-27 | Accounted transaction received
3844138 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-02-20 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1340.95 | 1 | LABOUR_OFFICE 62756/4 |  | Currency | -1340.95 |  | 6250 | شيلد للانشاءات المتخصصه |  | LABOUR_OFFICE 62756/4 |  | Finacial | Received | 2023-02-22 | Accounted transaction received
3846212 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-22 | Bank Fees |  |  |  | Finance cost | Alrowad Construction_OU | 18415.9 | 1 | lg BM 2/2023 astoria cairo | lg BM 2/2023 astoria cairo | Currency | 18415.9 | 22119431 | 2131 | Miscellaneous supplier | RME | lg BM 2/2023 astoria cairo |  | Finacial | Received | 2023-02-23 | Accounted transaction received
3848116 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 29550 | 1 | 2.3 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 2.3 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848110 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 59312 | 1 | 1.1.08 60674/7 |  | Currency | 8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.08 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848111 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 232000 | 1 | 1.1.05 60674/7 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.05 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848112 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 6490 | 1 | 1.1.01 60674/7 |  | Currency | 4.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.01 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848113 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 105000 | 1 | 1.1.28 60674/7 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.28 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848114 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 26000 | 1 | 1.1.27 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.27 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848115 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 216000 | 1 | 1.1.26 60674/7 |  | Currency | 8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.26 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848117 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 148400 | 1 | 2.4 60674/7 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 2.4 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848118 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 592000 | 1 | 2.5 60674/7 |  | Currency | 5 |  | 10767 | النديم للصناعات المشربيه |  | 2.5 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848119 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 48000 | 1 | 1.1.31 60674/7 |  | Currency | 8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.31 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848120 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 382500 | 1 | 1.1.85 60674/7 |  | Currency | 0.9 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.85 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848121 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 360000 | 1 | 1.1.63 60674/7 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.63 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848122 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 209000 | 1 | 1.1.84 60674/7 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.84 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848123 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9100 | 1 | 1.1.87 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.87 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848124 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 490000 | 1 | 1.1.99 60674/7 |  | Currency | 28 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.99 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848125 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 760950 | 1 | 1.1.97 60674/7 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.97 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848126 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 180000 | 1 | 1.1.92 60674/7 |  | Currency | 0.9 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.92 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848127 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 56430 | 1 | 1.1.115 60674/7 |  | Currency | 0.9 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.115 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848128 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 20400 | 1 | 1.1.91 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.91 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848129 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -10600 | 1 | 2.9 60674/7 |  | Currency | -4 |  | 10767 | النديم للصناعات المشربيه |  | 2.9 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848130 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 418600 | 1 | 1.1.118 60674/7 |  | Currency | 2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.118 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848131 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 377000 | 1 | 1.1.12 60674/7 |  | Currency | 2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.12 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848132 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 17782.8 | 1 | 1.1.122 60674/7 |  | Currency | 1.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.122 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848133 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3762 | 1 | 1.1.136 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.136 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848134 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9690 | 1 | 1.1.135 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.135 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848135 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 22000 | 1 | 1.1.141 60674/7 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.141 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848136 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9750 | 1 | 1.1.145 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.145 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848137 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5000 | 1 | 1.1.146 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.146 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848138 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1700 | 1 | 1.1.138 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.138 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848139 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 11330 | 1 | 1.1.152 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.152 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848140 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 34485 | 1 | 1.1.151 60674/7 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.151 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848141 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 91450 | 1 | 1.1.147 60674/7 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.147 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848142 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 122892 | 1 | 1.1.149 60674/7 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.149 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848143 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 102350 | 1 | 1.1.148 60674/7 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.148 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848144 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 18810 | 1 | 2.10 60674/7 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 2.10 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848145 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 35328 | 1 | 1.1.16 60674/7 |  | Currency | 3.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.16 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848146 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 8160 | 1 | 1.1.166 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.166 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848147 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 236160 | 1 | 1.1.155 60674/7 |  | Currency | 6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.155 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848148 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 17280 | 1 | 1.1.167 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.167 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848149 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 24288 | 1 | 1.1.159 60674/7 |  | Currency | 2.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.159 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848150 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7968 | 1 | 1.1.162 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.162 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848151 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9600 | 1 | 1.1.163 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.163 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848152 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 15504 | 1 | 1.1.165 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.165 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848153 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 153600 | 1 | 1.1.156 60674/7 |  | Currency | 3.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.156 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848154 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9600 | 1 | 1.1.164 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.164 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848155 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9792 | 1 | 1.1.157 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.157 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848156 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7872 | 1 | 1.1.161 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.161 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848157 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 52992 | 1 | 1.1.158 60674/7 |  | Currency | 4.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.158 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848158 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 8112 | 1 | 1.1.17 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.17 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848159 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 8160 | 1 | 1.1.168 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.168 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848160 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 10560 | 1 | 1.1.174 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.174 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848161 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 80640 | 1 | 1.1.179 60674/7 |  | Currency | 8.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.179 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848162 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1488 | 1 | 1.1.18 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.18 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848163 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 14400 | 1 | 1.1.172 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.172 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848164 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2208 | 1 | 1.1.175 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.175 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848165 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 36096 | 1 | 1.1.181 60674/7 |  | Currency | 9.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.181 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848166 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 16320 | 1 | 1.1.171 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.171 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848167 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5904 | 1 | 1.1.169 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.169 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848168 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3744 | 1 | 1.1.173 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.173 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848169 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7680 | 1 | 1.1.186 60674/7 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.186 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848170 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 232200 | 1 | 1.1.197 60674/7 |  | Currency | 6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.197 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848171 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 24552 | 1 | 1.1.182 60674/7 |  | Currency | 6.6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.182 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848172 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 80640 | 1 | 1.1.196 60674/7 |  | Currency | 4.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.196 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848173 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 11520 | 1 | 1.1.188 60674/7 |  | Currency | 1.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.188 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848174 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3840 | 1 | 1.1.189 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.189 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848175 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3840 | 1 | 1.1.184 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.184 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848176 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 768 | 1 | 1.1.185 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.185 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848177 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7680 | 1 | 1.1.183 60674/7 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.183 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848178 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3840 | 1 | 1.1.187 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.187 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848179 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5760 | 1 | 1.1.194 60674/7 |  | Currency | 0.6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.194 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848180 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9500 | 1 | 3.7 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 3.7 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848181 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4000 | 1 | 3.8 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 3.8 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848182 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1920 | 1 | 3.9 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 3.9 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848184 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 24000 | 1 | 1.1.142 60674/7 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.142 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848185 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 29000 | 1 | 1.1.143 60674/7 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.143 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848186 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 276000 | 1 | 1.1.144 60674/7 |  | Currency | 46 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.144 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848187 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 24000 | 1 | 1.1.14 60674/7 |  | Currency | 1.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.14 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848188 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -30121.42 | 1 | LABOUR_OFFICE 60674/7 |  | Currency | -30121.42 |  | 10767 | النديم للصناعات المشربيه |  | LABOUR_OFFICE 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848267 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 59312 | 1 | 1.1.08 60674/7 |  | Currency | 8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.08 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848268 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 232000 | 1 | 1.1.05 60674/7 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.05 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848269 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 6490 | 1 | 1.1.01 60674/7 |  | Currency | 4.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.01 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848270 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 105000 | 1 | 1.1.28 60674/7 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.28 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848271 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 26000 | 1 | 1.1.27 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.27 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848272 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 216000 | 1 | 1.1.26 60674/7 |  | Currency | 8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.26 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848273 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 29550 | 1 | 2.3 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 2.3 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848274 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 148400 | 1 | 2.4 60674/7 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 2.4 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848275 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 592000 | 1 | 2.5 60674/7 |  | Currency | 5 |  | 10767 | النديم للصناعات المشربيه |  | 2.5 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848276 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 48000 | 1 | 1.1.31 60674/7 |  | Currency | 8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.31 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848277 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 382500 | 1 | 1.1.85 60674/7 |  | Currency | 0.9 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.85 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848278 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 360000 | 1 | 1.1.63 60674/7 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.63 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848279 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 209000 | 1 | 1.1.84 60674/7 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.84 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848280 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9100 | 1 | 1.1.87 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.87 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848281 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 490000 | 1 | 1.1.99 60674/7 |  | Currency | 28 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.99 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848282 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 760950 | 1 | 1.1.97 60674/7 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.97 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848283 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 180000 | 1 | 1.1.92 60674/7 |  | Currency | 0.9 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.92 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848284 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 56430 | 1 | 1.1.115 60674/7 |  | Currency | 0.9 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.115 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848285 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 20400 | 1 | 1.1.91 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.91 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848286 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -10600 | 1 | 2.9 60674/7 |  | Currency | -4 |  | 10767 | النديم للصناعات المشربيه |  | 2.9 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848287 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 418600 | 1 | 1.1.118 60674/7 |  | Currency | 2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.118 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848288 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 377000 | 1 | 1.1.12 60674/7 |  | Currency | 2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.12 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848289 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 17782.8 | 1 | 1.1.122 60674/7 |  | Currency | 1.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.122 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848290 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3762 | 1 | 1.1.136 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.136 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848291 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9690 | 1 | 1.1.135 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.135 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848292 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 22000 | 1 | 1.1.141 60674/7 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.141 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848293 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9750 | 1 | 1.1.145 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.145 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848294 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5000 | 1 | 1.1.146 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.146 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848295 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1700 | 1 | 1.1.138 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.138 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848296 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 11330 | 1 | 1.1.152 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.152 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848297 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 34485 | 1 | 1.1.151 60674/7 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.151 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848298 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 91450 | 1 | 1.1.147 60674/7 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.147 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848299 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 122892 | 1 | 1.1.149 60674/7 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.149 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848300 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 102350 | 1 | 1.1.148 60674/7 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.148 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848301 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 18810 | 1 | 2.10 60674/7 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 2.10 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848302 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 35328 | 1 | 1.1.16 60674/7 |  | Currency | 3.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.16 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848303 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 8160 | 1 | 1.1.166 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.166 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848304 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 236160 | 1 | 1.1.155 60674/7 |  | Currency | 6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.155 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848305 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 17280 | 1 | 1.1.167 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.167 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848306 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 24288 | 1 | 1.1.159 60674/7 |  | Currency | 2.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.159 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848307 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7968 | 1 | 1.1.162 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.162 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848308 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9600 | 1 | 1.1.163 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.163 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848309 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 15504 | 1 | 1.1.165 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.165 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848310 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 153600 | 1 | 1.1.156 60674/7 |  | Currency | 3.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.156 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848311 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9600 | 1 | 1.1.164 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.164 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848312 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9792 | 1 | 1.1.157 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.157 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848313 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7872 | 1 | 1.1.161 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.161 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848314 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 52992 | 1 | 1.1.158 60674/7 |  | Currency | 4.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.158 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848315 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 8112 | 1 | 1.1.17 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.17 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848316 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 8160 | 1 | 1.1.168 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.168 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848317 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 10560 | 1 | 1.1.174 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.174 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848318 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 80640 | 1 | 1.1.179 60674/7 |  | Currency | 8.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.179 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848319 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1488 | 1 | 1.1.18 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.18 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848320 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 14400 | 1 | 1.1.172 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.172 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848321 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2208 | 1 | 1.1.175 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.175 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848322 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 36096 | 1 | 1.1.181 60674/7 |  | Currency | 9.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.181 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848323 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 16320 | 1 | 1.1.171 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.171 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848324 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5904 | 1 | 1.1.169 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.169 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848325 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3744 | 1 | 1.1.173 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.173 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848326 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7680 | 1 | 1.1.186 60674/7 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.186 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848327 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 232200 | 1 | 1.1.197 60674/7 |  | Currency | 6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.197 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848328 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 24552 | 1 | 1.1.182 60674/7 |  | Currency | 6.6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.182 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848329 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 80640 | 1 | 1.1.196 60674/7 |  | Currency | 4.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.196 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848330 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 11520 | 1 | 1.1.188 60674/7 |  | Currency | 1.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.188 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848331 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3840 | 1 | 1.1.189 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.189 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848332 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3840 | 1 | 1.1.184 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.184 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848333 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 768 | 1 | 1.1.185 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.185 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848334 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7680 | 1 | 1.1.183 60674/7 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.183 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848335 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3840 | 1 | 1.1.187 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.187 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848336 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5760 | 1 | 1.1.194 60674/7 |  | Currency | 0.6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.194 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848337 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9500 | 1 | 3.7 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 3.7 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848338 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4000 | 1 | 3.8 60674/7 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 3.8 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848339 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1920 | 1 | 3.9 60674/7 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 3.9 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848341 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 24000 | 1 | 1.1.142 60674/7 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.142 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848342 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 29000 | 1 | 1.1.143 60674/7 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.143 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848343 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 276000 | 1 | 1.1.144 60674/7 |  | Currency | 46 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.144 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848344 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 24000 | 1 | 1.1.14 60674/7 |  | Currency | 1.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.14 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848345 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -30121.42 | 1 | LABOUR_OFFICE 60674/7 |  | Currency | -30121.42 |  | 10767 | النديم للصناعات المشربيه |  | LABOUR_OFFICE 60674/7 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848752 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.08.00 | Gypsum Board(G) | 9 | FINISHES WORK |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7560 | 1 | 5.1 80045/4 |  | Currency | 0 |  | 12187 | اركاد للترميم |  | 5.1 80045/4 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848706 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 12415.6 | 1 | 1.1 80733/1 |  | Currency | 620.78 |  | 6238 | محمد بسطاوي حامد سعيد-ذاتى |  | 1.1 80733/1 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848750 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.08.00 | Gypsum Board(G) | 9 | FINISHES WORK |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 54000 | 1 | 5.1 80045/4 |  | Currency | 1 |  | 12187 | اركاد للترميم |  | 5.1 80045/4 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3848751 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.08.00 | Gypsum Board(G) | 9 | FINISHES WORK |  | 2023-02-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -243 | 1 | LABOUR_OFFICE 80045/4 |  | Currency | -243 |  | 12187 | اركاد للترميم |  | LABOUR_OFFICE 80045/4 |  | Finacial | Received | 2023-02-26 | Accounted transaction received
3850340 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-02-01 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | -206435 | 1 | يوميات عماله الفتره 2 ش 1 التقديري | يوميات عماله الفتره 2 ش 1 التقديري | Currency | -206435 | 22139844 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 2 ش 1 التقديري |  | Finacial | Received | 2023-02-27 | Accounted transaction received
3891060 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 10.06. | Mat | 10 | SPECIALITIES | 78179 | 2023-02-27 | Materials |  |  |  | Materials | Alrowad Construction_OU | -3135 | 1 | استوريا الندى ف/6705 12/1 150 | 6705 | Currency | -3135 | 22189190 | 3379 | الندى للتكييف والصناعات الهندسيه | Rowad | استوريا الندى ف/6705 12/1 150 |  | Mechanical | Received | 2023-02-27 | Accounted transaction received
3893540 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.08 | Electrical Expenses | 17 | Indirect Cost |  | 2023-02-28 | Electrical Expenses |  |  |  | Indirect | Alrowad Construction_OU | 1350.92 | 1 | تسويه ك /85-88-93-94-97-100-101-102-103-104-105-106- متنوعات | st-85-88-93-94-97-100-101-102-103-104-105-106-2-23 | Currency | 1350.92 | 22192950 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /85-88-93-94-97-100-101-102-103-104-105-106- متنوعات |  | Finacial | Received | 2023-02-28 | Accounted transaction received
3893541 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-02-28 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 2575.45 | 1 | تسويه ك /85-88-93-94-97-100-101-102-103-104-105-106- متنوعات | st-85-88-93-94-97-100-101-102-103-104-105-106-2-23 | Currency | 2575.45 | 22192950 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /85-88-93-94-97-100-101-102-103-104-105-106- متنوعات |  | Finacial | Received | 2023-02-28 | Accounted transaction received
3893542 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2023-02-28 | Stationary |  |  |  | Office and Site expenses | Alrowad Construction_OU | 675 | 1 | تسويه ك /85-88-93-94-97-100-101-102-103-104-105-106- متنوعات | st-85-88-93-94-97-100-101-102-103-104-105-106-2-23 | Currency | 675 | 22192950 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /85-88-93-94-97-100-101-102-103-104-105-106- متنوعات |  | Finacial | Received | 2023-02-28 | Accounted transaction received
3893543 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-02-28 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 8344 | 1 | تسويه ك /85-88-93-94-97-100-101-102-103-104-105-106- متنوعات | st-85-88-93-94-97-100-101-102-103-104-105-106-2-23 | Currency | 8344 | 22192950 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /85-88-93-94-97-100-101-102-103-104-105-106- متنوعات |  | Finacial | Received | 2023-02-28 | Accounted transaction received
3896985 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-28 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1596 | 1 | كورنر TDF |  | Each | 400 | 60434191 |  |  |  | كورنر TDF | 350010000035 | MEP | Received | 2023-02-28 | Accounted transaction received
3896986 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-28 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 51111.9 | 1 | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² |  | Kilogram | 915 | 60434192 |  |  |  | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² | 060040200001 | MEP | Received | 2023-02-28 | Accounted transaction received
3896987 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 15.96 | 1 | شربون صاروخ 9 بوصة |  | Each | 2 | 60178637 |  |  |  | شربون صاروخ 9 بوصة | 330040000111 | Equipment | Received | 2023-02-28 | Accounted transaction received
3896988 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 17.1 | 1 | رولمان بلى 6300 |  | Set | 1 | 60178638 |  |  |  | رولمان بلى 6300 | 330020000148 | Equipment | Received | 2023-02-28 | Accounted transaction received
3896989 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-02-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 57 | 1 | مفتاح تشغيل صاروخ بولت 9 بوصه |  | Each | 1 | 60178639 |  |  |  | مفتاح تشغيل صاروخ بولت 9 بوصه | 330040002846 | Equipment | Received | 2023-02-28 | Accounted transaction received
3896990 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-02-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4250.72 | 1 | Wall Paper WC-6 Monsoon Fact -75300-75310 textured wit geometric pattern in dark blue color Solid vinyl weight to be minimum of 480gr /sqm |  | Roll | 1 | 60225722 |  |  |  | Wall Paper WC-6 Monsoon Fact -75300-75310 textured wit geometric pattern in dark blue color Solid vinyl weight to be minimum of 480gr /sqm | 050020000016 | Purchasing | Received | 2023-02-28 | Accounted transaction received
3896991 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 233.7 | 1 | تيب مسلح |  | Each | 5 | 60226514 |  |  |  | تيب مسلح | 200010000382 | Purchasing | Received | 2023-02-28 | Accounted transaction received
3896992 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 256.5 | 1 | قلم ماركر احمر |  | Each | 5 | 60226515 |  |  |  | قلم ماركر احمر | 200010000918 | Purchasing | Received | 2023-02-28 | Accounted transaction received
3896993 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1567.5 | 1 | شيكارة بلاستيك فارغة |  | Each | 500 | 60226516 |  |  |  | شيكارة بلاستيك فارغة | 200010000115 | Purchasing | Received | 2023-02-28 | Accounted transaction received
3896994 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 171 | 1 | اسبراي الوان |  | Each | 3 | 60226517 |  |  |  | اسبراي الوان | 200010001522 | Purchasing | Received | 2023-02-28 | Accounted transaction received
3896995 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 798 | 1 | كرتونة مقاس 35 * 35 * 75 |  | Each | 10 | 60226518 |  |  |  | كرتونة مقاس 35 * 35 * 75 | 910010000557 | Administration | Received | 2023-02-28 | Accounted transaction received
3896996 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2558.72 | 1 | HDMI PRE-CONN 1M Code 572596 |  | Each | 2 | 60307383 |  |  |  | HDMI PRE-CONN 1M Code 572596 | 030060100165 | MEP | Received | 2023-02-28 | Accounted transaction received
3896997 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 12793.6 | 1 | HDMI PRE-CONN 1M Code 572596 |  | Each | 10 | 60307384 |  |  |  | HDMI PRE-CONN 1M Code 572596 | 030060100165 | MEP | Received | 2023-02-28 | Accounted transaction received
3896998 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1237.66 | 1 | SWITCH 20AX 1 WAY 1 MOD Code 572509 |  | Each | 9 | 60307385 |  |  |  | SWITCH 20AX 1 WAY 1 MOD Code 572509 | 030060100048 | MEP | Received | 2023-02-28 | Accounted transaction received
3896999 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 550.07 | 1 | SWITCH 20AX 1 WAY 1 MOD Code 572509 |  | Each | 4 | 60307386 |  |  |  | SWITCH 20AX 1 WAY 1 MOD Code 572509 | 030060100048 | MEP | Received | 2023-02-28 | Accounted transaction received
3897000 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 308.71 | 1 | 10AX 2 WAY SWITCH 2 MOD Code 572535 |  | Each | 5 | 60307387 |  |  |  | 10AX 2 WAY SWITCH 2 MOD Code 572535 | 030060100125 | MEP | Received | 2023-02-28 | Accounted transaction received
3897001 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2991.9 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 46 | 60307388 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-02-28 | Accounted transaction received
3897002 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 585.37 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 9 | 60307389 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-02-28 | Accounted transaction received
3897003 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 195.12 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 3 | 60307390 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-02-28 | Accounted transaction received
3897004 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 325.21 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 5 | 60307391 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-02-28 | Accounted transaction received
3897005 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 260.17 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 4 | 60307392 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-02-28 | Accounted transaction received
3897006 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2964.89 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 24 | 60307393 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-02-28 | Accounted transaction received
3897007 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 494.15 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 4 | 60307394 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-02-28 | Accounted transaction received
3897008 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 988.3 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 8 | 60307395 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-02-28 | Accounted transaction received
3897009 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 63.33 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 5 | 60307396 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-02-28 | Accounted transaction received
3897010 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 101.33 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 8 | 60307397 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-02-28 | Accounted transaction received
3897011 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 86.12 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 2 | 60307398 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-02-28 | Accounted transaction received
3897012 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3364.71 | 1 | CARRIER PLATE SYNERGY code 730094 |  | Each | 50 | 60307399 |  |  |  | CARRIER PLATE SYNERGY code 730094 | 030060100534 | MEP | Received | 2023-02-28 | Accounted transaction received
3897013 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 394.12 | 1 | Wiring Devices (54000) METAL FLUSH-MOUNTING BOX FOR INSTALLATION IN CONCRETE FLOOR - 3 MODULES |  | Each | 4 | 60307400 |  |  |  | Wiring Devices (54000) METAL FLUSH-MOUNTING BOX FOR INSTALLATION IN CONCRETE FLOOR - 3 MODULES | 030060100618 | MEP | Received | 2023-02-28 | Accounted transaction received
3897014 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 379.98 | 1 | SOCKET ARTEOR - GERMAN - 16 A - 2P+E SHUTTERED - 2 MODULES - ORANGE-code 572460 |  | Each | 4 | 60307401 |  |  |  | SOCKET ARTEOR - GERMAN - 16 A - 2P+E SHUTTERED - 2 MODULES - ORANGE-code 572460 | 030060100673 | MEP | Received | 2023-02-28 | Accounted transaction received
3897015 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 796.07 | 1 | LID & TRIM 3 COMPARTMENTS GREY ( Legrand 689631 ) |  | Each | 1 | 60307402 |  |  |  | LID & TRIM 3 COMPARTMENTS GREY ( Legrand 689631 ) | 030060100738 | MEP | Received | 2023-02-28 | Accounted transaction received
3897016 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1592.14 | 1 | LID & TRIM 3 COMPARTMENTS GREY ( Legrand 689631 ) |  | Each | 2 | 60307403 |  |  |  | LID & TRIM 3 COMPARTMENTS GREY ( Legrand 689631 ) | 030060100738 | MEP | Received | 2023-02-28 | Accounted transaction received
3897017 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5226.93 | 1 | BACKBOX FOR 3 COMPARTMENTS LI ( Legrand 689634 ) |  | Each | 2 | 60307404 |  |  |  | BACKBOX FOR 3 COMPARTMENTS LI ( Legrand 689634 ) | 030060100739 | MEP | Received | 2023-02-28 | Accounted transaction received
3897018 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1168.64 | 1 | FRAME 8 MOD MOSAIC ( Legrand 689658 ) |  | Each | 6 | 60307405 |  |  |  | FRAME 8 MOD MOSAIC ( Legrand 689658 ) | 030060100740 | MEP | Received | 2023-02-28 | Accounted transaction received
3897019 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1168.64 | 1 | FRAME 8 MOD MOSAIC ( Legrand 689658 ) |  | Each | 6 | 60307406 |  |  |  | FRAME 8 MOD MOSAIC ( Legrand 689658 ) | 030060100740 | MEP | Received | 2023-02-28 | Accounted transaction received
3897020 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 501.05 | 1 | WA PLATE 77MM 2X2MOD MOSAIC ( Legrand 689673 ) |  | Each | 4 | 60307407 |  |  |  | WA PLATE 77MM 2X2MOD MOSAIC ( Legrand 689673 ) | 030060100741 | MEP | Received | 2023-02-28 | Accounted transaction received
3897021 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 751.58 | 1 | WA PLATE 77MM 2X2MOD MOSAIC ( Legrand 689673 ) |  | Each | 6 | 60307408 |  |  |  | WA PLATE 77MM 2X2MOD MOSAIC ( Legrand 689673 ) | 030060100741 | MEP | Received | 2023-02-28 | Accounted transaction received
3897022 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1176.02 | 1 | Plate British standard Arteor - square - 3 modules - graphite - 575072 |  | Each | 20 | 60307409 |  |  |  | Plate British standard Arteor - square - 3 modules - graphite - 575072 | 030060100898 | MEP | Received | 2023-02-28 | Accounted transaction received
3897023 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 501.06 | 1 | Plate Arteor -British standard - square - 1 module – graphite - 575122 |  | Each | 6 | 60307410 |  |  |  | Plate Arteor -British standard - square - 1 module – graphite - 575122 | 030060100901 | MEP | Received | 2023-02-28 | Accounted transaction received
3897024 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2052 | 1 | Micro Switch Hafele/ Marckophon - 820.22.110/4321 - Switches 230 VDoor contact switches - Built-in switch |  | Each | 2 | 60307411 |  |  |  | Micro Switch Hafele/ Marckophon - 820.22.110/4321 - Switches 230 VDoor contact switches - Built-in switch | 030060200070 | MEP | Received | 2023-02-28 | Accounted transaction received
3897025 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1509.13 | 1 | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 |  | Each | 2 | 60307412 |  |  |  | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 | 030060100957 | MEP | Received | 2023-02-28 | Accounted transaction received
3897026 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1509.13 | 1 | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 |  | Each | 2 | 60307413 |  |  |  | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 | 030060100957 | MEP | Received | 2023-02-28 | Accounted transaction received
3897027 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 754.57 | 1 | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 |  | Each | 1 | 60307414 |  |  |  | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 | 030060100957 | MEP | Received | 2023-02-28 | Accounted transaction received
3897028 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1509.13 | 1 | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 |  | Each | 2 | 60307415 |  |  |  | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 | 030060100957 | MEP | Received | 2023-02-28 | Accounted transaction received
3897029 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1197 | 1 | ماسورة 25مم UPVC قطر خارجي 25 قطر داخلي 22مم اللفة= 20×3 متر(اللون رمادى) |  | Meter | 120 | 60309135 |  |  |  | ماسورة 25مم UPVC قطر خارجي 25 قطر داخلي 22مم اللفة= 20×3 متر(اللون رمادى) | 030010000034 | MEP | Received | 2023-02-28 | Accounted transaction received
3897030 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2188.78 | 1 | فلكسيبل معدن المقاس ¾ " |  | Meter | 88 | 60309136 |  |  |  | فلكسيبل معدن المقاس ¾ " | 030020100091 | MEP | Received | 2023-02-28 | Accounted transaction received
3897031 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 555.51 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 2 | 60309137 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) | 030010000059 | MEP | Received | 2023-02-28 | Accounted transaction received
3897032 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 8841.49 | 1 | سلك نحاس مصمت مقاس 1.5 مم اللون أسود (cu/pvc) جهد (750/450) |  | Meter | 900 | 60309138 |  |  |  | سلك نحاس مصمت مقاس 1.5 مم اللون أسود (cu/pvc) جهد (750/450) | 030030100253 | MEP | Received | 2023-02-28 | Accounted transaction received
3897033 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 687.59 | 1 | SWITCH 20AX 1 WAY 1 MOD Code 572509 |  | Each | 5 | 60309139 |  |  |  | SWITCH 20AX 1 WAY 1 MOD Code 572509 | 030060100048 | MEP | Received | 2023-02-28 | Accounted transaction received
3897034 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 325.21 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 5 | 60309140 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-02-28 | Accounted transaction received
3897035 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 63.33 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 5 | 60309141 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-02-28 | Accounted transaction received
3897036 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3050.24 | 1 | سلك نحاس مجدول مقاس4 مم اللون أحمر (cu/pvc) |  | Meter | 300 | 60309142 |  |  |  | سلك نحاس مجدول مقاس4 مم اللون أحمر (cu/pvc) | 030030101023 | MEP | Received | 2023-02-28 | Accounted transaction received
3897037 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3333.75 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أصفر (cu/pvc) |  | Meter | 400 | 60309143 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أصفر (cu/pvc) | 030030101024 | MEP | Received | 2023-02-28 | Accounted transaction received
3897038 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 6893.45 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) |  | Meter | 900 | 60309144 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) | 030030101026 | MEP | Received | 2023-02-28 | Accounted transaction received
3897039 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1531.88 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) |  | Meter | 200 | 60309145 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) | 030030101026 | MEP | Received | 2023-02-28 | Accounted transaction received
3897040 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4055.58 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أصفر × أخضر (cu/pvc) |  | Meter | 500 | 60309146 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أصفر × أخضر (cu/pvc) | 030030101027 | MEP | Received | 2023-02-28 | Accounted transaction received
3897041 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 756.71 | 1 | سلك نحاس مجدول مقاس 3 مم اللون أزرق (cu/pvc) |  | Meter | 100 | 60309147 |  |  |  | سلك نحاس مجدول مقاس 3 مم اللون أزرق (cu/pvc) | 030030101020 | MEP | Received | 2023-02-28 | Accounted transaction received
3897042 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2247.09 | 1 | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 |  | Each | 5 | 60309148 |  |  |  | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 | 030060100572 | MEP | Received | 2023-02-28 | Accounted transaction received
3897043 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 57596.02 | 1 | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser |  | Each | 150 | 60309149 |  |  |  | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser | 030040700472 | MEP | Received | 2023-02-28 | Accounted transaction received
3897044 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3772.83 | 1 | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 |  | Each | 5 | 60309150 |  |  |  | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 | 030060100957 | MEP | Received | 2023-02-28 | Accounted transaction received
3897045 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3772.83 | 1 | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 |  | Each | 5 | 60309151 |  |  |  | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 | 030060100957 | MEP | Received | 2023-02-28 | Accounted transaction received
3897046 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-02-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 124452 | 1 | Wall covering – WC-3 – Cole & Son- The Ardmore Collection, Narina Linen 109/10049 |  | Roll | 40 | 60309403 |  |  |  | Wall covering – WC-3 – Cole & Son- The Ardmore Collection, Narina Linen 109/10049 | 050020000013 | Purchasing | Received | 2023-02-28 | Accounted transaction received
3897047 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.06.00 | Hashma & Stone Cladd | 9 | FINISHES WORK |  | 2023-02-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4136.83 | 1 | Black Lava Washed River Pebbles size 4-5 cm |  | Square Meter | 14 | 60311941 |  |  |  | Black Lava Washed River Pebbles size 4-5 cm | 140010000084 | Purchasing | Received | 2023-02-28 | Accounted transaction received
3897048 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.06.00 | Hashma & Stone Cladd | 9 | FINISHES WORK |  | 2023-02-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 73359 | 1 | Beige Washed River Pebbles size 4-5 cm |  | Square Meter | 137.5 | 60311942 |  |  |  | Beige Washed River Pebbles size 4-5 cm | 140010000085 | Purchasing | Received | 2023-02-28 | Accounted transaction received
3897049 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 767.45 | 1 | ماسورة 20مم UPVC سمك ثقيل قطر خارجي 20 قطر داخلي 15.8مم اللفة= 34×3 متر(اللون أبيض) |  | Meter | 102 | 60316316 |  |  |  | ماسورة 20مم UPVC سمك ثقيل قطر خارجي 20 قطر داخلي 15.8مم اللفة= 34×3 متر(اللون أبيض) | 030010000051 | MEP | Received | 2023-02-28 | Accounted transaction received
3897050 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 177.62 | 1 | جلبة ماسورة 20مم UPVC (اللون أبيض) |  | Each | 100 | 60316317 |  |  |  | جلبة ماسورة 20مم UPVC (اللون أبيض) | 030010000067 | MEP | Received | 2023-02-28 | Accounted transaction received
3897051 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 168.15 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 50 | 60316318 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-02-28 | Accounted transaction received
3897052 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1105.8 | 1 | لاكور ماسورة EMT المقاس ¾ " |  | Each | 50 | 60316319 |  |  |  | لاكور ماسورة EMT المقاس ¾ " | 030020100015 | MEP | Received | 2023-02-28 | Accounted transaction received
3897053 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 205.2 | 1 | غطاء بواط معدن مقاس 4*4 |  | Each | 30 | 60316320 |  |  |  | غطاء بواط معدن مقاس 4*4 | 030020100129 | MEP | Received | 2023-02-28 | Accounted transaction received
3897054 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 550.07 | 1 | SWITCH 20AX 1 WAY 1 MOD Code 572509 |  | Each | 4 | 60316321 |  |  |  | SWITCH 20AX 1 WAY 1 MOD Code 572509 | 030060100048 | MEP | Received | 2023-02-28 | Accounted transaction received
3897055 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 260.17 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 4 | 60316322 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-02-28 | Accounted transaction received
3897056 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 253.33 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 20 | 60316323 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-02-28 | Accounted transaction received
3897057 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2638.07 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أزرق (cu/pvc) |  | Meter | 300 | 60316324 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أزرق (cu/pvc) | 030030101025 | MEP | Received | 2023-02-28 | Accounted transaction received
3897058 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1531.88 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) |  | Meter | 200 | 60316325 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) | 030030101026 | MEP | Received | 2023-02-28 | Accounted transaction received
3897059 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1622.23 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أصفر × أخضر (cu/pvc) |  | Meter | 200 | 60316326 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أصفر × أخضر (cu/pvc) | 030030101027 | MEP | Received | 2023-02-28 | Accounted transaction received
3840493 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-02-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 48959.9 | 1 | Hardware Accessories for Wooden Doors Concealed hinge system & Bathroom Concealed Hinges Simonswerk completely concealed hinge system with load capacity 80.0 kg two hinges per door leaf (1x2m) |  | Each | 18 | 59986525 |  |  |  | Hardware Accessories for Wooden Doors Concealed hinge system & Bathroom Concealed Hinges Simonswerk completely concealed hinge system with load capacity 80.0 kg two hinges per door leaf (1x2m) | 250010001515 | Procurement | Received | 2023-02-21 | Accounted transaction received
3840494 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-02-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 403.85 | 1 | Shell RimR3X 20w50 - زيت شل |  | Liter | 7 | 59992569 |  |  |  | Shell RimR3X 20w50 - زيت شل | 340020000068 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840495 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-02-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 32639.93 | 1 | Hardware Accessories for Wooden Doors Concealed hinge system & Bathroom Concealed Hinges Simonswerk completely concealed hinge system with load capacity 80.0 kg two hinges per door leaf (1x2m) |  | Each | 12 | 59992677 |  |  |  | Hardware Accessories for Wooden Doors Concealed hinge system & Bathroom Concealed Hinges Simonswerk completely concealed hinge system with load capacity 80.0 kg two hinges per door leaf (1x2m) | 250010001515 | Procurement | Received | 2023-02-21 | Accounted transaction received
3840496 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 71659.2 | 1 | UP17 جلد طبيعي خاص بالتنجيد ومقاوم للإحتكاك الجاف والرطب |  | Square Meter | 114.29 | 59994836 |  |  |  | UP17 جلد طبيعي خاص بالتنجيد ومقاوم للإحتكاك الجاف والرطب | 700020000216 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840497 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-02-15 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 8501.44 | 1 | Wall Paper WC-6 Monsoon Fact -75300-75310 textured wit geometric pattern in dark blue color Solid vinyl weight to be minimum of 480gr /sqm |  | Roll | 2 | 60065887 |  |  |  | Wall Paper WC-6 Monsoon Fact -75300-75310 textured wit geometric pattern in dark blue color Solid vinyl weight to be minimum of 480gr /sqm | 050020000016 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840498 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-02-15 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 81022.63 | 1 | Wall Paper WC-4 Solid vinyl fabric backed min weight 480/gr /sqm. Textured with geometric pattern in metallic color |  | Meter | 16 | 60065888 |  |  |  | Wall Paper WC-4 Solid vinyl fabric backed min weight 480/gr /sqm. Textured with geometric pattern in metallic color | 050020000014 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840499 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-02-15 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 80943.19 | 1 | Wall Paper WC-7 vinyl snakeskin 8072 vicious venom Osnaburg backing anti-microbial Untrimmed |  | linear yard | 60 | 60065889 |  |  |  | Wall Paper WC-7 vinyl snakeskin 8072 vicious venom Osnaburg backing anti-microbial Untrimmed | 050020000017 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840500 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-02-15 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 28001.7 | 1 | Wall covering – WC-3 – Cole & Son- The Ardmore Collection, Narina Linen 109/10049 |  | Roll | 9 | 60066020 |  |  |  | Wall covering – WC-3 – Cole & Son- The Ardmore Collection, Narina Linen 109/10049 | 050020000013 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840501 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-02-15 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 40471.6 | 1 | Wall Paper WC-5 vinyl snake skin 8071 buttermilk racer wallcovering osnaburg backing anti-microbial additives untrimmed |  | linear yard | 30 | 60066021 |  |  |  | Wall Paper WC-5 vinyl snake skin 8071 buttermilk racer wallcovering osnaburg backing anti-microbial additives untrimmed | 050020000015 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840502 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-02-15 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 98958.56 | 1 | Wall Paper WC-14 Vinyl Leos Luxe linen 7700 French Forth Construction : Solid Sheet Vinyl |  | linear yard | 75 | 60066269 |  |  |  | Wall Paper WC-14 Vinyl Leos Luxe linen 7700 French Forth Construction : Solid Sheet Vinyl | 050020000023 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840503 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-02-15 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 6063.64 | 1 | Wall Paper WC-15 Arte Ref : curiosa,grove,13521 Construction : vinyl wallpaper on fabric backing |  | Roll | 1 | 60066396 |  |  |  | Wall Paper WC-15 Arte Ref : curiosa,grove,13521 Construction : vinyl wallpaper on fabric backing | 050020000024 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840504 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-02-15 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 406083.08 | 1 | Wall Paper WC-12 Ref Chipper-46859 Textured beige vinyl wall covering Fabric Backed Vinyl Fire rating : pass euroclass c /class 0 and 1 to BS476 |  | Meter | 269.58 | 60068077 |  |  |  | Wall Paper WC-12 Ref Chipper-46859 Textured beige vinyl wall covering Fabric Backed Vinyl Fire rating : pass euroclass c /class 0 and 1 to BS476 | 050020000021 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840505 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-02-15 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 326686.5 | 1 | Wall covering – WC-3 – Cole & Son- The Ardmore Collection, Narina Linen 109/10049 |  | Roll | 105 | 60069548 |  |  |  | Wall covering – WC-3 – Cole & Son- The Ardmore Collection, Narina Linen 109/10049 | 050020000013 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840506 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-02-15 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 56003.4 | 1 | Wall covering – WC-3 – Cole & Son- The Ardmore Collection, Narina Linen 109/10049 |  | Roll | 18 | 60069577 |  |  |  | Wall covering – WC-3 – Cole & Son- The Ardmore Collection, Narina Linen 109/10049 | 050020000013 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840507 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-02-15 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 142.5 | 1 | فلتر جاز طويل نيسان بيك اب |  | Each | 1 | 60070116 |  |  |  | فلتر جاز طويل نيسان بيك اب | 330030000097 | Equipment | Received | 2023-02-21 | Accounted transaction received
3840508 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-02-15 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 94.6 | 1 | فلتر جاز قصير نيسان بيك اب |  | Each | 1 | 60070117 |  |  |  | فلتر جاز قصير نيسان بيك اب | 330030000098 | Equipment | Received | 2023-02-21 | Accounted transaction received
3840509 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 6922.08 | 1 | لاكور ماسورة على فلكسبيل EMT المقاس 2 " |  | Each | 80 | 60071618 |  |  |  | لاكور ماسورة على فلكسبيل EMT المقاس 2 " | 030020100055 | MEP | Received | 2023-02-21 | Accounted transaction received
3840510 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 519.16 | 1 | لاكور ماسورة على فلكسبيل EMT المقاس 2 " |  | Each | 6 | 60071619 |  |  |  | لاكور ماسورة على فلكسبيل EMT المقاس 2 " | 030020100055 | MEP | Received | 2023-02-21 | Accounted transaction received
3840511 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 17.09 | 1 | أفيز هانجر EMT المقاس 2 " |  | Each | 1 | 60071620 |  |  |  | أفيز هانجر EMT المقاس 2 " | 030020100080 | MEP | Received | 2023-02-21 | Accounted transaction received
3840512 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2156.65 | 1 | ماسورة 50مم UPVC سمك ثقيل قطر خارجي 50 قطر داخلي 43.2مم اللفة= 5×3 متر(اللون أبيض) |  | Meter | 45 | 60071621 |  |  |  | ماسورة 50مم UPVC سمك ثقيل قطر خارجي 50 قطر داخلي 43.2مم اللفة= 5×3 متر(اللون أبيض) | 030010000056 | MEP | Received | 2023-02-21 | Accounted transaction received
3840513 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 211.06 | 1 | بواط 10 * 10 عالى المقاس 1 " |  | Each | 3 | 60071622 |  |  |  | بواط 10 * 10 عالى المقاس 1 " | 030020100104 | MEP | Received | 2023-02-21 | Accounted transaction received
3840514 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 168.15 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 50 | 60071623 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-02-21 | Accounted transaction received
3840515 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 252.22 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 75 | 60071624 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-02-21 | Accounted transaction received
3840516 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1388.78 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 5 | 60071625 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) | 030010000059 | MEP | Received | 2023-02-21 | Accounted transaction received
3840517 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 126.2 | 1 | جلبة ماسورة50مم UPVC (اللون أبيض) |  | Each | 10 | 60071626 |  |  |  | جلبة ماسورة50مم UPVC (اللون أبيض) | 030010000071 | MEP | Received | 2023-02-21 | Accounted transaction received
3840518 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 271.08 | 1 | بواط إمتداد UPVC لماسورة 20مم(اللون أبيض) |  | Each | 40 | 60071627 |  |  |  | بواط إمتداد UPVC لماسورة 20مم(اللون أبيض) | 030010000082 | MEP | Received | 2023-02-21 | Accounted transaction received
3840519 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 91.13 | 1 | أدابتور UPVC لماسورة 32مم(اللون أبيض) |  | Each | 7 | 60071628 |  |  |  | أدابتور UPVC لماسورة 32مم(اللون أبيض) | 030010000098 | MEP | Received | 2023-02-21 | Accounted transaction received
3840520 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1111.73 | 1 | جلاند فلكسبل مقاس 25 مم |  | Each | 80 | 60071629 |  |  |  | جلاند فلكسبل مقاس 25 مم | 030010000170 | MEP | Received | 2023-02-21 | Accounted transaction received
3840521 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 26023.77 | 1 | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 |  | Meter | 277.55 | 60071630 |  |  |  | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 | 030020100002 | MEP | Received | 2023-02-21 | Accounted transaction received
3840522 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 11439.02 | 1 | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 |  | Meter | 122 | 60071631 |  |  |  | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 | 030020100002 | MEP | Received | 2023-02-21 | Accounted transaction received
3840523 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 684 | 1 | غطاء بواط معدن مقاس 4*4 |  | Each | 100 | 60071632 |  |  |  | غطاء بواط معدن مقاس 4*4 | 030020100129 | MEP | Received | 2023-02-21 | Accounted transaction received
3840524 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 684 | 1 | غطاء بواط معدن مقاس 4*4 |  | Each | 100 | 60071633 |  |  |  | غطاء بواط معدن مقاس 4*4 | 030020100129 | MEP | Received | 2023-02-21 | Accounted transaction received
3840525 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 902.16 | 1 | جلبة ماسورة EMT المقاس ¾ " |  | Each | 50 | 60071634 |  |  |  | جلبة ماسورة EMT المقاس ¾ " | 030020100021 | MEP | Received | 2023-02-21 | Accounted transaction received
3840526 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 123.48 | 1 | 10AX 2 WAY SWITCH 2 MOD Code 572535 |  | Each | 2 | 60071635 |  |  |  | 10AX 2 WAY SWITCH 2 MOD Code 572535 | 030060100125 | MEP | Received | 2023-02-21 | Accounted transaction received
3840527 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 65.04 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 1 | 60071636 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-02-21 | Accounted transaction received
3840528 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 260.17 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 4 | 60071637 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-02-21 | Accounted transaction received
3840529 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 63.33 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 5 | 60071638 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-02-21 | Accounted transaction received
3840530 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 53.03 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 3 | 60071639 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-02-21 | Accounted transaction received
3840531 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 106.06 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 6 | 60071640 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-02-21 | Accounted transaction received
3840532 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 265.14 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 15 | 60071641 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-02-21 | Accounted transaction received
3840533 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 258.35 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 6 | 60071642 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-02-21 | Accounted transaction received
3840534 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1665.62 | 1 | INTERNAL CONTROL UNIT FOR HOTEL BEDROOM Code 572554 |  | Each | 4 | 60071643 |  |  |  | INTERNAL CONTROL UNIT FOR HOTEL BEDROOM Code 572554 | 030060100175 | MEP | Received | 2023-02-21 | Accounted transaction received
3840535 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 688.91 | 1 | SHAVER SOCKET 230V/120-230V WITH EARTH CONNECTOR Code 572653 |  | Each | 1 | 60071644 |  |  |  | SHAVER SOCKET 230V/120-230V WITH EARTH CONNECTOR Code 572653 | 030060100178 | MEP | Received | 2023-02-21 | Accounted transaction received
3840536 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2709.77 | 1 | LINE DYING DOWN 100 V 25-30 W Code 572784 |  | Each | 1 | 60071645 |  |  |  | LINE DYING DOWN 100 V 25-30 W Code 572784 | 030060100224 | MEP | Received | 2023-02-21 | Accounted transaction received
3840537 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 969 | 1 | جلو شفاف |  | Can | 17 | 60071646 |  |  |  | جلو شفاف | 200010001116 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840538 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 19.01 | 1 | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 |  | Each | 1 | 60071647 |  |  |  | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 | 150020000178 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840539 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 285.26 | 1 | mosaic adapter code 69580 |  | Each | 3 | 60071648 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-02-21 | Accounted transaction received
3840540 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 380.35 | 1 | mosaic adapter code 69580 |  | Each | 4 | 60071649 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-02-21 | Accounted transaction received
3840541 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 240.74 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 3 | 60071650 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-02-21 | Accounted transaction received
3840542 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 320.99 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 4 | 60071651 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-02-21 | Accounted transaction received
3840543 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 23.89 | 1 | Metal Galvanized back box 7x14 cm with deep 47 mm |  | Each | 1 | 60071652 |  |  |  | Metal Galvanized back box 7x14 cm with deep 47 mm | 030069000027 | MEP | Received | 2023-02-21 | Accounted transaction received
3840544 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 57596.02 | 1 | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser |  | Each | 150 | 60071653 |  |  |  | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser | 030040700472 | MEP | Received | 2023-02-21 | Accounted transaction received
3840619 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 171 | 1 | دفتر Material Request |  | Each | 10 | 59888462 |  |  |  | دفتر Material Request | 910010000269 | Administration | Received | 2023-02-21 | Accounted transaction received
3840545 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2223 | 1 | لاكور بواط على فليكسبل EMT المقاس 3/4 " |  | Each | 75 | 60071654 |  |  |  | لاكور بواط على فليكسبل EMT المقاس 3/4 " | 030020100214 | MEP | Received | 2023-02-21 | Accounted transaction received
3840546 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 11856 | 1 | لاكور بواط على فليكسبل EMT المقاس 3/4 " |  | Each | 400 | 60071655 |  |  |  | لاكور بواط على فليكسبل EMT المقاس 3/4 " | 030020100214 | MEP | Received | 2023-02-21 | Accounted transaction received
3840547 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 492.41 | 1 | DS , 4 pole , 25A , 400V , abs enclosure IP 65 Code : KEM 425u y/r abs |  | Each | 1 | 60071656 |  |  |  | DS , 4 pole , 25A , 400V , abs enclosure IP 65 Code : KEM 425u y/r abs | 030060200072 | MEP | Received | 2023-02-21 | Accounted transaction received
3840548 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 282.72 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 5 | 60071657 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-02-21 | Accounted transaction received
3840549 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-16 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 765.94 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) |  | Meter | 100 | 60081135 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) | 030030101026 | MEP | Received | 2023-02-21 | Accounted transaction received
3840550 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-16 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5214.45 | 1 | Acolyte - ARB95SWBC653.027 - Rapid Ribbon 95+ - LED Strip with 9.8 W/M, 2700K, CRI/97 IP65, 24VDC, with aluminum profile and Opal diffuser |  | Each | 10.4 | 60081136 |  |  |  | Acolyte - ARB95SWBC653.027 - Rapid Ribbon 95+ - LED Strip with 9.8 W/M, 2700K, CRI/97 IP65, 24VDC, with aluminum profile and Opal diffuser | 030040700470 | MEP | Received | 2023-02-21 | Accounted transaction received
3840551 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 13.03. | Reinforced Earth blo | 13 | SPECIAL CONSTRUCTIO |  | 2023-02-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 5119.97 | 1 | طوب مصمت 6*10*20 |  | Each | 4000 | 60114129 |  |  |  | طوب مصمت 6*10*20 | 140020000045 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840552 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-07 | Materials |  |  |  | Materials | Alrowad Construction_OU | -2565.36 | 1 | Compact Ceiling Loudspeaker with 76 mm (3 in) Full-Range Driver. 68 Hz – 17 kHz bandwidth, wide 130° coverage, 84 dB sensitivity Blind-mount backcan for quick and easy installation, dual conduit/cable clamp for in and thru cables. |  | Each | -1 | 59849353 |  |  |  | Compact Ceiling Loudspeaker with 76 mm (3 in) Full-Range Driver. 68 Hz – 17 kHz bandwidth, wide 130° coverage, 84 dB sensitivity Blind-mount backcan for quick and easy installation, dual conduit/cable clamp for in and thru cables. | 031060000046 | MEP | Received | 2023-02-21 | Accounted transaction received
3840553 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 47473.25 | 1 | فلكسيبل معدن المقاس ¾ " |  | Meter | 765.5 | 59888259 |  |  |  | فلكسيبل معدن المقاس ¾ " | 030020100091 | MEP | Received | 2023-02-21 | Accounted transaction received
3840554 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1477.39 | 1 | بواط 10 * 10 عالى المقاس 1 " |  | Each | 21 | 59888260 |  |  |  | بواط 10 * 10 عالى المقاس 1 " | 030020100104 | MEP | Received | 2023-02-21 | Accounted transaction received
3840555 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2017.54 | 1 | بواط 10 * 10 عالى المقاس ¾ " |  | Each | 30 | 59888261 |  |  |  | بواط 10 * 10 عالى المقاس ¾ " | 030020100105 | MEP | Received | 2023-02-21 | Accounted transaction received
3840556 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 530.91 | 1 | بواط إكستنشن 10 * 10 المقاس ¾ " |  | Each | 8 | 59888262 |  |  |  | بواط إكستنشن 10 * 10 المقاس ¾ " | 030020100109 | MEP | Received | 2023-02-21 | Accounted transaction received
3840557 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 707.94 | 1 | بواط إكستنشن 10 * 10 المقاس 1 " |  | Each | 10 | 59888263 |  |  |  | بواط إكستنشن 10 * 10 المقاس 1 " | 030020100111 | MEP | Received | 2023-02-21 | Accounted transaction received
3840558 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 336.3 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 100 | 59888264 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-02-21 | Accounted transaction received
3840559 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 555.51 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 2 | 59888265 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) | 030010000059 | MEP | Received | 2023-02-21 | Accounted transaction received
3840560 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1763.68 | 1 | سلك نحاس مصمت مقاس 1.5 مم اللون أسود (cu/pvc) جهد (750/450) |  | Meter | 300 | 59888266 |  |  |  | سلك نحاس مصمت مقاس 1.5 مم اللون أسود (cu/pvc) جهد (750/450) | 030030100253 | MEP | Received | 2023-02-21 | Accounted transaction received
3840561 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 24.16 | 1 | كوع ماسورة 50مم UPVC(اللون أبيض) |  | Each | 1 | 59888267 |  |  |  | كوع ماسورة 50مم UPVC(اللون أبيض) | 030010000077 | MEP | Received | 2023-02-21 | Accounted transaction received
3840562 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1172.66 | 1 | أدابتور UPVC لماسورة 25مم(اللون أبيض) |  | Each | 150 | 59888268 |  |  |  | أدابتور UPVC لماسورة 25مم(اللون أبيض) | 030010000097 | MEP | Received | 2023-02-21 | Accounted transaction received
3840563 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 694.83 | 1 | جلاند فلكسبل مقاس 25 مم |  | Each | 50 | 59888269 |  |  |  | جلاند فلكسبل مقاس 25 مم | 030010000170 | MEP | Received | 2023-02-21 | Accounted transaction received
3840564 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 40075.56 | 1 | كابل نحاس مجدول مصمت مقاس 3 × 10 مم (xlpe/pvc) جهد (500/300) |  | Meter | 600 | 59888270 |  |  |  | كابل نحاس مجدول مصمت مقاس 3 × 10 مم (xlpe/pvc) جهد (500/300) | 030030100138 | MEP | Received | 2023-02-21 | Accounted transaction received
3840565 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2793 | 1 | بواط واتر بروف بفتحات مقاس 30 × 38 × 12 سم |  | Each | 7 | 59888271 |  |  |  | بواط واتر بروف بفتحات مقاس 30 × 38 × 12 سم | 030010000185 | MEP | Received | 2023-02-21 | Accounted transaction received
3840566 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2859.76 | 1 | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 |  | Meter | 30.5 | 59888272 |  |  |  | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 | 030020100002 | MEP | Received | 2023-02-21 | Accounted transaction received
3840567 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2746.83 | 1 | ماسورة صلب مجلفن EMT المقاس 2 " طول الماسورة 3.05 |  | Meter | 6.1 | 59888273 |  |  |  | ماسورة صلب مجلفن EMT المقاس 2 " طول الماسورة 3.05 | 030020100005 | MEP | Received | 2023-02-21 | Accounted transaction received
3840568 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3789.08 | 1 | جلبة ماسورة EMT المقاس ¾ " |  | Each | 210 | 59888274 |  |  |  | جلبة ماسورة EMT المقاس ¾ " | 030020100021 | MEP | Received | 2023-02-21 | Accounted transaction received
3840569 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 250.43 | 1 | أفيز أثنين جناح لماسورة EMT المقاس ¾ " |  | Each | 100 | 59888275 |  |  |  | أفيز أثنين جناح لماسورة EMT المقاس ¾ " | 030020100033 | MEP | Received | 2023-02-21 | Accounted transaction received
3840570 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2750.36 | 1 | SWITCH 20AX 1 WAY 1 MOD Code 572509 |  | Each | 20 | 59888276 |  |  |  | SWITCH 20AX 1 WAY 1 MOD Code 572509 | 030060100048 | MEP | Received | 2023-02-21 | Accounted transaction received
3840571 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1300.83 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 20 | 59888277 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-02-21 | Accounted transaction received
3840572 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 325.21 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 5 | 59888278 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-02-21 | Accounted transaction received
3840573 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 63.33 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 5 | 59888279 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-02-21 | Accounted transaction received
3840574 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 530.28 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 30 | 59888280 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-02-21 | Accounted transaction received
3840575 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 541.5 | 1 | Mechanical anchor (Drop in anchor) size M10 |  | Each | 100 | 59888281 |  |  |  | Mechanical anchor (Drop in anchor) size M10 | 060190100003 | MEP | Received | 2023-02-21 | Accounted transaction received
3840576 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 642.96 | 1 | Threaded rod size M10 |  | Each | 15 | 59888282 |  |  |  | Threaded rod size M10 | 060190300003 | MEP | Received | 2023-02-21 | Accounted transaction received
3840577 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2033.49 | 1 | سلك نحاس مجدول مقاس4 مم اللون أحمر (cu/pvc) |  | Meter | 200 | 59888283 |  |  |  | سلك نحاس مجدول مقاس4 مم اللون أحمر (cu/pvc) | 030030101023 | MEP | Received | 2023-02-21 | Accounted transaction received
3840578 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1531.88 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) |  | Meter | 200 | 59888284 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) | 030030101026 | MEP | Received | 2023-02-21 | Accounted transaction received
3840579 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 811.12 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أصفر × أخضر (cu/pvc) |  | Meter | 100 | 59888285 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أصفر × أخضر (cu/pvc) | 030030101027 | MEP | Received | 2023-02-21 | Accounted transaction received
3840580 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1117.89 | 1 | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS |  | Each | 5 | 59888286 |  |  |  | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS | 030060100617 | MEP | Received | 2023-02-21 | Accounted transaction received
3840581 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 492.66 | 1 | Wiring Devices (54000) METAL FLUSH-MOUNTING BOX FOR INSTALLATION IN CONCRETE FLOOR - 3 MODULES |  | Each | 5 | 59888287 |  |  |  | Wiring Devices (54000) METAL FLUSH-MOUNTING BOX FOR INSTALLATION IN CONCRETE FLOOR - 3 MODULES | 030060100618 | MEP | Received | 2023-02-21 | Accounted transaction received
3840582 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 380.21 | 1 | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 |  | Each | 20 | 59888288 |  |  |  | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 | 150020000178 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840583 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 950.87 | 1 | mosaic adapter code 69580 |  | Each | 10 | 59888289 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-02-21 | Accounted transaction received
3840584 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2949.75 | 1 | Hot dip Galvanized after fabrication, Cable Tray Trunk Type, 200mm Width, 100mm height of Side,1.5mm thickness,10mmReturnFlange ,3000mm Length. |  | Meter | 15 | 59888290 |  |  |  | Hot dip Galvanized after fabrication, Cable Tray Trunk Type, 200mm Width, 100mm height of Side,1.5mm thickness,10mmReturnFlange ,3000mm Length. | 030101400048 | MEP | Received | 2023-02-21 | Accounted transaction received
3840585 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 793.39 | 1 | DS 2 pole , 63A, ABS Enclsosure IP 65 , PART NUMBER : kem 263u y/r abs |  | Each | 1 | 59888291 |  |  |  | DS 2 pole , 63A, ABS Enclsosure IP 65 , PART NUMBER : kem 263u y/r abs | 030060200023 | MEP | Received | 2023-02-21 | Accounted transaction received
3840586 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 902.09 | 1 | Surface mounting socket P17 Pro ? IP 66/67 ? 200/250 V~ ? 63 A ? 2P+E (Legrand 555554) |  | Each | 1 | 59888292 |  |  |  | Surface mounting socket P17 Pro ? IP 66/67 ? 200/250 V~ ? 63 A ? 2P+E (Legrand 555554) | 030060300022 | MEP | Received | 2023-02-21 | Accounted transaction received
3840587 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 507.29 | 1 | Straight plug P17 Pro ? IP 66/67 ? 200/250 V~ ? 63 A ? 2P+E (Legrand 555524) |  | Each | 1 | 59888293 |  |  |  | Straight plug P17 Pro ? IP 66/67 ? 200/250 V~ ? 63 A ? 2P+E (Legrand 555524) | 030060300023 | MEP | Received | 2023-02-21 | Accounted transaction received
3840588 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1065.9 | 1 | Hot Dip Galvanized c-channel 40x20x2.5mm |  | Meter | 17 | 59888294 |  |  |  | Hot Dip Galvanized c-channel 40x20x2.5mm | 030100200219 | MEP | Received | 2023-02-21 | Accounted transaction received
3840589 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 802.48 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 10 | 59888295 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-02-21 | Accounted transaction received
3840590 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1338.14 | 1 | أدابتور 3/4 مواسير EMT |  | Each | 75 | 59888296 |  |  |  | أدابتور 3/4 مواسير EMT | 030020100207 | MEP | Received | 2023-02-21 | Accounted transaction received
3840591 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2883.04 | 1 | Reading lamp - Recessed down light LED 12W, IP 65, 2700K, CRI 90, Optics 30°, Aluminum with textured powder coat finish body |  | Each | 2 | 59888297 |  |  |  | Reading lamp - Recessed down light LED 12W, IP 65, 2700K, CRI 90, Optics 30°, Aluminum with textured powder coat finish body | 030040700461 | MEP | Received | 2023-02-21 | Accounted transaction received
3840592 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1441.52 | 1 | Reading lamp - Recessed down light LED 12W, IP 65, 2700K, CRI 90, Optics 30°, Aluminum with textured powder coat finish body |  | Each | 1 | 59888298 |  |  |  | Reading lamp - Recessed down light LED 12W, IP 65, 2700K, CRI 90, Optics 30°, Aluminum with textured powder coat finish body | 030040700461 | MEP | Received | 2023-02-21 | Accounted transaction received
3840593 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 19198.67 | 1 | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser |  | Each | 50 | 59888299 |  |  |  | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser | 030040700472 | MEP | Received | 2023-02-21 | Accounted transaction received
3840594 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5928 | 1 | لاكور بواط على فليكسبل EMT المقاس 3/4 " |  | Each | 200 | 59888300 |  |  |  | لاكور بواط على فليكسبل EMT المقاس 3/4 " | 030020100214 | MEP | Received | 2023-02-21 | Accounted transaction received
3840595 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 501.94 | 1 | SPLASH PROOF COVER Code : 617636 |  | Each | 5 | 59888301 |  |  |  | SPLASH PROOF COVER Code : 617636 | 030060100927 | MEP | Received | 2023-02-21 | Accounted transaction received
3840596 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 492.41 | 1 | DS , 4 pole , 25A , 400V , abs enclosure IP 65 Code : KEM 425u y/r abs |  | Each | 1 | 59888302 |  |  |  | DS , 4 pole , 25A , 400V , abs enclosure IP 65 Code : KEM 425u y/r abs | 030060200072 | MEP | Received | 2023-02-21 | Accounted transaction received
3840597 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 112.68 | 1 | 1G 20A DP SWT + NEON + E WH - 617671 |  | Each | 1 | 59888303 |  |  |  | 1G 20A DP SWT + NEON + E WH - 617671 | 030060100942 | MEP | Received | 2023-02-21 | Accounted transaction received
3840598 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 563.39 | 1 | 1G 20A DP SWT + NEON + E WH - 617671 |  | Each | 5 | 59888304 |  |  |  | 1G 20A DP SWT + NEON + E WH - 617671 | 030060100942 | MEP | Received | 2023-02-21 | Accounted transaction received
3840599 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 114 | 1 | PVC Box 110x150x70 mm ip66 |  | Each | 1 | 59888305 |  |  |  | PVC Box 110x150x70 mm ip66 | 030069000031 | MEP | Received | 2023-02-21 | Accounted transaction received
3840600 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4309.2 | 1 | Driver Model RS-15-12. I/P 220VAC Output 12VDC Single Output at 1.3A |  | Each | 12 | 59888306 |  |  |  | Driver Model RS-15-12. I/P 220VAC Output 12VDC Single Output at 1.3A | 030049100070 | MEP | Received | 2023-02-21 | Accounted transaction received
3840601 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 934.54 | 1 | سيفتي عمال |  | Each | 3 | 59888328 |  |  |  | سيفتي عمال | 010030000002 | Safety | Received | 2023-02-21 | Accounted transaction received
3840602 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 95.46 | 1 | جوانتي جلد ثقيل ( خرسانة ) |  | Each | 3 | 59888329 |  |  |  | جوانتي جلد ثقيل ( خرسانة ) | 010010000003 | Safety | Received | 2023-02-21 | Accounted transaction received
3840603 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 31.92 | 1 | فيست برتقالي |  | Each | 1 | 59888330 |  |  |  | فيست برتقالي | 010020000008 | Safety | Received | 2023-02-21 | Accounted transaction received
3840604 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 20.96 | 1 | صابون سائل |  | Can | 1 | 59888331 |  |  |  | صابون سائل | 700020000013 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840605 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 50.16 | 1 | سدادة أذن |  | Each | 11 | 59888332 |  |  |  | سدادة أذن | 010020000015 | Safety | Received | 2023-02-21 | Accounted transaction received
3840606 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 85 | 1 | بخاخة يدوي |  | Each | 1 | 59888333 |  |  |  | بخاخة يدوي | 200010000810 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840607 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 340 | 1 | تنر |  | Each | 4 | 59888334 |  |  |  | تنر | 060019000008 | MEP | Received | 2023-02-21 | Accounted transaction received
3840608 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 78 | 1 | فنيك |  | Each | 4 | 59888335 |  |  |  | فنيك | 700020000050 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840609 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 330 | 1 | ملاثيون ( رش مبيدات ) |  | Each | 1 | 59888336 |  |  |  | ملاثيون ( رش مبيدات ) | 700020000099 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840610 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.18 | HSE | 17 | Indirect Cost |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 400 | 1 | مبيد حشرى (رش شقق ) |  | Each | 1 | 59888337 |  |  |  | مبيد حشرى (رش شقق ) | 700020000120 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840611 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 6.03. | Architectural Wood W | 6 | WOOD & PLASTIC WORK |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 90 | 1 | شريط قياس 5م |  | Each | 2 | 59888454 |  |  |  | شريط قياس 5م | 200010000105 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840612 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 6.03. | Architectural Wood W | 6 | WOOD & PLASTIC WORK |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 12255 | 1 | تيب دوكو |  | Each | 500 | 59888455 |  |  |  | تيب دوكو | 200010000048 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840613 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 6.03. | Architectural Wood W | 6 | WOOD & PLASTIC WORK |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 104.79 | 1 | صابون سائل |  | Can | 5 | 59888456 |  |  |  | صابون سائل | 700020000013 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840614 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 6.03. | Architectural Wood W | 6 | WOOD & PLASTIC WORK |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 182.63 | 1 | جبس |  | Ton | 0.12 | 59888457 |  |  |  | جبس | 140010000004 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840615 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 6.03. | Architectural Wood W | 6 | WOOD & PLASTIC WORK |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3431.4 | 1 | بولي ايثيلين 100 ميكرون ابيض |  | Kilogram | 43 | 59888458 |  |  |  | بولي ايثيلين 100 ميكرون ابيض | 040010000034 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840616 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.07.16 | Construction & Trimm | 2 | SITE WORK |  | 2023-02-08 | Cement |  |  |  | Materials | Waldorf Astoria-0164 | 43750 | 1 | اسمنت اسود رتبة 32 |  | Ton | 25 | 59888459 |  |  |  | اسمنت اسود رتبة 32 | 140010000016 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840617 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 6.03. | Architectural Wood W | 6 | WOOD & PLASTIC WORK |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 199.5 | 1 | سلاح كتر |  | Each | 5 | 59888460 |  |  |  | سلاح كتر | 200010000411 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840618 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 6.03. | Architectural Wood W | 6 | WOOD & PLASTIC WORK |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 524.4 | 1 | معجون ممتاز |  | Bag | 4 | 59888461 |  |  |  | معجون ممتاز | 200010001077 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840620 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 6.03. | Architectural Wood W | 6 | WOOD & PLASTIC WORK |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 684.68 | 1 | كرتون مضلع - تغليف |  | Kilogram | 46.2 | 59888463 |  |  |  | كرتون مضلع - تغليف | 910010000387 | Administration | Received | 2023-02-21 | Accounted transaction received
3840621 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 6.03. | Architectural Wood W | 6 | WOOD & PLASTIC WORK |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 250 | 1 | اديبوند 65 |  | Kilogram | 2 | 59888464 |  |  |  | اديبوند 65 | 360010000273 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840622 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.07.16 | Construction & Trimm | 2 | SITE WORK |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 23370 | 1 | Master Seal NP 472 |  | Kit | 205 | 59888465 |  |  |  | Master Seal NP 472 | 360010000355 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840623 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.07.16 | Construction & Trimm | 2 | SITE WORK |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 100.8 | 1 | مادة لاصق فيوتك (كرنيشة جبسية) |  | Kilogram | 5 | 59888466 |  |  |  | مادة لاصق فيوتك (كرنيشة جبسية) | 050020000007 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840624 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 5.02.09 | Metal access Doors | 5 | METAL WORK |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 6270 | 1 | Comprising Brass frame MT-1 for Bathroom vanity cabinet including all necessary accessories; preparations; WAH-GR-60 DT; detail 02 Size 1540 x 600 x 1050 mm Materials: Steel frame 30x30mm Dimensions: 144x57x82 cm Finish: Galvanized steel |  | Each | 1 | 59888467 |  |  |  | Comprising Brass frame MT-1 for Bathroom vanity cabinet including all necessary accessories; preparations; WAH-GR-60 DT; detail 02 Size 1540 x 600 x 1050 mm Materials: Steel frame 30x30mm Dimensions: 144x57x82 cm Finish: Galvanized steel | 250010001358 | Procurement | Received | 2023-02-21 | Accounted transaction received
3840625 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.02.01 | Wooden doors | 8 | DOORS & WINDOWS WOR |  | 2023-02-08 | Wood |  |  |  | Materials | Waldorf Astoria-0164 | 924330.24 | 1 | Oak wood (WD-8) panel cladding |  | Square Meter | 247.2 | 59888468 |  |  |  | Oak wood (WD-8) panel cladding | 090011000008 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840626 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.03 | Mosaic | 9 | FINISHES WORK |  | 2023-02-08 | Mosaic |  |  |  | Materials | Waldorf Astoria-0164 | 202837.43 | 1 | Custom Mosaic Wall feature (CT-9) |  | Square Meter | 36 | 59888469 |  |  |  | Custom Mosaic Wall feature (CT-9) | 170010000630 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840627 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.05. | Hardware | 8 | DOORS & WINDOWS WOR |  | 2023-02-08 | Hardware |  |  |  | Materials | Waldorf Astoria-0164 | 14004.01 | 1 | Hardware Accessories for Wooden Doors Concealed Door closer TESA Concealed Door closer Size 3: suitable for door width up to 95cm and can be used in Fire Doors. |  | Each | 6 | 59888470 |  |  |  | Hardware Accessories for Wooden Doors Concealed Door closer TESA Concealed Door closer Size 3: suitable for door width up to 95cm and can be used in Fire Doors. | 250010001516 | Procurement | Received | 2023-02-21 | Accounted transaction received
3840628 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.05. | Hardware | 8 | DOORS & WINDOWS WOR |  | 2023-02-08 | Hardware |  |  |  | Materials | Waldorf Astoria-0164 | 302.4 | 1 | Hardware Accessories for Wooden Doors Bathroom Mortice Lock for Sliding Doors with Thumb turn Cylinder Lock Hook AGB B089225034 Silver |  | Each | 1 | 59888471 |  |  |  | Hardware Accessories for Wooden Doors Bathroom Mortice Lock for Sliding Doors with Thumb turn Cylinder Lock Hook AGB B089225034 Silver | 250010001521 | Procurement | Received | 2023-02-21 | Accounted transaction received
3840629 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.05. | Hardware | 8 | DOORS & WINDOWS WOR |  | 2023-02-08 | Hardware |  |  |  | Materials | Waldorf Astoria-0164 | 169905.6 | 1 | Hardware accessories for doors HW-115 Bespoke Floor Door Stopper MT-1 |  | Each | 276 | 59888472 |  |  |  | Hardware accessories for doors HW-115 Bespoke Floor Door Stopper MT-1 | 250010001543 | Procurement | Received | 2023-02-21 | Accounted transaction received
3840630 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.05. | Hardware | 8 | DOORS & WINDOWS WOR |  | 2023-02-08 | Hardware |  |  |  | Materials | Waldorf Astoria-0164 | 75103.2 | 1 | Hardware accessories for doors HW-115 (IR-14) Door Stopper MT-4 |  | Each | 122 | 59888473 |  |  |  | Hardware accessories for doors HW-115 (IR-14) Door Stopper MT-4 | 250010001544 | Procurement | Received | 2023-02-21 | Accounted transaction received
3840631 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.05. | Hardware | 8 | DOORS & WINDOWS WOR |  | 2023-02-08 | Hardware |  |  |  | Materials | Waldorf Astoria-0164 | 6156 | 1 | Hardware accessories for doors HW-115 Door Stopper MT-5 |  | Each | 10 | 59888474 |  |  |  | Hardware accessories for doors HW-115 Door Stopper MT-5 | 250010001545 | Procurement | Received | 2023-02-21 | Accounted transaction received
3840632 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.05. | Hardware | 8 | DOORS & WINDOWS WOR |  | 2023-02-08 | Hardware |  |  |  | Materials | Waldorf Astoria-0164 | 1254 | 1 | Hardware accessories for doors HW-03 Towel Rail for Vanities MT-1 |  | Each | 1 | 59888475 |  |  |  | Hardware accessories for doors HW-03 Towel Rail for Vanities MT-1 | 250010001549 | Procurement | Received | 2023-02-21 | Accounted transaction received
3840633 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.05. | Hardware | 8 | DOORS & WINDOWS WOR |  | 2023-02-08 | Hardware |  |  |  | Materials | Waldorf Astoria-0164 | 228 | 1 | Hardware accessories for doors HW-102 Knob for Minibar |  | Each | 1 | 59888476 |  |  |  | Hardware accessories for doors HW-102 Knob for Minibar | 250010001569 | Procurement | Received | 2023-02-21 | Accounted transaction received
3840634 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 6.03. | Architectural Wood W | 6 | WOOD & PLASTIC WORK |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 104843.52 | 1 | Majilite wall panels UP-2 (Faux Leather) cladding; including but not limited to backing; fixing; finish and all necessary accessories; preparations; to Cabinet walls (Excluding Fabric). |  | Square Meter | 38.4 | 59888477 |  |  |  | Majilite wall panels UP-2 (Faux Leather) cladding; including but not limited to backing; fixing; finish and all necessary accessories; preparations; to Cabinet walls (Excluding Fabric). | 250010001650 | Procurement | Received | 2023-02-21 | Accounted transaction received
3840635 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 6.01.03 | Cabinets | 6 | WOOD & PLASTIC WORK |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 51300 | 1 | Decorative shelf brackets ADD Finish MT-4 |  | Each | 30 | 59888478 |  |  |  | Decorative shelf brackets ADD Finish MT-4 | 250010001665 | Procurement | Received | 2023-02-21 | Accounted transaction received
3840636 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 6.01.03 | Cabinets | 6 | WOOD & PLASTIC WORK |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 34200 | 1 | Antique brass (MT-4) frame; WAH_PA_GL_PT_70 DT; to Existing vanity mirrors |  | Meter | 60 | 59888479 |  |  |  | Antique brass (MT-4) frame; WAH_PA_GL_PT_70 DT; to Existing vanity mirrors | 250010001673 | Procurement | Received | 2023-02-21 | Accounted transaction received
3840637 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 5.02.09 | Metal access Doors | 5 | METAL WORK |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 68400 | 1 | Brass partitions @ Peacock Alley Main frame 32mm brass tubes, Middle frame FB 50x10mm. Finish: Antique brass |  | Each | 2 | 59888480 |  |  |  | Brass partitions @ Peacock Alley Main frame 32mm brass tubes, Middle frame FB 50x10mm. Finish: Antique brass | 250010001728 | Procurement | Received | 2023-02-21 | Accounted transaction received
3840638 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 6.01.03 | Cabinets | 6 | WOOD & PLASTIC WORK |  | 2023-02-08 | Hose Reel Cabinet |  |  |  | Materials | Waldorf Astoria-0164 | 48016.8 | 1 | Cabinet floors - hand rubbed brass brass inlay MT-1 |  | Each | 468 | 59888481 |  |  |  | Cabinet floors - hand rubbed brass brass inlay MT-1 | 039010200026 | MEP | Received | 2023-02-21 | Accounted transaction received
3840639 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-02-08 | Ceramic |  |  |  | Materials | Waldorf Astoria-0164 | 32062.5 | 1 | Ceramic fan shape wall tiles FS-026 Sheet Size 20*25 cm |  | Sheet | 300 | 59888482 |  |  |  | Ceramic fan shape wall tiles FS-026 Sheet Size 20*25 cm | 170010000654 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840640 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 6.01.03 | Cabinets | 6 | WOOD & PLASTIC WORK |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 10260 | 1 | Metal trim MT-01 separating between ST-18 and existing marble @ Typical Suit |  | Meter | 7.5 | 59888483 |  |  |  | Metal trim MT-01 separating between ST-18 and existing marble @ Typical Suit | 250010001925 | Procurement | Received | 2023-02-21 | Accounted transaction received
3874069 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.02 | Health Care | 17 | Indirect Cost |  | 2023-02-27 | Medical Care |  |  |  | Direct Manpower | Alrowad Construction_OU | 57051.06 | 1 | استحقاق ف التأمين التكافلي عن الربع الثالث22/23 | استحقاق ف التأمين التكافلي عن الربع الثالث22/23 | Currency | 57051.06 | 22141331 | 3671 | المصرية للتأمين التكافلى | Rowad | استحقاق ف التأمين التكافلي عن الربع الثالث22/23 |  | Finacial | Received | 2023-02-27 | Accounted transaction received
3874079 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 10.06. | Mat | 10 | SPECIALITIES | 79409 | 2023-02-27 | Materials |  |  |  | Materials | Alrowad Construction_OU | -29625.21 | 1 | استوريا جراند ف/4201 8/2 178 | 4201 c.m | Currency | -991.07 | 22141331 | 1554 | جراند ووتر تكنولوجيز | Egypt | استوريا جراند ف/4201 8/2 178 |  | Mechanical | Received | 2023-02-27 | Accounted transaction received
3874080 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 10.06. | Mat | 10 | SPECIALITIES | 79409 | 2023-02-27 | Materials |  |  |  | Materials | Alrowad Construction_OU | 29625.21 | 1 | استوريا جراند ف/4201 8/2 178 | 4201 | Currency | 29625.21 | 22141331 | 1554 | جراند ووتر تكنولوجيز | Egypt | استوريا جراند ف/4201 8/2 178 |  | Mechanical | Received | 2023-02-27 | Accounted transaction received
3874081 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.03 | Hirings daily wages | 17 | Indirect Cost |  | 2023-02-27 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 77670.68 | 1 | يوميات عماله م07-astoria | يوميات عماله م07-astoria | Currency | 77670.68 | 22141331 | 12252 | حامد حسين احمد خالد – ذاتى | rowad | يوميات عماله م07-astoria |  | Finacial | Received | 2023-02-27 | Accounted transaction received
3918239 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.07.05 | Gravel | 2 | SITE WORK |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4320 | 1 | 5.1 64204/9 |  | Currency | 36 |  | 8108 | سامى عياد فهيم حليم |  | 5.1 64204/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3902250 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-02-28 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 900 | 1 |  | FA-Depreciation - Feb23 | Currency | 900 | 22205686 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-03-02 | Accounted transaction received
3902251 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.06 | Surveying Equipment | 17 | Indirect Cost |  | 2023-02-28 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 2764.5 | 1 |  | FA-Depreciation - Feb23 | Currency | 2764.5 | 22205686 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-03-02 | Accounted transaction received
3902252 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.10 | Scaffolding | 17 | Indirect Cost |  | 2023-02-28 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 5611.65 | 1 |  | FA-Depreciation - Feb23 | Currency | 5611.65 | 22205686 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-03-02 | Accounted transaction received
3902253 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-28 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 14.98 | 1 |  | FA-Depreciation - Feb23 | Currency | 14.98 | 22205686 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-03-02 | Accounted transaction received
3902254 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-28 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 1080.93 | 1 |  | FA-Depreciation - Feb23 | Currency | 1080.93 | 22205686 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-03-02 | Accounted transaction received
3902255 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-02-28 | Furniture Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 8324.58 | 1 |  | FA-Depreciation - Feb23 | Currency | 8324.58 | 22205686 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-03-02 | Accounted transaction received
3902256 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-02-28 | Electrical appliance Deprectia |  |  |  | Depreciation | Alrowad Construction_OU | 1316.5 | 1 |  | FA-Depreciation - Feb23 | Currency | 1316.5 | 22205686 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-03-02 | Accounted transaction received
3902257 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2023-02-28 | Electrical appliance Deprectia |  |  |  | Depreciation | Alrowad Construction_OU | 3076.19 | 1 |  | FA-Depreciation - Feb23 | Currency | 3076.19 | 22205686 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-03-02 | Accounted transaction received
3902258 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.07 | Computers | 17 | Indirect Cost |  | 2023-02-28 | Computers Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 5568.13 | 1 |  | FA-Depreciation - Feb23 | Currency | 5568.13 | 22205686 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-03-02 | Accounted transaction received
3902259 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.10 | Printers / Photo Cop | 17 | Indirect Cost |  | 2023-02-28 | Electrical appliance Deprectia |  |  |  | Depreciation | Alrowad Construction_OU | 2583.29 | 1 |  | FA-Depreciation - Feb23 | Currency | 2583.29 | 22205686 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-03-02 | Accounted transaction received
3902260 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.01 | Private Cars | 17 | Indirect Cost |  | 2023-02-28 | Vehicles Depreciations |  |  |  | Depreciation | Alrowad Construction_OU | 5265.21 | 1 |  | FA-Depreciation - Feb23 | Currency | 5265.21 | 22205686 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-03-02 | Accounted transaction received
3902380 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK | 61571 | 2023-02-28 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 137443.36 | 1 | 7* Waldorf Astoria Cairo 61571/7 | 7* Waldorf Astoria Cairo 61571/7 | Currency | 137443.36 | 22205686 | 8598 | جرابل للتجارة والصناعه | rowad | 7* Waldorf Astoria Cairo 61571/7 |  | Procurement | Received | 2023-03-02 | Accounted transaction received
3909091 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-03-05 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 20 | 1 | تسويه ك /1-2-3-4-5- انتقالات,واكراميه | st-1-2-3-4-5-3-23 | Currency | 20 | 22223211 | 2162 | Petty Cash | Said Abd Allah Aziz Attia | تسويه ك /1-2-3-4-5- انتقالات,واكراميه |  | Finacial | Received | 2023-03-05 | Accounted transaction received
3909146 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-02-28 | Computers Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 14645.09 | 1 |  | FA Depreciation from Dep.To Projects feb-23 | Currency | 14645.09 | 22223211 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-03-05 | Accounted transaction received
3909202 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-02-28 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 40087.73 | 1 |  | FA Depreciation from Dep.To Projects feb-23 | Currency | 40087.73 | 22223211 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-03-05 | Accounted transaction received
3909258 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-02-28 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 88021.88 | 1 |  | FA Depreciation from Dep.To Projects feb-23 | Currency | 88021.88 | 22223211 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-03-05 | Accounted transaction received
3918599 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 31075.2 | 1 | 1.1 80894/1 |  | Currency | 1553.76 |  | 12636 | مصطفي شعبان عطية بيومي-ذاتى |  | 1.1 80894/1 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3919051 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 10.06. | Mat | 10 | SPECIALITIES | 67092 | 2023-03-07 | Materials |  |  |  | Materials | Alrowad Construction_OU | -747.84 | 1 | استوريا موبل الشرق ف/14134 12/2 003 مستخلص 2 | 14134 | Currency | -747.84 | 22250746 | 11513 | مصنع موبل الشرق لصناعة وتجارة منتجات الاخشاب | rowad | استوريا موبل الشرق ف/14134 12/2 003 مستخلص 2 |  | Procurement | Received | 2023-03-09 | Accounted transaction received
3919052 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 10.06. | Mat | 10 | SPECIALITIES | 67092 | 2023-03-07 | Materials |  |  |  | Materials | Alrowad Construction_OU | -5750 | 1 | استوريا موبل الشرق ف/14134 12/2 003 مستخلص 2 | 14134 | Currency | -5750 | 22250746 | 11513 | مصنع موبل الشرق لصناعة وتجارة منتجات الاخشاب | rowad | استوريا موبل الشرق ف/14134 12/2 003 مستخلص 2 |  | Procurement | Received | 2023-03-09 | Accounted transaction received
3932510 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 336.26 | 1 | بواط 10 * 10 عالى المقاس ¾ " |  | Each | 5 | 60701059 |  |  |  | بواط 10 * 10 عالى المقاس ¾ " | 030020100105 | MEP | Received | 2023-03-15 | Accounted transaction received
3897060 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 894.31 | 1 | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS |  | Each | 4 | 60316327 |  |  |  | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS | 030060100617 | MEP | Received | 2023-02-28 | Accounted transaction received
3897061 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1026.51 | 1 | UPVC BACK BOX 10X10 |  | Each | 45 | 60316328 |  |  |  | UPVC BACK BOX 10X10 | 030069000025 | MEP | Received | 2023-02-28 | Accounted transaction received
3897762 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-02-28 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 216535 | 1 | يوميات عماله الفتره 1 ش 02 الفعلي | يوميات عماله الفتره 1 ش 02 الفعلي | Currency | 216535 | 22193386 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 1 ش 02 الفعلي |  | Finacial | Received | 2023-02-28 | Accounted transaction received
3900555 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-02-28 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 720 | 1 | تسويه ك /108-109-111 - مهمات | st-108-109-111-2-23 | Currency | 720 | 22198956 | 2162 | Petty Cash | Ibrahim Ahmed Ibrahim Kabel | تسويه ك /108-109-111 - مهمات |  | Finacial | Received | 2023-03-01 | Accounted transaction received
3900556 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-02-28 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | -720 | 1 | تسويه ك /108-109-111 - مهمات | st-108-109-111-2-23 | Currency | -720 | 22198956 | 2162 | Petty Cash | Ibrahim Ahmed Ibrahim Kabel | تسويه ك /108-109-111 - مهمات |  | Finacial | Received | 2023-03-01 | Accounted transaction received
3900557 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-02-28 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 720 | 1 | تسويه ك /108-109-111 - مهمات | st-108-109-111-2-23. | Currency | 720 | 22198956 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /108-109-111 - مهمات |  | Finacial | Received | 2023-03-01 | Accounted transaction received
3900565 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.08 | Trafic Permission & | 17 | Indirect Cost |  | 2023-02-28 | Trafic Perm-Station Fees |  |  |  | Indirect | Alrowad Construction_OU | 6500 | 1 | تسوية22/23/24-م.سيارات | st-22/23/24-2-23 | Currency | 6500 | 22198956 | 2162 | Petty Cash | Mohamed Gamal Abdel Moneim Mohamed | تسوية22/23/24-م.سيارات |  | Finacial | Received | 2023-03-01 | Accounted transaction received
3900578 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-02-28 | Fees - stamp |  |  |  | Indirect | Alrowad Construction_OU | 5000 | 1 | تسويه ك / 1 -اعمال منتظمه بالمشاريع | st-1-2-23 | Currency | 5000 | 22198956 | 2162 | Petty Cash | Mohamed Ibrahim Abd El Rahman | تسويه ك / 1 -اعمال منتظمه بالمشاريع |  | Finacial | Received | 2023-03-01 | Accounted transaction received
3900579 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-02-28 | Fees - stamp |  |  |  | Indirect | Alrowad Construction_OU | 10000 | 1 | تسويه ك / 1 -اعمال منتظمه بالمشاريع | st-1-2-23 | Currency | 10000 | 22198956 | 2162 | Petty Cash | Mohamed Ibrahim Abd El Rahman | تسويه ك / 1 -اعمال منتظمه بالمشاريع |  | Finacial | Received | 2023-03-01 | Accounted transaction received
3901115 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-02-28 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 216535 | 1 | يوميات عماله الفتره 2 ش 2 التقديري | يوميات عماله الفتره 2 ش 2 التقديري | Currency | 216535 | 22200019 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 2 ش 2 التقديري |  | Finacial | Received | 2023-03-01 | Accounted transaction received
3901721 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK | 63247 | 2023-02-01 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 27787.5 | 1 | 3 Waldorf Astoria Cairo 63247/3 | 3 Waldorf Astoria Cairo 63247/3 | Currency | 27787.5 | 22201401 | 10037 | ايه وان للمقاولات | rowad | 3 Waldorf Astoria Cairo 63247/3 |  | Procurement | Received | 2023-03-01 | Accounted transaction received
3901722 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK | 63247 | 2023-02-01 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -125.04 | 1 | 3 Waldorf Astoria Cairo 63247/3 | 3 Waldorf Astoria Cairo 63247/3 | Currency | -125.04 | 22201401 | 10037 | ايه وان للمقاولات | rowad | 3 Waldorf Astoria Cairo 63247/3 |  | Procurement | Received | 2023-03-01 | Accounted transaction received
3901725 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -4043.41 | 1 | 7 Waldorf Astoria Cairo 67059/7 | 7 Waldorf Astoria Cairo 67059/7 | Currency | -4043.41 | 22201401 | 4820 | سيجاب للهندسه والتجاره | rowad | 7 Waldorf Astoria Cairo 67059/7 |  | Finacial | Received | 2023-03-01 | Accounted transaction received
3901726 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -9.51 | 1 | 7 Waldorf Astoria Cairo 67059/7 | 7 Waldorf Astoria Cairo 67059/7 | Currency | -9.51 | 22201401 | 4820 | سيجاب للهندسه والتجاره | rowad | 7 Waldorf Astoria Cairo 67059/7 |  | Finacial | Received | 2023-03-01 | Accounted transaction received
3901727 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-08 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 600 | 1 | 7 Waldorf Astoria Cairo 67059/7 | 7 Waldorf Astoria Cairo 67059/7 | Currency | 600 | 22201401 | 4820 | سيجاب للهندسه والتجاره | rowad | 7 Waldorf Astoria Cairo 67059/7 |  | Finacial | Received | 2023-03-01 | Accounted transaction received
3918238 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.07.05 | Gravel | 2 | SITE WORK |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1440 | 1 | 4.1 64204/9 |  | Currency | 12 |  | 8108 | سامى عياد فهيم حليم |  | 4.1 64204/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3909314 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-02-28 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 63625.74 | 1 |  | FA Depreciation from Dep.To Projects feb-23 | Currency | 63625.74 | 22223211 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-03-05 | Accounted transaction received
3909370 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-02-28 | Furniture Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 5725.73 | 1 |  | FA Depreciation from Dep.To Projects feb-23 | Currency | 5725.73 | 22223211 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-03-05 | Accounted transaction received
3909426 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-02-28 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 10402.27 | 1 |  | FA Depreciation from Dep.To Projects feb-23 | Currency | 10402.27 | 22223211 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-03-05 | Accounted transaction received
3910083 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2023-03-05 | Accomodation |  |  |  | Indirect | Alrowad Construction_OU | 5600 | 1 | ايجارات شهر 3 استوريا | ايجارات شهر 3 استوريا | Currency | 5600 | 22226174 | 2131 | Miscellaneous supplier | RME | ايجارات شهر 3 استوريا |  | Finacial | Received | 2023-03-06 | Accounted transaction received
3916087 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-02-28 | Hirings Payrool |  |  |  | Indirect | Alrowad Construction_OU | 1407181.52 | 1 | قيد مرتبات شهر فبراير 2023 | Salary-Feb-2023 | Currency | 1407181.52 | 22241286 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر فبراير 2023 |  | Finacial | Received | 2023-03-08 | Accounted transaction received
3916130 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-02-28 | Honouring of terrorism 0.0005 |  |  |  | Indirect | Alrowad Construction_OU | 401.44 | 1 | قيد مرتبات شهر فبراير 2023 | Salary-Feb-2023 | Currency | 401.44 | 22241286 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر فبراير 2023 |  | Finacial | Received | 2023-03-08 | Accounted transaction received
3916172 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.06 | Telephones | 17 | Indirect Cost |  | 2023-02-28 | Telephones |  |  |  | Indirect | Alrowad Construction_OU | -330.38 | 1 | قيد مرتبات شهر فبراير 2023 | Salary-Feb-2023 | Currency | -330.38 | 22241286 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر فبراير 2023 |  | Finacial | Received | 2023-03-08 | Accounted transaction received
3916211 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.02 | Health Care | 17 | Indirect Cost |  | 2023-02-28 | Medical Care |  |  |  | Direct Manpower | Alrowad Construction_OU | -3541.55 | 1 | قيد مرتبات شهر فبراير 2023 | Salary-Feb-2023 | Currency | -3541.55 | 22241286 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر فبراير 2023 |  | Finacial | Received | 2023-03-08 | Accounted transaction received
3916252 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-02-28 | Hirings Payrool |  |  |  | Indirect | Alrowad Construction_OU | -44966.59 | 1 | قيد مرتبات شهر فبراير 2023 | Salary-Feb-2023 | Currency | -44966.59 | 22241286 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر فبراير 2023 |  | Finacial | Received | 2023-03-08 | Accounted transaction received
3918237 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.07.05 | Gravel | 2 | SITE WORK |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2172 | 1 | 3.2 64204/9 |  | Currency | 6 |  | 8108 | سامى عياد فهيم حليم |  | 3.2 64204/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918240 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.07.05 | Gravel | 2 | SITE WORK |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -35.69 | 1 | LABOUR_OFFICE 64204/9 |  | Currency | -35.69 |  | 8108 | سامى عياد فهيم حليم |  | LABOUR_OFFICE 64204/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918244 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.03.02 | Repair | 2 | SITE WORK |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 46560 | 1 | 1.3 74900/5 |  | Currency | 388 |  | 8108 | سامى عياد فهيم حليم |  | 1.3 74900/5 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918245 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.03.02 | Repair | 2 | SITE WORK |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -209.52 | 1 | LABOUR_OFFICE 74900/5 |  | Currency | -209.52 |  | 8108 | سامى عياد فهيم حليم |  | LABOUR_OFFICE 74900/5 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918247 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 193800 | 1 | 1.21 61155/7 |  | Currency | 5 |  | 10847 | برونكس لتشغيل المعادن |  | 1.21 61155/7 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918248 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 26046.15 | 1 | 1.29 61155/7 |  | Currency | 61.75 |  | 10847 | برونكس لتشغيل المعادن |  | 1.29 61155/7 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918249 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 90617.18 | 1 | 1.77 61155/7 |  | Currency | 47 |  | 10847 | برونكس لتشغيل المعادن |  | 1.77 61155/7 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918250 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1928.03 | 1 | 1.78 61155/7 |  | Currency | 1 |  | 10847 | برونكس لتشغيل المعادن |  | 1.78 61155/7 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918251 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 10313.01 | 1 | 2.2 61155/7 |  | Currency | 24.45 |  | 10847 | برونكس لتشغيل المعادن |  | 2.2 61155/7 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918252 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 8664 | 1 | 2.13 61155/7 |  | Currency | 2 |  | 10847 | برونكس لتشغيل المعادن |  | 2.13 61155/7 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918253 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1491.16 | 1 | LABOUR_OFFICE 61155/7 |  | Currency | -1491.16 |  | 10847 | برونكس لتشغيل المعادن |  | LABOUR_OFFICE 61155/7 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918260 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 22019.81 | 1 | 1.1 62820/12 |  | Currency | 2.35 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 1.1 62820/12 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918261 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2529.93 | 1 | 1.2 62820/12 |  | Currency | 0.18 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 1.2 62820/12 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918262 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2951.59 | 1 | 1.3 62820/12 |  | Currency | 0.18 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 1.3 62820/12 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918263 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -123.76 | 1 | LABOUR_OFFICE 62820/12 |  | Currency | -123.76 |  | 11007 | الاسراء للمقاولات والتوريدات |  | LABOUR_OFFICE 62820/12 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3932511 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1111.02 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 4 | 60701060 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) | 030010000059 | MEP | Received | 2023-03-15 | Accounted transaction received
3932512 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2859.76 | 1 | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 |  | Meter | 30.5 | 60701061 |  |  |  | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 | 030020100002 | MEP | Received | 2023-03-15 | Accounted transaction received
3932513 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4102.86 | 1 | ماسورة صلب مجلفن EMT المقاس 1 " طول الماسورة 3.05 |  | Meter | 30.5 | 60701062 |  |  |  | ماسورة صلب مجلفن EMT المقاس 1 " طول الماسورة 3.05 | 030020100003 | MEP | Received | 2023-03-15 | Accounted transaction received
3932514 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 975.62 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 15 | 60701063 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-03-15 | Accounted transaction received
3932515 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 319.58 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 18 | 60701064 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-03-15 | Accounted transaction received
3932516 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 92.07 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 2 | 60701065 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-03-15 | Accounted transaction received
3932517 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 10333.62 | 1 | SHAVER SOCKET 230V/120-230V WITH EARTH CONNECTOR Code 572653 |  | Each | 15 | 60701066 |  |  |  | SHAVER SOCKET 230V/120-230V WITH EARTH CONNECTOR Code 572653 | 030060100178 | MEP | Received | 2023-03-15 | Accounted transaction received
3932518 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1348.26 | 1 | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 |  | Each | 3 | 60701067 |  |  |  | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 | 030060100572 | MEP | Received | 2023-03-15 | Accounted transaction received
3932519 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 670.74 | 1 | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS |  | Each | 3 | 60701068 |  |  |  | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS | 030060100617 | MEP | Received | 2023-03-15 | Accounted transaction received
3932520 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 19.01 | 1 | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 |  | Each | 1 | 60701069 |  |  |  | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 | 150020000178 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932541 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1539 | 1 | بكرة تيب فضي |  | Each | 30 | 60538825 |  |  |  | بكرة تيب فضي | 060019000005 | MEP | Received | 2023-03-15 | Accounted transaction received
3932521 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 437.24 | 1 | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 |  | Each | 23 | 60701070 |  |  |  | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 | 150020000178 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932522 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 10944 | 1 | Honeywell thermostat model (WS8B4WB/U) |  | Each | 20 | 60701071 |  |  |  | Honeywell thermostat model (WS8B4WB/U) | 060081900004 | MEP | Received | 2023-03-15 | Accounted transaction received
3932523 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2340.08 | 1 | Category 6A Field Terminated Plug and Boot with Black Latch Protector Clip |  | Each | 26 | 60701072 |  |  |  | Category 6A Field Terminated Plug and Boot with Black Latch Protector Clip | 031030000447 | MEP | Received | 2023-03-15 | Accounted transaction received
3932524 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2480.66 | 1 | CEILING MOUNT SPEAKER, Model No. PC-648R |  | Each | 6 | 60701073 |  |  |  | CEILING MOUNT SPEAKER, Model No. PC-648R | 031070000015 | MEP | Received | 2023-03-15 | Accounted transaction received
3932525 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 18298.37 | 1 | FLUSH MOUNT.STEEL BOX 1GD48 - IP44 code 89117 |  | Each | 880 | 60701124 |  |  |  | FLUSH MOUNT.STEEL BOX 1GD48 - IP44 code 89117 | 030060100540 | MEP | Received | 2023-03-15 | Accounted transaction received
3932526 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2092.99 | 1 | بستلة فوستر |  | Each | 1 | 60533582 |  |  |  | بستلة فوستر | 060019000039 | MEP | Received | 2023-03-15 | Accounted transaction received
3932527 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 12672.06 | 1 | Duct insulation (thikness 1" -density 24 kg/m3) |  | Each | 16 | 60533583 |  |  |  | Duct insulation (thikness 1" -density 24 kg/m3) | 060050300008 | MEP | Received | 2023-03-15 | Accounted transaction received
3932528 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1938 | 1 | Flexible air duct - insulated Diameter 6" |  | Meter | 20 | 60533584 |  |  |  | Flexible air duct - insulated Diameter 6" | 060041200015 | MEP | Received | 2023-03-15 | Accounted transaction received
3932529 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 16800 | 1 | Geberit Duofix element for wall?hung WC, 112 cm, with Alpha concealed cistern 12 cm Code : 458.233.00.1 |  | Each | 6 | 60533585 |  |  |  | Geberit Duofix element for wall?hung WC, 112 cm, with Alpha concealed cistern 12 cm Code : 458.233.00.1 | 060030200049 | MEP | Received | 2023-03-15 | Accounted transaction received
3932530 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1176.82 | 1 | Plenum Slot Diffuser 1" spacing for 1 Slot Length 1.2 Meter C/W galvanized round volume damper 6" |  | Each | 1 | 60533586 |  |  |  | Plenum Slot Diffuser 1" spacing for 1 Slot Length 1.2 Meter C/W galvanized round volume damper 6" | 060070300116 | MEP | Received | 2023-03-15 | Accounted transaction received
3932531 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 10474.78 | 1 | Plenum Slot Diffuser 1" spacing for 2 Slot Length 1.2 Meter C/W galvanized round volume damper 6" |  | Each | 8 | 60533587 |  |  |  | Plenum Slot Diffuser 1" spacing for 2 Slot Length 1.2 Meter C/W galvanized round volume damper 6" | 060070300120 | MEP | Received | 2023-03-15 | Accounted transaction received
3932532 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 40903.2 | 1 | CABLE ASB-CBL-12 |  | Meter | 138 | 60533588 |  |  |  | CABLE ASB-CBL-12 | 060170200132 | MEP | Received | 2023-03-15 | Accounted transaction received
3932533 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 68.4 | 1 | رولة دهان صغيرة |  | Each | 4 | 60538817 |  |  |  | رولة دهان صغيرة | 200010000074 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932534 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1368 | 1 | مسمار 16*100 بالصامولة و الورده |  | Each | 40 | 60538818 |  |  |  | مسمار 16*100 بالصامولة و الورده | 200020000020 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932535 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3420 | 1 | كوع حديد 1بوصة |  | Each | 60 | 60538819 |  |  |  | كوع حديد 1بوصة | 240010000090 | MEP | Received | 2023-03-15 | Accounted transaction received
3932536 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 969 | 1 | مواسير استانليس 51 مم |  | Meter | 4 | 60538820 |  |  |  | مواسير استانليس 51 مم | 150030000001 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932537 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 58.7 | 1 | جلبه لصق UPVC مقاس 75 مم ضغط رمادى |  | Each | 1 | 60538821 |  |  |  | جلبه لصق UPVC مقاس 75 مم ضغط رمادى | 060010100460 | MEP | Received | 2023-03-15 | Accounted transaction received
3932538 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 44.71 | 1 | طبه لصق UPVC مقاس 75 مم ضغط رمادى |  | Each | 1 | 60538822 |  |  |  | طبه لصق UPVC مقاس 75 مم ضغط رمادى | 060010100391 | MEP | Received | 2023-03-15 | Accounted transaction received
3932539 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 136.8 | 1 | صرف حوض |  | Each | 6 | 60538823 |  |  |  | صرف حوض | 200010000912 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932540 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1026 | 1 | بكرة تيفلون |  | Each | 30 | 60538824 |  |  |  | بكرة تيفلون | 060019000003 | MEP | Received | 2023-03-15 | Accounted transaction received
3932542 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 461.7 | 1 | برايمر |  | Each | 3 | 60538826 |  |  |  | برايمر | 060019000007 | MEP | Received | 2023-03-15 | Accounted transaction received
3932543 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 290.7 | 1 | وردة سوستة 10 مم |  | Kilogram | 3 | 60538827 |  |  |  | وردة سوستة 10 مم | 200020000193 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932544 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1140 | 1 | جلبة تطويل نيكل 20 مم 2/11 سم |  | Each | 50 | 60538828 |  |  |  | جلبة تطويل نيكل 20 مم 2/11 سم | 060019000021 | MEP | Received | 2023-03-15 | Accounted transaction received
3932545 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 114 | 1 | غيار رولة دهان صغيرة |  | Each | 10 | 60538829 |  |  |  | غيار رولة دهان صغيرة | 200010001439 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932546 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 410.4 | 1 | صامولة 10 مم |  | Kilogram | 3 | 60538830 |  |  |  | صامولة 10 مم | 200020000343 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932547 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 410.4 | 1 | جوان كاوتش 90 مم خاص بماسورة PVC رمادى |  | Each | 6 | 60538831 |  |  |  | جوان كاوتش 90 مم خاص بماسورة PVC رمادى | 060010100887 | MEP | Received | 2023-03-15 | Accounted transaction received
3932548 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 912 | 1 | كيما بوكس 165 |  | Can | 5 | 60539047 |  |  |  | كيما بوكس 165 | 050010000020 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932549 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 171 | 1 | مسمار صلب 5سم |  | Bag | 2 | 60539048 |  |  |  | مسمار صلب 5سم | 200020000074 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932550 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 57 | 1 | بنطة حدادي 8 مم |  | Each | 2 | 60539049 |  |  |  | بنطة حدادي 8 مم | 200010000342 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932551 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 262.2 | 1 | مكنسة بلدية |  | Each | 2 | 60539050 |  |  |  | مكنسة بلدية | 700010000044 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932552 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 20 | 1 | رزة |  | Each | 2 | 60539051 |  |  |  | رزة | 200010000653 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932553 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 184.75 | 1 | منظف زجاج |  | Each | 5 | 60539052 |  |  |  | منظف زجاج | 200010000693 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932554 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 171 | 1 | مسمار خشابي 6 سم |  | Kilogram | 2 | 60539053 |  |  |  | مسمار خشابي 6 سم | 200020000081 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932555 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2166 | 1 | سيكا جراوت 214 |  | Bag | 10 | 60539054 |  |  |  | سيكا جراوت 214 | 360010000033 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932556 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 5472 | 1 | الواح كونتر 1.22م*2.44م*18مم |  | Each | 6 | 60539055 |  |  |  | الواح كونتر 1.22م*2.44م*18مم | 090040000018 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932557 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 142.5 | 1 | أسطوانة قطعيه 4.5 بوصه بسكوته |  | Each | 5 | 60539056 |  |  |  | أسطوانة قطعيه 4.5 بوصه بسكوته | 039020200002 | MEP | Received | 2023-03-15 | Accounted transaction received
3932558 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 205.2 | 1 | سلسلة حديد |  | Meter | 4 | 60539057 |  |  |  | سلسلة حديد | 200010001129 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932559 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 250.8 | 1 | قفل عادى |  | Each | 4 | 60539058 |  |  |  | قفل عادى | 039020100060 | MEP | Received | 2023-03-15 | Accounted transaction received
3932560 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1624.5 | 1 | كيما بوكس 131 |  | Can | 3 | 60539059 |  |  |  | كيما بوكس 131 | 050010000089 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932561 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1482 | 1 | خواشة 75 مم |  | Each | 2 | 60539060 |  |  |  | خواشة 75 مم | 200010001494 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932562 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1448.45 | 1 | سيلكون عظم |  | Each | 10 | 60539061 |  |  |  | سيلكون عظم | 330040000420 | Equipment | Received | 2023-03-15 | Accounted transaction received
3932563 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 150 | 1 | قفل كمبيوتر 2.5 |  | Each | 2 | 60539062 |  |  |  | قفل كمبيوتر 2.5 | 200010001612 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932564 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 220 | 1 | سلك شبك فايبر 20سم |  | Roll | 2 | 60539063 |  |  |  | سلك شبك فايبر 20سم | 200010001675 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932565 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 513 | 1 | ورق جرائد |  | Kilogram | 10 | 60539064 |  |  |  | ورق جرائد | 200010001755 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932566 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 615.6 | 1 | اديبوند 65 |  | Kilogram | 4 | 60539065 |  |  |  | اديبوند 65 | 360010000273 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932567 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 114 | 1 | بنطة شنيور 6 مم |  | Each | 4 | 60539066 |  |  |  | بنطة شنيور 6 مم | 200010002134 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932568 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 541.5 | 1 | دهان ايبوكسى 131 |  | Gallon | 1 | 60539067 |  |  |  | دهان ايبوكسى 131 | 050010000356 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932569 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 32626.8 | 1 | Bisazza glass mosaic (Random Mix) Color: Blue Mix as close as possible to the existing Tile Size: 2*2 cm |  | Square Meter | 5.05 | 60539068 |  |  |  | Bisazza glass mosaic (Random Mix) Color: Blue Mix as close as possible to the existing Tile Size: 2*2 cm | 310010000024 | Fleets | Received | 2023-03-15 | Accounted transaction received
3932570 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 13530.77 | 1 | Bisazza glass mosaic - VTC 20.23 Color: Light Blue for jacuzzi stairs Tile Size: 2*2 cm |  | Square Meter | 3.43 | 60539069 |  |  |  | Bisazza glass mosaic - VTC 20.23 Color: Light Blue for jacuzzi stairs Tile Size: 2*2 cm | 310010000025 | Fleets | Received | 2023-03-15 | Accounted transaction received
3932571 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1815.69 | 1 | فلكسيبل معدن المقاس ¾ " |  | Meter | 73 | 60545758 |  |  |  | فلكسيبل معدن المقاس ¾ " | 030020100091 | MEP | Received | 2023-03-15 | Accounted transaction received
3932572 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 547.2 | 1 | فلكسيبل معدن المقاس ¾ " |  | Meter | 22 | 60545759 |  |  |  | فلكسيبل معدن المقاس ¾ " | 030020100091 | MEP | Received | 2023-03-15 | Accounted transaction received
3932573 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 672.51 | 1 | بواط 10 * 10 عالى المقاس ¾ " |  | Each | 10 | 60545760 |  |  |  | بواط 10 * 10 عالى المقاس ¾ " | 030020100105 | MEP | Received | 2023-03-15 | Accounted transaction received
3932574 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 555.51 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 2 | 60545761 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) | 030010000059 | MEP | Received | 2023-03-15 | Accounted transaction received
3932575 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 555.51 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 2 | 60545762 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) | 030010000059 | MEP | Received | 2023-03-15 | Accounted transaction received
3932576 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2859.76 | 1 | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 |  | Meter | 30.5 | 60545763 |  |  |  | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 | 030020100002 | MEP | Received | 2023-03-15 | Accounted transaction received
3932577 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 13680 | 1 | كابل نحاس مجدول شعر مقاس 2 × 1 مم (pvc/pvc) جهد (500/300) |  | Meter | 500 | 60545764 |  |  |  | كابل نحاس مجدول شعر مقاس 2 × 1 مم (pvc/pvc) جهد (500/300) | 030030100151 | MEP | Received | 2023-03-15 | Accounted transaction received
3932578 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1368 | 1 | غطاء بواط معدن مقاس 4*4 |  | Each | 200 | 60545765 |  |  |  | غطاء بواط معدن مقاس 4*4 | 030020100129 | MEP | Received | 2023-03-15 | Accounted transaction received
3932579 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 142.5 | 1 | اكستنشن 10*10 مقاس 3/4" |  | Each | 5 | 60545766 |  |  |  | اكستنشن 10*10 مقاس 3/4" | 030020100146 | MEP | Received | 2023-03-15 | Accounted transaction received
3932580 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 275.04 | 1 | SWITCH 20AX 1 WAY 1 MOD Code 572509 |  | Each | 2 | 60545767 |  |  |  | SWITCH 20AX 1 WAY 1 MOD Code 572509 | 030060100048 | MEP | Received | 2023-03-15 | Accounted transaction received
3932581 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1821.16 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 28 | 60545768 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-03-15 | Accounted transaction received
3932582 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2601.66 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 40 | 60545769 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-03-15 | Accounted transaction received
3932583 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 325.21 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 5 | 60545770 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-03-15 | Accounted transaction received
3932584 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1482.45 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 12 | 60545771 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-03-15 | Accounted transaction received
3932585 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 741.22 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 6 | 60545772 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-03-15 | Accounted transaction received
3932586 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 177.33 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 14 | 60545773 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-03-15 | Accounted transaction received
3932587 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 106.06 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 6 | 60545774 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-03-15 | Accounted transaction received
3932588 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 353.52 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 20 | 60545775 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-03-15 | Accounted transaction received
3932589 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 861.16 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 20 | 60545776 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-03-15 | Accounted transaction received
3932590 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 232.42 | 1 | PLATE 1SQ MOD SCH GRAPHITE Code 576552 |  | Each | 6 | 60545777 |  |  |  | PLATE 1SQ MOD SCH GRAPHITE Code 576552 | 030060100297 | MEP | Received | 2023-03-15 | Accounted transaction received
3932591 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2058.04 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 35 | 60545778 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-03-15 | Accounted transaction received
3932592 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2292.3 | 1 | 576562 Code وش مربع فضي |  | Each | 70 | 60545779 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-03-15 | Accounted transaction received
3932593 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 269.18 | 1 | CARRIER PLATE SYNERGY code 730094 |  | Each | 4 | 60545780 |  |  |  | CARRIER PLATE SYNERGY code 730094 | 030060100534 | MEP | Received | 2023-03-15 | Accounted transaction received
3932594 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 898.84 | 1 | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 |  | Each | 2 | 60545781 |  |  |  | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 | 030060100572 | MEP | Received | 2023-03-15 | Accounted transaction received
3932595 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1348.26 | 1 | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 |  | Each | 3 | 60545782 |  |  |  | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 | 030060100572 | MEP | Received | 2023-03-15 | Accounted transaction received
3932596 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3577.26 | 1 | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS |  | Each | 16 | 60545783 |  |  |  | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS | 030060100617 | MEP | Received | 2023-03-15 | Accounted transaction received
3932597 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 855.79 | 1 | mosaic adapter code 69580 |  | Each | 9 | 60545784 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-03-15 | Accounted transaction received
3932598 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 401.24 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 5 | 60545785 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-03-15 | Accounted transaction received
3932599 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2337.28 | 1 | FRAME 8 MOD MOSAIC ( Legrand 689658 ) |  | Each | 12 | 60545786 |  |  |  | FRAME 8 MOD MOSAIC ( Legrand 689658 ) | 030060100740 | MEP | Received | 2023-03-15 | Accounted transaction received
3932600 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 352.81 | 1 | Plate British standard Arteor - square - 3 modules - graphite - 575072 |  | Each | 6 | 60545787 |  |  |  | Plate British standard Arteor - square - 3 modules - graphite - 575072 | 030060100898 | MEP | Received | 2023-03-15 | Accounted transaction received
3932721 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1150.01 | 1 | جاسكت |  | Roll | 20 | 60634899 |  |  |  | جاسكت | 200010001335 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932601 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 26647.5 | 1 | Connector for Led strip - Acolyte |  | Each | 550 | 60545788 |  |  |  | Connector for Led strip - Acolyte | 030040700476 | MEP | Received | 2023-03-15 | Accounted transaction received
3932602 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1317.55 | 1 | WA PLATE - 77MM - 2X3MOD MOSA Code : 689677 |  | Each | 12 | 60545789 |  |  |  | WA PLATE - 77MM - 2X3MOD MOSA Code : 689677 | 030060100931 | MEP | Received | 2023-03-15 | Accounted transaction received
3932603 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3018.26 | 1 | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 |  | Each | 4 | 60545790 |  |  |  | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 | 030060100957 | MEP | Received | 2023-03-15 | Accounted transaction received
3932604 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3772.83 | 1 | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 |  | Each | 5 | 60545791 |  |  |  | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 | 030060100957 | MEP | Received | 2023-03-15 | Accounted transaction received
3932605 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 613.51 | 1 | سيفتي عمال |  | Each | 2 | 60545885 |  |  |  | سيفتي عمال | 010030000002 | Safety | Received | 2023-03-15 | Accounted transaction received
3932606 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 180.12 | 1 | كوزلك |  | Each | 2 | 60545886 |  |  |  | كوزلك | 010030000005 | Safety | Received | 2023-03-15 | Accounted transaction received
3932607 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 280.76 | 1 | خوذة صفراء |  | Each | 7 | 60545887 |  |  |  | خوذة صفراء | 010040000010 | Safety | Received | 2023-03-15 | Accounted transaction received
3932608 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 78.79 | 1 | فيست برتقالي |  | Each | 2 | 60545888 |  |  |  | فيست برتقالي | 010020000008 | Safety | Received | 2023-03-15 | Accounted transaction received
3932609 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 270 | 1 | اسمنت ابيض |  | Ton | 0.1 | 60545934 |  |  |  | اسمنت ابيض | 140010000001 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932610 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 513 | 1 | فوطة صفراء |  | Each | 10 | 60545935 |  |  |  | فوطة صفراء | 200010000478 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932611 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 114 | 1 | اسبراي فوم |  | Each | 1 | 60545936 |  |  |  | اسبراي فوم | 200010000471 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932612 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 79.8 | 1 | فرشة دهان 2 بوصة |  | Each | 2 | 60545937 |  |  |  | فرشة دهان 2 بوصة | 200010000870 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932613 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 76.95 | 1 | مسمار بورمة 10 سم |  | Kilogram | 0.5 | 60545938 |  |  |  | مسمار بورمة 10 سم | 200020000232 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932614 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 136.8 | 1 | بنطة رباط |  | Each | 15 | 60545939 |  |  |  | بنطة رباط | 200010001006 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932615 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 410.4 | 1 | معجون ممتاز |  | Bag | 3 | 60545940 |  |  |  | معجون ممتاز | 200010001077 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932616 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 50 | 1 | بنطة حدادى 6 مم |  | Each | 2 | 60545941 |  |  |  | بنطة حدادى 6 مم | 039020200004 | MEP | Received | 2023-03-15 | Accounted transaction received
3932617 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 171 | 1 | مفك صليبه كبير |  | Each | 5 | 60545942 |  |  |  | مفك صليبه كبير | 039020300013 | MEP | Received | 2023-03-15 | Accounted transaction received
3932618 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2280 | 1 | الواح ام دي اف MDF سمك 5 مم |  | Each | 8 | 60545943 |  |  |  | الواح ام دي اف MDF سمك 5 مم | 090040000023 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932619 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 150 | 1 | مشترك كهرباء 4 عين |  | Each | 1 | 60545944 |  |  |  | مشترك كهرباء 4 عين | 039010000030 | MEP | Received | 2023-03-15 | Accounted transaction received
3932620 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 444.6 | 1 | مسمار سن صاج 5 سم |  | Kilogram | 3 | 60545945 |  |  |  | مسمار سن صاج 5 سم | 200020000342 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932621 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 684 | 1 | سيلكون فواصل |  | Each | 10 | 60545946 |  |  |  | سيلكون فواصل | 330040000882 | Equipment | Received | 2023-03-15 | Accounted transaction received
3932622 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 763.8 | 1 | مسمار سن صاج 1.5 سم |  | Kilogram | 5 | 60545947 |  |  |  | مسمار سن صاج 1.5 سم | 200020000392 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932623 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 76.95 | 1 | مسمار بورمة 7.5 سم |  | Kilogram | 0.5 | 60545948 |  |  |  | مسمار بورمة 7.5 سم | 200020000483 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932624 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 228 | 1 | فرخ صنفرة 180 |  | Each | 2 | 60545949 |  |  |  | فرخ صنفرة 180 | 200010002002 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932625 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 855 | 1 | مادة لاصق لورق الحائط |  | Kilogram | 10 | 60545950 |  |  |  | مادة لاصق لورق الحائط | 050020000006 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932626 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 570 | 1 | تيب دوكو 2سم |  | Each | 20 | 60545951 |  |  |  | تيب دوكو 2سم | 200010002032 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932627 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 21318 | 1 | Master Seal NP 472 |  | Kit | 187 | 60545952 |  |  |  | Master Seal NP 472 | 360010000355 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932628 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 427.5 | 1 | فوطة حمام قطن |  | Each | 25 | 60545953 |  |  |  | فوطة حمام قطن | 700020000193 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932629 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 74812.5 | 1 | Ceramic fan shape wall tiles FS-026 Sheet Size 20*25 cm |  | Sheet | 700 | 60545954 |  |  |  | Ceramic fan shape wall tiles FS-026 Sheet Size 20*25 cm | 170010000654 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932630 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 277.76 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 1 | 60547606 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) | 030010000059 | MEP | Received | 2023-03-15 | Accounted transaction received
3932631 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2859.76 | 1 | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 |  | Meter | 30.5 | 60547607 |  |  |  | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 | 030020100002 | MEP | Received | 2023-03-15 | Accounted transaction received
3932632 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2859.76 | 1 | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 |  | Meter | 30.5 | 60547608 |  |  |  | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 | 030020100002 | MEP | Received | 2023-03-15 | Accounted transaction received
3932633 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 684 | 1 | غطاء بواط معدن مقاس 4*4 |  | Each | 100 | 60547609 |  |  |  | غطاء بواط معدن مقاس 4*4 | 030020100129 | MEP | Received | 2023-03-15 | Accounted transaction received
3932634 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 57 | 1 | اكستنشن 10*10 مقاس 3/4" |  | Each | 2 | 60547610 |  |  |  | اكستنشن 10*10 مقاس 3/4" | 030020100146 | MEP | Received | 2023-03-15 | Accounted transaction received
3932635 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1100.15 | 1 | SWITCH 20AX 1 WAY 1 MOD Code 572509 |  | Each | 8 | 60547611 |  |  |  | SWITCH 20AX 1 WAY 1 MOD Code 572509 | 030060100048 | MEP | Received | 2023-03-15 | Accounted transaction received
3932636 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2062.77 | 1 | SWITCH 20AX 1 WAY 1 MOD Code 572509 |  | Each | 15 | 60547612 |  |  |  | SWITCH 20AX 1 WAY 1 MOD Code 572509 | 030060100048 | MEP | Received | 2023-03-15 | Accounted transaction received
3932637 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 130.08 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 2 | 60547613 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-03-15 | Accounted transaction received
3932638 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 585.37 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 9 | 60547614 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-03-15 | Accounted transaction received
3932639 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 520.33 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 8 | 60547615 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-03-15 | Accounted transaction received
3932640 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 455.29 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 7 | 60547616 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-03-15 | Accounted transaction received
3932641 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1951.24 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 30 | 60547617 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-03-15 | Accounted transaction received
3932642 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 390.25 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 6 | 60547618 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-03-15 | Accounted transaction received
3932643 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 975.62 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 15 | 60547619 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-03-15 | Accounted transaction received
3932644 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1560.99 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 24 | 60547620 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-03-15 | Accounted transaction received
3932645 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1482.45 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 12 | 60547621 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-03-15 | Accounted transaction received
3932646 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4447.34 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 36 | 60547622 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-03-15 | Accounted transaction received
3932647 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4941.49 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 40 | 60547623 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-03-15 | Accounted transaction received
3932648 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 494.15 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 4 | 60547624 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-03-15 | Accounted transaction received
3932649 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3459.04 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 28 | 60547625 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-03-15 | Accounted transaction received
3932650 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 53.03 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 3 | 60547626 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-03-15 | Accounted transaction received
3932651 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 53.03 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 3 | 60547627 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-03-15 | Accounted transaction received
3932652 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 17.68 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 1 | 60547628 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-03-15 | Accounted transaction received
3932653 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 35.35 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 2 | 60547629 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-03-15 | Accounted transaction received
3932654 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 106.06 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 6 | 60547630 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-03-15 | Accounted transaction received
3932655 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 258.35 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 6 | 60547631 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-03-15 | Accounted transaction received
3932656 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 129.17 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 3 | 60547632 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-03-15 | Accounted transaction received
3932657 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 172.23 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 4 | 60547633 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-03-15 | Accounted transaction received
3932658 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 387.52 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 9 | 60547634 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-03-15 | Accounted transaction received
3932659 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 688.91 | 1 | SHAVER SOCKET 230V/120-230V WITH EARTH CONNECTOR Code 572653 |  | Each | 1 | 60547635 |  |  |  | SHAVER SOCKET 230V/120-230V WITH EARTH CONNECTOR Code 572653 | 030060100178 | MEP | Received | 2023-03-15 | Accounted transaction received
3932660 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 469.91 | 1 | FUSED 13A SWITCH +NEON SQ ALU Code 572651 |  | Each | 1 | 60547636 |  |  |  | FUSED 13A SWITCH +NEON SQ ALU Code 572651 | 030060100186 | MEP | Received | 2023-03-15 | Accounted transaction received
3932661 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 672.94 | 1 | CARRIER PLATE SYNERGY code 730094 |  | Each | 10 | 60547637 |  |  |  | CARRIER PLATE SYNERGY code 730094 | 030060100534 | MEP | Received | 2023-03-15 | Accounted transaction received
3932662 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 449.42 | 1 | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 |  | Each | 1 | 60547638 |  |  |  | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 | 030060100572 | MEP | Received | 2023-03-15 | Accounted transaction received
3932663 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2012.21 | 1 | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS |  | Each | 9 | 60547639 |  |  |  | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS | 030060100617 | MEP | Received | 2023-03-15 | Accounted transaction received
3932664 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1565.05 | 1 | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS |  | Each | 7 | 60547640 |  |  |  | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS | 030060100617 | MEP | Received | 2023-03-15 | Accounted transaction received
3932665 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2012.21 | 1 | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS |  | Each | 9 | 60547641 |  |  |  | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS | 030060100617 | MEP | Received | 2023-03-15 | Accounted transaction received
3932666 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 15680.79 | 1 | BACKBOX FOR 3 COMPARTMENTS LI ( Legrand 689634 ) |  | Each | 6 | 60547642 |  |  |  | BACKBOX FOR 3 COMPARTMENTS LI ( Legrand 689634 ) | 030060100739 | MEP | Received | 2023-03-15 | Accounted transaction received
3932667 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 584.32 | 1 | FRAME 8 MOD MOSAIC ( Legrand 689658 ) |  | Each | 3 | 60547643 |  |  |  | FRAME 8 MOD MOSAIC ( Legrand 689658 ) | 030060100740 | MEP | Received | 2023-03-15 | Accounted transaction received
3932668 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 779.09 | 1 | FRAME 8 MOD MOSAIC ( Legrand 689658 ) |  | Each | 4 | 60547644 |  |  |  | FRAME 8 MOD MOSAIC ( Legrand 689658 ) | 030060100740 | MEP | Received | 2023-03-15 | Accounted transaction received
3932669 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2337.28 | 1 | FRAME 8 MOD MOSAIC ( Legrand 689658 ) |  | Each | 12 | 60547645 |  |  |  | FRAME 8 MOD MOSAIC ( Legrand 689658 ) | 030060100740 | MEP | Received | 2023-03-15 | Accounted transaction received
3932670 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 876.84 | 1 | WA PLATE 77MM 2X2MOD MOSAIC ( Legrand 689673 ) |  | Each | 7 | 60547646 |  |  |  | WA PLATE 77MM 2X2MOD MOSAIC ( Legrand 689673 ) | 030060100741 | MEP | Received | 2023-03-15 | Accounted transaction received
3932671 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 878.37 | 1 | WA PLATE - 77MM - 2X3MOD MOSA Code : 689677 |  | Each | 8 | 60547647 |  |  |  | WA PLATE - 77MM - 2X3MOD MOSA Code : 689677 | 030060100931 | MEP | Received | 2023-03-15 | Accounted transaction received
3932672 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1509.13 | 1 | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 |  | Each | 2 | 60547648 |  |  |  | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 | 030060100957 | MEP | Received | 2023-03-15 | Accounted transaction received
3932673 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-06 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 13582.19 | 1 | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 |  | Each | 18 | 60547649 |  |  |  | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 | 030060100957 | MEP | Received | 2023-03-15 | Accounted transaction received
3932674 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3072.3 | 1 | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² |  | Kilogram | 55 | 60558665 |  |  |  | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² | 060040200001 | MEP | Received | 2023-03-15 | Accounted transaction received
3932675 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 374.03 | 1 | شنابر حزام للعزل |  | Kilogram | 17 | 60558666 |  |  |  | شنابر حزام للعزل | 060019000037 | MEP | Received | 2023-03-15 | Accounted transaction received
3932676 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 150.02 | 1 | كليبسات لشنابر العزل |  | Kilogram | 5 | 60558667 |  |  |  | كليبسات لشنابر العزل | 060019000038 | MEP | Received | 2023-03-15 | Accounted transaction received
3932677 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1900 | 1 | بستلة فوستر |  | Each | 1 | 60558668 |  |  |  | بستلة فوستر | 060019000039 | MEP | Received | 2023-03-15 | Accounted transaction received
3932678 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 23399.98 | 1 | Duct insulation (thikness 1" -density 24 kg/m3) |  | Each | 30 | 60558669 |  |  |  | Duct insulation (thikness 1" -density 24 kg/m3) | 060050300008 | MEP | Received | 2023-03-15 | Accounted transaction received
3932679 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-07 | Materials |  |  |  | Materials | Alrowad Construction_OU | -3072.3 | 1 | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² |  | Kilogram | -55 | 60559864 |  |  |  | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² | 060040200001 | MEP | Received | 2023-03-15 | Accounted transaction received
3932680 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1805.76 | 1 | ماسورة 20مم UPVC سمك ثقيل قطر خارجي 20 قطر داخلي 15.8مم اللفة= 34×3 متر(اللون أبيض) |  | Meter | 240 | 60566443 |  |  |  | ماسورة 20مم UPVC سمك ثقيل قطر خارجي 20 قطر داخلي 15.8مم اللفة= 34×3 متر(اللون أبيض) | 030010000051 | MEP | Received | 2023-03-15 | Accounted transaction received
3932681 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 177.62 | 1 | جلبة ماسورة 20مم UPVC (اللون أبيض) |  | Each | 100 | 60566444 |  |  |  | جلبة ماسورة 20مم UPVC (اللون أبيض) | 030010000067 | MEP | Received | 2023-03-15 | Accounted transaction received
3932682 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 168.15 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 50 | 60566445 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-03-15 | Accounted transaction received
3932683 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 168.15 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 50 | 60566446 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-03-15 | Accounted transaction received
3932684 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 324.16 | 1 | أدابتور UPVC لماسورة 20مم(اللون أبيض) |  | Each | 100 | 60566447 |  |  |  | أدابتور UPVC لماسورة 20مم(اللون أبيض) | 030010000096 | MEP | Received | 2023-03-15 | Accounted transaction received
3932685 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1172.66 | 1 | أدابتور UPVC لماسورة 25مم(اللون أبيض) |  | Each | 150 | 60566448 |  |  |  | أدابتور UPVC لماسورة 25مم(اللون أبيض) | 030010000097 | MEP | Received | 2023-03-15 | Accounted transaction received
3932686 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 661.2 | 1 | جلاند فلكسبل مقاس 16 مم |  | Each | 100 | 60566449 |  |  |  | جلاند فلكسبل مقاس 16 مم | 030010000167 | MEP | Received | 2023-03-15 | Accounted transaction received
3932687 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 684 | 1 | غطاء بواط معدن مقاس 4*4 |  | Each | 100 | 60566450 |  |  |  | غطاء بواط معدن مقاس 4*4 | 030020100129 | MEP | Received | 2023-03-15 | Accounted transaction received
3932688 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 325.21 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 5 | 60566451 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-03-15 | Accounted transaction received
3932689 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 325.21 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 5 | 60566452 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-03-15 | Accounted transaction received
3932690 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 86.12 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 2 | 60566453 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-03-15 | Accounted transaction received
3932691 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 833.44 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أصفر (cu/pvc) |  | Meter | 100 | 60566454 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أصفر (cu/pvc) | 030030101024 | MEP | Received | 2023-03-15 | Accounted transaction received
3932692 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1531.88 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) |  | Meter | 200 | 60566455 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) | 030030101026 | MEP | Received | 2023-03-15 | Accounted transaction received
3932693 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1622.23 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أصفر × أخضر (cu/pvc) |  | Meter | 200 | 60566456 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أصفر × أخضر (cu/pvc) | 030030101027 | MEP | Received | 2023-03-15 | Accounted transaction received
3932694 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 756.71 | 1 | سلك نحاس مجدول مقاس 3 مم اللون أزرق (cu/pvc) |  | Meter | 100 | 60566457 |  |  |  | سلك نحاس مجدول مقاس 3 مم اللون أزرق (cu/pvc) | 030030101020 | MEP | Received | 2023-03-15 | Accounted transaction received
3932695 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 475.44 | 1 | mosaic adapter code 69580 |  | Each | 5 | 60566458 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-03-15 | Accounted transaction received
3932696 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 401.24 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 5 | 60566459 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-03-15 | Accounted transaction received
3932697 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 492.41 | 1 | DS , 4 pole , 25A , 400V , abs enclosure IP 65 Code : KEM 425u y/r abs |  | Each | 1 | 60566460 |  |  |  | DS , 4 pole , 25A , 400V , abs enclosure IP 65 Code : KEM 425u y/r abs | 030060200072 | MEP | Received | 2023-03-15 | Accounted transaction received
3932698 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 291657.6 | 1 | Oak wood (WD-8) panel cladding |  | Square Meter | 78 | 60631781 |  |  |  | Oak wood (WD-8) panel cladding | 090011000008 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932699 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 114 | 1 | مربع / مدور - 12 * 10" / 25 سم خاص بالصاج المجلفن |  | Each | 1 | 60634839 |  |  |  | مربع / مدور - 12 * 10" / 25 سم خاص بالصاج المجلفن | 060040800006 | MEP | Received | 2023-03-15 | Accounted transaction received
3932700 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 228 | 1 | HVAC DUCT Square to Round , 12" ? 10" * 14 |  | Each | 1 | 60634840 |  |  |  | HVAC DUCT Square to Round , 12" ? 10" * 14 | 060040800041 | MEP | Received | 2023-03-15 | Accounted transaction received
3932701 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 456 | 1 | Duct Square to Round 26" * 18" Phi 18" |  | Each | 2 | 60634841 |  |  |  | Duct Square to Round 26" * 18" Phi 18" | 060040800059 | MEP | Received | 2023-03-15 | Accounted transaction received
3932702 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 228 | 1 | Duct Square to Round 18" * 16" Phi 18" |  | Each | 1 | 60634842 |  |  |  | Duct Square to Round 18" * 16" Phi 18" | 060040800060 | MEP | Received | 2023-03-15 | Accounted transaction received
3932703 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 228 | 1 | Duct Square to Round 24" * 14" Phi 18" |  | Each | 1 | 60634843 |  |  |  | Duct Square to Round 24" * 14" Phi 18" | 060040800061 | MEP | Received | 2023-03-15 | Accounted transaction received
3932704 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 228 | 1 | Duct Square to Round 24" * 12" Phi 18" |  | Each | 1 | 60634844 |  |  |  | Duct Square to Round 24" * 12" Phi 18" | 060040800062 | MEP | Received | 2023-03-15 | Accounted transaction received
3932705 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 228 | 1 | Duct Square to Round 20" * 12" Phi 12" |  | Each | 1 | 60634845 |  |  |  | Duct Square to Round 20" * 12" Phi 12" | 060040800063 | MEP | Received | 2023-03-15 | Accounted transaction received
3932706 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 228 | 1 | Duct Square to Round 16" * 10" Phi 12" |  | Each | 1 | 60634846 |  |  |  | Duct Square to Round 16" * 10" Phi 12" | 060040800064 | MEP | Received | 2023-03-15 | Accounted transaction received
3932707 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 228 | 1 | Duct Square to Round 18" * 14" Phi 12" |  | Each | 1 | 60634847 |  |  |  | Duct Square to Round 18" * 14" Phi 12" | 060040800065 | MEP | Received | 2023-03-15 | Accounted transaction received
3932708 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 228 | 1 | Duct Square to Round 24" * 12" Phi 12" |  | Each | 1 | 60634848 |  |  |  | Duct Square to Round 24" * 12" Phi 12" | 060040800066 | MEP | Received | 2023-03-15 | Accounted transaction received
3932709 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 228 | 1 | Duct Square to Round 20" * 10" Phi 10" |  | Each | 2 | 60634849 |  |  |  | Duct Square to Round 20" * 10" Phi 10" | 060040800069 | MEP | Received | 2023-03-15 | Accounted transaction received
3932710 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 114 | 1 | Duct Square to Round 14" * 10" Phi 10" |  | Each | 1 | 60634850 |  |  |  | Duct Square to Round 14" * 10" Phi 10" | 060040800070 | MEP | Received | 2023-03-15 | Accounted transaction received
3932711 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 114 | 1 | Duct Square to Round 16" * 10" Phi 6" |  | Each | 1 | 60634851 |  |  |  | Duct Square to Round 16" * 10" Phi 6" | 060040800071 | MEP | Received | 2023-03-15 | Accounted transaction received
3932712 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 228 | 1 | Duct Square to Round 10" * 6" Phi 6" |  | Each | 2 | 60634852 |  |  |  | Duct Square to Round 10" * 6" Phi 6" | 060040800072 | MEP | Received | 2023-03-15 | Accounted transaction received
3932713 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 228 | 1 | Duct Square to Round 12" * 10" Phi 12" |  | Each | 1 | 60634870 |  |  |  | Duct Square to Round 12" * 10" Phi 12" | 060040800067 | MEP | Received | 2023-03-15 | Accounted transaction received
3932714 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2599.2 | 1 | قلب خلاط 2/1 (نص ) بوصة |  | Each | 12 | 60634892 |  |  |  | قلب خلاط 2/1 (نص ) بوصة | 200010000169 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932715 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2280 | 1 | جلبة لحام 3بوصة الشريف |  | Each | 50 | 60634893 |  |  |  | جلبة لحام 3بوصة الشريف | 240020000043 | MEP | Received | 2023-03-15 | Accounted transaction received
3932716 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2565 | 1 | طبة تسليك مقاس 75 مم |  | Each | 50 | 60634894 |  |  |  | طبة تسليك مقاس 75 مم | 060010100189 | MEP | Received | 2023-03-15 | Accounted transaction received
3932717 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 997.5 | 1 | مشترك 90 درجه لصق UPVC مقاس 32 مم ضغط رمادى |  | Each | 25 | 60634895 |  |  |  | مشترك 90 درجه لصق UPVC مقاس 32 مم ضغط رمادى | 060010100367 | MEP | Received | 2023-03-15 | Accounted transaction received
3932718 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 50 | 1 | صرف حوض |  | Each | 1 | 60634896 |  |  |  | صرف حوض | 200010000912 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932719 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 32264.99 | 1 | بكرة تيب فضي |  | Each | 590 | 60634897 |  |  |  | بكرة تيب فضي | 060019000005 | MEP | Received | 2023-03-15 | Accounted transaction received
3932720 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1596 | 1 | بكرة تيب شفاف عرض 5 سم |  | Each | 70 | 60634898 |  |  |  | بكرة تيب شفاف عرض 5 سم | 060019000041 | MEP | Received | 2023-03-15 | Accounted transaction received
3932722 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.11 | Site Store | 17 | Indirect Cost |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 193.8 | 1 | شريط قياس 5م |  | Each | 2 | 60634947 |  |  |  | شريط قياس 5م | 200010000105 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932723 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.11 | Site Store | 17 | Indirect Cost |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2565 | 1 | تيب دوكو |  | Each | 90 | 60634948 |  |  |  | تيب دوكو | 200010000048 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932724 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.11 | Site Store | 17 | Indirect Cost |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 399 | 1 | مقص صاج |  | Each | 2 | 60634949 |  |  |  | مقص صاج | 200010000286 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932725 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.11 | Site Store | 17 | Indirect Cost |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 412.5 | 1 | بنطة هيلتي 6 مم بلس |  | Each | 15 | 60634950 |  |  |  | بنطة هيلتي 6 مم بلس | 200010000319 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932726 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.11 | Site Store | 17 | Indirect Cost |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 541.5 | 1 | بنطة معلقة 32 مم |  | Each | 1 | 60634951 |  |  |  | بنطة معلقة 32 مم | 200010000357 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932727 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.11 | Site Store | 17 | Indirect Cost |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 399 | 1 | مكنسة ناعمة |  | Each | 10 | 60634952 |  |  |  | مكنسة ناعمة | 200010000449 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932728 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.11 | Site Store | 17 | Indirect Cost |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 399 | 1 | فيشر 6 مم |  | Each | 200 | 60634953 |  |  |  | فيشر 6 مم | 200010000679 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932729 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.11 | Site Store | 17 | Indirect Cost |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 364.8 | 1 | تنر |  | Each | 4 | 60634954 |  |  |  | تنر | 060019000008 | MEP | Received | 2023-03-15 | Accounted transaction received
3932730 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.11 | Site Store | 17 | Indirect Cost |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 45 | 1 | قفل عادى |  | Each | 1 | 60634955 |  |  |  | قفل عادى | 039020100060 | MEP | Received | 2023-03-15 | Accounted transaction received
3932731 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.11 | Site Store | 17 | Indirect Cost |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 20 | 1 | رزة قفل |  | Each | 2 | 60634956 |  |  |  | رزة قفل | 039020100061 | MEP | Received | 2023-03-15 | Accounted transaction received
3932732 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.11 | Site Store | 17 | Indirect Cost |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 307.8 | 1 | مسمار سن صاج 5 سم |  | Kilogram | 2 | 60634957 |  |  |  | مسمار سن صاج 5 سم | 200020000342 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932733 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 6.04. | Wood Flooring | 6 | WOOD & PLASTIC WORK |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 28215 | 1 | Wood flooring Piano Podium wood |  | Square Meter | 9.9 | 60635370 |  |  |  | Wood flooring Piano Podium wood | 090040000098 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932734 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 75958.71 | 1 | Wall Paper WC-4 Solid vinyl fabric backed min weight 480/gr /sqm. Textured with geometric pattern in metallic color |  | Meter | 15 | 60639993 |  |  |  | Wall Paper WC-4 Solid vinyl fabric backed min weight 480/gr /sqm. Textured with geometric pattern in metallic color | 050020000014 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932735 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 41304.24 | 1 | Wall Paper WC-12 Ref Chipper-46859 Textured beige vinyl wall covering Fabric Backed Vinyl Fire rating : pass euroclass c /class 0 and 1 to BS476 |  | Meter | 27.42 | 60640001 |  |  |  | Wall Paper WC-12 Ref Chipper-46859 Textured beige vinyl wall covering Fabric Backed Vinyl Fire rating : pass euroclass c /class 0 and 1 to BS476 | 050020000021 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932736 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 227124.9 | 1 | Wall covering – WC-3 – Cole & Son- The Ardmore Collection, Narina Linen 109/10049 |  | Roll | 73 | 60640055 |  |  |  | Wall covering – WC-3 – Cole & Son- The Ardmore Collection, Narina Linen 109/10049 | 050020000013 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932737 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4560 | 1 | فلكسيبل معدن المقاس ¾ " |  | Meter | 300 | 60641822 |  |  |  | فلكسيبل معدن المقاس ¾ " | 030020100091 | MEP | Received | 2023-03-15 | Accounted transaction received
3932738 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 570 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 12مم وقطر خارجى 16.8مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 5 | 60641823 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 12مم وقطر خارجى 16.8مم طول اللفه 30 متر(اللون رمادى) | 030010000057 | MEP | Received | 2023-03-15 | Accounted transaction received
3932739 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 672.6 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 200 | 60641824 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-03-15 | Accounted transaction received
3932740 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2511.31 | 1 | ادابتور فلكسبل 25 مم |  | Each | 420 | 60641825 |  |  |  | ادابتور فلكسبل 25 مم | 030010000141 | MEP | Received | 2023-03-15 | Accounted transaction received
3932741 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5985 | 1 | بواط واتر بروف بفتحات مقاس 30 × 38 × 12 سم |  | Each | 15 | 60641826 |  |  |  | بواط واتر بروف بفتحات مقاس 30 × 38 × 12 سم | 030010000185 | MEP | Received | 2023-03-15 | Accounted transaction received
3932742 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5719.51 | 1 | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 |  | Meter | 61 | 60641827 |  |  |  | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 | 030020100002 | MEP | Received | 2023-03-15 | Accounted transaction received
3918267 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | 34860 | 1 | 67059/9 |  | Currency | 34860 |  | 4820 | سيجاب للهندسه والتجاره |  | 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918268 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 323 | 1 | 2.2.028 67059/9 |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.028 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918269 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 570 | 1 | 4.4.004 67059/9 |  | Currency | 12 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.004 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918270 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 380 | 1 | 4.4.005 67059/9 |  | Currency | 8 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.005 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918271 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 570 | 1 | 4.4.006 67059/9 |  | Currency | 12 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.006 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918272 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 190 | 1 | 4.4.007 67059/9 |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.007 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918273 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 617.5 | 1 | 4.4.008 67059/9 |  | Currency | 13 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.008 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918274 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 285 | 1 | 4.4.009 67059/9 |  | Currency | 6 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.009 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918275 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 500 | 1 | 5.5.051 67059/9 |  | Currency | 50 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.051 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918276 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 10 | 1 | 5.5.052 67059/9 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.052 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918277 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1656 | 1 | 5.5.054 67059/9 |  | Currency | 46 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.054 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918278 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 70 | 1 | 5.5.053 67059/9 |  | Currency | 7 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.053 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918279 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 432 | 1 | 5.5.055 67059/9 |  | Currency | 16 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.055 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918280 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1950 | 1 | 5.5.057 67059/9 |  | Currency | 52 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.057 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918281 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1950 | 1 | 5.5.058 67059/9 |  | Currency | 52 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.058 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918282 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 300 | 1 | 5.5.059 67059/9 |  | Currency | 8 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.059 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918283 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 363 | 1 | 5.5.06 67059/9 |  | Currency | 11 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.06 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918284 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 512.18 | 1 | 6.6.04 67059/9 |  | Currency | 9 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.04 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918285 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 137.38 | 1 | 6.6.041 67059/9 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.041 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918286 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 283.43 | 1 | 6.6.043 67059/9 |  | Currency | 3 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.043 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918287 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 500.18 | 1 | 6.6.044 67059/9 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.044 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918288 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3249 | 1 | 7.7.032 67059/9 |  | Currency | 38 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.032 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918289 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 85.5 | 1 | 7.7.035 67059/9 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.035 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918290 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 569.09 | 1 | 7.7.04 67059/9 |  | Currency | 10 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.04 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918291 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 581.4 | 1 | 7.7.044 67059/9 |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.044 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918292 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 571.83 | 1 | 7.7.08 67059/9 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.08 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918293 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 42.75 | 1 | 7.7.081 67059/9 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.081 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918294 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2289.26 | 1 | 8.8.037 67059/9 |  | Currency | 7 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.037 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918295 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1368 | 1 | 8.8.04 67059/9 |  | Currency | 16 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.04 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918296 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 341.45 | 1 | 8.8.042 67059/9 |  | Currency | 6 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.042 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918297 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 988 | 1 | 8.8.076 67059/9 |  | Currency | 10 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.076 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918298 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5400 | 1 | 5.5.025 67059/9 |  | Currency | 25 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.025 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3918299 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -121.89 | 1 | LABOUR_OFFICE 67059/9 |  | Currency | -121.89 |  | 4820 | سيجاب للهندسه والتجاره |  | LABOUR_OFFICE 67059/9 |  | Finacial | Received | 2023-03-09 | Accounted transaction received
3935275 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-03-16 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 14979.3 | 1 | 1.1 76599/2 |  | Currency | 213.99 |  | 12357 | عماد عبدالناصر ابراهيم حسين-ذاتى |  | 1.1 76599/2 |  | Finacial | Received | 2023-03-16 | Accounted transaction received
3935277 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-03-16 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 14979.3 | 1 | 1.1 76599/2 |  | Currency | 213.99 |  | 12357 | عماد عبدالناصر ابراهيم حسين-ذاتى |  | 1.1 76599/2 |  | Finacial | Received | 2023-03-16 | Accounted transaction received
3940266 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.06 | Material Transportat | 17 | Indirect Cost |  | 2023-03-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 116314.6 | 1 | Waldorf Astoria نقل ثقيل يناير 2023 | Waldorf Astoria نقل ثقيل يناير 2023 | Currency | 116314.6 | 22320355 | 4551 | الزمزم للنقل بالسيارات وتجارة وتوريدات مواد البناء | rowad | Waldorf Astoria نقل ثقيل يناير 2023 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3940336 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.06 | Material Transportat | 17 | Indirect Cost |  | 2023-03-12 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 163959 | 1 | اعمال نقل ثقيلWaldorf Astorie يناير 2023 | اعمال نقل ثقيلWaldorf Astorie يناير 2023 | Currency | 163959 | 22320355 | 2740 | حمدى محمود دياب غطاس | CAIRO | اعمال نقل ثقيلWaldorf Astorie يناير 2023 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3940360 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.06 | Material Transportat | 17 | Indirect Cost |  | 2023-03-12 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9120 | 1 | Waldorf Astoria نقل ثقيل يناير 2023 | Waldorf Astoria نقل ثقيل يناير 2023 | Currency | 9120 | 22320355 | 10410 | للنقل البرى للبضائع بالسيارات A.M.A | rowad | Waldorf Astoria نقل ثقيل يناير 2023 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3940392 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.06 | Material Transportat | 17 | Indirect Cost |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 46027 | 1 | - اعمال نقل شهر يناير 2023 waldorf نقل ثقيل 2023 | - اعمال نقل شهر يناير 2023 waldorf نقل ثقيل 2023 | Currency | 46027 | 22320355 | 710 | المصطفي للنقل (مصطفي سعد محمد ) | Egypt | - اعمال نقل شهر يناير 2023 waldorf نقل ثقيل 2023 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3940405 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.06 | Material Transportat | 17 | Indirect Cost |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 12105 | 1 | WALDORF ASTORIA اعمال النقل الثقيل يناير الثقيل | WALDORF ASTORIA اعمال النقل الثقيل يناير | Currency | 12105 | 22320355 | 3084 | محمد احمد محمد محمد | Rowad | WALDORF ASTORIA اعمال النقل الثقيل يناير الثقيل |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3932743 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 684 | 1 | غطاء بواط معدن مقاس 4*4 |  | Each | 100 | 60641828 |  |  |  | غطاء بواط معدن مقاس 4*4 | 030020100129 | MEP | Received | 2023-03-15 | Accounted transaction received
3932744 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 684 | 1 | غطاء بواط معدن مقاس 4*4 |  | Each | 100 | 60641829 |  |  |  | غطاء بواط معدن مقاس 4*4 | 030020100129 | MEP | Received | 2023-03-15 | Accounted transaction received
3932745 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 412.55 | 1 | SWITCH 20AX 1 WAY 1 MOD Code 572509 |  | Each | 3 | 60641830 |  |  |  | SWITCH 20AX 1 WAY 1 MOD Code 572509 | 030060100048 | MEP | Received | 2023-03-15 | Accounted transaction received
3932746 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 7544.8 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 116 | 60641831 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-03-15 | Accounted transaction received
3932747 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 370.61 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 3 | 60641832 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-03-15 | Accounted transaction received
3932748 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 71.02 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 4 | 60641833 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-03-15 | Accounted transaction received
3932749 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 387.37 | 1 | PLATE 1SQ MOD SCH GRAPHITE Code 576552 |  | Each | 10 | 60641834 |  |  |  | PLATE 1SQ MOD SCH GRAPHITE Code 576552 | 030060100297 | MEP | Received | 2023-03-15 | Accounted transaction received
3932750 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2058.04 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 35 | 60641835 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-03-15 | Accounted transaction received
3932751 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 20667.24 | 1 | SHAVER SOCKET 230V/120-230V WITH EARTH CONNECTOR Code 572653 |  | Each | 30 | 60641836 |  |  |  | SHAVER SOCKET 230V/120-230V WITH EARTH CONNECTOR Code 572653 | 030060100178 | MEP | Received | 2023-03-15 | Accounted transaction received
3932752 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2292.3 | 1 | 576562 Code وش مربع فضي |  | Each | 70 | 60641837 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-03-15 | Accounted transaction received
3932753 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1026 | 1 | Metal Galvanized back box 75x135 mm with deep 38 mm according to Specs (Section 16130) |  | Each | 50 | 60641838 |  |  |  | Metal Galvanized back box 75x135 mm with deep 38 mm according to Specs (Section 16130) | 030069000006 | MEP | Received | 2023-03-15 | Accounted transaction received
3932754 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 879.36 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أزرق (cu/pvc) |  | Meter | 100 | 60641839 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أزرق (cu/pvc) | 030030101025 | MEP | Received | 2023-03-15 | Accounted transaction received
3932755 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2297.82 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) |  | Meter | 300 | 60641840 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) | 030030101026 | MEP | Received | 2023-03-15 | Accounted transaction received
3932756 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2433.35 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أصفر × أخضر (cu/pvc) |  | Meter | 300 | 60641841 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أصفر × أخضر (cu/pvc) | 030030101027 | MEP | Received | 2023-03-15 | Accounted transaction received
3932757 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1592.14 | 1 | LID & TRIM 3 COMPARTMENTS GREY ( Legrand 689631 ) |  | Each | 2 | 60641842 |  |  |  | LID & TRIM 3 COMPARTMENTS GREY ( Legrand 689631 ) | 030060100738 | MEP | Received | 2023-03-15 | Accounted transaction received
3932758 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 10021 | 1 | Copper Cable UTP Cat6A, 4Pair, LSZH, Roll= 305Mt. |  | Each | 2 | 60641843 |  |  |  | Copper Cable UTP Cat6A, 4Pair, LSZH, Roll= 305Mt. | 031030000359 | MEP | Received | 2023-03-15 | Accounted transaction received
3932759 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 191.16 | 1 | Metal Galvanized back box 7x14 cm with deep 47 mm |  | Each | 8 | 60641844 |  |  |  | Metal Galvanized back box 7x14 cm with deep 47 mm | 030069000027 | MEP | Received | 2023-03-15 | Accounted transaction received
3932778 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3595.35 | 1 | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 |  | Each | 8 | 60642372 |  |  |  | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 | 030060100572 | MEP | Received | 2023-03-15 | Accounted transaction received
3932760 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2111.85 | 1 | Reading lamp - Recessed down light LED 12W, IP 65, 2700K, CRI 90, Optics 30°, Aluminum with textured powder coat finish body |  | Each | 1 | 60641845 |  |  |  | Reading lamp - Recessed down light LED 12W, IP 65, 2700K, CRI 90, Optics 30°, Aluminum with textured powder coat finish body | 030040700461 | MEP | Received | 2023-03-15 | Accounted transaction received
3932761 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 588.01 | 1 | Plate British standard Arteor - square - 3 modules - graphite - 575072 |  | Each | 10 | 60641846 |  |  |  | Plate British standard Arteor - square - 3 modules - graphite - 575072 | 030060100898 | MEP | Received | 2023-03-15 | Accounted transaction received
3932762 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 29960.41 | 1 | Acolyte - ARB95SWBC203. 027 - Rapid Ribbon 95+ - LED Strip with 9.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser |  | Each | 70 | 60641847 |  |  |  | Acolyte - ARB95SWBC203. 027 - Rapid Ribbon 95+ - LED Strip with 9.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser | 030040700471 | MEP | Received | 2023-03-15 | Accounted transaction received
3932763 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 6851.63 | 1 | Intelligent multi-criteria optical smoke and Heat detector - SIGA-OSHD |  | Each | 9 | 60641848 |  |  |  | Intelligent multi-criteria optical smoke and Heat detector - SIGA-OSHD | 031010000240 | MEP | Received | 2023-03-15 | Accounted transaction received
3932764 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 9473.86 | 1 | Audible (Sounder) Base - SIGA-AB4G |  | Each | 14 | 60641849 |  |  |  | Audible (Sounder) Base - SIGA-AB4G | 031010000243 | MEP | Received | 2023-03-15 | Accounted transaction received
3932765 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 47675.9 | 1 | Micro Switch Hafele/ Marckophon - 820.22.110/4321 - Switches 230 VDoor contact switches - Built-in switch |  | Each | 43 | 60641850 |  |  |  | Micro Switch Hafele/ Marckophon - 820.22.110/4321 - Switches 230 VDoor contact switches - Built-in switch | 030060200070 | MEP | Received | 2023-03-15 | Accounted transaction received
3932766 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 10396.8 | 1 | LED transformer - ET-E 10 W LED 220-240V |  | Each | 96 | 60641851 |  |  |  | LED transformer - ET-E 10 W LED 220-240V | 039019000062 | MEP | Received | 2023-03-15 | Accounted transaction received
3932767 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 247.36 | 1 | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 |  | Each | 2 | 60641852 |  |  |  | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 | 030060100951 | MEP | Received | 2023-03-15 | Accounted transaction received
3932768 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 340.9 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 6 | 60641853 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-03-15 | Accounted transaction received
3932769 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1710 | 1 | PVC Box 110x150x70 mm ip66 |  | Each | 15 | 60641854 |  |  |  | PVC Box 110x150x70 mm ip66 | 030069000031 | MEP | Received | 2023-03-15 | Accounted transaction received
3932770 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 36961.12 | 1 | Floor box 6 Module with double socket, space for 2 data socket complete with back box , IP66, Part Number GESR2 - OBO Germany |  | Each | 3 | 60641856 |  |  |  | Floor box 6 Module with double socket, space for 2 data socket complete with back box , IP66, Part Number GESR2 - OBO Germany | 030060100992 | MEP | Received | 2023-03-15 | Accounted transaction received
3932771 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1100.15 | 1 | SWITCH 20AX 1 WAY 1 MOD Code 572509 |  | Each | 8 | 60642365 |  |  |  | SWITCH 20AX 1 WAY 1 MOD Code 572509 | 030060100048 | MEP | Received | 2023-03-15 | Accounted transaction received
3932772 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 860 | 1 | FEMALE 3.5 MM JACK SOCKET - PRECONNECTED - 1M Code 572091 |  | Each | 1 | 60642366 |  |  |  | FEMALE 3.5 MM JACK SOCKET - PRECONNECTED - 1M Code 572091 | 030060100081 | MEP | Received | 2023-03-15 | Accounted transaction received
3932773 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2594.28 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 21 | 60642367 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-03-15 | Accounted transaction received
3932774 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 195.3 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 11 | 60642368 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-03-15 | Accounted transaction received
3932775 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1936.86 | 1 | PLATE 1SQ MOD SCH GRAPHITE Code 576552 |  | Each | 50 | 60642369 |  |  |  | PLATE 1SQ MOD SCH GRAPHITE Code 576552 | 030060100297 | MEP | Received | 2023-03-15 | Accounted transaction received
3932776 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 7433.6 | 1 | 576562 Code وش مربع فضي |  | Each | 227 | 60642370 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-03-15 | Accounted transaction received
3932777 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1884.24 | 1 | CARRIER PLATE SYNERGY code 730094 |  | Each | 28 | 60642371 |  |  |  | CARRIER PLATE SYNERGY code 730094 | 030060100534 | MEP | Received | 2023-03-15 | Accounted transaction received
3932779 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2459.36 | 1 | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS |  | Each | 11 | 60642373 |  |  |  | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS | 030060100617 | MEP | Received | 2023-03-15 | Accounted transaction received
3932780 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 95.09 | 1 | mosaic adapter code 69580 |  | Each | 1 | 60642374 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-03-15 | Accounted transaction received
3932781 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 125.26 | 1 | WA PLATE 77MM 2X2MOD MOSAIC ( Legrand 689673 ) |  | Each | 1 | 60642375 |  |  |  | WA PLATE 77MM 2X2MOD MOSAIC ( Legrand 689673 ) | 030060100741 | MEP | Received | 2023-03-15 | Accounted transaction received
3932782 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 912.46 | 1 | UPVC BACK BOX 10X10 |  | Each | 40 | 60642376 |  |  |  | UPVC BACK BOX 10X10 | 030069000025 | MEP | Received | 2023-03-15 | Accounted transaction received
3932783 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3020.87 | 1 | 4" Cone Speaker (70VRMS), Round - WHITE - 965-1A-4RW |  | Each | 4 | 60642377 |  |  |  | 4" Cone Speaker (70VRMS), Round - WHITE - 965-1A-4RW | 031010000244 | MEP | Received | 2023-03-15 | Accounted transaction received
3932784 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 401.55 | 1 | SPLASH PROOF COVER Code : 617636 |  | Each | 4 | 60642378 |  |  |  | SPLASH PROOF COVER Code : 617636 | 030060100927 | MEP | Received | 2023-03-15 | Accounted transaction received
3932785 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 123.68 | 1 | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 |  | Each | 1 | 60642379 |  |  |  | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 | 030060100951 | MEP | Received | 2023-03-15 | Accounted transaction received
3932786 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5281.96 | 1 | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 |  | Each | 7 | 60642380 |  |  |  | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 | 030060100957 | MEP | Received | 2023-03-15 | Accounted transaction received
3932787 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 792.3 | 1 | Full Mortise Ball Bearing Hinge For Wooden Doors Brand: Yale Art No.: 36-1000-0403-30-31-12 Size: 4''*3''*3'' Finish: Stainless Steel Unit: No. |  | Each | 5 | 60642759 |  |  |  | Full Mortise Ball Bearing Hinge For Wooden Doors Brand: Yale Art No.: 36-1000-0403-30-31-12 Size: 4''*3''*3'' Finish: Stainless Steel Unit: No. | 250010000260 | Procurement | Received | 2023-03-15 | Accounted transaction received
3932788 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 810.54 | 1 | Bathroom Lock Yale -Sss 20-H372-007S-60-31-11 |  | Each | 1 | 60642760 |  |  |  | Bathroom Lock Yale -Sss 20-H372-007S-60-31-11 | 250010000426 | Procurement | Received | 2023-03-15 | Accounted transaction received
3932789 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 377.34 | 1 | Lever Handle on rose with cyl. Escutcheon Yale SSS 35-SS04-T101-CE-31-11 |  | Each | 1 | 60642761 |  |  |  | Lever Handle on rose with cyl. Escutcheon Yale SSS 35-SS04-T101-CE-31-11 | 250010000875 | Procurement | Received | 2023-03-15 | Accounted transaction received
3932790 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 342 | 1 | Hardware Accessories for Wooden Doors Mortice lock without Double Cylinder TESA Entrance Mortice Lock without Cylinder - Sash lock for timber doors. |  | Each | 1 | 60642762 |  |  |  | Hardware Accessories for Wooden Doors Mortice lock without Double Cylinder TESA Entrance Mortice Lock without Cylinder - Sash lock for timber doors. | 250010001518 | Procurement | Received | 2023-03-15 | Accounted transaction received
3932791 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 285 | 1 | Push Plate - YALE - Code 30089028 - Art No. 35-9004-2102-00-31-50 |  | Each | 1 | 60642961 |  |  |  | Push Plate - YALE - Code 30089028 - Art No. 35-9004-2102-00-31-50 | 250010000321 | Procurement | Received | 2023-03-15 | Accounted transaction received
3932792 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 615.6 | 1 | Kick Plate ,, France Metal ,, ST.ST ,, Up to 200 x 1000 mm |  | Each | 1 | 60642962 |  |  |  | Kick Plate ,, France Metal ,, ST.ST ,, Up to 200 x 1000 mm | 250010000569 | Procurement | Received | 2023-03-15 | Accounted transaction received
3932793 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 684 | 1 | Hardware Accessories for Wooden Doors Mortice lock without Double Cylinder TESA Entrance Mortice Lock without Cylinder - Sash lock for timber doors. |  | Each | 2 | 60642963 |  |  |  | Hardware Accessories for Wooden Doors Mortice lock without Double Cylinder TESA Entrance Mortice Lock without Cylinder - Sash lock for timber doors. | 250010001518 | Procurement | Received | 2023-03-15 | Accounted transaction received
3932794 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 432.01 | 1 | Hardware Accessories for Wooden Doors Ball Catch Ball Catch Size:25.5x39mm Material: Brass Finish: NP TESA DDBC002 S.S.S |  | Each | 4 | 60642964 |  |  |  | Hardware Accessories for Wooden Doors Ball Catch Ball Catch Size:25.5x39mm Material: Brass Finish: NP TESA DDBC002 S.S.S | 250010001523 | Procurement | Received | 2023-03-15 | Accounted transaction received
3932795 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 35879.97 | 1 | Hardware Accessories For Wooden Doors Concealed Hinge Simonswerk completely concealed hinge system load capacity 120 kg two hinges per door leaf (1x2m) overall |  | Each | 6 | 60642965 |  |  |  | Hardware Accessories For Wooden Doors Concealed Hinge Simonswerk completely concealed hinge system load capacity 120 kg two hinges per door leaf (1x2m) overall | 250010001606 | Procurement | Received | 2023-03-15 | Accounted transaction received
3932796 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 44460 | 1 | Action floor spring max 180kg for Glass doors, brand Stanley |  | Each | 6 | 60642966 |  |  |  | Action floor spring max 180kg for Glass doors, brand Stanley | 310010000018 | Fleets | Received | 2023-03-15 | Accounted transaction received
3932797 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-03-11 | Wooden Doors |  |  |  | Materials | Waldorf Astoria-0164 | 4863.24 | 1 | Bathroom Lock Yale -Sss 20-H372-007S-60-31-11 |  | Each | 6 | 60643113 |  |  |  | Bathroom Lock Yale -Sss 20-H372-007S-60-31-11 | 250010000426 | Procurement | Received | 2023-03-15 | Accounted transaction received
3932798 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-03-11 | Wooden Doors |  |  |  | Materials | Waldorf Astoria-0164 | 1209.59 | 1 | Hardware Accessories for Wooden Doors Bathroom Mortice Lock for Sliding Doors with Thumb turn Cylinder Lock Hook AGB B089225034 Silver |  | Each | 4 | 60643114 |  |  |  | Hardware Accessories for Wooden Doors Bathroom Mortice Lock for Sliding Doors with Thumb turn Cylinder Lock Hook AGB B089225034 Silver | 250010001521 | Procurement | Received | 2023-03-15 | Accounted transaction received
3932799 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 581.4 | 1 | Hardware Accessories for Doors Eye Viewer VEKTR 1014/35-60XG-SN SN |  | Each | 6 | 60643115 |  |  |  | Hardware Accessories for Doors Eye Viewer VEKTR 1014/35-60XG-SN SN | 250010001572 | Procurement | Received | 2023-03-15 | Accounted transaction received
3932800 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.11 | Site Store | 17 | Indirect Cost |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1191.3 | 1 | تيب مسلح |  | Each | 25 | 60643620 |  |  |  | تيب مسلح | 200010000382 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932801 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.11 | Site Store | 17 | Indirect Cost |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 598.5 | 1 | زاوية فلسبيكو 5*5 |  | Each | 15 | 60643621 |  |  |  | زاوية فلسبيكو 5*5 | 200010000399 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932802 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.11 | Site Store | 17 | Indirect Cost |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 712.5 | 1 | خواشة 54 مم |  | Each | 1 | 60643622 |  |  |  | خواشة 54 مم | 200010000650 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932803 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.11 | Site Store | 17 | Indirect Cost |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3249 | 1 | سيكا جراوت 214 |  | Bag | 15 | 60643623 |  |  |  | سيكا جراوت 214 | 360010000033 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932804 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.11 | Site Store | 17 | Indirect Cost |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2172.56 | 1 | سيتوسيل 400 أبيض |  | Each | 15 | 60643624 |  |  |  | سيتوسيل 400 أبيض | 050010000066 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3932805 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.11 | Site Store | 17 | Indirect Cost |  | 2023-03-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 7068 | 1 | Master Seal NP 472 |  | Kit | 62 | 60643676 |  |  |  | Master Seal NP 472 | 360010000355 | Purchasing | Received | 2023-03-15 | Accounted transaction received
3942162 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | 29700 | 1 | 67059/8 |  | Currency | 29700 |  | 4820 | سيجاب للهندسه والتجاره |  | 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942163 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3240 | 1 | 2.2.003 67059/8 |  | Currency | 20 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.003 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942164 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1080 | 1 | 2.2.005 67059/8 |  | Currency | 6 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.005 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942165 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 8100 | 1 | 2.2.009 67059/8 |  | Currency | 6 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.009 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942166 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 152 | 1 | 2.2.013 67059/8 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.013 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942167 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 152 | 1 | 2.2.014 67059/8 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.014 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942168 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 532 | 1 | 2.2.015 67059/8 |  | Currency | 7 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.015 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942169 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 304 | 1 | 2.2.016 67059/8 |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.016 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942170 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1824 | 1 | 2.2.017 67059/8 |  | Currency | 24 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.017 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942171 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 532 | 1 | 2.2.018 67059/8 |  | Currency | 7 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.018 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942172 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1386 | 1 | 2.2.031 67059/8 |  | Currency | 7 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.031 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942173 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 396 | 1 | 2.2.032 67059/8 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.032 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942174 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2808 | 1 | 3.3.004 67059/8 |  | Currency | 13 |  | 4820 | سيجاب للهندسه والتجاره |  | 3.3.004 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942175 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4968 | 1 | 4.4.003 67059/8 |  | Currency | 23 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.003 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942176 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 456 | 1 | 4.4.004 67059/8 |  | Currency | 12 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.004 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942177 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 304 | 1 | 4.4.005 67059/8 |  | Currency | 8 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.005 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942178 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 152 | 1 | 4.4.007 67059/8 |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.007 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942179 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 456 | 1 | 4.4.006 67059/8 |  | Currency | 12 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.006 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942180 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 494 | 1 | 4.4.008 67059/8 |  | Currency | 13 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.008 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942181 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 228 | 1 | 4.4.009 67059/8 |  | Currency | 6 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.009 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942182 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3456 | 1 | 4.4.016 67059/8 |  | Currency | 16 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.016 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942183 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7680 | 1 | 5.5.051 67059/8 |  | Currency | 48 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.051 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942184 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 406.13 | 1 | 6.6.014 67059/8 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.014 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942185 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5557.5 | 1 | 6.6.019 67059/8 |  | Currency | 13 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.019 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942186 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1672 | 1 | 6.6.079 67059/8 |  | Currency | 8 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.079 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942187 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5940 | 1 | 6.6.084 67059/8 |  | Currency | 30 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.084 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942188 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2964 | 1 | 6.6.085 67059/8 |  | Currency | 13 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.085 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942189 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1368 | 1 | 7.7.006 67059/8 |  | Currency | 8 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.006 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942190 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2052 | 1 | 7.7.009 67059/8 |  | Currency | 12 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.009 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942191 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 338.44 | 1 | 7.7.013 67059/8 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.013 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942192 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 595.65 | 1 | 7.7.022 67059/8 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.022 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942193 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1944 | 1 | 7.7.098 67059/8 |  | Currency | 9 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.098 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942194 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 855 | 1 | 8.8.005 67059/8 |  | Currency | 5 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.005 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942195 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1965.65 | 1 | 8.8.098 67059/8 |  | Currency | 9 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.098 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942196 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 6384 | 1 | 9.9.002 67059/8 |  | Currency | 28 |  | 4820 | سيجاب للهندسه والتجاره |  | 9.9.002 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942197 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 342 | 1 | 9.9.013 67059/8 |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 9.9.013 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942198 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 82593 | 1 | 11.5 67059/8 |  | Currency | 1932 |  | 4820 | سيجاب للهندسه والتجاره |  | 11.5 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942199 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1064 | 1 | 8.8.076 67059/8 |  | Currency | 14 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.076 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942200 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3510 | 1 | 11.11 67059/8 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 11.11 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942201 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 560 | 1 | 5.5.023 67059/8 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.023 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942203 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1197 | 1 | 6.6.005 67059/8 |  | Currency | 7 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.005 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942204 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1710 | 1 | 6.6.006 67059/8 |  | Currency | 10 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.006 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942205 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -13500 | 1 | 7.7.099 67059/8 |  | Currency | -1 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.099 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942206 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 16610 | 1 | 11.6 67059/8 |  | Currency | 550 |  | 4820 | سيجاب للهندسه والتجاره |  | 11.6 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942207 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | -38500 | 1 | 67059/8 |  | Currency | -38500 |  | 4820 | سيجاب للهندسه والتجاره |  | 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942208 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -741.73 | 1 | LABOUR_OFFICE 67059/8 |  | Currency | -741.73 |  | 4820 | سيجاب للهندسه والتجاره |  | LABOUR_OFFICE 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942253 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | 29700 | 1 | 67059/8 |  | Currency | 29700 |  | 4820 | سيجاب للهندسه والتجاره |  | 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942254 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3240 | 1 | 2.2.003 67059/8 |  | Currency | 20 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.003 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942255 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1080 | 1 | 2.2.005 67059/8 |  | Currency | 6 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.005 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942256 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 8100 | 1 | 2.2.009 67059/8 |  | Currency | 6 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.009 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942257 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 152 | 1 | 2.2.013 67059/8 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.013 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942258 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 152 | 1 | 2.2.014 67059/8 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.014 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942259 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 532 | 1 | 2.2.015 67059/8 |  | Currency | 7 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.015 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942260 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 304 | 1 | 2.2.016 67059/8 |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.016 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942261 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1824 | 1 | 2.2.017 67059/8 |  | Currency | 24 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.017 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942262 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 532 | 1 | 2.2.018 67059/8 |  | Currency | 7 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.018 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942263 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1386 | 1 | 2.2.031 67059/8 |  | Currency | 7 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.031 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942264 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 396 | 1 | 2.2.032 67059/8 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.032 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942265 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2808 | 1 | 3.3.004 67059/8 |  | Currency | 13 |  | 4820 | سيجاب للهندسه والتجاره |  | 3.3.004 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942266 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4968 | 1 | 4.4.003 67059/8 |  | Currency | 23 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.003 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942267 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 456 | 1 | 4.4.004 67059/8 |  | Currency | 12 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.004 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942268 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 304 | 1 | 4.4.005 67059/8 |  | Currency | 8 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.005 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942269 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 152 | 1 | 4.4.007 67059/8 |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.007 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942270 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 456 | 1 | 4.4.006 67059/8 |  | Currency | 12 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.006 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942271 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 494 | 1 | 4.4.008 67059/8 |  | Currency | 13 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.008 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942272 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 228 | 1 | 4.4.009 67059/8 |  | Currency | 6 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.009 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942273 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3456 | 1 | 4.4.016 67059/8 |  | Currency | 16 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.016 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942274 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7680 | 1 | 5.5.051 67059/8 |  | Currency | 48 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.051 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942275 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 406.13 | 1 | 6.6.014 67059/8 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.014 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942276 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5557.5 | 1 | 6.6.019 67059/8 |  | Currency | 13 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.019 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942277 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1672 | 1 | 6.6.079 67059/8 |  | Currency | 8 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.079 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942278 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5940 | 1 | 6.6.084 67059/8 |  | Currency | 30 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.084 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942279 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2964 | 1 | 6.6.085 67059/8 |  | Currency | 13 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.085 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942280 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1368 | 1 | 7.7.006 67059/8 |  | Currency | 8 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.006 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942281 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2052 | 1 | 7.7.009 67059/8 |  | Currency | 12 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.009 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942282 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 338.44 | 1 | 7.7.013 67059/8 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.013 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942283 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 595.65 | 1 | 7.7.022 67059/8 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.022 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942284 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1944 | 1 | 7.7.098 67059/8 |  | Currency | 9 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.098 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942285 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 855 | 1 | 8.8.005 67059/8 |  | Currency | 5 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.005 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942286 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1965.65 | 1 | 8.8.098 67059/8 |  | Currency | 9 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.098 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942287 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 6384 | 1 | 9.9.002 67059/8 |  | Currency | 28 |  | 4820 | سيجاب للهندسه والتجاره |  | 9.9.002 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942288 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 342 | 1 | 9.9.013 67059/8 |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 9.9.013 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942289 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 82593 | 1 | 11.5 67059/8 |  | Currency | 1932 |  | 4820 | سيجاب للهندسه والتجاره |  | 11.5 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942290 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1064 | 1 | 8.8.076 67059/8 |  | Currency | 14 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.076 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942291 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3510 | 1 | 11.11 67059/8 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 11.11 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942292 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 560 | 1 | 5.5.023 67059/8 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.023 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942294 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1197 | 1 | 6.6.005 67059/8 |  | Currency | 7 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.005 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942295 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1710 | 1 | 6.6.006 67059/8 |  | Currency | 10 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.006 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942296 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -13500 | 1 | 7.7.099 67059/8 |  | Currency | -1 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.099 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942297 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 16610 | 1 | 11.6 67059/8 |  | Currency | 550 |  | 4820 | سيجاب للهندسه والتجاره |  | 11.6 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942298 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | -38500 | 1 | 67059/8 |  | Currency | -38500 |  | 4820 | سيجاب للهندسه والتجاره |  | 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942299 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -741.73 | 1 | LABOUR_OFFICE 67059/8 |  | Currency | -741.73 |  | 4820 | سيجاب للهندسه والتجاره |  | LABOUR_OFFICE 67059/8 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942344 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-03-15 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7318.85 | 1 | 1.1 74495/5 |  | Currency | 133.07 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | 1.1 74495/5 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942345 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-03-15 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2661.4 | 1 | 2.1 74495/5 |  | Currency | 133.07 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | 2.1 74495/5 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3942346 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-03-15 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -44.91 | 1 | LABOUR_OFFICE 74495/5 |  | Currency | -44.91 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | LABOUR_OFFICE 74495/5 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3943401 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-03-01 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | -216535 | 1 | يوميات عماله الفتره 2 ش 2 التقديري | يوميات عماله الفتره 2 ش 2 التقديري | Currency | -216535 | 22322682 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 2 ش 2 التقديري |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3940428 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2023-03-13 | Accomodation |  |  |  | Indirect | Alrowad Construction_OU | 41250 | 1 | تسويه ك / 130 ايجارات شهر مارس- استوريا | st-130-3-23. | Currency | 41250 | 22320355 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك / 130 ايجارات شهر مارس- استوريا |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3940429 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2023-03-13 | Accomodation |  |  |  | Indirect | Alrowad Construction_OU | -41250 | 1 | تسويه ك / 130 ايجارات شهر مارس- استوريا | st-130-3-23. | Currency | -41250 | 22320355 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك / 130 ايجارات شهر مارس- استوريا |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3940430 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2023-03-13 | Accomodation |  |  |  | Indirect | Alrowad Construction_OU | 41250 | 1 | تسويه ك / 130 ايجارات شهر مارس- استوريا | st-130-3-23.. | Currency | 41250 | 22320355 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك / 130 ايجارات شهر مارس- استوريا |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3940438 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.10 | Printers / Photo Cop | 17 | Indirect Cost |  | 2023-03-14 | Printers/Photo Copiers |  |  |  | Indirect | Alrowad Construction_OU | 24 | 1 | تسويه ك / 112-116-117-118-119-120-121-122-125-126-128 - متنوعات | st-112-116-117-118-119-120-121-122-125-126-128-3- | Currency | 24 | 22320355 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك / 112-116-117-118-119-120-121-122-125-126-128 - متنوعات |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3940439 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2023-03-14 | Stationary |  |  |  | Office and Site expenses | Alrowad Construction_OU | 200 | 1 | تسويه ك / 112-116-117-118-119-120-121-122-125-126-128 - متنوعات | st-112-116-117-118-119-120-121-122-125-126-128-3- | Currency | 200 | 22320355 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك / 112-116-117-118-119-120-121-122-125-126-128 - متنوعات |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3940440 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-03-14 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 14100 | 1 | تسويه ك / 112-116-117-118-119-120-121-122-125-126-128 - متنوعات | st-112-116-117-118-119-120-121-122-125-126-128-3- | Currency | 14100 | 22320355 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك / 112-116-117-118-119-120-121-122-125-126-128 - متنوعات |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3940441 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2023-03-14 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 6585.1 | 1 | تسويه ك / 112-116-117-118-119-120-121-122-125-126-128 - متنوعات | st-112-116-117-118-119-120-121-122-125-126-128-3- | Currency | 6585.1 | 22320355 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك / 112-116-117-118-119-120-121-122-125-126-128 - متنوعات |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3940472 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 10.06. | Mat | 10 | SPECIALITIES |  | 2023-03-14 | Bank Fees |  |  |  | Finance cost | Alrowad Construction_OU | 304420 | 1 | استوريا محمد امين ف/5 1/3 | 5 | Currency | 304420 | 22320355 | 6907 | محمد امين طلبه | rowad | استوريا محمد امين ف/5 1/3 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3940633 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.02 | Rented Cars | 17 | Indirect Cost |  | 2023-03-14 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 30330 | 1 | 4 Waldorf Astoria | 4 Waldorf Astoria | Currency | 30330 | 22320355 | 9182 | مؤسسة الجينيرال لتأجير السيارات | rowad | 4 Waldorf Astoria |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3940635 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.02 | Rented Cars | 17 | Indirect Cost |  | 2023-03-14 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 37500 | 1 | 4 Waldorf Astoria | 4 Waldorf Astoria | Currency | 37500 | 22320355 | 5214 | المتحدة لايجار وتوريد السيارات | rowad | 4 Waldorf Astoria |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3940662 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.02 | Rented Cars | 17 | Indirect Cost |  | 2023-03-14 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 19314.67 | 1 | 4 Waldorf Astoria | 4 Waldorf Astoria | Currency | 19314.67 | 22320355 | 3084 | محمد احمد محمد محمد | Rowad | 4 Waldorf Astoria |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3941272 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.03 | Hirings daily wages | 17 | Indirect Cost |  | 2023-03-16 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 70491.05 | 1 | يوميات عماله م08-astoria | يوميات عماله م08-astoria | Currency | 70491.05 | 22320355 | 12252 | حامد حسين احمد خالد – ذاتى | rowad | يوميات عماله م08-astoria |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3941279 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-03-16 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 189900 | 1 | يوميات عماله الفتره 2 ش 2 الفعلي | يوميات عماله الفتره 2 ش 2 الفعلي | Currency | 189900 | 22320355 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 2 ش 2 الفعلي |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3941473 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost | 71977 | 2023-03-19 | Materials |  |  |  | Materials | Alrowad Construction_OU | -2765.07 | 1 | 19515 USD C.M | 19515 USD C.M | Currency | -143.64 | 22320355 | 1026 | اوديو للتكنولوجيا Audio Technology | Egypt | 19515 USD C.M |  | Mechanical | Received | 2023-03-20 | Accounted transaction received
3941478 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-03-19 | Materials |  |  |  | Materials | Alrowad Construction_OU | 2765.07 | 1 | استوريا اوديو للتكنولوجيا ف/19515 21/2 117 | 19515 | Currency | 2765.07 | 22320355 | 1026 | اوديو للتكنولوجيا Audio Technology | Egypt | استوريا اوديو للتكنولوجيا ف/19515 21/2 117 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3941507 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.06 | Telephones | 17 | Indirect Cost |  | 2023-03-19 | Telephones |  |  |  | Indirect | Alrowad Construction_OU | 7013.51 | 1 | استحقاق ف اورانج عن ش ديسمبر2022 | استحقاق ف اورانج عن ش ديسمبر2022 | Currency | 7013.51 | 22320355 | 2135 | اورنج مصر للاتصالات | Egypt | استحقاق ف اورانج عن ش ديسمبر2022 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3941700 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-03-15 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | 13000 | 1 | 77834/2 |  | Currency | 13000 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | 77834/2 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3941701 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-03-15 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9126.7 | 1 | 1.1 77834/2 |  | Currency | 82.97 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | 1.1 77834/2 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3941702 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-03-15 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2470.4 | 1 | 1.2 77834/2 |  | Currency | 15.44 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | 1.2 77834/2 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3941703 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-03-15 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2300.8 | 1 | 1.3 77834/2 |  | Currency | 14.38 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | 1.3 77834/2 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3941704 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-03-15 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5464 | 1 | 1.4 77834/2 |  | Currency | 34.15 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | 1.4 77834/2 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3941705 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-03-15 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 978.75 | 1 | 2.1 77834/2 |  | Currency | 21.75 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | 2.1 77834/2 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3941706 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-03-15 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 849.2 | 1 | 2.2 77834/2 |  | Currency | 21.23 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | 2.2 77834/2 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3941707 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-03-15 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1289.25 | 1 | 2.3 77834/2 |  | Currency | 51.57 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | 2.3 77834/2 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3941708 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-03-15 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3136.5 | 1 | 3.1 77834/2 |  | Currency | 104.55 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | 3.1 77834/2 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3941709 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-03-15 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2550.3 | 1 | 3.2 77834/2 |  | Currency | 85.01 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | 3.2 77834/2 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3941710 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-03-15 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1080.9 | 1 | 3.3 77834/2 |  | Currency | 36.03 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | 3.3 77834/2 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3941711 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-03-15 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 8800 | 1 | 4.1 77834/2 |  | Currency | 80 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | 4.1 77834/2 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3941712 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-03-15 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | -29500 | 1 | 77834/2 |  | Currency | -29500 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | 77834/2 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3941713 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-03-15 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -171.21 | 1 | LABOUR_OFFICE 77834/2 |  | Currency | -171.21 |  | 12229 | النصر للمقاولات - هانى عاطف فرغلى سليمان |  | LABOUR_OFFICE 77834/2 |  | Finacial | Received | 2023-03-20 | Accounted transaction received
3965182 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-03-15 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1533.77 | 1 | سيفتي عمال |  | Each | 5 | 60718390 |  |  |  | سيفتي عمال | 010030000002 | Safety | Received | 2023-03-23 | Accounted transaction received
3965183 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-03-15 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 540.36 | 1 | كوزلك |  | Each | 6 | 60718391 |  |  |  | كوزلك | 010030000005 | Safety | Received | 2023-03-23 | Accounted transaction received
3965184 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-03-15 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 80.22 | 1 | خوذة صفراء |  | Each | 2 | 60718392 |  |  |  | خوذة صفراء | 010040000010 | Safety | Received | 2023-03-23 | Accounted transaction received
3965185 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-03-15 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 31.82 | 1 | جوانتي جلد ثقيل ( خرسانة ) |  | Each | 1 | 60718393 |  |  |  | جوانتي جلد ثقيل ( خرسانة ) | 010010000003 | Safety | Received | 2023-03-23 | Accounted transaction received
3965186 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-03-15 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 590.93 | 1 | فيست برتقالي |  | Each | 15 | 60718394 |  |  |  | فيست برتقالي | 010020000008 | Safety | Received | 2023-03-23 | Accounted transaction received
3965187 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-03-15 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 548.34 | 1 | Mortice Sash Lock Non Fire Rate Yale SSS 20-8560-0001-00-31-11 |  | Each | 1 | 60719341 |  |  |  | Mortice Sash Lock Non Fire Rate Yale SSS 20-8560-0001-00-31-11 | 250010000779 | Procurement | Received | 2023-03-23 | Accounted transaction received
3965188 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 471.87 | 1 | RJ45 SOCKET - CAT. 6 UTP - 8 CONTACTS - 1 MOD Code 572302 |  | Each | 3 | 60719734 |  |  |  | RJ45 SOCKET - CAT. 6 UTP - 8 CONTACTS - 1 MOD Code 572302 | 030060100031 | MEP | Received | 2023-03-23 | Accounted transaction received
3965189 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 195.12 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 3 | 60719735 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-03-23 | Accounted transaction received
3965190 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 88.77 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 5 | 60719736 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-03-23 | Accounted transaction received
3965191 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 106.53 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 6 | 60719737 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-03-23 | Accounted transaction received
3965192 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 177.54 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 10 | 60719738 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-03-23 | Accounted transaction received
3965193 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 104.99 | 1 | 576540 Code وش 1 فتحة |  | Each | 3 | 60719739 |  |  |  | 576540 Code وش 1 فتحة | 030060100266 | MEP | Received | 2023-03-23 | Accounted transaction received
3965194 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 387.37 | 1 | PLATE 1SQ MOD SCH GRAPHITE Code 576552 |  | Each | 10 | 60719740 |  |  |  | PLATE 1SQ MOD SCH GRAPHITE Code 576552 | 030060100297 | MEP | Received | 2023-03-23 | Accounted transaction received
3965195 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1764.04 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 30 | 60719741 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-03-23 | Accounted transaction received
3965196 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 196.48 | 1 | 576562 Code وش مربع فضي |  | Each | 6 | 60719742 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-03-23 | Accounted transaction received
3965197 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 13548.86 | 1 | LINE DYING DOWN 100 V 25-30 W Code 572784 |  | Each | 5 | 60719743 |  |  |  | LINE DYING DOWN 100 V 25-30 W Code 572784 | 030060100224 | MEP | Received | 2023-03-23 | Accounted transaction received
3965198 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 210 | 1 | Pop-up box to be equipped - 4 modules - matt aluminum finish code 54011 |  | Each | 1 | 60719744 |  |  |  | Pop-up box to be equipped - 4 modules - matt aluminum finish code 54011 | 030060100593 | MEP | Received | 2023-03-23 | Accounted transaction received
3965199 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 8600.16 | 1 | أنبوبة سليكون |  | Each | 200 | 60766779 |  |  |  | أنبوبة سليكون | 060019000001 | MEP | Received | 2023-03-23 | Accounted transaction received
3965200 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 265 | 1 | جلبة تطويل نيكل 2 سم |  | Each | 15 | 60766780 |  |  |  | جلبة تطويل نيكل 2 سم | 060019000020 | MEP | Received | 2023-03-23 | Accounted transaction received
3965201 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1385.78 | 1 | وصلة مرنة 50 سم |  | Each | 20 | 60766781 |  |  |  | وصلة مرنة 50 سم | 060021000009 | MEP | Received | 2023-03-23 | Accounted transaction received
3965202 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1425 | 1 | بكرة تيب شفاف عرض 5 سم |  | Each | 50 | 60766782 |  |  |  | بكرة تيب شفاف عرض 5 سم | 060019000041 | MEP | Received | 2023-03-23 | Accounted transaction received
3965203 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 456 | 1 | ورده مجلفنة 10 مم |  | Kilogram | 5 | 60766784 |  |  |  | ورده مجلفنة 10 مم | 030120700002 | MEP | Received | 2023-03-23 | Accounted transaction received
3965204 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 839.95 | 1 | مجموعة تطويل ضواغط لخزانات ألفا Duravit |  | Each | 12 | 60766785 |  |  |  | مجموعة تطويل ضواغط لخزانات ألفا Duravit | 060030100463 | MEP | Received | 2023-03-23 | Accounted transaction received
3965205 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 5472 | 1 | ASB-CBL-12 (sleeves) |  | Each | 120 | 60766786 |  |  |  | ASB-CBL-12 (sleeves) | 060170200059 | MEP | Received | 2023-03-23 | Accounted transaction received
3965206 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 11292.16 | 1 | External Duct Heater - 3.75 KW - C/W 2 Adaptor, Model : ZDH |  | Each | 2 | 60766787 |  |  |  | External Duct Heater - 3.75 KW - C/W 2 Adaptor, Model : ZDH | 060082100005 | MEP | Received | 2023-03-23 | Accounted transaction received
3965207 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 17753.9 | 1 | External Duct Heater - 4.5 KW - C/W 2 Adaptor, Model : ZDH |  | Each | 3 | 60766788 |  |  |  | External Duct Heater - 4.5 KW - C/W 2 Adaptor, Model : ZDH | 060082100006 | MEP | Received | 2023-03-23 | Accounted transaction received
3965208 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 7452.86 | 1 | External Duct Heater - 5.5 KW - C/W 2 Adaptor, Model : ZDH |  | Each | 1 | 60766789 |  |  |  | External Duct Heater - 5.5 KW - C/W 2 Adaptor, Model : ZDH | 060082100007 | MEP | Received | 2023-03-23 | Accounted transaction received
3965209 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3405.29 | 1 | External Duct Heater - 1.5 KW - C/W 2 Adaptor, Model : ZDH |  | Each | 1 | 60766790 |  |  |  | External Duct Heater - 1.5 KW - C/W 2 Adaptor, Model : ZDH | 060082100008 | MEP | Received | 2023-03-23 | Accounted transaction received
3965210 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 820.8 | 1 | Bracket ASB-CBL-12/18 |  | Each | 24 | 60766791 |  |  |  | Bracket ASB-CBL-12/18 | 060170200129 | MEP | Received | 2023-03-23 | Accounted transaction received
3965211 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3283.2 | 1 | Bracket ASB-CBL-12/18 |  | Each | 96 | 60766792 |  |  |  | Bracket ASB-CBL-12/18 | 060170200129 | MEP | Received | 2023-03-23 | Accounted transaction received
3965212 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4149.6 | 1 | CABLE ASB-CBL-12 |  | Meter | 14 | 60766793 |  |  |  | CABLE ASB-CBL-12 | 060170200132 | MEP | Received | 2023-03-23 | Accounted transaction received
3965253 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3249 | 1 | سيكا جراوت 214 |  | Bag | 15 | 60769732 |  |  |  | سيكا جراوت 214 | 360010000033 | Purchasing | Received | 2023-03-23 | Accounted transaction received
3965213 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4104 | 1 | Geberit connection set for Wall Hang WC, Length 8.5 cm code ( 152.422.46.1) |  | Each | 12 | 60766794 |  |  |  | Geberit connection set for Wall Hang WC, Length 8.5 cm code ( 152.422.46.1) | 060030200052 | MEP | Received | 2023-03-23 | Accounted transaction received
3965214 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 130.9 | 1 | كوع 90° EMT مجلفن المقاس ½ 1 " |  | Each | 2 | 60767460 |  |  |  | كوع 90° EMT مجلفن المقاس ½ 1 " | 030020100009 | MEP | Received | 2023-03-23 | Accounted transaction received
3965215 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 353.19 | 1 | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 |  | Each | 12 | 60767461 |  |  |  | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 | 030060100021 | MEP | Received | 2023-03-23 | Accounted transaction received
3965216 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 157.29 | 1 | RJ45 SOCKET - CAT. 6 UTP - 8 CONTACTS - 1 MOD Code 572302 |  | Each | 1 | 60767462 |  |  |  | RJ45 SOCKET - CAT. 6 UTP - 8 CONTACTS - 1 MOD Code 572302 | 030060100031 | MEP | Received | 2023-03-23 | Accounted transaction received
3965217 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1415.61 | 1 | RJ45 SOCKET - CAT. 6 UTP - 8 CONTACTS - 1 MOD Code 572302 |  | Each | 9 | 60767463 |  |  |  | RJ45 SOCKET - CAT. 6 UTP - 8 CONTACTS - 1 MOD Code 572302 | 030060100031 | MEP | Received | 2023-03-23 | Accounted transaction received
3965218 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 780.5 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 12 | 60767464 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-03-23 | Accounted transaction received
3965219 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 53.26 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 3 | 60767465 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-03-23 | Accounted transaction received
3965220 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 368.29 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 8 | 60767466 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-03-23 | Accounted transaction received
3965221 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 349.98 | 1 | PLATE 2SQ MOD F-G WHITE Code 576560 |  | Each | 10 | 60767467 |  |  |  | PLATE 2SQ MOD F-G WHITE Code 576560 | 030060100267 | MEP | Received | 2023-03-23 | Accounted transaction received
3965222 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 193.69 | 1 | PLATE 1SQ MOD SCH GRAPHITE Code 576552 |  | Each | 5 | 60767468 |  |  |  | PLATE 1SQ MOD SCH GRAPHITE Code 576552 | 030060100297 | MEP | Received | 2023-03-23 | Accounted transaction received
3965223 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 464.85 | 1 | PLATE 1SQ MOD SCH GRAPHITE Code 576552 |  | Each | 12 | 60767469 |  |  |  | PLATE 1SQ MOD SCH GRAPHITE Code 576552 | 030060100297 | MEP | Received | 2023-03-23 | Accounted transaction received
3965224 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 352.81 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 6 | 60767470 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-03-23 | Accounted transaction received
3965225 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2940.06 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 50 | 60767471 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-03-23 | Accounted transaction received
3965226 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4822.36 | 1 | SHAVER SOCKET 230V/120-230V WITH EARTH CONNECTOR Code 572653 |  | Each | 7 | 60767472 |  |  |  | SHAVER SOCKET 230V/120-230V WITH EARTH CONNECTOR Code 572653 | 030060100178 | MEP | Received | 2023-03-23 | Accounted transaction received
3965227 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1637.36 | 1 | 576562 Code وش مربع فضي |  | Each | 50 | 60767473 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-03-23 | Accounted transaction received
3965228 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 419.98 | 1 | COVER 4 M SQUARE 2X2 WHITE F 576000 Code 575080 |  | Each | 6 | 60767474 |  |  |  | COVER 4 M SQUARE 2X2 WHITE F 576000 Code 575080 | 030060100231 | MEP | Received | 2023-03-23 | Accounted transaction received
3965229 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1050 | 1 | Pop-up box to be equipped - 4 modules - matt aluminum finish code 54011 |  | Each | 5 | 60767475 |  |  |  | Pop-up box to be equipped - 4 modules - matt aluminum finish code 54011 | 030060100593 | MEP | Received | 2023-03-23 | Accounted transaction received
3965230 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1293.63 | 1 | Plate British standard Arteor - square - 3 modules - graphite - 575072 |  | Each | 22 | 60767476 |  |  |  | Plate British standard Arteor - square - 3 modules - graphite - 575072 | 030060100898 | MEP | Received | 2023-03-23 | Accounted transaction received
3965231 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3018.26 | 1 | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 |  | Each | 4 | 60767477 |  |  |  | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 | 030060100957 | MEP | Received | 2023-03-23 | Accounted transaction received
3965232 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1681.28 | 1 | بواط 10 * 10 عالى المقاس ¾ " |  | Each | 25 | 60768841 |  |  |  | بواط 10 * 10 عالى المقاس ¾ " | 030020100105 | MEP | Received | 2023-03-23 | Accounted transaction received
3965233 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 22878.04 | 1 | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 |  | Meter | 244 | 60768842 |  |  |  | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 | 030020100002 | MEP | Received | 2023-03-23 | Accounted transaction received
3965234 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 552.9 | 1 | لاكور ماسورة EMT المقاس ¾ " |  | Each | 25 | 60768843 |  |  |  | لاكور ماسورة EMT المقاس ¾ " | 030020100015 | MEP | Received | 2023-03-23 | Accounted transaction received
3965235 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 50.09 | 1 | أفيز أثنين جناح لماسورة EMT المقاس ¾ " |  | Each | 20 | 60768844 |  |  |  | أفيز أثنين جناح لماسورة EMT المقاس ¾ " | 030020100033 | MEP | Received | 2023-03-23 | Accounted transaction received
3965236 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 250 | 1 | شريط لحام اللون أحمر |  | Each | 10 | 60768845 |  |  |  | شريط لحام اللون أحمر | 030130400007 | MEP | Received | 2023-03-23 | Accounted transaction received
3965237 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2052 | 1 | جلاند بلاستيك مقاس 11 PG |  | Each | 300 | 60768846 |  |  |  | جلاند بلاستيك مقاس 11 PG | 030130500036 | MEP | Received | 2023-03-23 | Accounted transaction received
3965238 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 570 | 1 | اسبراي الوان |  | Each | 10 | 60768847 |  |  |  | اسبراي الوان | 200010001522 | Purchasing | Received | 2023-03-23 | Accounted transaction received
3965239 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 50 | 1 | مسمار سن صاج 1.5 سم |  | Kilogram | 0.5 | 60768848 |  |  |  | مسمار سن صاج 1.5 سم | 200020000392 | Purchasing | Received | 2023-03-23 | Accounted transaction received
3965240 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1026 | 1 | Wire Nut 4mm |  | Each | 15 | 60768849 |  |  |  | Wire Nut 4mm | 030130800016 | MEP | Received | 2023-03-23 | Accounted transaction received
3965241 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 741 | 1 | لاكور بواط على فليكسبل EMT المقاس 3/4 " |  | Each | 25 | 60768850 |  |  |  | لاكور بواط على فليكسبل EMT المقاس 3/4 " | 030020100214 | MEP | Received | 2023-03-23 | Accounted transaction received
3965242 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.11 | Site Store | 17 | Indirect Cost |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 171 | 1 | دفتر Material Request |  | Each | 10 | 60769641 |  |  |  | دفتر Material Request | 910010000269 | Administration | Received | 2023-03-23 | Accounted transaction received
3965243 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1140 | 1 | بكرة شريط لحام |  | Each | 50 | 60769692 |  |  |  | بكرة شريط لحام | 039010000003 | MEP | Received | 2023-03-23 | Accounted transaction received
3965244 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2593.5 | 1 | تيب دوكو |  | Each | 91 | 60769710 |  |  |  | تيب دوكو | 200010000048 | Purchasing | Received | 2023-03-23 | Accounted transaction received
3965245 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 28.5 | 1 | سكينة معجون صغيرة |  | Each | 1 | 60769711 |  |  |  | سكينة معجون صغيرة | 200010000081 | Purchasing | Received | 2023-03-23 | Accounted transaction received
3965246 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 79.8 | 1 | مساحة |  | Each | 2 | 60769712 |  |  |  | مساحة | 700010000011 | Purchasing | Received | 2023-03-23 | Accounted transaction received
3965247 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 71.5 | 1 | صابون سائل |  | Can | 2 | 60769713 |  |  |  | صابون سائل | 700020000013 | Purchasing | Received | 2023-03-23 | Accounted transaction received
3965248 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 39.9 | 1 | سلاح كتر |  | Each | 1 | 60769714 |  |  |  | سلاح كتر | 200010000411 | Purchasing | Received | 2023-03-23 | Accounted transaction received
3965249 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 513 | 1 | فوطة صفراء |  | Each | 10 | 60769715 |  |  |  | فوطة صفراء | 200010000478 | Purchasing | Received | 2023-03-23 | Accounted transaction received
3965250 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 370.5 | 1 | سلك مواعين |  | Kilogram | 5 | 60769716 |  |  |  | سلك مواعين | 700020000122 | Purchasing | Received | 2023-03-23 | Accounted transaction received
3965251 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4902 | 1 | Master Seal NP 472 |  | Kit | 43 | 60769717 |  |  |  | Master Seal NP 472 | 360010000355 | Purchasing | Received | 2023-03-23 | Accounted transaction received
3965252 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 250.8 | 1 | خواشة 25 مم |  | Each | 1 | 60769731 |  |  |  | خواشة 25 مم | 200010000649 | Purchasing | Received | 2023-03-23 | Accounted transaction received
3965254 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 364.8 | 1 | خواشة 32 مم |  | Each | 1 | 60769733 |  |  |  | خواشة 32 مم | 200010000762 | Purchasing | Received | 2023-03-23 | Accounted transaction received
3965255 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 70 | 1 | قفل عادى |  | Each | 1 | 60769734 |  |  |  | قفل عادى | 039020100060 | MEP | Received | 2023-03-23 | Accounted transaction received
3965256 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 119.7 | 1 | ورق جرائد |  | Kilogram | 3 | 60769735 |  |  |  | ورق جرائد | 200010001755 | Purchasing | Received | 2023-03-23 | Accounted transaction received
3965257 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 342 | 1 | تيب دوكو 2سم |  | Each | 20 | 60769736 |  |  |  | تيب دوكو 2سم | 200010002032 | Purchasing | Received | 2023-03-23 | Accounted transaction received
3965258 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2342.7 | 1 | بولي ايثيلين 200 ميكرون شفاف |  | Kilogram | 27.4 | 60769789 |  |  |  | بولي ايثيلين 200 ميكرون شفاف | 040010000042 | Purchasing | Received | 2023-03-23 | Accounted transaction received
3965259 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2540.83 | 1 | مشمع اسود حفيف |  | Roll | 1 | 60769790 |  |  |  | مشمع اسود حفيف | 040010000055 | Purchasing | Received | 2023-03-23 | Accounted transaction received
3965260 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1200 | 1 | طقم مسمار تثبيت قاعدة حمام جانبى |  | Each | 1 | 60769794 |  |  |  | طقم مسمار تثبيت قاعدة حمام جانبى | 240070000282 | MEP | Received | 2023-03-23 | Accounted transaction received
3965261 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 24022.08 | 1 | Privacy Door Latch Brand Welder part # 43702424 Finish Silver |  | Each | 48 | 60769845 |  |  |  | Privacy Door Latch Brand Welder part # 43702424 Finish Silver | 250010001658 | Procurement | Received | 2023-03-23 | Accounted transaction received
3965262 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 130674.6 | 1 | Wall covering – WC-3 – Cole & Son- The Ardmore Collection, Narina Linen 109/10049 |  | Roll | 42 | 60769855 |  |  |  | Wall covering – WC-3 – Cole & Son- The Ardmore Collection, Narina Linen 109/10049 | 050020000013 | Purchasing | Received | 2023-03-23 | Accounted transaction received
3965263 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 12752.15 | 1 | Wall Paper WC-6 Monsoon Fact -75300-75310 textured wit geometric pattern in dark blue color Solid vinyl weight to be minimum of 480gr /sqm |  | Roll | 3 | 60769856 |  |  |  | Wall Paper WC-6 Monsoon Fact -75300-75310 textured wit geometric pattern in dark blue color Solid vinyl weight to be minimum of 480gr /sqm | 050020000016 | Purchasing | Received | 2023-03-23 | Accounted transaction received
3965264 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 236084.31 | 1 | Wall Paper WC-5 vinyl snake skin 8071 buttermilk racer wallcovering osnaburg backing anti-microbial additives untrimmed |  | linear yard | 175 | 60769857 |  |  |  | Wall Paper WC-5 vinyl snake skin 8071 buttermilk racer wallcovering osnaburg backing anti-microbial additives untrimmed | 050020000015 | Purchasing | Received | 2023-03-23 | Accounted transaction received
3965265 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-03-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 87688.46 | 1 | Wall Paper WC-7 vinyl snakeskin 8072 vicious venom Osnaburg backing anti-microbial Untrimmed |  | linear yard | 65 | 60769858 |  |  |  | Wall Paper WC-7 vinyl snakeskin 8072 vicious venom Osnaburg backing anti-microbial Untrimmed | 050020000017 | Purchasing | Received | 2023-03-23 | Accounted transaction received
3965266 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 35471.1 | 1 | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² |  | Kilogram | 635 | 60779139 |  |  |  | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² | 060040200001 | MEP | Received | 2023-03-23 | Accounted transaction received
3965267 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-03-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1227.02 | 1 | سيفتي عمال |  | Each | 4 | 60782292 |  |  |  | سيفتي عمال | 010030000002 | Safety | Received | 2023-03-23 | Accounted transaction received
3965268 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-03-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 90.06 | 1 | كوزلك |  | Each | 1 | 60782293 |  |  |  | كوزلك | 010030000005 | Safety | Received | 2023-03-23 | Accounted transaction received
3965269 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-03-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 41.04 | 1 | فيست ليموني |  | Each | 1 | 60782294 |  |  |  | فيست ليموني | 010020000009 | Safety | Received | 2023-03-23 | Accounted transaction received
3965270 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-19 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 277.76 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 1 | 60785268 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) | 030010000059 | MEP | Received | 2023-03-23 | Accounted transaction received
3965271 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-19 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 687.59 | 1 | SWITCH 20AX 1 WAY 1 MOD Code 572509 |  | Each | 5 | 60785269 |  |  |  | SWITCH 20AX 1 WAY 1 MOD Code 572509 | 030060100048 | MEP | Received | 2023-03-23 | Accounted transaction received
3965272 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-19 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1691.08 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 26 | 60785270 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-03-23 | Accounted transaction received
3965273 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-19 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 178.84 | 1 | TV "F" TYPE 1 MOD Code 572663 |  | Each | 2 | 60785271 |  |  |  | TV "F" TYPE 1 MOD Code 572663 | 030060100134 | MEP | Received | 2023-03-23 | Accounted transaction received
3965274 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-19 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1065.25 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 60 | 60785272 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-03-23 | Accounted transaction received
3965275 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-19 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 244.99 | 1 | PLATE 2SQ MOD F-G WHITE Code 576560 |  | Each | 7 | 60785273 |  |  |  | PLATE 2SQ MOD F-G WHITE Code 576560 | 030060100267 | MEP | Received | 2023-03-23 | Accounted transaction received
3965276 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-19 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 244.99 | 1 | PLATE 2SQ MOD F-G WHITE Code 576560 |  | Each | 7 | 60785274 |  |  |  | PLATE 2SQ MOD F-G WHITE Code 576560 | 030060100267 | MEP | Received | 2023-03-23 | Accounted transaction received
3965277 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-19 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 489.97 | 1 | COVER 4 M SQUARE 2X2 WHITE F 576000 Code 575080 |  | Each | 7 | 60785275 |  |  |  | COVER 4 M SQUARE 2X2 WHITE F 576000 Code 575080 | 030060100231 | MEP | Received | 2023-03-23 | Accounted transaction received
3965278 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-19 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2033.49 | 1 | سلك نحاس مجدول مقاس4 مم اللون أحمر (cu/pvc) |  | Meter | 200 | 60785276 |  |  |  | سلك نحاس مجدول مقاس4 مم اللون أحمر (cu/pvc) | 030030101023 | MEP | Received | 2023-03-23 | Accounted transaction received
3965279 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-19 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1797.67 | 1 | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 |  | Each | 4 | 60785277 |  |  |  | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 | 030060100572 | MEP | Received | 2023-03-23 | Accounted transaction received
3965280 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-19 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1079.51 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 19 | 60785278 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-03-23 | Accounted transaction received
3965281 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-03-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3498.03 | 1 | Hardware Accessories for Wooden Doors Privacy Door Latch Privacy Door Latch Welder 43702424 Silver |  | Each | 11 | 60786100 |  |  |  | Hardware Accessories for Wooden Doors Privacy Door Latch Privacy Door Latch Welder 43702424 Silver | 250010001514 | Procurement | Received | 2023-03-23 | Accounted transaction received
3965282 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-03-19 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 11010.12 | 1 | Privacy Door Latch Brand Welder part # 43702424 Finish Silver |  | Each | 22 | 60786101 |  |  |  | Privacy Door Latch Brand Welder part # 43702424 Finish Silver | 250010001658 | Procurement | Received | 2023-03-23 | Accounted transaction received
3967797 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 4.01. | Masonry Work | 4 | MASONRY WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 140.27 | 1 | 4.2 65733/5 |  | Currency | 31.17 |  | 9028 | مارينا للصناعات الخشبيه والمعدنيه-حنا منصور برسوم روفائيل |  | 4.2 65733/5 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967803 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 4.01. | Masonry Work | 4 | MASONRY WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -12.64 | 1 | LABOUR_OFFICE 65733/5 |  | Currency | -12.64 |  | 9028 | مارينا للصناعات الخشبيه والمعدنيه-حنا منصور برسوم روفائيل |  | LABOUR_OFFICE 65733/5 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967812 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 115600 | 1 | 1.1 78897/1 |  | Currency | 289 |  | 1222 | ابراهيم رجب سيد حسين (الشرق للمقاولات والتجارة) |  | 1.1 78897/1 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967813 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -520.2 | 1 | LABOUR_OFFICE 78897/1 |  | Currency | -520.2 |  | 1222 | ابراهيم رجب سيد حسين (الشرق للمقاولات والتجارة) |  | LABOUR_OFFICE 78897/1 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967815 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 52000 | 1 | 1.1.06 60674/8 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.06 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967816 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 118624 | 1 | 1.1.08 60674/8 |  | Currency | 16 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.08 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967817 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2040 | 1 | 1.1.02 60674/8 |  | Currency | 1.36 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.02 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967818 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5900 | 1 | 1.1.01 60674/8 |  | Currency | 4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.01 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967819 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5600 | 1 | 1.1.62 60674/8 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.62 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967820 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 10000 | 1 | 1.1.65 60674/8 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.65 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967821 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 28400 | 1 | 1.1.68 60674/8 |  | Currency | 14.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.68 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967822 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 690000 | 1 | 1.1.29 60674/8 |  | Currency | 23 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.29 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967823 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7920 | 1 | 1.1.76 60674/8 |  | Currency | 8.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.76 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967824 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 24000 | 1 | 1.1.7 60674/8 |  | Currency | 12 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.7 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967825 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 16000 | 1 | 1.1.64 60674/8 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.64 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967826 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 28400 | 1 | 1.1.69 60674/8 |  | Currency | 14.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.69 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967827 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1368 | 1 | 1.1.72 60674/8 |  | Currency | -0.72 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.72 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967828 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -2640 | 1 | 1.1.77 60674/8 |  | Currency | -2.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.77 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967829 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 222600 | 1 | 2.4 60674/8 |  | Currency | 1.2 |  | 10767 | النديم للصناعات المشربيه |  | 2.4 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967830 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 91300 | 1 | 2.6 60674/8 |  | Currency | 1 |  | 10767 | النديم للصناعات المشربيه |  | 2.6 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967832 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4700 | 1 | 1.1.81 60674/8 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.81 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967833 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7300 | 1 | 1.1.82 60674/8 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.82 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967834 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5760 | 1 | 1.1.83 60674/8 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.83 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967835 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 42500 | 1 | 1.1.85 60674/8 |  | Currency | 0.1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.85 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967836 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1429756 | 1 | 4.1 60674/8 |  | Currency | 1429756 |  | 10767 | النديم للصناعات المشربيه |  | 4.1 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967837 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 16000 | 1 | 1.1.14 60674/8 |  | Currency | 0.8 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.14 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967838 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 86000 | 1 | 1.1.9 60674/8 |  | Currency | 2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.9 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967839 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 20000 | 1 | 1.1.92 60674/8 |  | Currency | 0.1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.92 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967840 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 6270 | 1 | 1.1.115 60674/8 |  | Currency | 0.1 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.115 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967841 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 75400 | 1 | 1.1.12 60674/8 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.12 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967842 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 612200 | 1 | 1.1.121 60674/8 |  | Currency | 4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.121 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967843 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5927.6 | 1 | 1.1.122 60674/8 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.122 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967844 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 47700 | 1 | 1.1.119 60674/8 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.119 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967845 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 60950 | 1 | 2.9 60674/8 |  | Currency | 23 |  | 10767 | النديم للصناعات المشربيه |  | 2.9 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967846 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3840 | 1 | 1.1.186 60674/8 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.186 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967847 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4080 | 1 | 1.1.166 60674/8 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.166 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967848 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 10560 | 1 | 1.1.174 60674/8 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.174 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967849 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 10200 | 1 | 1.1.177 60674/8 |  | Currency | 0.6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.177 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967850 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3984 | 1 | 1.1.162 60674/8 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.162 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967851 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4800 | 1 | 1.1.163 60674/8 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.163 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967852 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7752 | 1 | 1.1.165 60674/8 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.165 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967853 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1920 | 1 | 1.1.184 60674/8 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.184 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967854 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4800 | 1 | 1.1.164 60674/8 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.164 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967855 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 184338 | 1 | 1.1.149 60674/8 |  | Currency | 1.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.149 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967856 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7524 | 1 | 2.10 60674/8 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 2.10 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967857 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 20160 | 1 | 1.1.196 60674/8 |  | Currency | 1.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.196 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967858 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 214200 | 1 | 1.1.198 60674/8 |  | Currency | 6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.198 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967860 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3840 | 1 | 1.1.188 60674/8 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.188 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967861 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1920 | 1 | 1.1.189 60674/8 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.189 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967862 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4608 | 1 | 1.1.191 60674/8 |  | Currency | 1.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.191 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967863 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5760 | 1 | 1.1.192 60674/8 |  | Currency | 0.6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.192 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967864 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 19200 | 1 | 1.1.193 60674/8 |  | Currency | 2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.193 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967865 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1920 | 1 | 1.1.187 60674/8 |  | Currency | 0.2 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.187 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967866 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 100800 | 1 | 1.1.195 60674/8 |  | Currency | 6 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.195 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967867 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4000 | 1 | 3.8 60674/8 |  | Currency | 0.4 |  | 10767 | النديم للصناعات المشربيه |  | 3.8 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967868 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | -1500 | 1 | 60674/8 |  | Currency | -1500 |  | 10767 | النديم للصناعات المشربيه |  | 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967869 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -19580.79 | 1 | LABOUR_OFFICE 60674/8 |  | Currency | -19580.79 |  | 10767 | النديم للصناعات المشربيه |  | LABOUR_OFFICE 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967891 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 200165.84 | 1 | 4.1 60674/8 |  | Currency | 0 |  | 10767 | النديم للصناعات المشربيه |  | 4.1 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3976108 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.10 | Printers / Photo Cop | 17 | Indirect Cost |  | 2023-03-28 | Printers/Photo Copiers |  |  |  | Indirect | Alrowad Construction_OU | 1000 | 1 | تصوير بالمشاريع | تصوير بالمشاريع | Currency | 1000 | 22463703 | 2131 | Miscellaneous supplier | RME | تصوير بالمشاريع |  | Finacial | Received | 2023-03-29 | Accounted transaction received
3976109 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.10 | Printers / Photo Cop | 17 | Indirect Cost |  | 2023-03-28 | Printers/Photo Copiers |  |  |  | Indirect | Alrowad Construction_OU | -1000 | 1 | تصوير بالمشاريع | تصوير بالمشاريع | Currency | -1000 | 22463703 | 2131 | Miscellaneous supplier | RME | تصوير بالمشاريع |  | Finacial | Received | 2023-03-29 | Accounted transaction received
3976110 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.10 | Printers / Photo Cop | 17 | Indirect Cost |  | 2023-03-28 | Printers/Photo Copiers |  |  |  | Indirect | Alrowad Construction_OU | 1000 | 1 | تصوير بالمشاريع | تصوير بالمشاريع | Currency | 1000 | 22463703 | 2131 | Miscellaneous supplier | RME | تصوير بالمشاريع |  | Finacial | Received | 2023-03-29 | Accounted transaction received
3976111 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.10 | Printers / Photo Cop | 17 | Indirect Cost |  | 2023-03-28 | Printers/Photo Copiers |  |  |  | Indirect | Alrowad Construction_OU | -1000 | 1 | تصوير بالمشاريع | تصوير بالمشاريع | Currency | -1000 | 22463703 | 2131 | Miscellaneous supplier | RME | تصوير بالمشاريع |  | Finacial | Received | 2023-03-29 | Accounted transaction received
3976116 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.10 | Printers / Photo Cop | 17 | Indirect Cost |  | 2023-03-28 | Printers/Photo Copiers |  |  |  | Indirect | Alrowad Construction_OU | 2000 | 1 | تصوير بالمشاريع | تصوير بالمشاريع. | Currency | 2000 | 22463703 | 7777 | محمد الشربيني على محمود خليل-ذاتى | rowad | تصوير بالمشاريع |  | Finacial | Received | 2023-03-29 | Accounted transaction received
3976394 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-29 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 285 | 1 | فيشر 8 مم |  | Carton | 10 | 61023754 |  |  |  | فيشر 8 مم | 200010000164 | Purchasing | Received | 2023-03-29 | Accounted transaction received
3976395 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-29 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3830.4 | 1 | فلكسيبل معدن المقاس ¾ " |  | Meter | 154 | 61023755 |  |  |  | فلكسيبل معدن المقاس ¾ " | 030020100091 | MEP | Received | 2023-03-29 | Accounted transaction received
3976396 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-29 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2736 | 1 | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) |  | Meter | 120 | 61023756 |  |  |  | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) | 030010000052 | MEP | Received | 2023-03-29 | Accounted transaction received
3976397 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-29 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 855 | 1 | شريط لحام اللون أحمر |  | Each | 50 | 61023757 |  |  |  | شريط لحام اللون أحمر | 030130400007 | MEP | Received | 2023-03-29 | Accounted transaction received
3976398 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-29 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 997.5 | 1 | فيشر 6 مم |  | Each | 7 | 61023758 |  |  |  | فيشر 6 مم | 200010000679 | Purchasing | Received | 2023-03-29 | Accounted transaction received
3976399 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-29 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 165.3 | 1 | افيز بلاستيك 50 سم |  | Each | 1 | 61023759 |  |  |  | افيز بلاستيك 50 سم | 200010000773 | Purchasing | Received | 2023-03-29 | Accounted transaction received
3976400 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-29 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 250.8 | 1 | ترامل بنز 6 مم |  | Each | 200 | 61023760 |  |  |  | ترامل بنز 6 مم | 030130700005 | MEP | Received | 2023-03-29 | Accounted transaction received
3976401 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-29 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 439.99 | 1 | شنابر حزام للعزل |  | Kilogram | 20 | 61023761 |  |  |  | شنابر حزام للعزل | 060019000037 | MEP | Received | 2023-03-29 | Accounted transaction received
3976402 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-29 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 150 | 1 | كليبسات لشنابر العزل |  | Kilogram | 5 | 61023762 |  |  |  | كليبسات لشنابر العزل | 060019000038 | MEP | Received | 2023-03-29 | Accounted transaction received
3976403 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-29 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 57 | 1 | حزام تيراب 30 سم |  | Each | 1 | 61023763 |  |  |  | حزام تيراب 30 سم | 200010001180 | Purchasing | Received | 2023-03-29 | Accounted transaction received
3976404 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-29 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 461.7 | 1 | مسمار مخ طاسة 6 مم بالورده و الصامولة |  | Kilogram | 3 | 61023764 |  |  |  | مسمار مخ طاسة 6 مم بالورده و الصامولة | 030120200001 | MEP | Received | 2023-03-29 | Accounted transaction received
3976405 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-03-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 513 | 1 | اسمنت ابيض |  | Ton | 0.15 | 61023808 |  |  |  | اسمنت ابيض | 140010000001 | Purchasing | Received | 2023-03-29 | Accounted transaction received
3976406 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-03-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 570 | 1 | اجنة تكسير هيلتي بلس |  | Each | 2 | 61023809 |  |  |  | اجنة تكسير هيلتي بلس | 200010000360 | Purchasing | Received | 2023-03-29 | Accounted transaction received
3976407 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-03-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 855 | 1 | فدية خرسانة 5 بوصة |  | Each | 6 | 61023810 |  |  |  | فدية خرسانة 5 بوصة | 200010000431 | Purchasing | Received | 2023-03-29 | Accounted transaction received
3976408 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-03-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 399 | 1 | مكنسة ناعمة |  | Each | 10 | 61023811 |  |  |  | مكنسة ناعمة | 200010000449 | Purchasing | Received | 2023-03-29 | Accounted transaction received
3976409 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-03-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 6498 | 1 | سيكا جراوت 214 |  | Bag | 30 | 61023812 |  |  |  | سيكا جراوت 214 | 360010000033 | Purchasing | Received | 2023-03-29 | Accounted transaction received
3976410 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-03-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 912 | 1 | كانة 200*50*30*2 مم |  | Each | 100 | 61023813 |  |  |  | كانة 200*50*30*2 مم | 200010000490 | Purchasing | Received | 2023-03-29 | Accounted transaction received
3976411 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-03-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 74.1 | 1 | مسمار خشابى 10 سم |  | Kilogram | 1 | 61023814 |  |  |  | مسمار خشابى 10 سم | 200020000307 | Purchasing | Received | 2023-03-29 | Accounted transaction received
3976412 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-03-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1795.5 | 1 | فوم ابيض 3 سم كثافة 20 كجم |  | Each | 35 | 61023815 |  |  |  | فوم ابيض 3 سم كثافة 20 كجم | 040010000089 | Purchasing | Received | 2023-03-29 | Accounted transaction received
3976413 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 285 | 1 | مسمار تك 1.50 سم |  | Kilogram | 2 | 61023827 |  |  |  | مسمار تك 1.50 سم | 200020000278 | Purchasing | Received | 2023-03-29 | Accounted transaction received
3976414 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 729.6 | 1 | مسامير سيلف دريل 8مم طول 3سم |  | Kilogram | 4 | 61023828 |  |  |  | مسامير سيلف دريل 8مم طول 3سم | 060191210002 | MEP | Received | 2023-03-29 | Accounted transaction received
3976415 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1900 | 1 | بستلة فوستر |  | Each | 1 | 61023829 |  |  |  | بستلة فوستر | 060019000039 | MEP | Received | 2023-03-29 | Accounted transaction received
3976416 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 8341.83 | 1 | بكرة تيب شفاف عرض 5 سم |  | Each | 180 | 61023830 |  |  |  | بكرة تيب شفاف عرض 5 سم | 060019000041 | MEP | Received | 2023-03-29 | Accounted transaction received
3976417 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 6156 | 1 | Extension for concealed bath and shower mixer |  | Each | 3 | 61023831 |  |  |  | Extension for concealed bath and shower mixer | 060031000119 | MEP | Received | 2023-03-29 | Accounted transaction received
3978030 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 789 | 1 | سخان قهوة |  | Each | 1 | 61029835 |  |  |  | سخان قهوة | 700020000116 | Purchasing | Received | 2023-03-30 | Accounted transaction received
3978179 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-03-29 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 235435 | 1 | يوميات عماله الفتره 1 ش 3 الفعلي | يوميات عماله الفتره 1 ش 3 الفعلي | Currency | 235435 | 22469338 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 1 ش 3 الفعلي |  | Finacial | Received | 2023-03-30 | Accounted transaction received
3978226 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-03-29 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 235435 | 1 | يوميات عماله الفتره 2 ش 3 التقديري | يوميات عماله الفتره 2 ش 3 التقديري | Currency | 235435 | 22469338 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 2 ش 3 التقديري |  | Finacial | Received | 2023-03-30 | Accounted transaction received
3978284 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-03-29 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 3074 | 1 | استوريا الماسه ف/25814 7/3 | 25814 | Currency | 3074 | 22469338 | 12416 | الماسه للتاجير ومعالجه المياه | rowad | استوريا الماسه ف/25814 7/3 |  | Finacial | Received | 2023-03-30 | Accounted transaction received
3981731 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -7016.54 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 25مم وقطر خارجى 31.1مم طول اللفه 30 متر(اللون رمادى) |  | Roll | -19 | 61046052 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 25مم وقطر خارجى 31.1مم طول اللفه 30 متر(اللون رمادى) | 030010000062 | MEP | Received | 2023-04-02 | Accounted transaction received
3981732 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -31526.11 | 1 | كابل نحاس مجدول مصمت مقاس 3 × 10 مم (xlpe/pvc) جهد (500/300) |  | Meter | -472 | 61046053 |  |  |  | كابل نحاس مجدول مصمت مقاس 3 × 10 مم (xlpe/pvc) جهد (500/300) | 030030100138 | MEP | Received | 2023-04-02 | Accounted transaction received
3981733 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -12313.82 | 1 | سلك نحاس مصمت مقاس 70 مم اللون أصفر × أخضر (cu/pvc) جهد (750/450) |  | Meter | -40 | 61046054 |  |  |  | سلك نحاس مصمت مقاس 70 مم اللون أصفر × أخضر (cu/pvc) جهد (750/450) | 030030100365 | MEP | Received | 2023-04-02 | Accounted transaction received
3981734 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -16520.22 | 1 | كابل نحاس ترمو ضغط منخفض مقاس 4 × 16 مم (xlpe/pvc) |  | Meter | -70 | 61046055 |  |  |  | كابل نحاس ترمو ضغط منخفض مقاس 4 × 16 مم (xlpe/pvc) | 030030100008 | MEP | Received | 2023-04-02 | Accounted transaction received
3981735 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -103794.72 | 1 | كابل نحاس ترمو ضغط منخفض مقاس 3 × 150 + 70 مم (xlpe/pvc) |  | Meter | -40 | 61046056 |  |  |  | كابل نحاس ترمو ضغط منخفض مقاس 3 × 150 + 70 مم (xlpe/pvc) | 030030100023 | MEP | Received | 2023-04-02 | Accounted transaction received
3981736 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -55404 | 1 | كابل نحاس ترمو ضغط منخفض مقاس 3 × 50 + 25 مم (xlpe/pvc) |  | Meter | -75 | 61046057 |  |  |  | كابل نحاس ترمو ضغط منخفض مقاس 3 × 50 + 25 مم (xlpe/pvc) | 030030100016 | MEP | Received | 2023-04-02 | Accounted transaction received
3981737 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -1197 | 1 | Threaded Mechanical Tee 2½''*1'' UL listed, FM approved |  | Each | -3 | 61046058 |  |  |  | Threaded Mechanical Tee 2½''*1'' UL listed, FM approved | 060011500213 | MEP | Received | 2023-04-02 | Accounted transaction received
3981738 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -798 | 1 | Threaded Mechanical Tee 2½''*1'' UL listed, FM approved |  | Each | -2 | 61046059 |  |  |  | Threaded Mechanical Tee 2½''*1'' UL listed, FM approved | 060011500213 | MEP | Received | 2023-04-02 | Accounted transaction received
3981739 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -5004.34 | 1 | Threaded Mechanical Tee 2.5''*1.25'' UL listed, FM approved |  | Each | -7 | 61046060 |  |  |  | Threaded Mechanical Tee 2.5''*1.25'' UL listed, FM approved | 060011500214 | MEP | Received | 2023-04-02 | Accounted transaction received
3981740 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -4305.52 | 1 | Threaded Mechanical Tee 2.5''*1.5'' UL listed, FM approved |  | Each | -5 | 61046061 |  |  |  | Threaded Mechanical Tee 2.5''*1.5'' UL listed, FM approved | 060011500215 | MEP | Received | 2023-04-02 | Accounted transaction received
3981741 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -1755.6 | 1 | 90° Elbow 2.50'' UL listed, FM approved |  | Each | -7 | 61046062 |  |  |  | 90° Elbow 2.50'' UL listed, FM approved | 060011500075 | MEP | Received | 2023-04-02 | Accounted transaction received
3981742 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -3009.6 | 1 | 90° Elbow 3'' UL listed, FM approved |  | Each | -6 | 61046063 |  |  |  | 90° Elbow 3'' UL listed, FM approved | 060011500076 | MEP | Received | 2023-04-02 | Accounted transaction received
3981743 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -2380.18 | 1 | Tee 4'' UL listed, FM approved |  | Each | -1 | 61046064 |  |  |  | Tee 4'' UL listed, FM approved | 060011500115 | MEP | Received | 2023-04-02 | Accounted transaction received
3981744 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -235.91 | 1 | Rigid Coupling 2'' UL listed, FM approved |  | Each | -1 | 61046065 |  |  |  | Rigid Coupling 2'' UL listed, FM approved | 060011500009 | MEP | Received | 2023-04-02 | Accounted transaction received
3981745 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -364.32 | 1 | Rigid Coupling 2.50'' UL listed, FM approved |  | Each | -4 | 61046066 |  |  |  | Rigid Coupling 2.50'' UL listed, FM approved | 060011500010 | MEP | Received | 2023-04-02 | Accounted transaction received
3981746 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -1140 | 1 | Threaded Mechanical Tee 4''*1'' UL listed, FM approved |  | Each | -2 | 61046067 |  |  |  | Threaded Mechanical Tee 4''*1'' UL listed, FM approved | 060011500223 | MEP | Received | 2023-04-02 | Accounted transaction received
3981747 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -1140 | 1 | Threaded Mechanical Tee 4''*1.25'' UL listed, FM approved |  | Each | -2 | 61046068 |  |  |  | Threaded Mechanical Tee 4''*1.25'' UL listed, FM approved | 060011500224 | MEP | Received | 2023-04-02 | Accounted transaction received
3981748 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -887.07 | 1 | Grooved Reducer 4''*3'' UL listed, FM approved |  | Each | -1 | 61046069 |  |  |  | Grooved Reducer 4''*3'' UL listed, FM approved | 060011500373 | MEP | Received | 2023-04-02 | Accounted transaction received
3981749 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -202837.43 | 1 | Custom Mosaic Wall feature (CT-9) |  | Square Meter | -36 | 61046070 |  |  |  | Custom Mosaic Wall feature (CT-9) | 170010000630 | Purchasing | Received | 2023-04-02 | Accounted transaction received
3981750 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4133.64 | 1 | سلك نحاس مجدول مقاس 6 مم اللون أسود (cu/pvc) |  | Meter | 200 | 61059672 |  |  |  | سلك نحاس مجدول مقاس 6 مم اللون أسود (cu/pvc) | 030030101031 | MEP | Received | 2023-04-02 | Accounted transaction received
3981751 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 336.26 | 1 | بواط 10 * 10 عالى المقاس ¾ " |  | Each | 5 | 61059692 |  |  |  | بواط 10 * 10 عالى المقاس ¾ " | 030020100105 | MEP | Received | 2023-04-02 | Accounted transaction received
3981752 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 442.32 | 1 | لاكور ماسورة EMT المقاس ¾ " |  | Each | 20 | 61059693 |  |  |  | لاكور ماسورة EMT المقاس ¾ " | 030020100015 | MEP | Received | 2023-04-02 | Accounted transaction received
3981753 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 17.24 | 1 | لاكور ماسورة EMT المقاس 1 " |  | Each | 2 | 61059694 |  |  |  | لاكور ماسورة EMT المقاس 1 " | 030020100016 | MEP | Received | 2023-04-02 | Accounted transaction received
3981754 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4253.24 | 1 | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser |  | Each | 10 | 61059695 |  |  |  | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser | 030040700472 | MEP | Received | 2023-04-02 | Accounted transaction received
3981755 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 247.36 | 1 | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 |  | Each | 2 | 61059696 |  |  |  | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 | 030060100951 | MEP | Received | 2023-04-02 | Accounted transaction received
3981756 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 618.41 | 1 | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 |  | Each | 5 | 61059697 |  |  |  | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 | 030060100951 | MEP | Received | 2023-04-02 | Accounted transaction received
3981757 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 227.27 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 4 | 61059698 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-04-02 | Accounted transaction received
3981758 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 227.27 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 4 | 61059699 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-04-02 | Accounted transaction received
3981759 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 158.03 | 1 | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 |  | Each | 2 | 61059700 |  |  |  | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 | 030060100956 | MEP | Received | 2023-04-02 | Accounted transaction received
3981760 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 70 | 1 | نظارة مهندسين M3 سوداء |  | Each | 2 | 61059708 |  |  |  | نظارة مهندسين M3 سوداء | 010060000005 | Safety | Received | 2023-04-02 | Accounted transaction received
3981761 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 45.6 | 1 | جوانتي باور جراب |  | Each | 2 | 61059709 |  |  |  | جوانتي باور جراب | 010010000009 | Safety | Received | 2023-04-02 | Accounted transaction received
3981762 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 150.48 | 1 | سدادة أذن |  | Each | 33 | 61059710 |  |  |  | سدادة أذن | 010020000015 | Safety | Received | 2023-04-02 | Accounted transaction received
3981763 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 17784 | 1 | Down Light IP 65 DAL 30250*035 AMBIANCE 100 DIRECTIONAL IP65 Recessed directional down lighter with satin silver reflector and white ceiling trim Overall diameter 100mm cut out diameter 90mm with PHILIPS LED Lamp 5.5W MR16 GU5.3, 2700K |  | Each | 5 | 61060589 |  |  |  | Down Light IP 65 DAL 30250*035 AMBIANCE 100 DIRECTIONAL IP65 Recessed directional down lighter with satin silver reflector and white ceiling trim Overall diameter 100mm cut out diameter 90mm with PHILIPS LED Lamp 5.5W MR16 GU5.3, 2700K | 030040700477 | MEP | Received | 2023-04-02 | Accounted transaction received
3982680 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-03-31 | Hirings Payrool |  |  |  | Indirect | Alrowad Construction_OU | 1294064.8 | 1 | قيد مرتبات شهر مارس 2023 | Salary-Mar-2023 | Currency | 1294064.8 | 22481631 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر مارس 2023 |  | Finacial | Received | 2023-04-02 | Accounted transaction received
3982722 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.02 | Health Care | 17 | Indirect Cost |  | 2023-03-31 | Honouring of terrorism 0.0005 |  |  |  | Indirect | Alrowad Construction_OU | 384.75 | 1 | قيد مرتبات شهر مارس 2023 | Salary-Mar-2023 | Currency | 384.75 | 22481631 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر مارس 2023 |  | Finacial | Received | 2023-04-02 | Accounted transaction received
3982763 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.06 | Telephones | 17 | Indirect Cost |  | 2023-03-31 | Telephones |  |  |  | Indirect | Alrowad Construction_OU | -543.16 | 1 | قيد مرتبات شهر مارس 2023 | Salary-Mar-2023 | Currency | -543.16 | 22481631 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر مارس 2023 |  | Finacial | Received | 2023-04-02 | Accounted transaction received
3982801 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.02 | Health Care | 17 | Indirect Cost |  | 2023-03-31 | Medical Care |  |  |  | Direct Manpower | Alrowad Construction_OU | -3541.55 | 1 | قيد مرتبات شهر مارس 2023 | Salary-Mar-2023 | Currency | -3541.55 | 22481631 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر مارس 2023 |  | Finacial | Received | 2023-04-02 | Accounted transaction received
3982842 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-03-31 | Hirings Payrool |  |  |  | Indirect | Alrowad Construction_OU | -48351.98 | 1 | قيد مرتبات شهر مارس 2023 | Salary-Mar-2023 | Currency | -48351.98 | 22481631 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر مارس 2023 |  | Finacial | Received | 2023-04-02 | Accounted transaction received
3983155 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-03-31 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 900 | 1 |  | FA Depreciation-march.23 | Currency | 900 | 22481631 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-04-02 | Accounted transaction received
3983156 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-03-31 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 2764.5 | 1 |  | FA Depreciation-march.23 | Currency | 2764.5 | 22481631 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-04-02 | Accounted transaction received
3983157 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-03-31 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 5469.17 | 1 |  | FA Depreciation-march.23 | Currency | 5469.17 | 22481631 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-04-02 | Accounted transaction received
3983158 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-03-31 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 14.98 | 1 |  | FA Depreciation-march.23 | Currency | 14.98 | 22481631 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-04-02 | Accounted transaction received
3983159 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-03-31 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 995.14 | 1 |  | FA Depreciation-march.23 | Currency | 995.14 | 22481631 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-04-02 | Accounted transaction received
3983160 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-03-31 | Furniture Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 8324.58 | 1 |  | FA Depreciation-march.23 | Currency | 8324.58 | 22481631 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-04-02 | Accounted transaction received
3983161 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-03-31 | Electrical appliance Deprectia |  |  |  | Depreciation | Alrowad Construction_OU | 1316.5 | 1 |  | FA Depreciation-march.23 | Currency | 1316.5 | 22481631 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-04-02 | Accounted transaction received
3983162 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-03-31 | Electrical appliance Deprectia |  |  |  | Depreciation | Alrowad Construction_OU | 3076.19 | 1 |  | FA Depreciation-march.23 | Currency | 3076.19 | 22481631 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-04-02 | Accounted transaction received
3983163 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-03-31 | Computers Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 5568.13 | 1 |  | FA Depreciation-march.23 | Currency | 5568.13 | 22481631 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-04-02 | Accounted transaction received
3983164 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-03-31 | Electrical appliance Deprectia |  |  |  | Depreciation | Alrowad Construction_OU | 2583.29 | 1 |  | FA Depreciation-march.23 | Currency | 2583.29 | 22481631 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-04-02 | Accounted transaction received
3983165 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-03-31 | Vehicles Depreciations |  |  |  | Depreciation | Alrowad Construction_OU | 5265.21 | 1 |  | FA Depreciation-march.23 | Currency | 5265.21 | 22481631 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-04-02 | Accounted transaction received
3984053 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.03 | Hirings daily wages | 17 | Indirect Cost |  | 2023-03-21 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | -23000 | 1 | يوميات عماله م04-استوريا ختامي | يوميات عماله م04-استوريا ختامي | Currency | -23000 | 22487823 | 11944 | ابراهيم جمعه سالم مشعل-ذاتي | rowad | يوميات عماله م04-استوريا ختامي |  | Finacial | Received | 2023-04-04 | Accounted transaction received
3984807 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2023-04-04 | Accomodation |  |  |  | Indirect | Alrowad Construction_OU | 5800 | 1 | ايجارات 4/2023 astoria | ايجارات 4/2023 astoria | Currency | 5800 | 22491002 | 2131 | Miscellaneous supplier | RME | ايجارات 4/2023 astoria |  | Finacial | Received | 2023-04-05 | Accounted transaction received
3984847 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-03-31 | Computers Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 4431.23 | 1 |  | FA Dep to projects Mar-23 | Currency | 4431.23 | 22491002 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-04-05 | Accounted transaction received
3984898 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-03-31 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 12043.72 | 1 |  | FA Dep to projects Mar-23 | Currency | 12043.72 | 22491002 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-04-05 | Accounted transaction received
3984949 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-03-31 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 26535.92 | 1 |  | FA Dep to projects Mar-23 | Currency | 26535.92 | 22491002 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-04-05 | Accounted transaction received
3985000 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-03-31 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 18746.83 | 1 |  | FA Dep to projects Mar-23 | Currency | 18746.83 | 22491002 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-04-05 | Accounted transaction received
3985051 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-03-31 | Furniture Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 1672.5 | 1 |  | FA Dep to projects Mar-23 | Currency | 1672.5 | 22491002 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-04-05 | Accounted transaction received
3985102 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-03-31 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 3048.08 | 1 |  | FA Dep to projects Mar-23 | Currency | 3048.08 | 22491002 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-04-05 | Accounted transaction received
3988131 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2023-04-05 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 570 | 1 | تسويه ك /148-150-156-157 - مهمات | st-148-150-156-157-4-23 | Currency | 570 | 22500151 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /148-150-156-157 - مهمات |  | Finacial | Received | 2023-04-06 | Accounted transaction received
3840641 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 6.01.03 | Cabinets | 6 | WOOD & PLASTIC WORK |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 23712 | 1 | Ring around fountain @ Reception and Arrival |  | Lumpsum | 1 | 59888484 |  |  |  | Ring around fountain @ Reception and Arrival | 250010001929 | Procurement | Received | 2023-02-21 | Accounted transaction received
3840642 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 6.01.03 | Cabinets | 6 | WOOD & PLASTIC WORK |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 5130 | 1 | Ring around palm tree @ Reception and Arrival |  | Each | 1 | 59888485 |  |  |  | Ring around palm tree @ Reception and Arrival | 250010001930 | Procurement | Received | 2023-02-21 | Accounted transaction received
3840643 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 6.01.03 | Cabinets | 6 | WOOD & PLASTIC WORK |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 62016 | 1 | Grommet for minibar 6mm @ Guest Rooms and Suites |  | Each | 136 | 59888486 |  |  |  | Grommet for minibar 6mm @ Guest Rooms and Suites | 250010001932 | Procurement | Received | 2023-02-21 | Accounted transaction received
3840644 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 6.01.03 | Cabinets | 6 | WOOD & PLASTIC WORK |  | 2023-02-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 15618 | 1 | Robe Hook Plate 70*70*10 |  | Each | 137 | 59888487 |  |  |  | Robe Hook Plate 70*70*10 | 250010001933 | Procurement | Received | 2023-02-21 | Accounted transaction received
3840645 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-08 | Other |  |  |  | Other | Waldorf Astoria-0164 | 80 | 1 | وردة صاج |  | Kilogram | 1 | 59888747 |  |  |  | وردة صاج | 200020000168 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840646 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-08 | Other |  |  |  | Other | Waldorf Astoria-0164 | 45805.2 | 1 | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² |  | Kilogram | 820 | 59888748 |  |  |  | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² | 060040200001 | MEP | Received | 2023-02-21 | Accounted transaction received
3840647 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-08 | Other |  |  |  | Other | Waldorf Astoria-0164 | 1795.5 | 1 | كورنر (TDF) |  | Each | 450 | 59888749 |  |  |  | كورنر (TDF) | 060040200002 | MEP | Received | 2023-02-21 | Accounted transaction received
3840648 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-08 | Other |  |  |  | Other | Waldorf Astoria-0164 | 498.75 | 1 | مسمار سلف دريل 2.5 سم |  | Each | 250 | 59888750 |  |  |  | مسمار سلف دريل 2.5 سم | 200020000317 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840649 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-08 | Other |  |  |  | Other | Waldorf Astoria-0164 | 855 | 1 | مسمار مخ طاسة 6 مم بالورده و الصامولة |  | Kilogram | 5 | 59888751 |  |  |  | مسمار مخ طاسة 6 مم بالورده و الصامولة | 030120200010 | MEP | Received | 2023-02-21 | Accounted transaction received
3840650 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-08 | Other |  |  |  | Other | Waldorf Astoria-0164 | 200 | 1 | جلبة تطويل تيش 8 مم |  | Each | 25 | 59888752 |  |  |  | جلبة تطويل تيش 8 مم | 060190300022 | MEP | Received | 2023-02-21 | Accounted transaction received
3840651 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 547.2 | 1 | جلبة حديد 1/2بوصة |  | Each | 8 | 59904012 |  |  |  | جلبة حديد 1/2بوصة | 240020000027 | MEP | Received | 2023-02-21 | Accounted transaction received
3840652 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 250.8 | 1 | جلبة حديد 1بوصة |  | Each | 2 | 59904013 |  |  |  | جلبة حديد 1بوصة | 240020000028 | MEP | Received | 2023-02-21 | Accounted transaction received
3840653 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1254 | 1 | افيز 8بوصة كوليه |  | Each | 40 | 59904014 |  |  |  | افيز 8بوصة كوليه | 240060000014 | MEP | Received | 2023-02-21 | Accounted transaction received
3840654 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3990 | 1 | كورنر TDF |  | Each | 1000 | 59904015 |  |  |  | كورنر TDF | 350010000035 | MEP | Received | 2023-02-21 | Accounted transaction received
3840655 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-09 | Other |  |  |  | Other | Waldorf Astoria-0164 | 780.9 | 1 | اكمون 16 مم |  | Each | 20 | 59904016 |  |  |  | اكمون 16 مم | 200020000091 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840656 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 430.01 | 1 | أنبوبة سليكون |  | Each | 10 | 59904017 |  |  |  | أنبوبة سليكون | 060019000001 | MEP | Received | 2023-02-21 | Accounted transaction received
3840657 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 14044.8 | 1 | 90° Elbow 3'' UL listed, FM approved |  | Each | 28 | 59904018 |  |  |  | 90° Elbow 3'' UL listed, FM approved | 060011500076 | MEP | Received | 2023-02-21 | Accounted transaction received
3840658 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1368 | 1 | 45° Elbow 3'' UL listed, FM approved |  | Each | 4 | 59904019 |  |  |  | 45° Elbow 3'' UL listed, FM approved | 060011500087 | MEP | Received | 2023-02-21 | Accounted transaction received
3840659 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-09 | Other |  |  |  | Other | Waldorf Astoria-0164 | 2120.4 | 1 | Threaded rod size M16 |  | Each | 16 | 59904020 |  |  |  | Threaded rod size M16 | 060190300006 | MEP | Received | 2023-02-21 | Accounted transaction received
3840660 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-09 | Other |  |  |  | Other | Waldorf Astoria-0164 | 2325.6 | 1 | Standard hex bolt size M16 length 8 cm complet with nut & washer |  | Each | 120 | 59904021 |  |  |  | Standard hex bolt size M16 length 8 cm complet with nut & washer | 061900700126 | MEP | Received | 2023-02-21 | Accounted transaction received
3840661 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 5586 | 1 | threaded elbows f 90° size 2" UL LISTED,FM APPROVED |  | Each | 28 | 59904022 |  |  |  | threaded elbows f 90° size 2" UL LISTED,FM APPROVED | 060010140059 | MEP | Received | 2023-02-21 | Accounted transaction received
3840662 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 323.76 | 1 | threaded reducing coupling size 2"*1.5" UL LISTED,FM APPROVED |  | Each | 2 | 59904023 |  |  |  | threaded reducing coupling size 2"*1.5" UL LISTED,FM APPROVED | 060010140351 | MEP | Received | 2023-02-21 | Accounted transaction received
3840663 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1283.64 | 1 | threaded union conical joint iron to iron f size 2" UL LISTED,FM APPROVED |  | Each | 2 | 59904024 |  |  |  | threaded union conical joint iron to iron f size 2" UL LISTED,FM APPROVED | 060010140599 | MEP | Received | 2023-02-21 | Accounted transaction received
3840664 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1590.3 | 1 | threaded reducing tees size 2"*1/2" UL LISTED,FM APPROVED |  | Each | 5 | 59904025 |  |  |  | threaded reducing tees size 2"*1/2" UL LISTED,FM APPROVED | 060010140168 | MEP | Received | 2023-02-21 | Accounted transaction received
3840665 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 902.88 | 1 | concentric reduser size 4"*3" SCH.40 UL LISTED,FM APPROVED |  | Each | 2 | 59904026 |  |  |  | concentric reduser size 4"*3" SCH.40 UL LISTED,FM APPROVED | 060011300302 | MEP | Received | 2023-02-21 | Accounted transaction received
3840666 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 594.97 | 1 | شنابر حزام للعزل |  | Kilogram | 17 | 59904027 |  |  |  | شنابر حزام للعزل | 060019000037 | MEP | Received | 2023-02-21 | Accounted transaction received
3840667 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 244.99 | 1 | كليبسات لشنابر العزل |  | Kilogram | 7 | 59904028 |  |  |  | كليبسات لشنابر العزل | 060019000038 | MEP | Received | 2023-02-21 | Accounted transaction received
3840668 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-09 | Other |  |  |  | Other | Waldorf Astoria-0164 | 23.71 | 1 | Standard flat washers size 16M |  | Each | 32 | 59904029 |  |  |  | Standard flat washers size 16M | 060190500018 | MEP | Received | 2023-02-21 | Accounted transaction received
3840669 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-02-09 | Other |  |  |  | Other | Waldorf Astoria-0164 | 69.31 | 1 | Standard hex nuts size M16 |  | Each | 32 | 59904030 |  |  |  | Standard hex nuts size M16 | 060190600021 | MEP | Received | 2023-02-21 | Accounted transaction received
3840670 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1710 | 1 | Round Coller ?( 6"" ) L = 20 cm مزود بعدد 1 كردونة بارزة لتثبيت الكوليهات |  | Each | 50 | 59904031 |  |  |  | Round Coller ?( 6"" ) L = 20 cm مزود بعدد 1 كردونة بارزة لتثبيت الكوليهات | 060019000141 | MEP | Received | 2023-02-21 | Accounted transaction received
3840671 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 598.5 | 1 | Round Coller ?( 8"" ) L = 20 cm مزود بعدد 1 كردونة بارزة لتثبيت الكوليهات |  | Each | 15 | 59904032 |  |  |  | Round Coller ?( 8"" ) L = 20 cm مزود بعدد 1 كردونة بارزة لتثبيت الكوليهات | 060019000142 | MEP | Received | 2023-02-21 | Accounted transaction received
3840672 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 684 | 1 | Round Coller ?( 10"" ) L = 20 cm مزود بعدد 1 كردونة بارزة لتثبيت الكوليهات |  | Each | 15 | 59904033 |  |  |  | Round Coller ?( 10"" ) L = 20 cm مزود بعدد 1 كردونة بارزة لتثبيت الكوليهات | 060019000144 | MEP | Received | 2023-02-21 | Accounted transaction received
3840673 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 427.5 | 1 | أفيز 6 بوصة كوليه |  | Each | 20 | 59904034 |  |  |  | أفيز 6 بوصة كوليه | 240060000033 | MEP | Received | 2023-02-21 | Accounted transaction received
3840674 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-02-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1111.5 | 1 | أفيز 10 بوصة كوليه |  | Each | 30 | 59904035 |  |  |  | أفيز 10 بوصة كوليه | 240060000034 | MEP | Received | 2023-02-21 | Accounted transaction received
3840675 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2017.8 | 1 | ماسورة 25مم UPVC قطر خارجي 25 قطر داخلي 22مم اللفة= 20×3 متر(اللون رمادى) |  | Meter | 120 | 59904091 |  |  |  | ماسورة 25مم UPVC قطر خارجي 25 قطر داخلي 22مم اللفة= 20×3 متر(اللون رمادى) | 030010000034 | MEP | Received | 2023-02-21 | Accounted transaction received
3840676 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 7814.02 | 1 | فلكسيبل معدن المقاس ¾ " |  | Meter | 126 | 59904092 |  |  |  | فلكسيبل معدن المقاس ¾ " | 030020100091 | MEP | Received | 2023-02-21 | Accounted transaction received
3840677 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1534.9 | 1 | ماسورة 20مم UPVC سمك ثقيل قطر خارجي 20 قطر داخلي 15.8مم اللفة= 34×3 متر(اللون أبيض) |  | Meter | 204 | 59904093 |  |  |  | ماسورة 20مم UPVC سمك ثقيل قطر خارجي 20 قطر داخلي 15.8مم اللفة= 34×3 متر(اللون أبيض) | 030010000051 | MEP | Received | 2023-02-21 | Accounted transaction received
3840678 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 177.62 | 1 | جلبة ماسورة 20مم UPVC (اللون أبيض) |  | Each | 100 | 59904094 |  |  |  | جلبة ماسورة 20مم UPVC (اللون أبيض) | 030010000067 | MEP | Received | 2023-02-21 | Accounted transaction received
3840679 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 168.15 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 50 | 59904095 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-02-21 | Accounted transaction received
3840680 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 555.51 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 2 | 59904096 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) | 030010000059 | MEP | Received | 2023-02-21 | Accounted transaction received
3840681 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1175.79 | 1 | سلك نحاس مصمت مقاس 1.5 مم اللون أسود (cu/pvc) جهد (750/450) |  | Meter | 200 | 59904097 |  |  |  | سلك نحاس مصمت مقاس 1.5 مم اللون أسود (cu/pvc) جهد (750/450) | 030030100253 | MEP | Received | 2023-02-21 | Accounted transaction received
3840682 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 324.16 | 1 | أدابتور UPVC لماسورة 20مم(اللون أبيض) |  | Each | 100 | 59904098 |  |  |  | أدابتور UPVC لماسورة 20مم(اللون أبيض) | 030010000096 | MEP | Received | 2023-02-21 | Accounted transaction received
3840683 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1146.84 | 1 | سلك نحاس مصمت مقاس 3 مم اللون أصفر (cu/xlpe) جهد (750/450) |  | Meter | 200 | 59904099 |  |  |  | سلك نحاس مصمت مقاس 3 مم اللون أصفر (cu/xlpe) جهد (750/450) | 030030100280 | MEP | Received | 2023-02-21 | Accounted transaction received
3840684 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 742.14 | 1 | سلك نحاس مصمت مقاس 4 مم اللون أسود (cu/xlpe) جهد (750/450) |  | Meter | 100 | 59904100 |  |  |  | سلك نحاس مصمت مقاس 4 مم اللون أسود (cu/xlpe) جهد (750/450) | 030030100294 | MEP | Received | 2023-02-21 | Accounted transaction received
3840685 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 23600.31 | 1 | كابل نحاس ترمو ضغط منخفض مقاس 4 × 16 مم (xlpe/pvc) |  | Meter | 100 | 59904101 |  |  |  | كابل نحاس ترمو ضغط منخفض مقاس 4 × 16 مم (xlpe/pvc) | 030030100008 | MEP | Received | 2023-02-21 | Accounted transaction received
3840686 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 451.08 | 1 | جلبة ماسورة EMT المقاس ¾ " |  | Each | 25 | 59904102 |  |  |  | جلبة ماسورة EMT المقاس ¾ " | 030020100021 | MEP | Received | 2023-02-21 | Accounted transaction received
3840687 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1756.12 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 27 | 59904103 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-02-21 | Accounted transaction received
3840688 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 38 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 3 | 59904104 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-02-21 | Accounted transaction received
3840689 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 171 | 1 | جلو شفاف |  | Can | 3 | 59904105 |  |  |  | جلو شفاف | 200010001116 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840690 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2131.8 | 1 | سلك نحاس مجدول مقاس 3 مم اللون أصفر × أخضر (cu/pvc) |  | Meter | 200 | 59904106 |  |  |  | سلك نحاس مجدول مقاس 3 مم اللون أصفر × أخضر (cu/pvc) | 030030101022 | MEP | Received | 2023-02-21 | Accounted transaction received
3840691 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 765.94 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) |  | Meter | 100 | 59904107 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) | 030030101026 | MEP | Received | 2023-02-21 | Accounted transaction received
3840692 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 670.74 | 1 | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS |  | Each | 3 | 59904108 |  |  |  | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS | 030060100617 | MEP | Received | 2023-02-21 | Accounted transaction received
3840693 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 295.59 | 1 | Wiring Devices (54000) METAL FLUSH-MOUNTING BOX FOR INSTALLATION IN CONCRETE FLOOR - 3 MODULES |  | Each | 3 | 59904109 |  |  |  | Wiring Devices (54000) METAL FLUSH-MOUNTING BOX FOR INSTALLATION IN CONCRETE FLOOR - 3 MODULES | 030060100618 | MEP | Received | 2023-02-21 | Accounted transaction received
3840694 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2567.36 | 1 | mosaic adapter code 69580 |  | Each | 27 | 59904110 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-02-21 | Accounted transaction received
3840695 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1179.9 | 1 | Hot dip Galvanized after fabrication, Cable Tray Trunk Type, 200mm Width, 100mm height of Side,1.5mm thickness,10mmReturnFlange ,3000mm Length. |  | Meter | 6 | 59904111 |  |  |  | Hot dip Galvanized after fabrication, Cable Tray Trunk Type, 200mm Width, 100mm height of Side,1.5mm thickness,10mmReturnFlange ,3000mm Length. | 030101400048 | MEP | Received | 2023-02-21 | Accounted transaction received
3840696 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2166.69 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 27 | 59904112 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-02-21 | Accounted transaction received
3840697 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 446.05 | 1 | أدابتور 3/4 مواسير EMT |  | Each | 25 | 59904113 |  |  |  | أدابتور 3/4 مواسير EMT | 030020100207 | MEP | Received | 2023-02-21 | Accounted transaction received
3840698 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1694.98 | 1 | أدابتور 3/4 مواسير EMT |  | Each | 95 | 59904114 |  |  |  | أدابتور 3/4 مواسير EMT | 030020100207 | MEP | Received | 2023-02-21 | Accounted transaction received
3840699 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 501.94 | 1 | SPLASH PROOF COVER Code : 617636 |  | Each | 5 | 59904115 |  |  |  | SPLASH PROOF COVER Code : 617636 | 030060100927 | MEP | Received | 2023-02-21 | Accounted transaction received
3840700 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 515.09 | 1 | DS , 4 pole , 40A , 400V , abs enclosure IP 65 Code : KEM 440U Y/R ABS |  | Each | 1 | 59904116 |  |  |  | DS , 4 pole , 40A , 400V , abs enclosure IP 65 Code : KEM 440U Y/R ABS | 030060200073 | MEP | Received | 2023-02-21 | Accounted transaction received
3840701 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 563.39 | 1 | 1G 20A DP SWT + NEON + E WH - 617671 |  | Each | 5 | 59904117 |  |  |  | 1G 20A DP SWT + NEON + E WH - 617671 | 030060100942 | MEP | Received | 2023-02-21 | Accounted transaction received
3840702 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.04.03 | Mosaic | 9 | FINISHES WORK |  | 2023-02-09 | Mosaic |  |  |  | Materials | Waldorf Astoria-0164 | 14592 | 1 | بلاط موزايكو زعفران 25*25 |  | Square Meter | 160 | 59904218 |  |  |  | بلاط موزايكو زعفران 25*25 | 140030000020 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840703 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 8071.2 | 1 | ماسورة 25مم UPVC قطر خارجي 25 قطر داخلي 22مم اللفة= 20×3 متر(اللون رمادى) |  | Meter | 480 | 59950173 |  |  |  | ماسورة 25مم UPVC قطر خارجي 25 قطر داخلي 22مم اللفة= 20×3 متر(اللون رمادى) | 030010000034 | MEP | Received | 2023-02-21 | Accounted transaction received
3840704 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2604.67 | 1 | فلكسيبل معدن المقاس ¾ " |  | Meter | 42 | 59950174 |  |  |  | فلكسيبل معدن المقاس ¾ " | 030020100091 | MEP | Received | 2023-02-21 | Accounted transaction received
3840705 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-12 | MATV system |  |  |  | Materials | Waldorf Astoria-0164 | 84.08 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 25 | 59950175 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-02-21 | Accounted transaction received
3840706 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2394 | 1 | بواط واتر بروف بفتحات مقاس 30 × 38 × 12 سم |  | Each | 6 | 59950176 |  |  |  | بواط واتر بروف بفتحات مقاس 30 × 38 × 12 سم | 030010000185 | MEP | Received | 2023-02-21 | Accounted transaction received
3840707 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3025.4 | 1 | SWITCH 20AX 1 WAY 1 MOD Code 572509 |  | Each | 22 | 59950177 |  |  |  | SWITCH 20AX 1 WAY 1 MOD Code 572509 | 030060100048 | MEP | Received | 2023-02-21 | Accounted transaction received
3840708 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3927.74 | 1 | 10AX SWITCH SP 2 WAY 1 MOD Code 572505 |  | Each | 30 | 59950178 |  |  |  | 10AX SWITCH SP 2 WAY 1 MOD Code 572505 | 030060100123 | MEP | Received | 2023-02-21 | Accounted transaction received
3840709 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1256.62 | 1 | 10A INTERMEDIATE SWITCH 1 MOD MAGNESIUM Code 572508 |  | Each | 6 | 59950179 |  |  |  | 10A INTERMEDIATE SWITCH 1 MOD MAGNESIUM Code 572508 | 030060100126 | MEP | Received | 2023-02-21 | Accounted transaction received
3840710 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 780.5 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 12 | 59950180 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-02-21 | Accounted transaction received
3840711 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1482.45 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 12 | 59950181 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-02-21 | Accounted transaction received
3840712 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 50.67 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 4 | 59950182 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-02-21 | Accounted transaction received
3840713 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 176.76 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 10 | 59950183 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-02-21 | Accounted transaction received
3840714 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 347.05 | 1 | RECTANGULAR 3 MODULES 2 GANG BOX BS Code 576002 |  | Each | 8 | 59950184 |  |  |  | RECTANGULAR 3 MODULES 2 GANG BOX BS Code 576002 | 030060100306 | MEP | Received | 2023-02-21 | Accounted transaction received
3840715 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1155.42 | 1 | FRAME 8 MOD MOSAIC ( Legrand 689658 ) |  | Each | 7 | 59950185 |  |  |  | FRAME 8 MOD MOSAIC ( Legrand 689658 ) | 030060100740 | MEP | Received | 2023-02-21 | Accounted transaction received
3840716 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1252.63 | 1 | WA PLATE 77MM 2X2MOD MOSAIC ( Legrand 689673 ) |  | Each | 10 | 59950186 |  |  |  | WA PLATE 77MM 2X2MOD MOSAIC ( Legrand 689673 ) | 030060100741 | MEP | Received | 2023-02-21 | Accounted transaction received
3840717 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 114.06 | 1 | UPVC BACK BOX 10X10 |  | Each | 5 | 59950187 |  |  |  | UPVC BACK BOX 10X10 | 030069000025 | MEP | Received | 2023-02-21 | Accounted transaction received
3840718 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 57596.02 | 1 | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser |  | Each | 150 | 59950188 |  |  |  | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser | 030040700472 | MEP | Received | 2023-02-21 | Accounted transaction received
3840719 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 119.7 | 1 | مكنسة خشنة |  | Each | 3 | 59950232 |  |  |  | مكنسة خشنة | 700020000004 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840720 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 6455.82 | 1 | بولي ايثيلين 100 ميكرون شفاف |  | Kilogram | 80.9 | 59950233 |  |  |  | بولي ايثيلين 100 ميكرون شفاف | 040010000040 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840721 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 47503.57 | 1 | بولي ايثيلين 200 ميكرون شفاف |  | Kilogram | 791.75 | 59950234 |  |  |  | بولي ايثيلين 200 ميكرون شفاف | 040010000042 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840722 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 279.3 | 1 | مكنسة ناعمة |  | Each | 7 | 59950235 |  |  |  | مكنسة ناعمة | 200010000449 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840723 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 142.99 | 1 | نهاية بياض 10 مم |  | Each | 5 | 59950236 |  |  |  | نهاية بياض 10 مم | 200010000462 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840724 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 193.8 | 1 | تنر |  | Each | 2 | 59950237 |  |  |  | تنر | 060019000008 | MEP | Received | 2023-02-21 | Accounted transaction received
3840725 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1567.5 | 1 | شيكارة بلاستيك فارغة |  | Each | 500 | 59950238 |  |  |  | شيكارة بلاستيك فارغة | 200010000115 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840726 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 5415 | 1 | سيكا جراوت 214 |  | Bag | 25 | 59950239 |  |  |  | سيكا جراوت 214 | 360010000033 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840727 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 399 | 1 | فيشر 6مم |  | Each | 2000 | 59950240 |  |  |  | فيشر 6مم | 200010001079 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840728 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2280 | 1 | إسطوانة بسكوتة 5 بوصة |  | Each | 20 | 59950241 |  |  |  | إسطوانة بسكوتة 5 بوصة | 140010000020 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840729 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 199.5 | 1 | بنطة تخريم 8 مم |  | Each | 5 | 59950242 |  |  |  | بنطة تخريم 8 مم | 200010001100 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840730 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 592.8 | 1 | غراء أبيض |  | Kilogram | 8 | 59950243 |  |  |  | غراء أبيض | 200010001270 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840731 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 20 | 1 | رزة قفل |  | Each | 2 | 59950244 |  |  |  | رزة قفل | 039020100061 | MEP | Received | 2023-02-21 | Accounted transaction received
3840732 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2565 | 1 | الواح ام دي اف MDF سمك 5 مم |  | Each | 9 | 59950245 |  |  |  | الواح ام دي اف MDF سمك 5 مم | 090040000023 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840733 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 142.5 | 1 | بنطة 6 مم استانلس |  | Each | 5 | 59950246 |  |  |  | بنطة 6 مم استانلس | 200010001356 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840734 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 15 | 1 | مفصله باب الومتيال |  | Each | 2 | 59950247 |  |  |  | مفصله باب الومتيال | 250010000208 | Procurement | Received | 2023-02-21 | Accounted transaction received
3840735 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 150 | 1 | قفل كمبيوتر 40 مم |  | Each | 2 | 59950248 |  |  |  | قفل كمبيوتر 40 مم | 200010001567 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840736 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1710 | 1 | مادة لاصق لورق الحائط |  | Kilogram | 20 | 59950249 |  |  |  | مادة لاصق لورق الحائط | 050020000006 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840737 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 285 | 1 | فوطة حمام قطن |  | Each | 10 | 59950250 |  |  |  | فوطة حمام قطن | 700020000193 | Purchasing | Received | 2023-02-21 | Accounted transaction received
3840738 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 48959.9 | 1 | Hardware Accessories for Wooden Doors Concealed hinge system & Bathroom Concealed Hinges Simonswerk completely concealed hinge system with load capacity 80.0 kg two hinges per door leaf (1x2m) |  | Each | 18 | 59950251 |  |  |  | Hardware Accessories for Wooden Doors Concealed hinge system & Bathroom Concealed Hinges Simonswerk completely concealed hinge system with load capacity 80.0 kg two hinges per door leaf (1x2m) | 250010001515 | Procurement | Received | 2023-02-21 | Accounted transaction received
3840739 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 10920.06 | 1 | Hardware Accessories For Wooden Doors Sliding Soft Close Door Sync 9820120 KG FUNICULAR SLIDING DOOR SYSTEM - HAS SOFT Closing with track 4 meter Albatur 73401211 Silver |  | Each | 2 | 59950252 |  |  |  | Hardware Accessories For Wooden Doors Sliding Soft Close Door Sync 9820120 KG FUNICULAR SLIDING DOOR SYSTEM - HAS SOFT Closing with track 4 meter Albatur 73401211 Silver | 250010001607 | Procurement | Received | 2023-02-21 | Accounted transaction received
3840740 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.09.04 | Fire Fighting Networ | 2 | SITE WORK |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 250 | 1 | برايمر |  | Each | 2 | 59950260 |  |  |  | برايمر | 060019000007 | MEP | Received | 2023-02-21 | Accounted transaction received
3840741 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.09.04 | Fire Fighting Networ | 2 | SITE WORK |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 34898.01 | 1 | seamless steel pipe size 3" SCH.40 |  | Meter | 96 | 59950261 |  |  |  | seamless steel pipe size 3" SCH.40 | 060010500028 | MEP | Received | 2023-02-21 | Accounted transaction received
3840742 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.09.04 | Fire Fighting Networ | 2 | SITE WORK |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1710 | 1 | أفيز 6 بوصة كوليه |  | Each | 80 | 59950262 |  |  |  | أفيز 6 بوصة كوليه | 240060000033 | MEP | Received | 2023-02-21 | Accounted transaction received
3840743 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2023-02-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 627 | 1 | Canon MF3010 Cartridge |  | Each | 1 | 59950266 |  |  |  | Canon MF3010 Cartridge | 800030000086 | IT | Received | 2023-02-21 | Accounted transaction received
3966517 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.13 | Maintenance | 17 | Indirect Cost |  | 2023-03-20 | Maintenance |  |  |  | Indirect | Alrowad Construction_OU | 2964 | 1 | تسويه ك /60-66-68-69-71-م. معدات | st-60-66-68-69-71-3-23 | Currency | 2964 | 22429235 | 2162 | Petty Cash | Mohamed Hassan Ibrahim Badawi | تسويه ك /60-66-68-69-71-م. معدات |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3966565 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.03 | Hirings daily wages | 17 | Indirect Cost |  | 2023-03-21 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 23000 | 1 | يوميات عماله م04-استوريا ختامي | يوميات عماله م04-استوريا ختامي | Currency | 23000 | 22429235 | 11944 | ابراهيم جمعه سالم مشعل-ذاتي | rowad | يوميات عماله م04-استوريا ختامي |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3966656 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.08 | Trafic Permission & | 17 | Indirect Cost |  | 2023-03-22 | Trafic Perm-Station Fees |  |  |  | Indirect | Alrowad Construction_OU | 195 | 1 | تسويه ك /107-152-153 - حركه | st-107-152-153-3-23 | Currency | 195 | 22429235 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /107-152-153 - حركه |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3966657 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.01 | Private Cars | 17 | Indirect Cost |  | 2023-03-22 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 300 | 1 | تسويه ك /107-152-153 - حركه | st-107-152-153-3-23 | Currency | 300 | 22429235 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /107-152-153 - حركه |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3966676 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3300 | 1 | 1.1 80895/1 |  | Currency | 11 |  | 12635 | خالد محمد نصر الدين احمد-ذاتى |  | 1.1 80895/1 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3966658 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-03-22 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 11626 | 1 | تسويه ك /110-140-143-144 - متنوعات | st-110-140-143-144-3-23 | Currency | 11626 | 22429235 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /110-140-143-144 - متنوعات |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3966659 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.08 | Electrical Expenses | 17 | Indirect Cost |  | 2023-03-22 | Electrical Expenses |  |  |  | Indirect | Alrowad Construction_OU | 562 | 1 | تسويه ك /110-140-143-144 - متنوعات | st-110-140-143-144-3-23 | Currency | 562 | 22429235 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /110-140-143-144 - متنوعات |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3966660 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-03-22 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 1115.35 | 1 | تسويه ك /110-140-143-144 - متنوعات | st-110-140-143-144-3-23 | Currency | 1115.35 | 22429235 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /110-140-143-144 - متنوعات |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3966677 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2200 | 1 | 1.2 80895/1 |  | Currency | 11 |  | 12635 | خالد محمد نصر الدين احمد-ذاتى |  | 1.2 80895/1 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3966678 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 11190 | 1 | 1.3 80895/1 |  | Currency | 18.65 |  | 12635 | خالد محمد نصر الدين احمد-ذاتى |  | 1.3 80895/1 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3966986 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.06.01 | Mirrors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 19000 | 1 | 1.1 80103/1 |  | Currency | 100 |  | 12560 | هيثم محمد عبدالحميد عبدالعزيز– ذاتى |  | 1.1 80103/1 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3966987 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.06.01 | Mirrors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2280 | 1 | 2.1 80103/1 |  | Currency | 12 |  | 12560 | هيثم محمد عبدالحميد عبدالعزيز– ذاتى |  | 2.1 80103/1 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967253 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 24000 | 1 | 1.1 76024/1 |  | Currency | 6 |  | 6177 | ابو طالب للمقاولات العامه |  | 1.1 76024/1 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967254 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4800 | 1 | 1.2 76024/1 |  | Currency | 1 |  | 6177 | ابو طالب للمقاولات العامه |  | 1.2 76024/1 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967255 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 12000 | 1 | 1.3 76024/1 |  | Currency | 3 |  | 6177 | ابو طالب للمقاولات العامه |  | 1.3 76024/1 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967256 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -183.6 | 1 | LABOUR_OFFICE 76024/1 |  | Currency | -183.6 |  | 6177 | ابو طالب للمقاولات العامه |  | LABOUR_OFFICE 76024/1 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967269 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2660 | 1 | 4.4 63247/4 |  | Currency | 2660 |  | 10037 | ايه وان للمقاولات |  | 4.4 63247/4 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967270 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 76500 | 1 | 6.1 63247/4 |  | Currency | 102 |  | 10037 | ايه وان للمقاولات |  | 6.1 63247/4 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967271 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -356.22 | 1 | LABOUR_OFFICE 63247/4 |  | Currency | -356.22 |  | 10037 | ايه وان للمقاولات |  | LABOUR_OFFICE 63247/4 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967274 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 4.02. | Glass Work | 4 | MASONRY WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 66625 | 1 | 2.1 70629/7 |  | Currency | 10.25 |  | 1108 | البركة للتوريدات العمومية والمقاولات-احم |  | 2.1 70629/7 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967275 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 4.02. | Glass Work | 4 | MASONRY WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 44100 | 1 | 3.1 70629/7 |  | Currency | 12.6 |  | 1108 | البركة للتوريدات العمومية والمقاولات-احم |  | 3.1 70629/7 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967276 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 4.02. | Glass Work | 4 | MASONRY WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -498.26 | 1 | LABOUR_OFFICE 70629/7 |  | Currency | -498.26 |  | 1108 | البركة للتوريدات العمومية والمقاولات-احم |  | LABOUR_OFFICE 70629/7 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967316 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 17.SS.03 | Consultancy | 17 | Indirect Cost |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 30457.5 | 1 | 1.3 62186/5 |  | Currency | 28.1 |  | 9189 | الهندسية مصر لادارة المشروعات |  | 1.3 62186/5 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967317 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 17.SS.03 | Consultancy | 17 | Indirect Cost |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3045.75 | 1 | 1.3 62186/5 |  | Currency | 0 |  | 9189 | الهندسية مصر لادارة المشروعات |  | 1.3 62186/5 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967318 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.01 | Epoxy | 9 | FINISHES WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 30800 | 1 | 2.1 67960/2 |  | Currency | 56 |  | 8099 | انترناشيونال سوبر سكريد |  | 2.1 67960/2 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967319 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.01 | Epoxy | 9 | FINISHES WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 208000 | 1 | 3.4 67960/2 |  | Currency | 320 |  | 8099 | انترناشيونال سوبر سكريد |  | 3.4 67960/2 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967320 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.01 | Epoxy | 9 | FINISHES WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 16500 | 1 | 4.1 67960/2 |  | Currency | 30 |  | 8099 | انترناشيونال سوبر سكريد |  | 4.1 67960/2 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967321 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.01 | Epoxy | 9 | FINISHES WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1148.85 | 1 | LABOUR_OFFICE 67960/2 |  | Currency | -1148.85 |  | 8099 | انترناشيونال سوبر سكريد |  | LABOUR_OFFICE 67960/2 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967325 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2860 | 1 | 1.2 79995/2 |  | Currency | 7.15 |  | 1753 | سهمان (محمود عبد العاطي وشريكه |  | 1.2 79995/2 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967326 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 14895 | 1 | 2.1 79995/2 |  | Currency | 16.55 |  | 1753 | سهمان (محمود عبد العاطي وشريكه |  | 2.1 79995/2 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967327 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.03.00 | Marble & Granite(G) | 9 | FINISHES WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -79.9 | 1 | LABOUR_OFFICE 79995/2 |  | Currency | -79.9 |  | 1753 | سهمان (محمود عبد العاطي وشريكه |  | LABOUR_OFFICE 79995/2 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967589 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 103558 | 1 | 4.1 62756/5 |  | Currency | 159.32 |  | 6250 | شيلد للانشاءات المتخصصه |  | 4.1 62756/5 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967590 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 7.05. | Special Insulation | 7 | THERMAL & MOISTURE P |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -466.01 | 1 | LABOUR_OFFICE 62756/5 |  | Currency | -466.01 |  | 6250 | شيلد للانشاءات المتخصصه |  | LABOUR_OFFICE 62756/5 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967592 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-23 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | 71200 | 1 | 69398/6 |  | Currency | 71200 |  | 8108 | سامى عياد فهيم حليم |  | 69398/6 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967593 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 14791.5 | 1 | 1.2 69398/6 |  | Currency | 32.87 |  | 8108 | سامى عياد فهيم حليم |  | 1.2 69398/6 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967594 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 23400 | 1 | 1.3 69398/6 |  | Currency | 36 |  | 8108 | سامى عياد فهيم حليم |  | 1.3 69398/6 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967595 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.03.02 | Repair | 2 | SITE WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 8800 | 1 | 2.1 69398/6 |  | Currency | 44 |  | 8108 | سامى عياد فهيم حليم |  | 2.1 69398/6 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967596 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.04.02 | Ceramic | 9 | FINISHES WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -211.46 | 1 | LABOUR_OFFICE 69398/6 |  | Currency | -211.46 |  | 8108 | سامى عياد فهيم حليم |  | LABOUR_OFFICE 69398/6 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967795 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 4.01. | Masonry Work | 4 | MASONRY WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1394 | 1 | 3.1 65733/5 |  | Currency | 328 |  | 9028 | مارينا للصناعات الخشبيه والمعدنيه-حنا منصور برسوم روفائيل |  | 3.1 65733/5 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967796 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 4.01. | Masonry Work | 4 | MASONRY WORK |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1275 | 1 | 4.1 65733/5 |  | Currency | 300 |  | 9028 | مارينا للصناعات الخشبيه والمعدنيه-حنا منصور برسوم روفائيل |  | 4.1 65733/5 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3967831 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-03-23 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 11840 | 1 | 1.1.79 60674/8 |  | Currency | 11.84 |  | 10767 | النديم للصناعات المشربيه |  | 1.1.79 60674/8 |  | Finacial | Received | 2023-03-23 | Accounted transaction received
3973240 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 40563.68 | 1 | 8 Waldorf Astoria Cairo 67059/8 | 8 Waldorf Astoria Cairo 67059/8 | Currency | 40563.68 | 22458200 | 4820 | سيجاب للهندسه والتجاره | rowad | 8 Waldorf Astoria Cairo 67059/8 |  | Mechanical | Received | 2023-03-28 | Accounted transaction received
3973241 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-03-13 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -25.48 | 1 | 8 Waldorf Astoria Cairo 67059/8 | 8 Waldorf Astoria Cairo 67059/8 | Currency | -25.48 | 22458200 | 4820 | سيجاب للهندسه والتجاره | rowad | 8 Waldorf Astoria Cairo 67059/8 |  | Mechanical | Received | 2023-03-28 | Accounted transaction received
3975253 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-27 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 15542.85 | 1 | بلوك اسمنتى مفرغ 12*20*40 |  | Each | 1980 | 60992472 |  |  |  | بلوك اسمنتى مفرغ 12*20*40 | 140020000019 | Purchasing | Received | 2023-03-28 | Accounted transaction received
3975254 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-27 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2384 | 1 | كمرة حديد UPN 120 |  | Kilogram | 200 | 60994268 |  |  |  | كمرة حديد UPN 120 | 060190800007 | MEP | Received | 2023-03-28 | Accounted transaction received
3975255 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-28 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 17002.87 | 1 | Wall Paper WC-8 Trapezium 26560 Arte International Vinyl wall /industriezone de waerde |  | Roll | 4 | 61009192 |  |  |  | Wall Paper WC-8 Trapezium 26560 Arte International Vinyl wall /industriezone de waerde | 050020000018 | Purchasing | Received | 2023-03-28 | Accounted transaction received
3975256 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-28 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 24534.22 | 1 | Supply Concealed Door closer to 80KG for wooden doors, including any requirements to complete the works as per consultant's approval & submittal approval. Consort CDCC3 Silver |  | Each | 3 | 61009193 |  |  |  | Supply Concealed Door closer to 80KG for wooden doors, including any requirements to complete the works as per consultant's approval & submittal approval. Consort CDCC3 Silver | 250010001608 | Procurement | Received | 2023-03-28 | Accounted transaction received
3975257 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-03-28 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 155565 | 1 | Wall covering – WC-3 – Cole & Son- The Ardmore Collection, Narina Linen 109/10049 |  | Roll | 50 | 61009462 |  |  |  | Wall covering – WC-3 – Cole & Son- The Ardmore Collection, Narina Linen 109/10049 | 050020000013 | Purchasing | Received | 2023-03-28 | Accounted transaction received
3975258 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-03-28 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 11510.58 | 1 | Privacy Door Latch Brand Welder part # 43702424 Finish Silver |  | Each | 23 | 61009463 |  |  |  | Privacy Door Latch Brand Welder part # 43702424 Finish Silver | 250010001658 | Procurement | Received | 2023-03-28 | Accounted transaction received
3975259 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-28 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4250.72 | 1 | Wall Paper WC-8 Trapezium 26560 Arte International Vinyl wall /industriezone de waerde |  | Roll | 1 | 61009530 |  |  |  | Wall Paper WC-8 Trapezium 26560 Arte International Vinyl wall /industriezone de waerde | 050020000018 | Purchasing | Received | 2023-03-28 | Accounted transaction received
3975260 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-28 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 395.99 | 1 | Hardware Accessories for Wooden Doors Double Cylinder TESA Security TE-5 Double Cylinder 35x35mm. 5 Spring Loaded Anti pick Pins. Made to EN-1303 Regulation. |  | Each | 2 | 61009531 |  |  |  | Hardware Accessories for Wooden Doors Double Cylinder TESA Security TE-5 Double Cylinder 35x35mm. 5 Spring Loaded Anti pick Pins. Made to EN-1303 Regulation. | 250010001519 | Procurement | Received | 2023-03-28 | Accounted transaction received
3975261 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2033.49 | 1 | سلك نحاس مجدول مقاس4 مم اللون أحمر (cu/pvc) |  | Meter | 200 | 61009622 |  |  |  | سلك نحاس مجدول مقاس4 مم اللون أحمر (cu/pvc) | 030030101023 | MEP | Received | 2023-03-28 | Accounted transaction received
3975262 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 6200.46 | 1 | سلك نحاس مجدول مقاس 6 مم اللون أسود (cu/pvc) |  | Meter | 300 | 61009623 |  |  |  | سلك نحاس مجدول مقاس 6 مم اللون أسود (cu/pvc) | 030030101031 | MEP | Received | 2023-03-28 | Accounted transaction received
3975263 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4133.64 | 1 | سلك نحاس مجدول مقاس 6 مم اللون أصفر × أخضر (cu/pvc) |  | Meter | 200 | 61009624 |  |  |  | سلك نحاس مجدول مقاس 6 مم اللون أصفر × أخضر (cu/pvc) | 030030101032 | MEP | Received | 2023-03-28 | Accounted transaction received
3975264 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 9586.26 | 1 | LV Power cable CU / PVC / PVC 3 X 6 mm2 (0.6/1 KV) |  | Meter | 150 | 61009625 |  |  |  | LV Power cable CU / PVC / PVC 3 X 6 mm2 (0.6/1 KV) | 030030101179 | MEP | Received | 2023-03-28 | Accounted transaction received
4003712 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 10.06. | Mat | 10 | SPECIALITIES |  | 2023-04-09 | Transportation |  |  |  | Indirect | Alrowad Construction_OU | 37500 | 1 | نقل افراد فبراير استوريا | نقل افراد فبراير استوريا | Currency | 37500 | 22539647 | 8742 | المتحدة ترافيل | rowad | نقل افراد فبراير استوريا |  | Finacial | Received | 2023-04-16 | Accounted transaction received
3975265 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5010.5 | 1 | Copper Cable UTP Cat6A, 4Pair, LSZH, Roll= 305Mt. |  | Each | 1 | 61009626 |  |  |  | Copper Cable UTP Cat6A, 4Pair, LSZH, Roll= 305Mt. | 031030000359 | MEP | Received | 2023-03-28 | Accounted transaction received
3975266 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2151.61 | 1 | LV Power cable CU / PVC / PVC Size 3 X 10 mm2 (0.6/1 KV) |  | Meter | 22 | 61009627 |  |  |  | LV Power cable CU / PVC / PVC Size 3 X 10 mm2 (0.6/1 KV) | 030030101206 | MEP | Received | 2023-03-28 | Accounted transaction received
3975267 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 718.2 | 1 | Driver Model RS-15-12. I/P 220VAC Output 12VDC Single Output at 1.3A |  | Each | 2 | 61009628 |  |  |  | Driver Model RS-15-12. I/P 220VAC Output 12VDC Single Output at 1.3A | 030049100070 | MEP | Received | 2023-03-28 | Accounted transaction received
3975268 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1026 | 1 | غطاء بواط معدن مقاس 4*4 |  | Each | 150 | 61009679 |  |  |  | غطاء بواط معدن مقاس 4*4 | 030020100129 | MEP | Received | 2023-03-28 | Accounted transaction received
3975269 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 68.4 | 1 | غطاء بواط معدن مقاس 4*4 |  | Each | 10 | 61009680 |  |  |  | غطاء بواط معدن مقاس 4*4 | 030020100129 | MEP | Received | 2023-03-28 | Accounted transaction received
3975270 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 12.52 | 1 | أفيز أثنين جناح لماسورة EMT المقاس ¾ " |  | Each | 5 | 61009681 |  |  |  | أفيز أثنين جناح لماسورة EMT المقاس ¾ " | 030020100033 | MEP | Received | 2023-03-28 | Accounted transaction received
3975271 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 275.04 | 1 | SWITCH 20AX 1 WAY 1 MOD Code 572509 |  | Each | 2 | 61009682 |  |  |  | SWITCH 20AX 1 WAY 1 MOD Code 572509 | 030060100048 | MEP | Received | 2023-03-28 | Accounted transaction received
3975272 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 100.82 | 1 | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 |  | Each | 1 | 61009683 |  |  |  | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 | 030060100114 | MEP | Received | 2023-03-28 | Accounted transaction received
3975273 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 260.17 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 4 | 61009684 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-03-28 | Accounted transaction received
3975274 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 130.08 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 2 | 61009685 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-03-28 | Accounted transaction received
3975275 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1111.84 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 9 | 61009686 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-03-28 | Accounted transaction received
3975276 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 710.17 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 40 | 61009687 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-03-28 | Accounted transaction received
3975277 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 92.07 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 2 | 61009688 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-03-28 | Accounted transaction received
3975278 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 163.74 | 1 | 576562 Code وش مربع فضي |  | Each | 5 | 61009689 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-03-28 | Accounted transaction received
3975279 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 201.88 | 1 | CARRIER PLATE SYNERGY code 730094 |  | Each | 3 | 61009690 |  |  |  | CARRIER PLATE SYNERGY code 730094 | 030060100534 | MEP | Received | 2023-03-28 | Accounted transaction received
3975280 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 223.58 | 1 | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS |  | Each | 1 | 61009691 |  |  |  | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS | 030060100617 | MEP | Received | 2023-03-28 | Accounted transaction received
3975281 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 190.17 | 1 | mosaic adapter code 69580 |  | Each | 2 | 61009692 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-03-28 | Accounted transaction received
3975282 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 160.5 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 2 | 61009693 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-03-28 | Accounted transaction received
3975283 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5928 | 1 | لاكور بواط على فليكسبل EMT المقاس 3/4 " |  | Each | 200 | 61009694 |  |  |  | لاكور بواط على فليكسبل EMT المقاس 3/4 " | 030020100214 | MEP | Received | 2023-03-28 | Accounted transaction received
3975284 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 754.57 | 1 | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 |  | Each | 1 | 61009695 |  |  |  | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 | 030060100957 | MEP | Received | 2023-03-28 | Accounted transaction received
3975285 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1289.11 | 1 | بواط ثماني فتحات ¾ المقاس ¾ " |  | Each | 20 | 60927788 |  |  |  | بواط ثماني فتحات ¾ المقاس ¾ " | 030020100098 | MEP | Received | 2023-03-28 | Accounted transaction received
3975286 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 958.74 | 1 | ماسورة 32مم UPVC سمك ثقيل قطر خارجي 32 قطر داخلي 26.6مم اللفة= 15×3 متر(اللون أبيض) |  | Meter | 45 | 60927789 |  |  |  | ماسورة 32مم UPVC سمك ثقيل قطر خارجي 32 قطر داخلي 26.6مم اللفة= 15×3 متر(اللون أبيض) | 030010000054 | MEP | Received | 2023-03-28 | Accounted transaction received
3975287 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1345.03 | 1 | بواط 10 * 10 عالى المقاس ¾ " |  | Each | 20 | 60927790 |  |  |  | بواط 10 * 10 عالى المقاس ¾ " | 030020100105 | MEP | Received | 2023-03-28 | Accounted transaction received
3975288 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 183.14 | 1 | جلبة ماسورة 32مم UPVC (اللون أبيض) |  | Each | 45 | 60927791 |  |  |  | جلبة ماسورة 32مم UPVC (اللون أبيض) | 030010000069 | MEP | Received | 2023-03-28 | Accounted transaction received
3975289 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 277.76 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 1 | 60927792 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) | 030010000059 | MEP | Received | 2023-03-28 | Accounted transaction received
3975290 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 75.13 | 1 | أفيز أثنين جناح لماسورة EMT المقاس ¾ " |  | Each | 30 | 60927793 |  |  |  | أفيز أثنين جناح لماسورة EMT المقاس ¾ " | 030020100033 | MEP | Received | 2023-03-28 | Accounted transaction received
3975291 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 147.16 | 1 | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 |  | Each | 5 | 60927794 |  |  |  | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 | 030060100021 | MEP | Received | 2023-03-28 | Accounted transaction received
3975292 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2558.72 | 1 | HDMI PRE-CONN 1M Code 572596 |  | Each | 2 | 60927795 |  |  |  | HDMI PRE-CONN 1M Code 572596 | 030060100165 | MEP | Received | 2023-03-28 | Accounted transaction received
3975293 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 629.16 | 1 | RJ45 SOCKET - CAT. 6 UTP - 8 CONTACTS - 1 MOD Code 572302 |  | Each | 4 | 60927796 |  |  |  | RJ45 SOCKET - CAT. 6 UTP - 8 CONTACTS - 1 MOD Code 572302 | 030060100031 | MEP | Received | 2023-03-28 | Accounted transaction received
3975294 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3437.96 | 1 | SWITCH 20AX 1 WAY 1 MOD Code 572509 |  | Each | 25 | 60927797 |  |  |  | SWITCH 20AX 1 WAY 1 MOD Code 572509 | 030060100048 | MEP | Received | 2023-03-28 | Accounted transaction received
3975295 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4097.61 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 63 | 60927798 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-03-28 | Accounted transaction received
3975296 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 178.84 | 1 | TV "F" TYPE 1 MOD Code 572663 |  | Each | 2 | 60927799 |  |  |  | TV "F" TYPE 1 MOD Code 572663 | 030060100134 | MEP | Received | 2023-03-28 | Accounted transaction received
3975297 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1482.45 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 12 | 60927800 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-03-28 | Accounted transaction received
3975298 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 368.29 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 8 | 60927801 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-03-28 | Accounted transaction received
3975299 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 314.98 | 1 | 576540 Code وش 1 فتحة |  | Each | 9 | 60927802 |  |  |  | 576540 Code وش 1 فتحة | 030060100266 | MEP | Received | 2023-03-28 | Accounted transaction received
3975300 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 654.94 | 1 | 576562 Code وش مربع فضي |  | Each | 20 | 60927803 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-03-28 | Accounted transaction received
3975301 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 765.94 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) |  | Meter | 100 | 60927804 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) | 030030101026 | MEP | Received | 2023-03-28 | Accounted transaction received
3975302 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 756.71 | 1 | سلك نحاس مجدول مقاس 3 مم اللون أزرق (cu/pvc) |  | Meter | 100 | 60927805 |  |  |  | سلك نحاس مجدول مقاس 3 مم اللون أزرق (cu/pvc) | 030030101020 | MEP | Received | 2023-03-28 | Accounted transaction received
3975303 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3184.27 | 1 | LID & TRIM 3 COMPARTMENTS GREY ( Legrand 689631 ) |  | Each | 4 | 60927806 |  |  |  | LID & TRIM 3 COMPARTMENTS GREY ( Legrand 689631 ) | 030060100738 | MEP | Received | 2023-03-28 | Accounted transaction received
3975304 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4253.24 | 1 | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser |  | Each | 10 | 60927807 |  |  |  | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser | 030040700472 | MEP | Received | 2023-03-28 | Accounted transaction received
3975305 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 592.8 | 1 | لاكور بواط على فليكسبل EMT المقاس 3/4 " |  | Each | 20 | 60927808 |  |  |  | لاكور بواط على فليكسبل EMT المقاس 3/4 " | 030020100214 | MEP | Received | 2023-03-28 | Accounted transaction received
3975306 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-03-23 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 237.05 | 1 | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 |  | Each | 3 | 60927809 |  |  |  | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 | 030060100956 | MEP | Received | 2023-03-28 | Accounted transaction received
3975307 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-23 | Hardware |  |  |  | Materials | Waldorf Astoria-0164 | 198 | 1 | Hardware Accessories for Wooden Doors Double Cylinder TESA Security TE-5 Double Cylinder 35x35mm. 5 Spring Loaded Anti pick Pins. Made to EN-1303 Regulation. |  | Each | 1 | 60927869 |  |  |  | Hardware Accessories for Wooden Doors Double Cylinder TESA Security TE-5 Double Cylinder 35x35mm. 5 Spring Loaded Anti pick Pins. Made to EN-1303 Regulation. | 250010001519 | Procurement | Received | 2023-03-28 | Accounted transaction received
3975308 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-23 | Hardware |  |  |  | Materials | Waldorf Astoria-0164 | 216.01 | 1 | Hardware Accessories for Wooden Doors Ball Catch Ball Catch Size:25.5x39mm Material: Brass Finish: NP TESA DDBC002 S.S.S |  | Each | 2 | 60927870 |  |  |  | Hardware Accessories for Wooden Doors Ball Catch Ball Catch Size:25.5x39mm Material: Brass Finish: NP TESA DDBC002 S.S.S | 250010001523 | Procurement | Received | 2023-03-28 | Accounted transaction received
3975309 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-23 | Hardware |  |  |  | Materials | Waldorf Astoria-0164 | 1046.52 | 1 | Hardware Accessories for Doors FLUSH BOLT FOR WOODEN DOORS with DUST PROOF STRIKE Rockwood 557 x 570 626 |  | Each | 1 | 60927871 |  |  |  | Hardware Accessories for Doors FLUSH BOLT FOR WOODEN DOORS with DUST PROOF STRIKE Rockwood 557 x 570 626 | 250010001573 | Procurement | Received | 2023-03-28 | Accounted transaction received
3975310 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-23 | Other |  |  |  | Other | Waldorf Astoria-0164 | 14820 | 1 | Action floor spring max 180kg for Glass doors, brand Stanley |  | Each | 2 | 60927872 |  |  |  | Action floor spring max 180kg for Glass doors, brand Stanley | 310010000018 | Fleets | Received | 2023-03-28 | Accounted transaction received
3975311 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-23 | Other |  |  |  | Other | Waldorf Astoria-0164 | 85.5 | 1 | Spring action Floor Bolt with Automatic mechanism Dust proof XA808B DUST PROOF STRIKE, with Satin Stainless-Steel Finish |  | Each | 1 | 60927873 |  |  |  | Spring action Floor Bolt with Automatic mechanism Dust proof XA808B DUST PROOF STRIKE, with Satin Stainless-Steel Finish | 250010001696 | Procurement | Received | 2023-03-28 | Accounted transaction received
3975312 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 7.04. | Joint Sealent | 7 | THERMAL & MOISTURE P |  | 2023-03-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 228 | 1 | Master Seal NP 472 |  | Kit | 2 | 60927880 |  |  |  | Master Seal NP 472 | 360010000355 | Purchasing | Received | 2023-03-28 | Accounted transaction received
3975313 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 7.04. | Joint Sealent | 7 | THERMAL & MOISTURE P |  | 2023-03-23 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 37335.6 | 1 | Wall covering – WC-3 – Cole & Son- The Ardmore Collection, Narina Linen 109/10049 |  | Roll | 12 | 60927881 |  |  |  | Wall covering – WC-3 – Cole & Son- The Ardmore Collection, Narina Linen 109/10049 | 050020000013 | Purchasing | Received | 2023-03-28 | Accounted transaction received
3975314 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 257.32 | 1 | بلية 6205 |  | Each | 6 | 60955951 |  |  |  | بلية 6205 | 330020000004 | Equipment | Received | 2023-03-28 | Accounted transaction received
3975315 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 45 | 1 | بيبة بوجية |  | Each | 3 | 60955952 |  |  |  | بيبة بوجية | 330040000285 | Equipment | Received | 2023-03-28 | Accounted transaction received
3975316 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 45 | 1 | مفتاح تشغيل معده ( دكاك ) |  | Each | 3 | 60955953 |  |  |  | مفتاح تشغيل معده ( دكاك ) | 330040000466 | Equipment | Received | 2023-03-28 | Accounted transaction received
3975317 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 240 | 1 | طقم صباب روبن A420 |  | Each | 3 | 60955954 |  |  |  | طقم صباب روبن A420 | 330040000981 | Equipment | Received | 2023-03-28 | Accounted transaction received
3975318 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1050 | 1 | بستم روبن A420 |  | Each | 3 | 60955955 |  |  |  | بستم روبن A420 | 330040001244 | Equipment | Received | 2023-03-28 | Accounted transaction received
3975319 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 675 | 1 | بيل روبن A420 |  | Each | 3 | 60955956 |  |  |  | بيل روبن A420 | 330040001245 | Equipment | Received | 2023-03-28 | Accounted transaction received
3975320 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 525 | 1 | كربراتير روبن A420 |  | Each | 3 | 60955957 |  |  |  | كربراتير روبن A420 | 330040001246 | Equipment | Received | 2023-03-28 | Accounted transaction received
3975321 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 90 | 1 | طقم جوان روبن A420 |  | Each | 3 | 60955958 |  |  |  | طقم جوان روبن A420 | 330040001247 | Equipment | Received | 2023-03-28 | Accounted transaction received
3975322 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 345 | 1 | وش شداد بالكوباية روبن |  | Each | 3 | 60955959 |  |  |  | وش شداد بالكوباية روبن | 330040001704 | Equipment | Received | 2023-03-28 | Accounted transaction received
3975323 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 443.69 | 1 | Shell RimR3X 20w50 - زيت شل |  | Liter | 7 | 60955960 |  |  |  | Shell RimR3X 20w50 - زيت شل | 340020000068 | Purchasing | Received | 2023-03-28 | Accounted transaction received
3975324 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 47.48 | 1 | هواية EY 20 |  | Each | 1 | 60955961 |  |  |  | هواية EY 20 | 330040004125 | Equipment | Received | 2023-03-28 | Accounted transaction received
3975325 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 90 | 1 | اويل سيل سوسته 20×35×7 |  | Each | 6 | 60955962 |  |  |  | اويل سيل سوسته 20×35×7 | 330040004816 | Equipment | Received | 2023-03-28 | Accounted transaction received
3975326 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 518.7 | 1 | طقم قلم فيسفوري استنجر الماني |  | Each | 20 | 60956161 |  |  |  | طقم قلم فيسفوري استنجر الماني | 910010000116 | Administration | Received | 2023-03-28 | Accounted transaction received
3975327 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1932.3 | 1 | دباسة متوسطة |  | Each | 20 | 60956162 |  |  |  | دباسة متوسطة | 910010000174 | Administration | Received | 2023-03-28 | Accounted transaction received
3975328 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2880 | 1 | رزمة ورق تصوير باور A4 |  | Each | 20 | 60956163 |  |  |  | رزمة ورق تصوير باور A4 | 910020000002 | Administration | Received | 2023-03-28 | Accounted transaction received
3975329 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1455 | 1 | كشكول سلك A5 |  | Each | 30 | 60956164 |  |  |  | كشكول سلك A5 | 910010000261 | Administration | Received | 2023-03-28 | Accounted transaction received
3975330 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 188.1 | 1 | قلم جاف Roto |  | Each | 60 | 60956165 |  |  |  | قلم جاف Roto | 910010000426 | Administration | Received | 2023-03-28 | Accounted transaction received
3975331 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 18468 | 1 | seamless steel pipe size 1" SCH.40 |  | Meter | 60 | 60957655 |  |  |  | seamless steel pipe size 1" SCH.40 | 060010500013 | MEP | Received | 2023-03-28 | Accounted transaction received
3975332 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 48153.6 | 1 | seamless steel pipe size 2" SCH.40 |  | Meter | 96 | 60957656 |  |  |  | seamless steel pipe size 2" SCH.40 | 060010500022 | MEP | Received | 2023-03-28 | Accounted transaction received
3975333 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 342 | 1 | Hardware Accessories for Wooden Doors Mortice lock without Double Cylinder TESA Entrance Mortice Lock without Cylinder - Sash lock for timber doors. |  | Each | 1 | 60958216 |  |  |  | Hardware Accessories for Wooden Doors Mortice lock without Double Cylinder TESA Entrance Mortice Lock without Cylinder - Sash lock for timber doors. | 250010001518 | Procurement | Received | 2023-03-28 | Accounted transaction received
3975334 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 375.31 | 1 | Exhaust Air Grille 6" * 6" |  | Each | 2 | 60959134 |  |  |  | Exhaust Air Grille 6" * 6" | 060070100202 | MEP | Received | 2023-03-28 | Accounted transaction received
3975335 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 15911.48 | 1 | Slot Diffuser 3 Slot 1" spacing Length 1.8 Meter C/W hit & miss damper |  | Each | 8 | 60959135 |  |  |  | Slot Diffuser 3 Slot 1" spacing Length 1.8 Meter C/W hit & miss damper | 060070300101 | MEP | Received | 2023-03-28 | Accounted transaction received
3975336 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 551.3 | 1 | Slot Diffuser 1 Slot 1" spacing Length 1 Meter C/W hit & miss damper |  | Each | 1 | 60959136 |  |  |  | Slot Diffuser 1 Slot 1" spacing Length 1 Meter C/W hit & miss damper | 060070300102 | MEP | Received | 2023-03-28 | Accounted transaction received
3975337 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 5805.66 | 1 | Slot Diffuser 2 Slot 1" spacing Length 1.8 Meter C/W hit & miss damper |  | Each | 4 | 60959137 |  |  |  | Slot Diffuser 2 Slot 1" spacing Length 1.8 Meter C/W hit & miss damper | 060070300103 | MEP | Received | 2023-03-28 | Accounted transaction received
3975338 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3977.87 | 1 | Slot Diffuser 3 Slot 1" spacing Length 3.6 Meter C/W hit & miss damper |  | Each | 1 | 60959138 |  |  |  | Slot Diffuser 3 Slot 1" spacing Length 3.6 Meter C/W hit & miss damper | 060070300104 | MEP | Received | 2023-03-28 | Accounted transaction received
3975339 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 12549.59 | 1 | Slot Diffuser 1 Slot 1" spacing Length 1.2 Meter C/W hit & miss damper |  | Each | 19 | 60959139 |  |  |  | Slot Diffuser 1 Slot 1" spacing Length 1.2 Meter C/W hit & miss damper | 060070300105 | MEP | Received | 2023-03-28 | Accounted transaction received
3975340 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3867.61 | 1 | Slot Diffuser 2 Slot 1" spacing Length 1.2 Meter C/W hit & miss damper |  | Each | 4 | 60959140 |  |  |  | Slot Diffuser 2 Slot 1" spacing Length 1.2 Meter C/W hit & miss damper | 060070300106 | MEP | Received | 2023-03-28 | Accounted transaction received
3975341 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2977.04 | 1 | Slot Diffuser 1 Slot 1" spacing Length 1.8 Meter C/W hit & miss damper |  | Each | 3 | 60959141 |  |  |  | Slot Diffuser 1 Slot 1" spacing Length 1.8 Meter C/W hit & miss damper | 060070300107 | MEP | Received | 2023-03-28 | Accounted transaction received
3975342 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2582.65 | 1 | Return Slot Diffuser 3 Slot 1" spacing Length 1.8 Meter |  | Each | 2 | 60959142 |  |  |  | Return Slot Diffuser 3 Slot 1" spacing Length 1.8 Meter | 060070300108 | MEP | Received | 2023-03-28 | Accounted transaction received
3975343 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3910.02 | 1 | Return Slot Diffuser 2 Slot 1" spacing Length 1.8 Meter |  | Each | 4 | 60959143 |  |  |  | Return Slot Diffuser 2 Slot 1" spacing Length 1.8 Meter | 060070300109 | MEP | Received | 2023-03-28 | Accounted transaction received
3988139 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-04-05 | Transportation |  |  |  | Indirect | Alrowad Construction_OU | 259 | 1 | تسويه ك /146-149-151-154-160-162-163-164-169-170-172-173- متنوعات-شهر4-23 | st-146-149-151-154-160-162-163-164-169-170-172-173 | Currency | 259 | 22500151 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /146-149-151-154-160-162-163-164-169-170-172-173- متنوعات-شهر4-23 |  | Finacial | Received | 2023-04-06 | Accounted transaction received
3988140 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-04-05 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 700 | 1 | تسويه ك /146-149-151-154-160-162-163-164-169-170-172-173- متنوعات-شهر4-23 | st-146-149-151-154-160-162-163-164-169-170-172-173 | Currency | 700 | 22500151 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /146-149-151-154-160-162-163-164-169-170-172-173- متنوعات-شهر4-23 |  | Finacial | Received | 2023-04-06 | Accounted transaction received
3988141 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.13 | Maintenance | 17 | Indirect Cost |  | 2023-04-05 | Maintenance |  |  |  | Indirect | Alrowad Construction_OU | 850 | 1 | تسويه ك /146-149-151-154-160-162-163-164-169-170-172-173- متنوعات-شهر4-23 | st-146-149-151-154-160-162-163-164-169-170-172-173 | Currency | 850 | 22500151 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /146-149-151-154-160-162-163-164-169-170-172-173- متنوعات-شهر4-23 |  | Finacial | Received | 2023-04-06 | Accounted transaction received
3988142 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.13 | Maintenance | 17 | Indirect Cost |  | 2023-04-05 | Maintenance |  |  |  | Indirect | Alrowad Construction_OU | 2574 | 1 | تسويه ك /146-149-151-154-160-162-163-164-169-170-172-173- متنوعات-شهر4-23 | st-146-149-151-154-160-162-163-164-169-170-172-173 | Currency | 2574 | 22500151 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /146-149-151-154-160-162-163-164-169-170-172-173- متنوعات-شهر4-23 |  | Finacial | Received | 2023-04-06 | Accounted transaction received
4002229 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 116977.75 | 1 | Acolyte - ARB95SWBC203. 027 - Rapid Ribbon 95+ - LED Strip with 9.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser |  | Each | 250 | 61235107 |  |  |  | Acolyte - ARB95SWBC203. 027 - Rapid Ribbon 95+ - LED Strip with 9.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser | 030040700471 | MEP | Received | 2023-04-16 | Accounted transaction received
4002230 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 351.76 | 1 | بواط 10 * 10 عالى المقاس 1 " |  | Each | 5 | 61236720 |  |  |  | بواط 10 * 10 عالى المقاس 1 " | 030020100104 | MEP | Received | 2023-04-16 | Accounted transaction received
4002231 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 742.14 | 1 | سلك نحاس مصمت مقاس 4 مم اللون أصفر (cu/xlpe) جهد (750/450) |  | Meter | 100 | 61236721 |  |  |  | سلك نحاس مصمت مقاس 4 مم اللون أصفر (cu/xlpe) جهد (750/450) | 030030100290 | MEP | Received | 2023-04-16 | Accounted transaction received
4002232 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5719.51 | 1 | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 |  | Meter | 61 | 61236722 |  |  |  | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 | 030020100002 | MEP | Received | 2023-04-16 | Accounted transaction received
4002233 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4102.86 | 1 | ماسورة صلب مجلفن EMT المقاس 1 " طول الماسورة 3.05 |  | Meter | 30.5 | 61236723 |  |  |  | ماسورة صلب مجلفن EMT المقاس 1 " طول الماسورة 3.05 | 030020100003 | MEP | Received | 2023-04-16 | Accounted transaction received
4002234 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 258.54 | 1 | لاكور ماسورة EMT المقاس 1 " |  | Each | 30 | 61236724 |  |  |  | لاكور ماسورة EMT المقاس 1 " | 030020100016 | MEP | Received | 2023-04-16 | Accounted transaction received
4002235 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 451.08 | 1 | جلبة ماسورة EMT المقاس ¾ " |  | Each | 25 | 61236725 |  |  |  | جلبة ماسورة EMT المقاس ¾ " | 030020100021 | MEP | Received | 2023-04-16 | Accounted transaction received
4002236 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 253.52 | 1 | جلبة ماسورة EMT المقاس 1 " |  | Each | 10 | 61236726 |  |  |  | جلبة ماسورة EMT المقاس 1 " | 030020100022 | MEP | Received | 2023-04-16 | Accounted transaction received
4002237 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 182.4 | 1 | أفيز أثنين جناح لماسورة EMT المقاس 1 " |  | Each | 50 | 61236727 |  |  |  | أفيز أثنين جناح لماسورة EMT المقاس 1 " | 030020100034 | MEP | Received | 2023-04-16 | Accounted transaction received
4002238 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 618.08 | 1 | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 |  | Each | 21 | 61236728 |  |  |  | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 | 030060100021 | MEP | Received | 2023-04-16 | Accounted transaction received
4002239 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 559.21 | 1 | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 |  | Each | 19 | 61236729 |  |  |  | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 | 030060100021 | MEP | Received | 2023-04-16 | Accounted transaction received
4002240 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 588.65 | 1 | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 |  | Each | 20 | 61236730 |  |  |  | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 | 030060100021 | MEP | Received | 2023-04-16 | Accounted transaction received
4002241 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1101.03 | 1 | RJ45 SOCKET - CAT. 6 UTP - 8 CONTACTS - 1 MOD Code 572302 |  | Each | 7 | 61236731 |  |  |  | RJ45 SOCKET - CAT. 6 UTP - 8 CONTACTS - 1 MOD Code 572302 | 030060100031 | MEP | Received | 2023-04-16 | Accounted transaction received
4002242 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1415.61 | 1 | RJ45 SOCKET - CAT. 6 UTP - 8 CONTACTS - 1 MOD Code 572302 |  | Each | 9 | 61236732 |  |  |  | RJ45 SOCKET - CAT. 6 UTP - 8 CONTACTS - 1 MOD Code 572302 | 030060100031 | MEP | Received | 2023-04-16 | Accounted transaction received
4002243 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1101.03 | 1 | RJ45 SOCKET - CAT. 6 UTP - 8 CONTACTS - 1 MOD Code 572302 |  | Each | 7 | 61236733 |  |  |  | RJ45 SOCKET - CAT. 6 UTP - 8 CONTACTS - 1 MOD Code 572302 | 030060100031 | MEP | Received | 2023-04-16 | Accounted transaction received
4002244 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1560.99 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 24 | 61236734 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-04-16 | Accounted transaction received
4002245 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1300.83 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 20 | 61236735 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-04-16 | Accounted transaction received
4002246 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 89.42 | 1 | TV "F" TYPE 1 MOD Code 572663 |  | Each | 1 | 61236736 |  |  |  | TV "F" TYPE 1 MOD Code 572663 | 030060100134 | MEP | Received | 2023-04-16 | Accounted transaction received
4002247 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 617.69 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 5 | 61236737 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-04-16 | Accounted transaction received
4002248 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 494.15 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 4 | 61236738 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-04-16 | Accounted transaction received
4002249 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 17.75 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 1 | 61236739 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-04-16 | Accounted transaction received
4002250 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 454.97 | 1 | PLATE 2SQ MOD F-G WHITE Code 576560 |  | Each | 13 | 61236740 |  |  |  | PLATE 2SQ MOD F-G WHITE Code 576560 | 030060100267 | MEP | Received | 2023-04-16 | Accounted transaction received
4002251 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 38.74 | 1 | PLATE 1SQ MOD SCH GRAPHITE Code 576552 |  | Each | 1 | 61236741 |  |  |  | PLATE 1SQ MOD SCH GRAPHITE Code 576552 | 030060100297 | MEP | Received | 2023-04-16 | Accounted transaction received
4002252 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 688.91 | 1 | SHAVER SOCKET 230V/120-230V WITH EARTH CONNECTOR Code 572653 |  | Each | 1 | 61236742 |  |  |  | SHAVER SOCKET 230V/120-230V WITH EARTH CONNECTOR Code 572653 | 030060100178 | MEP | Received | 2023-04-16 | Accounted transaction received
4002253 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 98.24 | 1 | 576562 Code وش مربع فضي |  | Each | 3 | 61236743 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-04-16 | Accounted transaction received
4002254 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 629.96 | 1 | COVER 4 M SQUARE 2X2 WHITE F 576000 Code 575080 |  | Each | 9 | 61236744 |  |  |  | COVER 4 M SQUARE 2X2 WHITE F 576000 Code 575080 | 030060100231 | MEP | Received | 2023-04-16 | Accounted transaction received
4002255 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 769.96 | 1 | COVER 4 M SQUARE 2X2 WHITE F 576000 Code 575080 |  | Each | 11 | 61236745 |  |  |  | COVER 4 M SQUARE 2X2 WHITE F 576000 Code 575080 | 030060100231 | MEP | Received | 2023-04-16 | Accounted transaction received
4002256 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 629.96 | 1 | COVER 4 M SQUARE 2X2 WHITE F 576000 Code 575080 |  | Each | 9 | 61236746 |  |  |  | COVER 4 M SQUARE 2X2 WHITE F 576000 Code 575080 | 030060100231 | MEP | Received | 2023-04-16 | Accounted transaction received
4002257 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 942.12 | 1 | CARRIER PLATE SYNERGY code 730094 |  | Each | 14 | 61236747 |  |  |  | CARRIER PLATE SYNERGY code 730094 | 030060100534 | MEP | Received | 2023-04-16 | Accounted transaction received
4002258 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 879.36 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أزرق (cu/pvc) |  | Meter | 100 | 61236748 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أزرق (cu/pvc) | 030030101025 | MEP | Received | 2023-04-16 | Accounted transaction received
4002259 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 765.94 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) |  | Meter | 100 | 61236749 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) | 030030101026 | MEP | Received | 2023-04-16 | Accounted transaction received
4002260 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 811.12 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أصفر × أخضر (cu/pvc) |  | Meter | 100 | 61236750 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أصفر × أخضر (cu/pvc) | 030030101027 | MEP | Received | 2023-04-16 | Accounted transaction received
4002261 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 449.42 | 1 | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 |  | Each | 1 | 61236751 |  |  |  | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 | 030060100572 | MEP | Received | 2023-04-16 | Accounted transaction received
4002262 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 38.02 | 1 | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 |  | Each | 2 | 61236752 |  |  |  | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 | 150020000178 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002263 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 95.09 | 1 | mosaic adapter code 69580 |  | Each | 1 | 61236753 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-04-16 | Accounted transaction received
4002264 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 80.25 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 1 | 61236754 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-04-16 | Accounted transaction received
4002265 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 501.05 | 1 | WA PLATE 77MM 2X2MOD MOSAIC ( Legrand 689673 ) |  | Each | 4 | 61236755 |  |  |  | WA PLATE 77MM 2X2MOD MOSAIC ( Legrand 689673 ) | 030060100741 | MEP | Received | 2023-04-16 | Accounted transaction received
4002266 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2254.74 | 1 | WA PLATE 77MM 2X2MOD MOSAIC ( Legrand 689673 ) |  | Each | 18 | 61236756 |  |  |  | WA PLATE 77MM 2X2MOD MOSAIC ( Legrand 689673 ) | 030060100741 | MEP | Received | 2023-04-16 | Accounted transaction received
4002267 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 200.78 | 1 | SPLASH PROOF COVER Code : 617636 |  | Each | 2 | 61236757 |  |  |  | SPLASH PROOF COVER Code : 617636 | 030060100927 | MEP | Received | 2023-04-16 | Accounted transaction received
4002268 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 225.36 | 1 | 1G 20A DP SWT + NEON + E WH - 617671 |  | Each | 2 | 61236758 |  |  |  | 1G 20A DP SWT + NEON + E WH - 617671 | 030060100942 | MEP | Received | 2023-04-16 | Accounted transaction received
4002269 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 260.01 | 1 | Double pole switches 32 A – 250V~ 1 gang 1?way switch + led power indicator - 617629 |  | Each | 2 | 61236759 |  |  |  | Double pole switches 32 A – 250V~ 1 gang 1?way switch + led power indicator - 617629 | 030060100943 | MEP | Received | 2023-04-16 | Accounted transaction received
4002270 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 494.72 | 1 | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 |  | Each | 4 | 61236760 |  |  |  | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 | 030060100951 | MEP | Received | 2023-04-16 | Accounted transaction received
4002271 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 247.36 | 1 | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 |  | Each | 2 | 61236761 |  |  |  | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 | 030060100951 | MEP | Received | 2023-04-16 | Accounted transaction received
4002272 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 371.04 | 1 | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 |  | Each | 3 | 61236762 |  |  |  | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 | 030060100951 | MEP | Received | 2023-04-16 | Accounted transaction received
4002273 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 284.08 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 5 | 61236763 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-04-16 | Accounted transaction received
4002274 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 113.63 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 2 | 61236764 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-04-16 | Accounted transaction received
4002275 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1136.33 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 20 | 61236765 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-04-16 | Accounted transaction received
4002276 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 474.1 | 1 | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 |  | Each | 6 | 61236766 |  |  |  | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 | 030060100956 | MEP | Received | 2023-04-16 | Accounted transaction received
4002277 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 170 | 1 | وردة 8 مم |  | Kilogram | 2 | 61252825 |  |  |  | وردة 8 مم | 200020000145 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002278 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2875.02 | 1 | جاسكت |  | Roll | 50 | 61252826 |  |  |  | جاسكت | 200010001335 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002279 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2188.83 | 1 | فلكسيبل معدن المقاس ¾ " |  | Meter | 84 | 61252892 |  |  |  | فلكسيبل معدن المقاس ¾ " | 030020100091 | MEP | Received | 2023-04-16 | Accounted transaction received
4002280 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 300 | 1 | سيليكون بيج |  | Each | 5 | 61252893 |  |  |  | سيليكون بيج | 200010000947 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002281 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 342 | 1 | حزام تيراب 20 سم |  | Each | 10 | 61252894 |  |  |  | حزام تيراب 20 سم | 200010001179 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002282 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 239.4 | 1 | ريكم ألوان 70 مم |  | Meter | 6 | 61252895 |  |  |  | ريكم ألوان 70 مم | 030131000023 | MEP | Received | 2023-04-16 | Accounted transaction received
4002283 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 912 | 1 | Network Tester |  | Each | 1 | 61252896 |  |  |  | Network Tester | 800040000024 | IT | Received | 2023-04-16 | Accounted transaction received
4002284 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 171 | 1 | ريكم ألوان 50 مم |  | Meter | 6 | 61252897 |  |  |  | ريكم ألوان 50 مم | 030131000037 | MEP | Received | 2023-04-16 | Accounted transaction received
4002285 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 171 | 1 | ريكم ألوان 25 مم |  | Meter | 6 | 61252898 |  |  |  | ريكم ألوان 25 مم | 030131000038 | MEP | Received | 2023-04-16 | Accounted transaction received
4002286 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 273.6 | 1 | ريكم فاى 150مم |  | Meter | 6 | 61252899 |  |  |  | ريكم فاى 150مم | 030060100599 | MEP | Received | 2023-04-16 | Accounted transaction received
4002287 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-04-12 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 524.4 | 1 | خواشة 20 مم |  | Each | 2 | 61252952 |  |  |  | خواشة 20 مم | 039020200035 | MEP | Received | 2023-04-16 | Accounted transaction received
4002288 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-04-12 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 1140 | 1 | خواشة 22 مم |  | Each | 4 | 61252953 |  |  |  | خواشة 22 مم | 039020200041 | MEP | Received | 2023-04-16 | Accounted transaction received
4002289 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 712.5 | 1 | تيب دوكو |  | Each | 25 | 61253019 |  |  |  | تيب دوكو | 200010000048 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002290 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 655.5 | 1 | جبس |  | Ton | 0.25 | 61253020 |  |  |  | جبس | 140010000004 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002291 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 79.8 | 1 | سلاح كتر |  | Each | 2 | 61253021 |  |  |  | سلاح كتر | 200010000411 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002292 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 513 | 1 | فوطة صفراء |  | Each | 10 | 61253022 |  |  |  | فوطة صفراء | 200010000478 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002293 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2561.58 | 1 | مشمع اسود حفيف |  | Roll | 1 | 61253023 |  |  |  | مشمع اسود حفيف | 040010000055 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002294 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 99624.88 | 1 | فوم ابيض سمك 20سم كثافة 35 |  | Cubic Meter | 25 | 61253834 |  |  |  | فوم ابيض سمك 20سم كثافة 35 | 040010000184 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002295 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 333.34 | 1 | بواط إمتداد UPVC لماسورة 25مم(اللون أبيض) |  | Each | 40 | 61254711 |  |  |  | بواط إمتداد UPVC لماسورة 25مم(اللون أبيض) | 030010000083 | MEP | Received | 2023-04-16 | Accounted transaction received
4002296 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2770.61 | 1 | سلك نحاس مصمت مقاس 70 مم اللون أصفر × أخضر (cu/pvc) جهد (750/450) |  | Meter | 9 | 61254712 |  |  |  | سلك نحاس مصمت مقاس 70 مم اللون أصفر × أخضر (cu/pvc) جهد (750/450) | 030030100365 | MEP | Received | 2023-04-16 | Accounted transaction received
4002297 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 15569.21 | 1 | كابل نحاس ترمو ضغط منخفض مقاس 3 × 150 + 70 مم (xlpe/pvc) |  | Meter | 6 | 61254713 |  |  |  | كابل نحاس ترمو ضغط منخفض مقاس 3 × 150 + 70 مم (xlpe/pvc) | 030030100023 | MEP | Received | 2023-04-16 | Accounted transaction received
4002298 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3693.6 | 1 | كابل نحاس ترمو ضغط منخفض مقاس 3 × 50 + 25 مم (xlpe/pvc) |  | Meter | 5 | 61254714 |  |  |  | كابل نحاس ترمو ضغط منخفض مقاس 3 × 50 + 25 مم (xlpe/pvc) | 030030100016 | MEP | Received | 2023-04-16 | Accounted transaction received
4002299 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 80.46 | 1 | أفيز أثنين جناح لماسورة EMT المقاس ½ 1 " |  | Each | 15 | 61254715 |  |  |  | أفيز أثنين جناح لماسورة EMT المقاس ½ 1 " | 030020100036 | MEP | Received | 2023-04-16 | Accounted transaction received
4002300 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 649.25 | 1 | LV Power cable SINGLECORE CU/PVC Size 10 MM (450/750 V) |  | Meter | 24 | 61254716 |  |  |  | LV Power cable SINGLECORE CU/PVC Size 10 MM (450/750 V) | 030030101204 | MEP | Received | 2023-04-16 | Accounted transaction received
4002301 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.09.04 | Fire Fighting Networ | 2 | SITE WORK |  | 2023-04-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 399 | 1 | Threaded Mechanical Tee 2½''*1'' UL listed, FM approved |  | Each | 1 | 61254726 |  |  |  | Threaded Mechanical Tee 2½''*1'' UL listed, FM approved | 060011500213 | MEP | Received | 2023-04-16 | Accounted transaction received
4002302 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.09.04 | Fire Fighting Networ | 2 | SITE WORK |  | 2023-04-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1601.33 | 1 | Threaded Mechanical Tee 4''*2'' UL listed, FM approved |  | Each | 1 | 61254727 |  |  |  | Threaded Mechanical Tee 4''*2'' UL listed, FM approved | 060011500226 | MEP | Received | 2023-04-16 | Accounted transaction received
4002303 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.09.04 | Fire Fighting Networ | 2 | SITE WORK |  | 2023-04-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 457.36 | 1 | threaded couplings size 2" UL LISTED,FM APPROVED |  | Each | 7 | 61254728 |  |  |  | threaded couplings size 2" UL LISTED,FM APPROVED | 060010140483 | MEP | Received | 2023-04-16 | Accounted transaction received
4002304 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 798 | 1 | بواط واتر بروف بفتحات مقاس 30 × 38 × 12 سم |  | Each | 2 | 61272196 |  |  |  | بواط واتر بروف بفتحات مقاس 30 × 38 × 12 سم | 030010000185 | MEP | Received | 2023-04-16 | Accounted transaction received
4002305 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 29.43 | 1 | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 |  | Each | 1 | 61272197 |  |  |  | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 | 030060100021 | MEP | Received | 2023-04-16 | Accounted transaction received
4002306 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1279.36 | 1 | HDMI PRE-CONN 1M Code 572596 |  | Each | 1 | 61272198 |  |  |  | HDMI PRE-CONN 1M Code 572596 | 030060100165 | MEP | Received | 2023-04-16 | Accounted transaction received
4002307 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 256.37 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 3 | 61272199 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-04-16 | Accounted transaction received
4002308 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 256.37 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 3 | 61272200 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-04-16 | Accounted transaction received
4002309 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 341.82 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 4 | 61272201 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-04-16 | Accounted transaction received
4002310 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1025.47 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 12 | 61272202 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-04-16 | Accounted transaction received
4002311 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1235.37 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 10 | 61272203 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-04-16 | Accounted transaction received
4002312 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 247.07 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 2 | 61272204 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-04-16 | Accounted transaction received
4002313 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 123.54 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 1 | 61272205 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-04-16 | Accounted transaction received
4002314 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 247.07 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 2 | 61272206 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-04-16 | Accounted transaction received
4002315 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 71.02 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 4 | 61272207 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-04-16 | Accounted transaction received
4002316 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 35.51 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 2 | 61272208 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-04-16 | Accounted transaction received
4002317 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 322.26 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 7 | 61272209 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-04-16 | Accounted transaction received
4002318 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 46.04 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 1 | 61272210 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-04-16 | Accounted transaction received
4002319 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 104.99 | 1 | 576540 Code وش 1 فتحة |  | Each | 3 | 61272211 |  |  |  | 576540 Code وش 1 فتحة | 030060100266 | MEP | Received | 2023-04-16 | Accounted transaction received
4002320 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 139.99 | 1 | PLATE 2SQ MOD F-G WHITE Code 576560 |  | Each | 4 | 61272212 |  |  |  | PLATE 2SQ MOD F-G WHITE Code 576560 | 030060100267 | MEP | Received | 2023-04-16 | Accounted transaction received
4002321 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 35 | 1 | PLATE 2SQ MOD F-G WHITE Code 576560 |  | Each | 1 | 61272213 |  |  |  | PLATE 2SQ MOD F-G WHITE Code 576560 | 030060100267 | MEP | Received | 2023-04-16 | Accounted transaction received
4002322 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 38.74 | 1 | PLATE 1SQ MOD SCH GRAPHITE Code 576552 |  | Each | 1 | 61272214 |  |  |  | PLATE 1SQ MOD SCH GRAPHITE Code 576552 | 030060100297 | MEP | Received | 2023-04-16 | Accounted transaction received
4002323 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 154.95 | 1 | PLATE 1SQ MOD SCH GRAPHITE Code 576552 |  | Each | 4 | 61272215 |  |  |  | PLATE 1SQ MOD SCH GRAPHITE Code 576552 | 030060100297 | MEP | Received | 2023-04-16 | Accounted transaction received
4002324 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 98.24 | 1 | 576562 Code وش مربع فضي |  | Each | 3 | 61272216 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-04-16 | Accounted transaction received
4002325 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 589.45 | 1 | 576562 Code وش مربع فضي |  | Each | 18 | 61272217 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-04-16 | Accounted transaction received
4002326 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 70 | 1 | COVER 4 M SQUARE 2X2 WHITE F 576000 Code 575080 |  | Each | 1 | 61272218 |  |  |  | COVER 4 M SQUARE 2X2 WHITE F 576000 Code 575080 | 030060100231 | MEP | Received | 2023-04-16 | Accounted transaction received
4002327 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 210 | 1 | B ENC BETON POPUP 4 MOD code 54001 |  | Each | 1 | 61272219 |  |  |  | B ENC BETON POPUP 4 MOD code 54001 | 030060100522 | MEP | Received | 2023-04-16 | Accounted transaction received
4002328 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 765.94 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) |  | Meter | 100 | 61272220 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أسود (cu/pvc) | 030030101026 | MEP | Received | 2023-04-16 | Accounted transaction received
4002329 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2682.94 | 1 | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS |  | Each | 12 | 61272221 |  |  |  | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS | 030060100617 | MEP | Received | 2023-04-16 | Accounted transaction received
4002330 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 570.52 | 1 | mosaic adapter code 69580 |  | Each | 6 | 61272222 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-04-16 | Accounted transaction received
4002331 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 481.49 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 6 | 61272223 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-04-16 | Accounted transaction received
4002332 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 584.32 | 1 | FRAME 8 MOD MOSAIC ( Legrand 689658 ) |  | Each | 3 | 61272224 |  |  |  | FRAME 8 MOD MOSAIC ( Legrand 689658 ) | 030060100740 | MEP | Received | 2023-04-16 | Accounted transaction received
4002333 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 222292.07 | 1 | LT.01-Pendant Circular luminaire Ring connected to 220v mains using AC/DC Driver, the luminaire- made of cast Aluminum.Polycarbonate diffuser ensures the diffusivity of the light giving a smooth sensation without any hot or dark spots |  | Each | 66 | 61272225 |  |  |  | LT.01-Pendant Circular luminaire Ring connected to 220v mains using AC/DC Driver, the luminaire- made of cast Aluminum.Polycarbonate diffuser ensures the diffusivity of the light giving a smooth sensation without any hot or dark spots | 030040700490 | MEP | Received | 2023-04-16 | Accounted transaction received
4002334 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 235985.43 | 1 | LT.02-Pendant Circular luminaire Ring connected to 220v mains using AC/DC Driver, the luminaire- made of cast Aluminum. Polycarbonate diffuser ensures the diffusivity of the light giving a smooth sensation without any hot or dark spots. |  | Each | 71 | 61272226 |  |  |  | LT.02-Pendant Circular luminaire Ring connected to 220v mains using AC/DC Driver, the luminaire- made of cast Aluminum. Polycarbonate diffuser ensures the diffusivity of the light giving a smooth sensation without any hot or dark spots. | 030040700491 | MEP | Received | 2023-04-16 | Accounted transaction received
4002335 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 112.68 | 1 | 1G 20A DP SWT + NEON + E WH - 617671 |  | Each | 1 | 61272227 |  |  |  | 1G 20A DP SWT + NEON + E WH - 617671 | 030060100942 | MEP | Received | 2023-04-16 | Accounted transaction received
4002336 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 12887.7 | 1 | LED transformer - ET-E 10 W LED 220-240V |  | Each | 119 | 61272228 |  |  |  | LED transformer - ET-E 10 W LED 220-240V | 039019000062 | MEP | Received | 2023-04-16 | Accounted transaction received
4002337 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 123.68 | 1 | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 |  | Each | 1 | 61272229 |  |  |  | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 | 030060100951 | MEP | Received | 2023-04-16 | Accounted transaction received
4002338 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 123.68 | 1 | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 |  | Each | 1 | 61272230 |  |  |  | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 | 030060100951 | MEP | Received | 2023-04-16 | Accounted transaction received
4002339 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1855.22 | 1 | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 |  | Each | 15 | 61272231 |  |  |  | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 | 030060100951 | MEP | Received | 2023-04-16 | Accounted transaction received
4002340 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1193.15 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 21 | 61272232 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-04-16 | Accounted transaction received
4002341 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 397.72 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 7 | 61272233 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-04-16 | Accounted transaction received
4002342 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 56.82 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 1 | 61272234 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-04-16 | Accounted transaction received
4002343 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1363.6 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 24 | 61272235 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-04-16 | Accounted transaction received
4002344 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 316.07 | 1 | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 |  | Each | 4 | 61272236 |  |  |  | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 | 030060100956 | MEP | Received | 2023-04-16 | Accounted transaction received
4002345 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3018.26 | 1 | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 |  | Each | 4 | 61272237 |  |  |  | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 | 030060100957 | MEP | Received | 2023-04-16 | Accounted transaction received
4002346 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4527.4 | 1 | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 |  | Each | 6 | 61272238 |  |  |  | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 | 030060100957 | MEP | Received | 2023-04-16 | Accounted transaction received
4002347 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 754.57 | 1 | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 |  | Each | 1 | 61272239 |  |  |  | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 | 030060100957 | MEP | Received | 2023-04-16 | Accounted transaction received
4002348 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3018.26 | 1 | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 |  | Each | 4 | 61272240 |  |  |  | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 | 030060100957 | MEP | Received | 2023-04-16 | Accounted transaction received
4002349 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 754.57 | 1 | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 |  | Each | 1 | 61272241 |  |  |  | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 | 030060100957 | MEP | Received | 2023-04-16 | Accounted transaction received
4002350 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 707.94 | 1 | بواط إكستنشن 10 * 10 المقاس 1 " |  | Each | 10 | 61272669 |  |  |  | بواط إكستنشن 10 * 10 المقاس 1 " | 030020100111 | MEP | Received | 2023-04-16 | Accounted transaction received
4002351 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 6783 | 1 | بواط واتر بروف بفتحات مقاس 30 × 38 × 12 سم |  | Each | 17 | 61272670 |  |  |  | بواط واتر بروف بفتحات مقاس 30 × 38 × 12 سم | 030010000185 | MEP | Received | 2023-04-16 | Accounted transaction received
4002352 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 825.11 | 1 | SWITCH 20AX 1 WAY 1 MOD Code 572509 |  | Each | 6 | 61272671 |  |  |  | SWITCH 20AX 1 WAY 1 MOD Code 572509 | 030060100048 | MEP | Received | 2023-04-16 | Accounted transaction received
4002353 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1512.7 | 1 | SWITCH 20AX 1 WAY 1 MOD Code 572509 |  | Each | 11 | 61272672 |  |  |  | SWITCH 20AX 1 WAY 1 MOD Code 572509 | 030060100048 | MEP | Received | 2023-04-16 | Accounted transaction received
4002354 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1235.37 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 10 | 61272673 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-04-16 | Accounted transaction received
4002355 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 988.3 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 8 | 61272674 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-04-16 | Accounted transaction received
4002356 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 271.16 | 1 | PLATE 1SQ MOD SCH GRAPHITE Code 576552 |  | Each | 7 | 61272675 |  |  |  | PLATE 1SQ MOD SCH GRAPHITE Code 576552 | 030060100297 | MEP | Received | 2023-04-16 | Accounted transaction received
4002357 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1473.62 | 1 | 576562 Code وش مربع فضي |  | Each | 45 | 61272676 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-04-16 | Accounted transaction received
4002358 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 807.53 | 1 | CARRIER PLATE SYNERGY code 730094 |  | Each | 12 | 61272677 |  |  |  | CARRIER PLATE SYNERGY code 730094 | 030060100534 | MEP | Received | 2023-04-16 | Accounted transaction received
4002359 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 447.16 | 1 | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS |  | Each | 2 | 61272678 |  |  |  | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS | 030060100617 | MEP | Received | 2023-04-16 | Accounted transaction received
4002360 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 190.17 | 1 | mosaic adapter code 69580 |  | Each | 2 | 61272679 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-04-16 | Accounted transaction received
4002361 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 190.17 | 1 | mosaic adapter code 69580 |  | Each | 2 | 61272680 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-04-16 | Accounted transaction received
4002362 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 570.52 | 1 | mosaic adapter code 69580 |  | Each | 6 | 61272681 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-04-16 | Accounted transaction received
4002363 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 481.49 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 6 | 61272682 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-04-16 | Accounted transaction received
4002364 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1528.83 | 1 | Plate British standard Arteor - square - 3 modules - graphite - 575072 |  | Each | 26 | 61272683 |  |  |  | Plate British standard Arteor - square - 3 modules - graphite - 575072 | 030060100898 | MEP | Received | 2023-04-16 | Accounted transaction received
4002365 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 454.53 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 8 | 61272684 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-04-16 | Accounted transaction received
4002366 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 113.63 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 2 | 61272685 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-04-16 | Accounted transaction received
4002403 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-14 | Other |  |  |  | Other | Waldorf Astoria-0164 | 455.92 | 1 | Shell RimR3X 20w50 - زيت شل |  | Liter | 7 | 61287744 |  |  |  | Shell RimR3X 20w50 - زيت شل | 340020000068 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002367 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 277.76 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 1 | 61273814 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) | 030010000059 | MEP | Received | 2023-04-16 | Accounted transaction received
4002368 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 66.12 | 1 | جلاند فلكسبل مقاس 16 مم |  | Each | 10 | 61273815 |  |  |  | جلاند فلكسبل مقاس 16 مم | 030010000167 | MEP | Received | 2023-04-16 | Accounted transaction received
4002369 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1105.8 | 1 | لاكور ماسورة EMT المقاس ¾ " |  | Each | 50 | 61273816 |  |  |  | لاكور ماسورة EMT المقاس ¾ " | 030020100015 | MEP | Received | 2023-04-16 | Accounted transaction received
4002370 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 570 | 1 | اكستنشن 10*10 مقاس 3/4" |  | Each | 20 | 61273817 |  |  |  | اكستنشن 10*10 مقاس 3/4" | 030020100146 | MEP | Received | 2023-04-16 | Accounted transaction received
4002371 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 57 | 1 | اكستنشن 10*10 مقاس 3/4" |  | Each | 2 | 61273818 |  |  |  | اكستنشن 10*10 مقاس 3/4" | 030020100146 | MEP | Received | 2023-04-16 | Accounted transaction received
4002372 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 570.31 | 1 | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 |  | Each | 30 | 61273819 |  |  |  | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 | 150020000178 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002373 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2126.62 | 1 | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser |  | Each | 5 | 61273820 |  |  |  | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser | 030040700472 | MEP | Received | 2023-04-16 | Accounted transaction received
4002374 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1240.33 | 1 | CEILING MOUNT SPEAKER, Model No. PC-648R |  | Each | 3 | 61273821 |  |  |  | CEILING MOUNT SPEAKER, Model No. PC-648R | 031070000015 | MEP | Received | 2023-04-16 | Accounted transaction received
4002375 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 199.5 | 1 | Hardware accessories for doors HW-103 Wall Doorstop MT-1 |  | Each | 1 | 61274700 |  |  |  | Hardware accessories for doors HW-103 Wall Doorstop MT-1 | 250010001542 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002376 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 13543.2 | 1 | Hardware accessories for doors HW-115 Bespoke Floor Door Stopper MT-1 |  | Each | 22 | 61274701 |  |  |  | Hardware accessories for doors HW-115 Bespoke Floor Door Stopper MT-1 | 250010001543 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002377 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2599.2 | 1 | Hardware accessories for doors Bespoke cover plates in MT-4 Antique brass finish for Floor Spring MT-4 |  | Each | 2 | 61274702 |  |  |  | Hardware accessories for doors Bespoke cover plates in MT-4 Antique brass finish for Floor Spring MT-4 | 250010001561 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002378 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 37905 | 1 | Hardware accessories for doors IR-03 Metal Trim for Lobby Lounge Bar |  | Meter | 50 | 61274703 |  |  |  | Hardware accessories for doors IR-03 Metal Trim for Lobby Lounge Bar | 250010001568 | Procurement | Received | 2023-04-16 | Accounted transaction received
4003713 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 10.06. | Mat | 10 | SPECIALITIES |  | 2023-04-09 | Transportation |  |  |  | Indirect | Alrowad Construction_OU | 19314.67 | 1 | نقل افراد فبراير استوريا | نقل افراد فبراير استوريا | Currency | 19314.67 | 22539647 | 3084 | محمد احمد محمد محمد | Rowad | نقل افراد فبراير استوريا |  | Finacial | Received | 2023-04-16 | Accounted transaction received
4003714 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 10.06. | Mat | 10 | SPECIALITIES |  | 2023-04-09 | Transportation |  |  |  | Indirect | Alrowad Construction_OU | 27412.95 | 1 | نقل افراد فبراير استوريا | نقل افراد فبراير استوريا | Currency | 27412.95 | 22539647 | 9182 | مؤسسة الجينيرال لتأجير السيارات | rowad | نقل افراد فبراير استوريا |  | Finacial | Received | 2023-04-16 | Accounted transaction received
4011321 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-12 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9346 | 1 | 1.1 80894/2 |  | Currency | 467.3 |  | 12636 | مصطفي شعبان عطية بيومي-ذاتى |  | 1.1 80894/2 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4002379 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 684 | 1 | Hardware accessories for doors HW-102 Knob for Minibar |  | Each | 3 | 61274704 |  |  |  | Hardware accessories for doors HW-102 Knob for Minibar | 250010001569 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002380 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1949.4 | 1 | Hardware accessories for doors IR-13 Magnetic Floor Door Holder MT-8 |  | Each | 2 | 61286810 |  |  |  | Hardware accessories for doors IR-13 Magnetic Floor Door Holder MT-8 | 250010001546 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002381 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 11696.4 | 1 | Hardware accessories for doors HW-114 Bespoke Door Pull as per Muza Lab Specification MT-5 |  | Each | 3 | 61286811 |  |  |  | Hardware accessories for doors HW-114 Bespoke Door Pull as per Muza Lab Specification MT-5 | 250010001552 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002382 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 433.2 | 1 | Hardware accessories for doors IR-05 Bespoke Door Pull as per ABD & UWS Specification MT-8 |  | Each | 2 | 61286812 |  |  |  | Hardware accessories for doors IR-05 Bespoke Door Pull as per ABD & UWS Specification MT-8 | 250010001557 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002383 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4765.2 | 1 | Hardware accessories for doors IR-32 Bespoke Door Pull as per ABD & UWS Specification MT-4 |  | Each | 2 | 61286813 |  |  |  | Hardware accessories for doors IR-32 Bespoke Door Pull as per ABD & UWS Specification MT-4 | 250010001559 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002384 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 68445.6 | 1 | Hardware accessories for doors IR-36 Pull Handle as per ABD & UWS Specification MT-4 |  | Each | 8 | 61286814 |  |  |  | Hardware accessories for doors IR-36 Pull Handle as per ABD & UWS Specification MT-4 | 250010001560 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002385 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 7797.6 | 1 | Hardware accessories for doors Bespoke cover plates in MT-4 Antique brass finish for Floor Spring MT-4 |  | Each | 6 | 61286815 |  |  |  | Hardware accessories for doors Bespoke cover plates in MT-4 Antique brass finish for Floor Spring MT-4 | 250010001561 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002386 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3420 | 1 | Mini bar Pull at Pool Bar Finish MT-6 |  | Each | 2 | 61286816 |  |  |  | Mini bar Pull at Pool Bar Finish MT-6 | 250010001660 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002387 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 6270 | 1 | Door pull at Peacock alley service station Finish Polished Brass |  | Each | 5 | 61286817 |  |  |  | Door pull at Peacock alley service station Finish Polished Brass | 250010001661 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002388 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 13338 | 1 | Handle for waiter station at LLB Finish MT-8 |  | Each | 13 | 61286818 |  |  |  | Handle for waiter station at LLB Finish MT-8 | 250010001662 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002389 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 15504 | 1 | Metal Pull Handle ADD Finish MT-4 |  | Each | 17 | 61286819 |  |  |  | Metal Pull Handle ADD Finish MT-4 | 250010001664 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002390 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 28842 | 1 | T-Bar Handle |  | Each | 23 | 61286820 |  |  |  | T-Bar Handle | 250010001667 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002391 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 6384 | 1 | Grommet 6 mm MT-1 |  | Each | 16 | 61286821 |  |  |  | Grommet 6 mm MT-1 | 250010001670 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002392 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 6840 | 1 | IR-25 @ All Day Dining |  | Each | 10 | 61286822 |  |  |  | IR-25 @ All Day Dining | 250010001931 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002393 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 10944 | 1 | Grommet for minibar 6mm @ Guest Rooms and Suites |  | Each | 24 | 61286823 |  |  |  | Grommet for minibar 6mm @ Guest Rooms and Suites | 250010001932 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002394 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.01 | Plumbing Networks | 15 | MECHANICAL WORKS |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1578.31 | 1 | لاكور تجميع ( للمحابس و عدادات المياه ) PPR مقاس 3/4"-25 مم |  | Each | 14 | 61287731 |  |  |  | لاكور تجميع ( للمحابس و عدادات المياه ) PPR مقاس 3/4"-25 مم | 060010300231 | MEP | Received | 2023-04-16 | Accounted transaction received
4002395 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.01 | Plumbing Networks | 15 | MECHANICAL WORKS |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 259.26 | 1 | لاكور تجميع ( للمحابس و عدادات المياه ) PPR مقاس 1"-32 مم |  | Each | 2 | 61287732 |  |  |  | لاكور تجميع ( للمحابس و عدادات المياه ) PPR مقاس 1"-32 مم | 060010300234 | MEP | Received | 2023-04-16 | Accounted transaction received
4002396 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.01 | Plumbing Networks | 15 | MECHANICAL WORKS |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 833.3 | 1 | لاكور تجميع ( للمحابس و عدادات المياه ) PPR مقاس 1.1/4"-40 مم |  | Each | 3 | 61287733 |  |  |  | لاكور تجميع ( للمحابس و عدادات المياه ) PPR مقاس 1.1/4"-40 مم | 060010300235 | MEP | Received | 2023-04-16 | Accounted transaction received
4002397 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.01 | Plumbing Networks | 15 | MECHANICAL WORKS |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 603.26 | 1 | لاكور تجميع ( للمحابس و عدادات المياه ) PPR مقاس 1.1/2"-50 مم |  | Each | 3 | 61287734 |  |  |  | لاكور تجميع ( للمحابس و عدادات المياه ) PPR مقاس 1.1/2"-50 مم | 060010300237 | MEP | Received | 2023-04-16 | Accounted transaction received
4002398 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.01 | Plumbing Networks | 15 | MECHANICAL WORKS |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 776.74 | 1 | جلبه بسن دكر PPR مقاس "1/2-20 مم |  | Each | 27 | 61287735 |  |  |  | جلبه بسن دكر PPR مقاس "1/2-20 مم | 060010300194 | MEP | Received | 2023-04-16 | Accounted transaction received
4002399 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.01 | Plumbing Networks | 15 | MECHANICAL WORKS |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 551.1 | 1 | جلبه بسن دكر PPR مقاس 1.1/4"-40 مم |  | Each | 3 | 61287736 |  |  |  | جلبه بسن دكر PPR مقاس 1.1/4"-40 مم | 060010300199 | MEP | Received | 2023-04-16 | Accounted transaction received
4002400 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.01 | Plumbing Networks | 15 | MECHANICAL WORKS |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1932.81 | 1 | Bronze Gate Valve Threaded DN 1.1/4" PN 16 |  | Each | 3 | 61287737 |  |  |  | Bronze Gate Valve Threaded DN 1.1/4" PN 16 | 060170100032 | MEP | Received | 2023-04-16 | Accounted transaction received
4002401 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.01 | Plumbing Networks | 15 | MECHANICAL WORKS |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2603.82 | 1 | Bronze Gate Valve Threaded DN 1.1/2" PN 16 |  | Each | 3 | 61287738 |  |  |  | Bronze Gate Valve Threaded DN 1.1/2" PN 16 | 060170100033 | MEP | Received | 2023-04-16 | Accounted transaction received
4002402 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.01 | Plumbing Networks | 15 | MECHANICAL WORKS |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1459.2 | 1 | Gate Valve D151 Crane UK DN 32 PN 20 |  | Each | 2 | 61287739 |  |  |  | Gate Valve D151 Crane UK DN 32 PN 20 | 060170100095 | MEP | Received | 2023-04-16 | Accounted transaction received
4002404 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.01 | Plumbing Networks | 15 | MECHANICAL WORKS |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2150.04 | 1 | أنبوبة سليكون |  | Each | 50 | 61288087 |  |  |  | أنبوبة سليكون | 060019000001 | MEP | Received | 2023-04-16 | Accounted transaction received
4002405 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.01 | Plumbing Networks | 15 | MECHANICAL WORKS |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 5872.6 | 1 | Grooved Reducing tee 6''*4'' UL listed, FM approved |  | Each | 1 | 61288088 |  |  |  | Grooved Reducing tee 6''*4'' UL listed, FM approved | 060011500143 | MEP | Received | 2023-04-16 | Accounted transaction received
4002406 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.01 | Plumbing Networks | 15 | MECHANICAL WORKS |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2066.68 | 1 | flexible coupling 4'' UL listed, FM approved |  | Each | 2 | 61288089 |  |  |  | flexible coupling 4'' UL listed, FM approved | 060011500036 | MEP | Received | 2023-04-16 | Accounted transaction received
4002407 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.01 | Plumbing Networks | 15 | MECHANICAL WORKS |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3618.1 | 1 | flexible coupling 6'' UL listed, FM approved |  | Each | 2 | 61288090 |  |  |  | flexible coupling 6'' UL listed, FM approved | 060011500038 | MEP | Received | 2023-04-16 | Accounted transaction received
4002408 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.01 | Plumbing Networks | 15 | MECHANICAL WORKS |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1596 | 1 | pipe clamp size 1.5" |  | Each | 25 | 61288091 |  |  |  | pipe clamp size 1.5" | 060191100006 | MEP | Received | 2023-04-16 | Accounted transaction received
4002409 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.01 | Plumbing Networks | 15 | MECHANICAL WORKS |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1211.25 | 1 | pipe clamp size 3" |  | Each | 25 | 61288092 |  |  |  | pipe clamp size 3" | 060191100009 | MEP | Received | 2023-04-16 | Accounted transaction received
4002410 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.01 | Plumbing Networks | 15 | MECHANICAL WORKS |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 200 | 1 | threaded bushings size 1"*1/2" UL LISTED,FM APPROVED |  | Each | 8 | 61288093 |  |  |  | threaded bushings size 1"*1/2" UL LISTED,FM APPROVED | 060010140393 | MEP | Received | 2023-04-16 | Accounted transaction received
4002411 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.01 | Plumbing Networks | 15 | MECHANICAL WORKS |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3225.06 | 1 | canvas |  | Meter | 75 | 61288094 |  |  |  | canvas | 060040600002 | MEP | Received | 2023-04-16 | Accounted transaction received
4002412 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.01 | Plumbing Networks | 15 | MECHANICAL WORKS |  | 2023-04-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 10387.68 | 1 | Housed spring type AH-S-1A-140 |  | Each | 4 | 61288095 |  |  |  | Housed spring type AH-S-1A-140 | 060081600013 | MEP | Received | 2023-04-16 | Accounted transaction received
4002413 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 44451.55 | 1 | Acolyte - ARB95SWBC203. 027 - Rapid Ribbon 95+ - LED Strip with 9.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser |  | Each | 95 | 61303109 |  |  |  | Acolyte - ARB95SWBC203. 027 - Rapid Ribbon 95+ - LED Strip with 9.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser | 030040700471 | MEP | Received | 2023-04-16 | Accounted transaction received
4002414 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4823.91 | 1 | Return Slot Diffuser 1 Slot 1" spacing Length 1.2 Meter |  | Each | 10 | 61154075 |  |  |  | Return Slot Diffuser 1 Slot 1" spacing Length 1.2 Meter | 060070300112 | MEP | Received | 2023-04-16 | Accounted transaction received
4002415 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2607.91 | 1 | Return Slot Diffuser 2 Slot 1" spacing Length 1.2 Meter |  | Each | 4 | 61154076 |  |  |  | Return Slot Diffuser 2 Slot 1" spacing Length 1.2 Meter | 060070300113 | MEP | Received | 2023-04-16 | Accounted transaction received
4002416 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3303.58 | 1 | Dummy Slot Diffuser 3 Slot 1" spacing Length 0.975 Meter |  | Each | 4 | 61154077 |  |  |  | Dummy Slot Diffuser 3 Slot 1" spacing Length 0.975 Meter | 060070300114 | MEP | Received | 2023-04-16 | Accounted transaction received
4002417 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 21044.97 | 1 | Plenum Slot Diffuser 1" spacing for 3 Slot Length 1.8 Meter C/W galvanized round volume damper 10" |  | Each | 10 | 61154078 |  |  |  | Plenum Slot Diffuser 1" spacing for 3 Slot Length 1.8 Meter C/W galvanized round volume damper 10" | 060070300115 | MEP | Received | 2023-04-16 | Accounted transaction received
4002418 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 34127.84 | 1 | Plenum Slot Diffuser 1" spacing for 1 Slot Length 1.2 Meter C/W galvanized round volume damper 6" |  | Each | 29 | 61154079 |  |  |  | Plenum Slot Diffuser 1" spacing for 1 Slot Length 1.2 Meter C/W galvanized round volume damper 6" | 060070300116 | MEP | Received | 2023-04-16 | Accounted transaction received
4002419 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 14774.95 | 1 | Plenum Slot Diffuser 1" spacing for 2 Slot Length 1.8 Meter C/W galvanized round volume damper 8" |  | Each | 8 | 61154080 |  |  |  | Plenum Slot Diffuser 1" spacing for 2 Slot Length 1.8 Meter C/W galvanized round volume damper 8" | 060070300117 | MEP | Received | 2023-04-16 | Accounted transaction received
3975344 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2583.71 | 1 | Return Slot Diffuser 3 Slot 1" spacing Length 3.6 Meter |  | Each | 1 | 60959144 |  |  |  | Return Slot Diffuser 3 Slot 1" spacing Length 3.6 Meter | 060070300110 | MEP | Received | 2023-03-28 | Accounted transaction received
3975345 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1448.23 | 1 | Return Slot Diffuser 1 Slot 1" spacing Length 1.8 Meter |  | Each | 2 | 60959145 |  |  |  | Return Slot Diffuser 1 Slot 1" spacing Length 1.8 Meter | 060070300111 | MEP | Received | 2023-03-28 | Accounted transaction received
3975346 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-03-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 23400 | 1 | Duct insulation (thikness 1" -density 24 kg/m3) |  | Each | 30 | 60975023 |  |  |  | Duct insulation (thikness 1" -density 24 kg/m3) | 060050300008 | MEP | Received | 2023-03-28 | Accounted transaction received
3975347 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 6.04. | Wood Flooring | 6 | WOOD & PLASTIC WORK |  | 2023-03-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2009785.8 | 1 | A class parquet flooring AA class IPE' wood pre-finished, Grad-A, kiln dried 2 Layers; (Code AW014) Including the skirting based on submitted sample |  | Square Meter | 341 | 60975113 |  |  |  | A class parquet flooring AA class IPE' wood pre-finished, Grad-A, kiln dried 2 Layers; (Code AW014) Including the skirting based on submitted sample | 090040000106 | Purchasing | Received | 2023-03-28 | Accounted transaction received
3975348 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-03-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4238.96 | 1 | بلوك اسمنتى مفرغ 12*20*40 |  | Each | 540 | 60975416 |  |  |  | بلوك اسمنتى مفرغ 12*20*40 | 140020000019 | Purchasing | Received | 2023-03-28 | Accounted transaction received
4003861 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-13 | Bank Fees |  |  |  | Finance cost | Alrowad Construction_OU | 6668.97 | 1 | lG BM 4/2023 astoria | lG BM 4/2023 astoria | Currency | 6668.97 | 22539647 | 2131 | Miscellaneous supplier | RME | lG BM 4/2023 astoria |  | Finacial | Received | 2023-04-16 | Accounted transaction received
4003862 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2023-04-13 | Accomodation |  |  |  | Indirect | Alrowad Construction_OU | 41400 | 1 | تسويه ك /182- ايجارات شهر ابريل- استوريا | st-182-4-23 | Currency | 41400 | 22539647 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /182- ايجارات شهر ابريل- استوريا |  | Finacial | Received | 2023-04-16 | Accounted transaction received
4003865 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-04-13 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 4000 | 1 | تسويه ك /158-159-161-171-176-177-178-179-180-184-186-187- متنوعات | st-158-159-161-171-176-177-178-179-180-184-186-187 | Currency | 4000 | 22539647 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /158-159-161-171-176-177-178-179-180-184-186-187- متنوعات |  | Finacial | Received | 2023-04-16 | Accounted transaction received
4003866 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.08 | Electrical Expenses | 17 | Indirect Cost |  | 2023-04-13 | Electrical Expenses |  |  |  | Indirect | Alrowad Construction_OU | 1245 | 1 | تسويه ك /158-159-161-171-176-177-178-179-180-184-186-187- متنوعات | st-158-159-161-171-176-177-178-179-180-184-186-187 | Currency | 1245 | 22539647 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /158-159-161-171-176-177-178-179-180-184-186-187- متنوعات |  | Finacial | Received | 2023-04-16 | Accounted transaction received
4003867 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2023-04-13 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 7760 | 1 | تسويه ك /158-159-161-171-176-177-178-179-180-184-186-187- متنوعات | st-158-159-161-171-176-177-178-179-180-184-186-187 | Currency | 7760 | 22539647 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /158-159-161-171-176-177-178-179-180-184-186-187- متنوعات |  | Finacial | Received | 2023-04-16 | Accounted transaction received
4003869 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2023-04-13 | Stationary |  |  |  | Office and Site expenses | Alrowad Construction_OU | 580 | 1 | تسويه ك /158-159-161-171-176-177-178-179-180-184-186-187- متنوعات | st-158-159-161-171-176-177-178-179-180-184-186-187 | Currency | 580 | 22539647 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /158-159-161-171-176-177-178-179-180-184-186-187- متنوعات |  | Finacial | Received | 2023-04-16 | Accounted transaction received
4003870 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-04-13 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 630 | 1 | تسويه ك /158-159-161-171-176-177-178-179-180-184-186-187- متنوعات | st-158-159-161-171-176-177-178-179-180-184-186-187 | Currency | 630 | 22539647 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /158-159-161-171-176-177-178-179-180-184-186-187- متنوعات |  | Finacial | Received | 2023-04-16 | Accounted transaction received
4003873 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.03 | Hirings daily wages | 17 | Indirect Cost |  | 2023-04-13 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 37868.31 | 1 | يوميات عماله م09-astoria cairo | يوميات عماله م09-astoria cairo | Currency | 37868.31 | 22539647 | 12252 | حامد حسين احمد خالد – ذاتى | rowad | يوميات عماله م09-astoria cairo |  | Finacial | Received | 2023-04-16 | Accounted transaction received
4008478 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-04-01 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | -235435 | 1 | يوميات عماله الفتره 2 ش 3 التقديري | يوميات عماله الفتره 2 ش 3 التقديري | Currency | -235435 | 22588193 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 2 ش 3 التقديري |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4008579 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 62820 | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 6345 | 1 | 13 Waldorf Astoria Cairo 62820/13 | 13 Waldorf Astoria Cairo 62820/13 | Currency | 6345 | 22588193 | 11007 | الاسراء للمقاولات والتوريدات | rowad | 13 Waldorf Astoria Cairo 62820/13 |  | Mechanical | Received | 2023-04-30 | Accounted transaction received
4008596 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-04-18 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 216315 | 1 | يوميات عماله الفتره 2 ش 3 الفعلي | يوميات عماله الفتره 2 ش 3 الفعلي | Currency | 216315 | 22588193 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 2 ش 3 الفعلي |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4008713 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-04-18 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 120440 | 1 | يوميات عماله الفتره 2 ش 3 الفعلي | يوميات عماله الفتره 1 ش 4 الفعلي | Currency | 120440 | 22588193 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 2 ش 3 الفعلي |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4008760 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-04-18 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 120440 | 1 | يوميات عماله الفتره 2 ش 4 التقديري | يوميات عماله الفتره 2 ش 4 التقديري | Currency | 120440 | 22588193 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 2 ش 4 التقديري |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4008907 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2023-04-26 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 400 | 1 | تسويه ك /87-88-89-90-91-94 - م . معدات | st-87-88-89-90-91-94-4-23 | Currency | 400 | 22588193 | 2162 | Petty Cash | Mohamed Hassan Ibrahim Badawi | تسويه ك /87-88-89-90-91-94 - م . معدات |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4010384 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 570 | 1 | مشترك 1.5بوصة |  | Each | 4 | 61469434 |  |  |  | مشترك 1.5بوصة | 240040000001 | MEP | Received | 2023-04-30 | Accounted transaction received
4010385 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 153.9 | 1 | مشترك 110مم /50مم |  | Each | 1 | 61469435 |  |  |  | مشترك 110مم /50مم | 240040000009 | MEP | Received | 2023-04-30 | Accounted transaction received
4010386 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 228 | 1 | محبس 3/4 |  | Each | 1 | 61469436 |  |  |  | محبس 3/4 | 240080000023 | MEP | Received | 2023-04-30 | Accounted transaction received
4010387 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 159.6 | 1 | كوع صرف ابيض قطر 4" ( 110 مم ) |  | Each | 4 | 61469437 |  |  |  | كوع صرف ابيض قطر 4" ( 110 مم ) | 060010100210 | MEP | Received | 2023-04-30 | Accounted transaction received
4010388 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 39.9 | 1 | كوع صرف ابيض 45 درجه قطر 1.5" ( 48 مم ) |  | Each | 2 | 61469438 |  |  |  | كوع صرف ابيض 45 درجه قطر 1.5" ( 48 مم ) | 060010100216 | MEP | Received | 2023-04-30 | Accounted transaction received
4010389 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 387.6 | 1 | مشترك صرف ابيض 45 درجه قطر 4" ( 110 مم ) |  | Each | 4 | 61469439 |  |  |  | مشترك صرف ابيض 45 درجه قطر 4" ( 110 مم ) | 060010100238 | MEP | Received | 2023-04-30 | Accounted transaction received
4010390 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 256.5 | 1 | جلبة اصلاح صرف ابيض قطر 4" ( 110 مم ) |  | Each | 5 | 61469440 |  |  |  | جلبة اصلاح صرف ابيض قطر 4" ( 110 مم ) | 060010100280 | MEP | Received | 2023-04-30 | Accounted transaction received
4010391 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 17.1 | 1 | مسلوب لحام PPR مقاس 25-20 مم |  | Each | 1 | 61469441 |  |  |  | مسلوب لحام PPR مقاس 25-20 مم | 060010300146 | MEP | Received | 2023-04-30 | Accounted transaction received
4010392 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 96.9 | 1 | كوع لحام 45 درجه PPR قطر 25 مم |  | Each | 10 | 61469442 |  |  |  | كوع لحام 45 درجه PPR قطر 25 مم | 060010300048 | MEP | Received | 2023-04-30 | Accounted transaction received
4010393 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 11.4 | 1 | مشترك لحام PPR قطر 25 مم |  | Each | 1 | 61469443 |  |  |  | مشترك لحام PPR قطر 25 مم | 060010300070 | MEP | Received | 2023-04-30 | Accounted transaction received
4010394 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 148.2 | 1 | جلبه لحام PPR قطر 25 مم |  | Each | 20 | 61469444 |  |  |  | جلبه لحام PPR قطر 25 مم | 060010300087 | MEP | Received | 2023-04-30 | Accounted transaction received
4010395 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 387.6 | 1 | لزق حار 717 (علبة ولدون |  | Each | 1 | 61469445 |  |  |  | لزق حار 717 (علبة ولدون | 200020000177 | Purchasing | Received | 2023-04-30 | Accounted transaction received
4010396 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4104 | 1 | صرف حوض |  | Each | 18 | 61469446 |  |  |  | صرف حوض | 200010000912 | Purchasing | Received | 2023-04-30 | Accounted transaction received
4010397 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 290.7 | 1 | تنر |  | Each | 3 | 61469447 |  |  |  | تنر | 060019000008 | MEP | Received | 2023-04-30 | Accounted transaction received
4010398 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 684 | 1 | مسامير سيلف دريل 8مم طول 3سم |  | Kilogram | 4 | 61469448 |  |  |  | مسامير سيلف دريل 8مم طول 3سم | 060191210002 | MEP | Received | 2023-04-30 | Accounted transaction received
4010399 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3475.58 | 1 | سيليكون أبيض |  | Each | 24 | 61469449 |  |  |  | سيليكون أبيض | 200010000945 | Purchasing | Received | 2023-04-30 | Accounted transaction received
4010400 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1026 | 1 | سيفون 4 بوصة |  | Each | 4 | 61469450 |  |  |  | سيفون 4 بوصة | 240070000179 | MEP | Received | 2023-04-30 | Accounted transaction received
4010401 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3078 | 1 | ماسورة 4 بوصة |  | Meter | 30 | 61469451 |  |  |  | ماسورة 4 بوصة | 240050000086 | MEP | Received | 2023-04-30 | Accounted transaction received
4010402 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 239.4 | 1 | ماسورة 1.5 بوصة الشريف |  | Meter | 6 | 61469452 |  |  |  | ماسورة 1.5 بوصة الشريف | 240050000089 | MEP | Received | 2023-04-30 | Accounted transaction received
4011322 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-12 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | -2500 | 1 | 80894/2 |  | Currency | -2500 |  | 12636 | مصطفي شعبان عطية بيومي-ذاتى |  | 80894/2 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011358 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | 54420 | 1 | 62820/13 |  | Currency | 54420 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 62820/13 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011359 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 52847.53 | 1 | 1.1 62820/13 |  | Currency | 5.64 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 1.1 62820/13 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011360 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 6605.94 | 1 | 1.2 62820/13 |  | Currency | 0.47 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 1.2 62820/13 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011361 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 16233.74 | 1 | 1.3 62820/13 |  | Currency | 0.99 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 1.3 62820/13 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011362 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -340.59 | 1 | LABOUR_OFFICE 62820/13 |  | Currency | -340.59 |  | 11007 | الاسراء للمقاولات والتوريدات |  | LABOUR_OFFICE 62820/13 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011384 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 8550 | 1 | 11.5 67059/10 |  | Currency | 200 |  | 4820 | سيجاب للهندسه والتجاره |  | 11.5 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011385 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2690.4 | 1 | 11.9 67059/10 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 11.9 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011386 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1197 | 1 | 2.2.029 67059/10 |  | Currency | 14 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.029 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011387 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1276.8 | 1 | 4.4.017 67059/10 |  | Currency | 21 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.017 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011388 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2394 | 1 | 4.4.025 67059/10 |  | Currency | 35 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.025 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011389 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 451.25 | 1 | 6.6.024 67059/10 |  | Currency | 5 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.024 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011390 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 90.25 | 1 | 6.6.025 67059/10 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.025 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011391 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3208.27 | 1 | 6.6.026 67059/10 |  | Currency | 22 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.026 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011392 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 541.5 | 1 | 6.6.027 67059/10 |  | Currency | 6 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.027 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011393 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 812.25 | 1 | 6.6.028 67059/10 |  | Currency | 9 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.028 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011394 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 451.25 | 1 | 6.6.029 67059/10 |  | Currency | 5 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.029 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011395 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1985.5 | 1 | 6.6.03 67059/10 |  | Currency | 22 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.03 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011396 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 170.73 | 1 | 6.6.04 67059/10 |  | Currency | 3 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.04 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011397 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9492.52 | 1 | 6.6.046 67059/10 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.046 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011398 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1187.5 | 1 | 6.6.055 67059/10 |  | Currency | 25 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.055 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011399 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 135 | 1 | 6.6.073 67059/10 |  | Currency | 3 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.073 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011400 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 360 | 1 | 6.6.074 67059/10 |  | Currency | 8 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.074 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011401 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 45 | 1 | 6.6.075 67059/10 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.075 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011402 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 90 | 1 | 6.6.076 67059/10 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.076 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011403 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 45 | 1 | 6.6.077 67059/10 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.077 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011404 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3933 | 1 | 7.7.009 67059/10 |  | Currency | 23 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.009 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011405 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 855 | 1 | 7.7.02 67059/10 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.02 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011406 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 99.28 | 1 | 7.7.026 67059/10 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.026 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011407 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 427.5 | 1 | 7.7.027 67059/10 |  | Currency | 5 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.027 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011408 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1243.4 | 1 | 7.7.028 67059/10 |  | Currency | 9 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.028 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011409 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 171 | 1 | 7.7.029 67059/10 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.029 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011410 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1282.5 | 1 | 7.7.03 67059/10 |  | Currency | 15 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.03 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011411 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 684 | 1 | 7.7.031 67059/10 |  | Currency | 8 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.031 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011412 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1026 | 1 | 7.7.032 67059/10 |  | Currency | 12 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.032 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011413 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 342 | 1 | 7.7.033 67059/10 |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.033 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011414 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 171 | 1 | 7.7.034 67059/10 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.034 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011415 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 68.69 | 1 | 7.7.042 67059/10 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.042 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011416 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 900 | 1 | 7.7.057 67059/10 |  | Currency | 20 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.057 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4002420 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 8914.16 | 1 | Plenum Slot Diffuser 1" spacing for 3 Slot Length 3.6 Meter C/W galvanized round volume damper 8" |  | Each | 2 | 61154081 |  |  |  | Plenum Slot Diffuser 1" spacing for 3 Slot Length 3.6 Meter C/W galvanized round volume damper 8" | 060070300118 | MEP | Received | 2023-04-16 | Accounted transaction received
4002421 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 8020.41 | 1 | Plenum Slot Diffuser 1" spacing for 1 Slot Length 1.8 Meter C/W galvanized round volume damper 6" |  | Each | 5 | 61154082 |  |  |  | Plenum Slot Diffuser 1" spacing for 1 Slot Length 1.8 Meter C/W galvanized round volume damper 6" | 060070300119 | MEP | Received | 2023-04-16 | Accounted transaction received
4002422 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4037.24 | 1 | Return Linear Grille Length 1.2 Meter , Width 200mm |  | Each | 4 | 61154083 |  |  |  | Return Linear Grille Length 1.2 Meter , Width 200mm | 060070100291 | MEP | Received | 2023-04-16 | Accounted transaction received
4002423 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 622.34 | 1 | Linear Grille C/W Damper Size 60 * 12.5 cm |  | Each | 1 | 61154084 |  |  |  | Linear Grille C/W Damper Size 60 * 12.5 cm | 060070100292 | MEP | Received | 2023-04-16 | Accounted transaction received
4002424 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 446.34 | 1 | Return Linear Grille Size 60 * 12.5 cm |  | Each | 1 | 61154085 |  |  |  | Return Linear Grille Size 60 * 12.5 cm | 060070100293 | MEP | Received | 2023-04-16 | Accounted transaction received
4002425 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2612.33 | 1 | Return Linear Grille Size 60 * 8 cm |  | Each | 8 | 61154086 |  |  |  | Return Linear Grille Size 60 * 8 cm | 060070100294 | MEP | Received | 2023-04-16 | Accounted transaction received
4002426 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 19300.2 | 1 | Fiber glass Thermal Insulation for chilled water piping system. Dn 50, 50 mm Thickness (K factor of 0.036 W/m.k & denisty 96 Kg/cu.m.) |  | Meter | 100 | 61154368 |  |  |  | Fiber glass Thermal Insulation for chilled water piping system. Dn 50, 50 mm Thickness (K factor of 0.036 W/m.k & denisty 96 Kg/cu.m.) | 060050400065 | MEP | Received | 2023-04-16 | Accounted transaction received
4002427 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 23399.64 | 1 | Fiber glass Thermal Insulation for chilled water piping system. Dn 80, 50 mm Thickness (K factor of 0.036 W/m.k & denisty 96 Kg/cu.m.) |  | Each | 100 | 61154369 |  |  |  | Fiber glass Thermal Insulation for chilled water piping system. Dn 80, 50 mm Thickness (K factor of 0.036 W/m.k & denisty 96 Kg/cu.m.) | 060050400095 | MEP | Received | 2023-04-16 | Accounted transaction received
4002428 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 35112 | 1 | Hardware accessories for doors HW-03 Towel Rail for Vanities MT-1 |  | Each | 28 | 61156174 |  |  |  | Hardware accessories for doors HW-03 Towel Rail for Vanities MT-1 | 250010001549 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002429 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 798 | 1 | Robe Hook Plate 70*70*10 |  | Each | 7 | 61156175 |  |  |  | Robe Hook Plate 70*70*10 | 250010001933 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002430 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 7.03. | Roofing Insulation | 7 | THERMAL & MOISTURE P |  | 2023-04-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 99624.88 | 1 | فوم ابيض سمك 20سم كثافة 35 |  | Cubic Meter | 25 | 61156236 |  |  |  | فوم ابيض سمك 20سم كثافة 35 | 040010000184 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002431 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-06 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 28732.56 | 1 | حبارة ألوان Ricoh IM C3000 |  | Each | 4 | 61156951 |  |  |  | حبارة ألوان Ricoh IM C3000 | 800030000103 | IT | Received | 2023-04-16 | Accounted transaction received
4002432 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-06 | ANSUL System |  |  |  | Materials | Waldorf Astoria-0164 | 43320 | 1 | Clear Mirror panels (GL-1); with antique brass (MT-4) frame; including but not limited to backing; framing; fixing; hinges; finish WAH_PA_ML_BS_70.1 DT Dimensions: 1350x325 mm x 2 1350x650mm x 1 Materials: Brass, Silver Mirror Finish: MT-04 |  | Each | 1 | 61158643 |  |  |  | Clear Mirror panels (GL-1); with antique brass (MT-4) frame; including but not limited to backing; framing; fixing; hinges; finish WAH_PA_ML_BS_70.1 DT Dimensions: 1350x325 mm x 2 1350x650mm x 1 Materials: Brass, Silver Mirror Finish: MT-04 | 310040000004 | Fleets | Received | 2023-04-16 | Accounted transaction received
4002433 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 12540 | 1 | Comprising brass frame MT-1 For Bathroom vanity cabinet including all necessary accessories; preparations; Size 1540 x 600 x 1050 mm Materials: Steel frame 30x30mm Dimensions: 144x57x82 cm Finish: Galvanized steel, Antique brass look paint |  | Each | 2 | 61173191 |  |  |  | Comprising brass frame MT-1 For Bathroom vanity cabinet including all necessary accessories; preparations; Size 1540 x 600 x 1050 mm Materials: Steel frame 30x30mm Dimensions: 144x57x82 cm Finish: Galvanized steel, Antique brass look paint | 250010001360 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002434 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 445740 | 1 | Vanity mirror; polished low iron clear GL-1; with brass frame MT-1; including all necessary accessories; preparations; Bathroom Materials: Brass special profile 10x20mm 6mm Mirror - 2cm edge chamfer 8mm Moisture proof plywood Dimensions |  | Each | 46 | 61173192 |  |  |  | Vanity mirror; polished low iron clear GL-1; with brass frame MT-1; including all necessary accessories; preparations; Bathroom Materials: Brass special profile 10x20mm 6mm Mirror - 2cm edge chamfer 8mm Moisture proof plywood Dimensions | 250010001361 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002435 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 63612 | 1 | Vanity mirror; polished low iron clear GL-1; with brass frame MT-1; including all necessary accessories; preparations; Mirror at bathroom; as per detail 04 drawing WAH- GR-60 DT Materials: Brass special profile 10x20mm 6mm Mirror - 2cm edge |  | Each | 6 | 61173193 |  |  |  | Vanity mirror; polished low iron clear GL-1; with brass frame MT-1; including all necessary accessories; preparations; Mirror at bathroom; as per detail 04 drawing WAH- GR-60 DT Materials: Brass special profile 10x20mm 6mm Mirror - 2cm edge | 250010001366 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002436 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 19380 | 1 | Vanity mirror; polished low iron clear GL-1; with brass frame MT-1; including but not limited to fixing and all necessary accessories; preparations; Mirror at bathroom; as per drawing WAH-GR-63 DT Materials: Brass special profile |  | Each | 2 | 61173194 |  |  |  | Vanity mirror; polished low iron clear GL-1; with brass frame MT-1; including but not limited to fixing and all necessary accessories; preparations; Mirror at bathroom; as per drawing WAH-GR-63 DT Materials: Brass special profile | 250010001367 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002437 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 19380 | 1 | Vanity mirror; polished low iron clear GL-1; with brass frame MT-1; including but not limited to fixing and all necessary accessories; preparations; Mirror at bathroom; as per drawing WAH-GR-64 DT Materials: Brass special profile |  | Each | 2 | 61173195 |  |  |  | Vanity mirror; polished low iron clear GL-1; with brass frame MT-1; including but not limited to fixing and all necessary accessories; preparations; Mirror at bathroom; as per drawing WAH-GR-64 DT Materials: Brass special profile | 250010001368 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002438 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 19380 | 1 | Vanity mirror; polished low iron clear GL-1; with brass frame MT-1; including but not limited to fixing and all necessary accessories; preparations; Mirror at bathroom; as per drawing WAH-GR-65 DT Materials: Brass special profile |  | Each | 2 | 61173196 |  |  |  | Vanity mirror; polished low iron clear GL-1; with brass frame MT-1; including but not limited to fixing and all necessary accessories; preparations; Mirror at bathroom; as per drawing WAH-GR-65 DT Materials: Brass special profile | 250010001369 | Procurement | Received | 2023-04-16 | Accounted transaction received
4002439 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 570 | 1 | تيب دوكو |  | Each | 20 | 61173409 |  |  |  | تيب دوكو | 200010000048 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002440 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 57 | 1 | سكينة معجون صغيرة |  | Each | 2 | 61173410 |  |  |  | سكينة معجون صغيرة | 200010000081 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002441 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 256.5 | 1 | تيب مسلح |  | Each | 5 | 61173411 |  |  |  | تيب مسلح | 200010000382 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002442 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 39.9 | 1 | سلاح كتر |  | Each | 1 | 61173412 |  |  |  | سلاح كتر | 200010000411 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002443 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 199.5 | 1 | مكنسة ناعمة |  | Each | 5 | 61173413 |  |  |  | مكنسة ناعمة | 200010000449 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002444 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 513 | 1 | فوطة صفراء |  | Each | 10 | 61173414 |  |  |  | فوطة صفراء | 200010000478 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002445 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 513 | 1 | قلم ماركر احمر |  | Each | 10 | 61173415 |  |  |  | قلم ماركر احمر | 200010000918 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002446 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1710 | 1 | شيكارة بلاستيك فارغة |  | Each | 500 | 61173416 |  |  |  | شيكارة بلاستيك فارغة | 200010000115 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002447 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 150 | 1 | مسمار برشام |  | Each | 50 | 61173417 |  |  |  | مسمار برشام | 200020000312 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002448 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 684 | 1 | اسبراي الوان |  | Each | 12 | 61173418 |  |  |  | اسبراي الوان | 200010001522 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002449 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 200 | 1 | فرشه سلك كوباية 5" |  | Each | 2 | 61173419 |  |  |  | فرشه سلك كوباية 5" | 200010002021 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002450 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1368 | 1 | زجاجة 40 مم |  | Each | 6 | 61173420 |  |  |  | زجاجة 40 مم | 200010002037 | Purchasing | Received | 2023-04-16 | Accounted transaction received
4002451 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1482 | 1 | part no.WL 2004/2 ابليك كريستال عصفور |  | Each | 13 | 61173421 |  |  |  | part no.WL 2004/2 ابليك كريستال عصفور | 030049100047 | MEP | Received | 2023-04-16 | Accounted transaction received
4012438 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.02 | Rented Cars | 17 | Indirect Cost |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 27163.5 | 1 | 6 waldorf astoria - 3/23 | 6 waldorf astoria - 3/23 | Currency | 27163.5 | 22589681 | 9182 | مؤسسة الجينيرال لتأجير السيارات | rowad | 6 waldorf astoria - 3/23 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013348 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 23750 | 1 | 1.3 60898/9 |  | Currency | 190 |  | 10796 | جلوبال بريما |  | 1.3 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013350 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4880 | 1 | 1.5 60898/9 |  | Currency | 52 |  | 10796 | جلوبال بريما |  | 1.5 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011417 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 135 | 1 | 7.7.077 67059/10 |  | Currency | 3 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.077 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011418 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 585 | 1 | 7.7.078 67059/10 |  | Currency | 13 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.078 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011419 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3430.95 | 1 | 7.7.08 67059/10 |  | Currency | 12 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.08 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011420 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 384.75 | 1 | 7.7.081 67059/10 |  | Currency | 9 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.081 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011421 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1197 | 1 | 8.8.004 67059/10 |  | Currency | 7 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.004 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011422 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2052 | 1 | 8.8.005 67059/10 |  | Currency | 12 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.005 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011423 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1539 | 1 | 8.8.027 67059/10 |  | Currency | 18 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.027 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011424 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 513 | 1 | 8.8.031 67059/10 |  | Currency | 6 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.031 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011425 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 171 | 1 | 8.8.032 67059/10 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.032 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011426 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 85.5 | 1 | 8.8.033 67059/10 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.033 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011427 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9636.71 | 1 | 8.8.036 67059/10 |  | Currency | 30 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.036 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011428 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1368 | 1 | 8.8.041 67059/10 |  | Currency | 16 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.041 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011429 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 62.69 | 1 | 8.8.045 67059/10 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.045 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011430 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 684 | 1 | 8.8.05 67059/10 |  | Currency | 8 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.05 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011431 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5044.5 | 1 | 8.8.051 67059/10 |  | Currency | 59 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.051 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013351 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -2400 | 1 | 1.7 60898/9 |  | Currency | 0 |  | 10796 | جلوبال بريما |  | 1.7 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013352 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -14640 | 1 | 1.8 60898/9 |  | Currency | 0 |  | 10796 | جلوبال بريما |  | 1.8 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013353 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -10880 | 1 | 1.9 60898/9 |  | Currency | 0 |  | 10796 | جلوبال بريما |  | 1.9 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013354 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -8125 | 1 | 1.10 60898/9 |  | Currency | 0 |  | 10796 | جلوبال بريما |  | 1.10 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013355 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9656.25 | 1 | 1.12 60898/9 |  | Currency | 77.25 |  | 10796 | جلوبال بريما |  | 1.12 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013358 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 6649.65 | 1 | 2.3 60898/9 |  | Currency | 189.99 |  | 10796 | جلوبال بريما |  | 2.3 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013360 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1830 | 1 | 2.5 60898/9 |  | Currency | 52 |  | 10796 | جلوبال بريما |  | 2.5 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013361 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -900 | 1 | 2.7 60898/9 |  | Currency | 0 |  | 10796 | جلوبال بريما |  | 2.7 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013362 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -5490 | 1 | 2.8 60898/9 |  | Currency | 0 |  | 10796 | جلوبال بريما |  | 2.8 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013363 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -4080 | 1 | 2.9 60898/9 |  | Currency | 0 |  | 10796 | جلوبال بريما |  | 2.9 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013364 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -2275 | 1 | 2.10 60898/9 |  | Currency | 0 |  | 10796 | جلوبال بريما |  | 2.10 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013365 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2703.75 | 1 | 2.12 60898/9 |  | Currency | 77.25 |  | 10796 | جلوبال بريما |  | 2.12 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013366 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 49500 | 1 | 7.4 60898/9 |  | Currency | 450 |  | 10796 | جلوبال بريما |  | 7.4 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013367 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7700 | 1 | 3.2 60898/9 |  | Currency | 70 |  | 10796 | جلوبال بريما |  | 3.2 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013368 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4427.5 | 1 | 3.5 60898/9 |  | Currency | 40.25 |  | 10796 | جلوبال بريما |  | 3.5 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013369 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 960 | 1 | 5.4 60898/9 |  | Currency | 24 |  | 10796 | جلوبال بريما |  | 5.4 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013370 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1460 | 1 | 5.5 60898/9 |  | Currency | 58.4 |  | 10796 | جلوبال بريما |  | 5.5 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013371 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 17391 | 1 | 7.3 60898/9 |  | Currency | 158.1 |  | 10796 | جلوبال بريما |  | 7.3 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013372 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1540 | 1 | 3.6 60898/9 |  | Currency | 14 |  | 10796 | جلوبال بريما |  | 3.6 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013373 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 6880 | 1 | 3.7 60898/9 |  | Currency | 43 |  | 10796 | جلوبال بريما |  | 3.7 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013374 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4950 | 1 | 3.13 60898/9 |  | Currency | 45 |  | 10796 | جلوبال بريما |  | 3.13 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013375 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 15400 | 1 | 4.11 60898/9 |  | Currency | 140 |  | 10796 | جلوبال بريما |  | 4.11 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013376 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2400 | 1 | 4.19 60898/9 |  | Currency | 15 |  | 10796 | جلوبال بريما |  | 4.19 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013377 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 6297.5 | 1 | 5.6 60898/9 |  | Currency | 57.25 |  | 10796 | جلوبال بريما |  | 5.6 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013378 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 30838.5 | 1 | 7.1 60898/9 |  | Currency | 280.35 |  | 10796 | جلوبال بريما |  | 7.1 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013379 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 512 | 1 | 7.2 60898/9 |  | Currency | 3.2 |  | 10796 | جلوبال بريما |  | 7.2 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013380 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 17120 | 1 | 3.10 60898/9 |  | Currency | 107 |  | 10796 | جلوبال بريما |  | 3.10 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013381 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -756.25 | 1 | LABOUR_OFFICE 60898/9 |  | Currency | -756.25 |  | 10796 | جلوبال بريما |  | LABOUR_OFFICE 60898/9 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013418 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.08.00 | Gypsum Board(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 104400 | 1 | 1.1 80045/5 |  | Currency | 144 |  | 12187 | اركاد للترميم |  | 1.1 80045/5 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013419 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.08.00 | Gypsum Board(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 39600 | 1 | 6.1 80045/5 |  | Currency | 144 |  | 12187 | اركاد للترميم |  | 6.1 80045/5 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013420 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.08.00 | Gypsum Board(G) | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -648 | 1 | LABOUR_OFFICE 80045/5 |  | Currency | -648 |  | 12187 | اركاد للترميم |  | LABOUR_OFFICE 80045/5 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013436 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.01 | Epoxy | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 247000 | 1 | 3.4 67960/3 |  | Currency | 380 |  | 8099 | انترناشيونال سوبر سكريد |  | 3.4 67960/3 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013437 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.01 | Epoxy | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 107588 | 1 | 5.1 67960/3 |  | Currency | 165.52 |  | 8099 | انترناشيونال سوبر سكريد |  | 5.1 67960/3 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4013438 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.01 | Epoxy | 9 | FINISHES WORK |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1595.65 | 1 | LABOUR_OFFICE 67960/3 |  | Currency | -1595.65 |  | 8099 | انترناشيونال سوبر سكريد |  | LABOUR_OFFICE 67960/3 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4014061 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.02 | Rented Cars | 17 | Indirect Cost |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 35799.15 | 1 | 5 waldorf astoria - 3/23 | 5 waldorf astoria - 3/23 | Currency | 35799.15 | 22593428 | 5214 | المتحدة لايجار وتوريد السيارات | rowad | 5 waldorf astoria - 3/23 |  | Finacial | Received | 2023-05-01 | Accounted transaction received
4014062 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.02 | Rented Cars | 17 | Indirect Cost |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 16649.33 | 1 | 6 waldorf astoria -3/23 | 6 waldorf astoria -3/23 | Currency | 16649.33 | 22593428 | 3084 | محمد احمد محمد محمد | Rowad | 6 waldorf astoria -3/23 |  | Finacial | Received | 2023-05-01 | Accounted transaction received
4014082 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-30 | Bank Fees |  |  |  | Finance cost | Alrowad Construction_OU | 81 | 1 | LgBm 4/2023 astoria | LgBm 4/2023 astoria | Currency | 81 | 22593428 | 2131 | Miscellaneous supplier | RME | LgBm 4/2023 astoria |  | Finacial | Received | 2023-05-01 | Accounted transaction received
4014388 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 218880 | 1 | Hardware accessories for doors HW-122 Bespoke Door Pull as per Muza Lab Specification MT-4 |  | Each | 16 | 61526673 |  |  |  | Hardware accessories for doors HW-122 Bespoke Door Pull as per Muza Lab Specification MT-4 | 250010001553 | Procurement | Received | 2023-05-01 | Accounted transaction received
4014389 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 7169.46 | 1 | Volume Dampers Size : 8" X 6" |  | Each | 20 | 61528411 |  |  |  | Volume Dampers Size : 8" X 6" | 060070700054 | MEP | Received | 2023-05-01 | Accounted transaction received
4014390 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2261.3 | 1 | Volume Dampers Size : 24" X 14" |  | Each | 2 | 61528412 |  |  |  | Volume Dampers Size : 24" X 14" | 060070700058 | MEP | Received | 2023-05-01 | Accounted transaction received
4014391 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1907.16 | 1 | Volume Dampers Size : 12" X 10" |  | Each | 3 | 61528413 |  |  |  | Volume Dampers Size : 12" X 10" | 060070700059 | MEP | Received | 2023-05-01 | Accounted transaction received
4014392 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1171.81 | 1 | Volume Dampers Size : 10" X 10" |  | Each | 2 | 61528414 |  |  |  | Volume Dampers Size : 10" X 10" | 060070700065 | MEP | Received | 2023-05-01 | Accounted transaction received
4014393 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1758.79 | 1 | Volume Dampers Size : 8" X 8" |  | Each | 4 | 61528415 |  |  |  | Volume Dampers Size : 8" X 8" | 060070700067 | MEP | Received | 2023-05-01 | Accounted transaction received
4014394 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 570.74 | 1 | Volume Dampers Size : 12" X 8" |  | Each | 1 | 61528416 |  |  |  | Volume Dampers Size : 12" X 8" | 060070700068 | MEP | Received | 2023-05-01 | Accounted transaction received
4014395 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2527.72 | 1 | Aluminium volume DamperSize : 25 x 15 cm |  | Each | 6 | 61528417 |  |  |  | Aluminium volume DamperSize : 25 x 15 cm | 060070700144 | MEP | Received | 2023-05-01 | Accounted transaction received
4014396 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1371.08 | 1 | Aluminium volume DamperSize : 35 x 25 cm |  | Each | 2 | 61528418 |  |  |  | Aluminium volume DamperSize : 35 x 25 cm | 060070700159 | MEP | Received | 2023-05-01 | Accounted transaction received
4011432 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 6754.5 | 1 | 8.8.058 67059/10 |  | Currency | 79 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.058 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011433 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2052 | 1 | 8.8.06 67059/10 |  | Currency | 24 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.06 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011434 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4788 | 1 | 8.8.062 67059/10 |  | Currency | 56 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.062 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011435 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 256.5 | 1 | 8.8.074 67059/10 |  | Currency | 3 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.074 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011436 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 940.5 | 1 | 8.8.079 67059/10 |  | Currency | 11 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.079 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011437 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 171 | 1 | 8.8.08 67059/10 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.08 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011438 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 225 | 1 | 8.8.094 67059/10 |  | Currency | 5 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.094 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011439 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 88.2 | 1 | 8.8.095 67059/10 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.095 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011440 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 8685.31 | 1 | 8.8.101 67059/10 |  | Currency | 32 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.101 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011441 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4446 | 1 | 9.9.01 67059/10 |  | Currency | 65 |  | 4820 | سيجاب للهندسه والتجاره |  | 9.9.01 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011442 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 410.4 | 1 | 9.9.011 67059/10 |  | Currency | 6 |  | 4820 | سيجاب للهندسه والتجاره |  | 9.9.011 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011443 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 427.5 | 1 | 8.8.03 67059/10 |  | Currency | 5 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.03 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011444 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 304 | 1 | 8.8.064 67059/10 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.064 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011445 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2340 | 1 | 11.11 67059/10 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 11.11 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011446 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1920 | 1 | 11.8 67059/10 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 11.8 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011447 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1404 | 1 | 2.2.011 67059/10 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.011 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011448 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 19 | 1 | 2.2.013 67059/10 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.013 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011449 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 19 | 1 | 2.2.014 67059/10 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.014 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011450 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 66.5 | 1 | 2.2.015 67059/10 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.015 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011451 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 38 | 1 | 2.2.016 67059/10 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.016 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011452 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 228 | 1 | 2.2.017 67059/10 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.017 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011453 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 66.5 | 1 | 2.2.018 67059/10 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.018 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011454 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 967.09 | 1 | 8.8.026 67059/10 |  | Currency | 7 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.026 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011455 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 171 | 1 | 6.6.035 67059/10 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.035 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011456 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3811.5 | 1 | 11.6 67059/10 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 11.6 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011457 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | -9000 | 1 | 67059/10 |  | Currency | -9000 |  | 4820 | سيجاب للهندسه والتجاره |  | 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011458 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -512.4 | 1 | LABOUR_OFFICE 67059/10 |  | Currency | -512.4 |  | 4820 | سيجاب للهندسه والتجاره |  | LABOUR_OFFICE 67059/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011536 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 18800 | 1 | 4.1 69063/6 |  | Currency | 47 |  | 11716 | بنه للديكورات والتشطيبات والتوريدات العموميه والتسويق العقارى |  | 4.1 69063/6 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011537 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 11025 | 1 | 4.2 69063/6 |  | Currency | 24.5 |  | 11716 | بنه للديكورات والتشطيبات والتوريدات العموميه والتسويق العقارى |  | 4.2 69063/6 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4010403 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1385.78 | 1 | وصلة مرنة 50 سم |  | Each | 20 | 61469453 |  |  |  | وصلة مرنة 50 سم | 060021000009 | MEP | Received | 2023-04-30 | Accounted transaction received
4010404 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2317.17 | 1 | بكرة تيب شفاف عرض 5 سم |  | Each | 50 | 61469454 |  |  |  | بكرة تيب شفاف عرض 5 سم | 060019000041 | MEP | Received | 2023-04-30 | Accounted transaction received
4010405 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 342 | 1 | وردة 8 مم |  | Kilogram | 3 | 61469455 |  |  |  | وردة 8 مم | 200020000145 | Purchasing | Received | 2023-04-30 | Accounted transaction received
4010406 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 359.1 | 1 | صمولة 8مم |  | Kilogram | 3 | 61469456 |  |  |  | صمولة 8مم | 200020000418 | Purchasing | Received | 2023-04-30 | Accounted transaction received
4010407 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 228 | 1 | صامولة مجلفنة 10 مم |  | Kilogram | 2 | 61469457 |  |  |  | صامولة مجلفنة 10 مم | 030120600002 | MEP | Received | 2023-04-30 | Accounted transaction received
4010408 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 228 | 1 | ورده مجلفنة 10 مم |  | Kilogram | 2 | 61469458 |  |  |  | ورده مجلفنة 10 مم | 030120700002 | MEP | Received | 2023-04-30 | Accounted transaction received
4010409 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 200 | 1 | جوان جرنجريت 100 مم ( 8 ثقب * 19.1 مم ) |  | Each | 5 | 61469459 |  |  |  | جوان جرنجريت 100 مم ( 8 ثقب * 19.1 مم ) | 060019000165 | MEP | Received | 2023-04-30 | Accounted transaction received
4010410 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 193.8 | 1 | لاكور سن خارجى PPR 25 mm |  | Each | 2 | 61469460 |  |  |  | لاكور سن خارجى PPR 25 mm | 060010300344 | MEP | Received | 2023-04-30 | Accounted transaction received
4010411 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 376.2 | 1 | مسمار 8 مم*3 سم |  | Kilogram | 3 | 61469461 |  |  |  | مسمار 8 مم*3 سم | 200020000535 | Purchasing | Received | 2023-04-30 | Accounted transaction received
4010412 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.03 | Equipment | 15 | MECHANICAL WORKS |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 469.68 | 1 | تانك هوندا |  | Each | 2 | 61469533 |  |  |  | تانك هوندا | 330040000018 | Equipment | Received | 2023-04-30 | Accounted transaction received
4010413 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.03 | Equipment | 15 | MECHANICAL WORKS |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 469.68 | 1 | بييل 160 |  | Each | 2 | 61469534 |  |  |  | بييل 160 | 330040000223 | Equipment | Received | 2023-04-30 | Accounted transaction received
4010414 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.03 | Equipment | 15 | MECHANICAL WORKS |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 353.4 | 1 | كربراتير هوندا gx160 |  | Each | 2 | 61469535 |  |  |  | كربراتير هوندا gx160 | 330040000982 | Equipment | Received | 2023-04-30 | Accounted transaction received
4010415 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.03 | Equipment | 15 | MECHANICAL WORKS |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 22.8 | 1 | طقم تيش وسوستة روبن لظبط دراع السرعة للدكاك |  | Set | 2 | 61469536 |  |  |  | طقم تيش وسوستة روبن لظبط دراع السرعة للدكاك | 330040001288 | Equipment | Received | 2023-04-30 | Accounted transaction received
4010416 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.03 | Equipment | 15 | MECHANICAL WORKS |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 234.84 | 1 | وش شداد بالكوباية لدكاك |  | Each | 2 | 61469537 |  |  |  | وش شداد بالكوباية لدكاك | 330040001702 | Equipment | Received | 2023-04-30 | Accounted transaction received
4010417 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.03 | Equipment | 15 | MECHANICAL WORKS |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 741 | 1 | بستم هوندا Gx 160 |  | Each | 2 | 61469538 |  |  |  | بستم هوندا Gx 160 | 330040001945 | Equipment | Received | 2023-04-30 | Accounted transaction received
4010418 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.03 | Equipment | 15 | MECHANICAL WORKS |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 413.06 | 1 | طقم صباب هوندا Gx 160 |  | Each | 2 | 61469539 |  |  |  | طقم صباب هوندا Gx 160 | 330040001949 | Equipment | Received | 2023-04-30 | Accounted transaction received
4010419 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.03 | Equipment | 15 | MECHANICAL WORKS |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 25.08 | 1 | بيبه بوجيه هوندا Gx 160 |  | Each | 2 | 61469540 |  |  |  | بيبه بوجيه هوندا Gx 160 | 330040001952 | Equipment | Received | 2023-04-30 | Accounted transaction received
4010420 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.03 | Equipment | 15 | MECHANICAL WORKS |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 70.68 | 1 | طقم جوان هوندا Gx 160 |  | Each | 2 | 61469541 |  |  |  | طقم جوان هوندا Gx 160 | 330040001955 | Equipment | Received | 2023-04-30 | Accounted transaction received
4010421 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.03 | Equipment | 15 | MECHANICAL WORKS |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 36.48 | 1 | بوجيه هوندا Gx 160 |  | Each | 2 | 61469542 |  |  |  | بوجيه هوندا Gx 160 | 330040001956 | Equipment | Received | 2023-04-30 | Accounted transaction received
4010422 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.03 | Equipment | 15 | MECHANICAL WORKS |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2280 | 1 | كلاتش دكاك |  | Each | 2 | 61469543 |  |  |  | كلاتش دكاك | 330030000260 | Equipment | Received | 2023-04-30 | Accounted transaction received
4010423 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5301 | 1 | ماسورة 25مم UPVC قطر خارجي 25 قطر داخلي 22مم اللفة= 20×3 متر(اللون رمادى) |  | Meter | 300 | 61469569 |  |  |  | ماسورة 25مم UPVC قطر خارجي 25 قطر داخلي 22مم اللفة= 20×3 متر(اللون رمادى) | 030010000034 | MEP | Received | 2023-04-30 | Accounted transaction received
4010424 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 193.8 | 1 | ترامل بنز 6 مم |  | Each | 200 | 61469570 |  |  |  | ترامل بنز 6 مم | 030130700005 | MEP | Received | 2023-04-30 | Accounted transaction received
4010425 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1425 | 1 | بكرة شريط لحام |  | Each | 50 | 61469571 |  |  |  | بكرة شريط لحام | 039010000003 | MEP | Received | 2023-04-30 | Accounted transaction received
4010426 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1425 | 1 | بارة نحاس معزولة 3 فاز |  | Each | 5 | 61469572 |  |  |  | بارة نحاس معزولة 3 فاز | 039019000002 | MEP | Received | 2023-04-30 | Accounted transaction received
4010427 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 136.8 | 1 | اكمن فراشة size M8 |  | Each | 20 | 61469573 |  |  |  | اكمن فراشة size M8 | 060190100007 | MEP | Received | 2023-04-30 | Accounted transaction received
4010428 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 140 | 1 | كوس نحاس 70 مم ألمانى |  | Each | 4 | 61469574 |  |  |  | كوس نحاس 70 مم ألمانى | 030130100088 | MEP | Received | 2023-04-30 | Accounted transaction received
4010429 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 44 | 1 | كوس نحاس 25 مم ألمانى |  | Each | 4 | 61469575 |  |  |  | كوس نحاس 25 مم ألمانى | 030130100090 | MEP | Received | 2023-04-30 | Accounted transaction received
4010430 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 60 | 1 | بطارية 9 فولت |  | Each | 2 | 61469576 |  |  |  | بطارية 9 فولت | 330010000012 | Equipment | Received | 2023-04-30 | Accounted transaction received
4010431 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 285 | 1 | اسبراي الوان |  | Each | 5 | 61469577 |  |  |  | اسبراي الوان | 200010001522 | Purchasing | Received | 2023-04-30 | Accounted transaction received
4010432 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 80 | 1 | كوس نحاس 50 م |  | Each | 4 | 61469578 |  |  |  | كوس نحاس 50 م | 030130100110 | MEP | Received | 2023-04-30 | Accounted transaction received
4010433 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 7182 | 1 | مفتاح فردى 16 A |  | Each | 30 | 61469579 |  |  |  | مفتاح فردى 16 A | 030110600079 | MEP | Received | 2023-04-30 | Accounted transaction received
4010434 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 96.9 | 1 | ترامل شوكه 3 مم |  | Each | 100 | 61469580 |  |  |  | ترامل شوكه 3 مم | 030130700028 | MEP | Received | 2023-04-30 | Accounted transaction received
4010435 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 23919.98 | 1 | Hardware Accessories For Wooden Doors Concealed Hinge Simonswerk completely concealed hinge system load capacity 120 kg two hinges per door leaf (1x2m) overall |  | Each | 4 | 61469631 |  |  |  | Hardware Accessories For Wooden Doors Concealed Hinge Simonswerk completely concealed hinge system load capacity 120 kg two hinges per door leaf (1x2m) overall | 250010001606 | Procurement | Received | 2023-04-30 | Accounted transaction received
4010436 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 58.86 | 1 | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 |  | Each | 2 | 61470288 |  |  |  | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 | 030060100021 | MEP | Received | 2023-04-30 | Accounted transaction received
4010437 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 29.43 | 1 | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 |  | Each | 1 | 61470289 |  |  |  | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 | 030060100021 | MEP | Received | 2023-04-30 | Accounted transaction received
4010438 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 744.96 | 1 | TV-FM-SAT SQ WH Code 572172 |  | Each | 1 | 61470290 |  |  |  | TV-FM-SAT SQ WH Code 572172 | 030060100059 | MEP | Received | 2023-04-30 | Accounted transaction received
4010439 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 170.91 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 2 | 61470291 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-04-30 | Accounted transaction received
4010440 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 940.02 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 11 | 61470292 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-04-30 | Accounted transaction received
4010441 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 617.69 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 5 | 61470293 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-04-30 | Accounted transaction received
4010442 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 35 | 1 | PLATE 2SQ MOD F-G WHITE Code 576560 |  | Each | 1 | 61470294 |  |  |  | PLATE 2SQ MOD F-G WHITE Code 576560 | 030060100267 | MEP | Received | 2023-04-30 | Accounted transaction received
4010443 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 77.47 | 1 | PLATE 1SQ MOD SCH GRAPHITE Code 576552 |  | Each | 2 | 61470295 |  |  |  | PLATE 1SQ MOD SCH GRAPHITE Code 576552 | 030060100297 | MEP | Received | 2023-04-30 | Accounted transaction received
4010444 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 65.49 | 1 | 576562 Code وش مربع فضي |  | Each | 2 | 61470296 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-04-30 | Accounted transaction received
4010445 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 70 | 1 | COVER 4 M SQUARE 2X2 WHITE F 576000 Code 575080 |  | Each | 1 | 61470297 |  |  |  | COVER 4 M SQUARE 2X2 WHITE F 576000 Code 575080 | 030060100231 | MEP | Received | 2023-04-30 | Accounted transaction received
4010446 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3192 | 1 | ريليه 24 فولت D . C بالقاعده |  | Each | 7 | 61470298 |  |  |  | ريليه 24 فولت D . C بالقاعده | 030110800001 | MEP | Received | 2023-04-30 | Accounted transaction received
4010447 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 67.29 | 1 | CARRIER PLATE SYNERGY code 730094 |  | Each | 1 | 61470299 |  |  |  | CARRIER PLATE SYNERGY code 730094 | 030060100534 | MEP | Received | 2023-04-30 | Accounted transaction received
4010448 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1016.75 | 1 | سلك نحاس مجدول مقاس4 مم اللون أحمر (cu/pvc) |  | Meter | 100 | 61470300 |  |  |  | سلك نحاس مجدول مقاس4 مم اللون أحمر (cu/pvc) | 030030101023 | MEP | Received | 2023-04-30 | Accounted transaction received
4010449 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 811.12 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أصفر × أخضر (cu/pvc) |  | Meter | 100 | 61470301 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أصفر × أخضر (cu/pvc) | 030030101027 | MEP | Received | 2023-04-30 | Accounted transaction received
4010450 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2066.82 | 1 | سلك نحاس مجدول مقاس 6 مم اللون أصفر × أخضر (cu/pvc) |  | Meter | 100 | 61470302 |  |  |  | سلك نحاس مجدول مقاس 6 مم اللون أصفر × أخضر (cu/pvc) | 030030101032 | MEP | Received | 2023-04-30 | Accounted transaction received
4010451 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 190.17 | 1 | mosaic adapter code 69580 |  | Each | 2 | 61470303 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-04-30 | Accounted transaction received
4010452 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1045.96 | 1 | mosaic adapter code 69580 |  | Each | 11 | 61470304 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-04-30 | Accounted transaction received
4010453 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 882.72 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 11 | 61470305 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-04-30 | Accounted transaction received
4010454 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 160.5 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 2 | 61470306 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-04-30 | Accounted transaction received
4010455 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4776.41 | 1 | LID & TRIM 3 COMPARTMENTS GREY ( Legrand 689631 ) |  | Each | 6 | 61470307 |  |  |  | LID & TRIM 3 COMPARTMENTS GREY ( Legrand 689631 ) | 030060100738 | MEP | Received | 2023-04-30 | Accounted transaction received
4010493 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-04-27 | Tools |  |  |  | Materials | Waldorf Astoria-0164 | 171 | 1 | شريط قياس 5م |  | Each | 2 | 61479913 |  |  |  | شريط قياس 5م | 200010000105 | Purchasing | Received | 2023-04-30 | Accounted transaction received
4010456 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 584.32 | 1 | FRAME 8 MOD MOSAIC ( Legrand 689658 ) |  | Each | 3 | 61470308 |  |  |  | FRAME 8 MOD MOSAIC ( Legrand 689658 ) | 030060100740 | MEP | Received | 2023-04-30 | Accounted transaction received
4010457 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5529.21 | 1 | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser |  | Each | 13 | 61470309 |  |  |  | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser | 030040700472 | MEP | Received | 2023-04-30 | Accounted transaction received
4010458 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 741 | 1 | لاكور بواط على فليكسبل EMT المقاس 3/4 " |  | Each | 25 | 61470310 |  |  |  | لاكور بواط على فليكسبل EMT المقاس 3/4 " | 030020100214 | MEP | Received | 2023-04-30 | Accounted transaction received
4010459 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1003.88 | 1 | SPLASH PROOF COVER Code : 617636 |  | Each | 10 | 61470311 |  |  |  | SPLASH PROOF COVER Code : 617636 | 030060100927 | MEP | Received | 2023-04-30 | Accounted transaction received
4010460 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 676.07 | 1 | 1G 20A DP SWT + NEON + E WH - 617671 |  | Each | 6 | 61470312 |  |  |  | 1G 20A DP SWT + NEON + E WH - 617671 | 030060100942 | MEP | Received | 2023-04-30 | Accounted transaction received
4010461 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 563.39 | 1 | 1G 20A DP SWT + NEON + E WH - 617671 |  | Each | 5 | 61470313 |  |  |  | 1G 20A DP SWT + NEON + E WH - 617671 | 030060100942 | MEP | Received | 2023-04-30 | Accounted transaction received
4010462 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 650.03 | 1 | Double pole switches 32 A – 250V~ 1 gang 1?way switch + led power indicator - 617629 |  | Each | 5 | 61470314 |  |  |  | Double pole switches 32 A – 250V~ 1 gang 1?way switch + led power indicator - 617629 | 030060100943 | MEP | Received | 2023-04-30 | Accounted transaction received
4010463 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3830.4 | 1 | Spot ring: Main scope: Supply only Dimensions: OD 100 - ID 82 Materials: Brass 1.25mm Finish: Brushed Stainless Steel |  | Each | 42 | 61470315 |  |  |  | Spot ring: Main scope: Supply only Dimensions: OD 100 - ID 82 Materials: Brass 1.25mm Finish: Brushed Stainless Steel | 250010002117 | Procurement | Received | 2023-04-30 | Accounted transaction received
4010464 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1083 | 1 | أسمنت أسود |  | Ton | 0.5 | 61470321 |  |  |  | أسمنت أسود | 140010000003 | Purchasing | Received | 2023-04-30 | Accounted transaction received
4010465 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1750 | 1 | اسمنت اسود رتبة 32 |  | Ton | 1 | 61470322 |  |  |  | اسمنت اسود رتبة 32 | 140010000016 | Purchasing | Received | 2023-04-30 | Accounted transaction received
4010466 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4468.8 | 1 | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² |  | Kilogram | 80 | 61470797 |  |  |  | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² | 060040200001 | MEP | Received | 2023-04-30 | Accounted transaction received
4010467 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 90.06 | 1 | كوزلك |  | Each | 1 | 61470807 |  |  |  | كوزلك | 010030000005 | Safety | Received | 2023-04-30 | Accounted transaction received
4010468 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 40.11 | 1 | خوذة صفراء |  | Each | 1 | 61470808 |  |  |  | خوذة صفراء | 010040000010 | Safety | Received | 2023-04-30 | Accounted transaction received
4010469 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 159.1 | 1 | جوانتي جلد ثقيل ( خرسانة ) |  | Each | 5 | 61470809 |  |  |  | جوانتي جلد ثقيل ( خرسانة ) | 010010000003 | Safety | Received | 2023-04-30 | Accounted transaction received
4010470 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 39.4 | 1 | فيست برتقالي |  | Each | 1 | 61470810 |  |  |  | فيست برتقالي | 010020000008 | Safety | Received | 2023-04-30 | Accounted transaction received
4010471 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 456 | 1 | كورنر (TDF) |  | Each | 100 | 61471127 |  |  |  | كورنر (TDF) | 060040200002 | MEP | Received | 2023-04-30 | Accounted transaction received
4010472 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 285 | 1 | كورنر فرنساوى TDC Corner - 2 mm . 35 |  | Each | 50 | 61471128 |  |  |  | كورنر فرنساوى TDC Corner - 2 mm . 35 | 060040200006 | MEP | Received | 2023-04-30 | Accounted transaction received
4010473 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3078 | 1 | كادر فرنساوى لتركيب الكانفس عند فواصل التمدد TDC-Flange-36 |  | Meter | 60 | 61471129 |  |  |  | كادر فرنساوى لتركيب الكانفس عند فواصل التمدد TDC-Flange-36 | 060040200007 | MEP | Received | 2023-04-30 | Accounted transaction received
4010474 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 513 | 1 | Duct Square to Round 110 * 60 cm ? 71 cm, Length 60 cm |  | Each | 1 | 61471130 |  |  |  | Duct Square to Round 110 * 60 cm ? 71 cm, Length 60 cm | 060040800073 | MEP | Received | 2023-04-30 | Accounted transaction received
4010475 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 34222.8 | 1 | Hardware accessories for doors IR-36 Pull Handle as per ABD & UWS Specification MT-4 |  | Each | 4 | 61471596 |  |  |  | Hardware accessories for doors IR-36 Pull Handle as per ABD & UWS Specification MT-4 | 250010001560 | Procurement | Received | 2023-04-30 | Accounted transaction received
4010476 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 201.63 | 1 | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 |  | Each | 2 | 61471891 |  |  |  | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 | 030060100114 | MEP | Received | 2023-04-30 | Accounted transaction received
4010477 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1281.84 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 15 | 61471892 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-04-30 | Accounted transaction received
4010478 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 123.54 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 1 | 61471893 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-04-30 | Accounted transaction received
4010479 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 71.02 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 4 | 61471894 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-04-30 | Accounted transaction received
4010480 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1280.9 | 1 | Wiring Devices (54000) METAL FLUSH-MOUNTING BOX FOR INSTALLATION IN CONCRETE FLOOR - 3 MODULES |  | Each | 13 | 61471895 |  |  |  | Wiring Devices (54000) METAL FLUSH-MOUNTING BOX FOR INSTALLATION IN CONCRETE FLOOR - 3 MODULES | 030060100618 | MEP | Received | 2023-04-30 | Accounted transaction received
4010481 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 285.26 | 1 | mosaic adapter code 69580 |  | Each | 3 | 61471896 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-04-30 | Accounted transaction received
4010482 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 240.74 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 3 | 61471897 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-04-30 | Accounted transaction received
4010483 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-04-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 275 | 1 | High Definition 4K HDMI Audio Video Cable Length 5 meter |  | Each | 1 | 61471898 |  |  |  | High Definition 4K HDMI Audio Video Cable Length 5 meter | 031060000033 | MEP | Received | 2023-04-30 | Accounted transaction received
4010484 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 39102 | 1 | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² |  | Kilogram | 700 | 61472087 |  |  |  | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² | 060040200001 | MEP | Received | 2023-04-30 | Accounted transaction received
4011538 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 8.02.00 | Wood & Plastic Doors | 8 | DOORS & WINDOWS WOR |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -134.21 | 1 | LABOUR_OFFICE 69063/6 |  | Currency | -134.21 |  | 11716 | بنه للديكورات والتشطيبات والتوريدات العموميه والتسويق العقارى |  | LABOUR_OFFICE 69063/6 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011541 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.07.05 | Gravel | 2 | SITE WORK |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2172 | 1 | 3.2 64204/10 |  | Currency | 6 |  | 8108 | سامى عياد فهيم حليم |  | 3.2 64204/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011542 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.07.05 | Gravel | 2 | SITE WORK |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4320 | 1 | 5.1 64204/10 |  | Currency | 36 |  | 8108 | سامى عياد فهيم حليم |  | 5.1 64204/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011543 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.07.05 | Gravel | 2 | SITE WORK |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -29.21 | 1 | LABOUR_OFFICE 64204/10 |  | Currency | -29.21 |  | 8108 | سامى عياد فهيم حليم |  | LABOUR_OFFICE 64204/10 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011547 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.03.02 | Repair | 2 | SITE WORK |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 17400 | 1 | 2.1 74900/6 |  | Currency | 145 |  | 8108 | سامى عياد فهيم حليم |  | 2.1 74900/6 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011548 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.03.02 | Repair | 2 | SITE WORK |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -78.3 | 1 | LABOUR_OFFICE 74900/6 |  | Currency | -78.3 |  | 8108 | سامى عياد فهيم حليم |  | LABOUR_OFFICE 74900/6 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011551 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 36000 | 1 | 5.2 63247/5 |  | Currency | 30 |  | 10037 | ايه وان للمقاولات |  | 5.2 63247/5 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011552 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 38250 | 1 | 6.1 63247/5 |  | Currency | 51 |  | 10037 | ايه وان للمقاولات |  | 6.1 63247/5 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011553 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 8700 | 1 | 7.1 63247/5 |  | Currency | 29 |  | 10037 | ايه وان للمقاولات |  | 7.1 63247/5 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011554 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2800 | 1 | 7.2 63247/5 |  | Currency | 2800 |  | 10037 | ايه وان للمقاولات |  | 7.2 63247/5 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011555 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5500 | 1 | 7.3 63247/5 |  | Currency | 5500 |  | 10037 | ايه وان للمقاولات |  | 7.3 63247/5 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011556 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3200 | 1 | 7.4 63247/5 |  | Currency | 8 |  | 10037 | ايه وان للمقاولات |  | 7.4 63247/5 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011557 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 8800 | 1 | 7.5 63247/5 |  | Currency | 16 |  | 10037 | ايه وان للمقاولات |  | 7.5 63247/5 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011558 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9600 | 1 | 7.6 63247/5 |  | Currency | 16 |  | 10037 | ايه وان للمقاولات |  | 7.6 63247/5 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4011559 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-04-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -507.83 | 1 | LABOUR_OFFICE 63247/5 |  | Currency | -507.83 |  | 10037 | ايه وان للمقاولات |  | LABOUR_OFFICE 63247/5 |  | Finacial | Received | 2023-04-30 | Accounted transaction received
4017868 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-04-30 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 900 | 1 |  | FA Dep-april-23 | Currency | 900 | 22602003 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-05-03 | Accounted transaction received
4017869 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-04-30 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 2764.5 | 1 |  | FA Dep-april-23 | Currency | 2764.5 | 22602003 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-05-03 | Accounted transaction received
4017870 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-04-30 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 4644.75 | 1 |  | FA Dep-april-23 | Currency | 4644.75 | 22602003 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-05-03 | Accounted transaction received
4017871 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-04-30 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 995.14 | 1 |  | FA Dep-april-23 | Currency | 995.14 | 22602003 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-05-03 | Accounted transaction received
4017872 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-04-30 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 14.98 | 1 |  | FA Dep-april-23 | Currency | 14.98 | 22602003 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-05-03 | Accounted transaction received
4017873 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-04-30 | Furniture Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 8324.58 | 1 |  | FA Dep-april-23 | Currency | 8324.58 | 22602003 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-05-03 | Accounted transaction received
4017874 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-04-30 | Electrical appliance Deprectia |  |  |  | Depreciation | Alrowad Construction_OU | 1316.5 | 1 |  | FA Dep-april-23 | Currency | 1316.5 | 22602003 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-05-03 | Accounted transaction received
4017875 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-04-30 | Electrical appliance Deprectia |  |  |  | Depreciation | Alrowad Construction_OU | 3076.19 | 1 |  | FA Dep-april-23 | Currency | 3076.19 | 22602003 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-05-03 | Accounted transaction received
4017876 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-04-30 | Computers Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 5568.13 | 1 |  | FA Dep-april-23 | Currency | 5568.13 | 22602003 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-05-03 | Accounted transaction received
4017877 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-04-30 | Electrical appliance Deprectia |  |  |  | Depreciation | Alrowad Construction_OU | 2583.29 | 1 |  | FA Dep-april-23 | Currency | 2583.29 | 22602003 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-05-03 | Accounted transaction received
4017878 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-04-30 | Vehicles Depreciations |  |  |  | Depreciation | Alrowad Construction_OU | 5265.21 | 1 |  | FA Dep-april-23 | Currency | 5265.21 | 22602003 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-05-03 | Accounted transaction received
4018056 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.02 | Rented Cars | 17 | Indirect Cost |  | 2023-04-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 37500 | 1 | نقل افراد فبراير استوريا | نقل افراد فبراير استوريا | Currency | 37500 | 22602003 | 5214 | المتحدة لايجار وتوريد السيارات | rowad | نقل افراد فبراير استوريا |  | Finacial | Received | 2023-05-03 | Accounted transaction received
4046688 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-10 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 2250 | 1 | الوزرات الماسه ف/37117 3/4 | 37117 | Currency | 2250 | 22725777 | 12416 | الماسه للتاجير ومعالجه المياه | rowad | الوزرات الماسه ف/37117 3/4 |  | Finacial | Received | 2023-05-17 | Accounted transaction received
4010485 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-27 | Materials |  |  |  | Materials | Alrowad Construction_OU | -15198.81 | 1 | بواط 10 * 10 عالى المقاس ¾ " |  | Each | -226 | 61479281 |  |  |  | بواط 10 * 10 عالى المقاس ¾ " | 030020100105 | MEP | Received | 2023-04-30 | Accounted transaction received
4010486 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-27 | Materials |  |  |  | Materials | Alrowad Construction_OU | -271.08 | 1 | بواط إمتداد UPVC لماسورة 20مم(اللون أبيض) |  | Each | -40 | 61479282 |  |  |  | بواط إمتداد UPVC لماسورة 20مم(اللون أبيض) | 030010000082 | MEP | Received | 2023-04-30 | Accounted transaction received
4010487 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-27 | Materials |  |  |  | Materials | Alrowad Construction_OU | -1633.9 | 1 | أدابتور UPVC لماسورة 25مم(اللون أبيض) |  | Each | -209 | 61479283 |  |  |  | أدابتور UPVC لماسورة 25مم(اللون أبيض) | 030010000097 | MEP | Received | 2023-04-30 | Accounted transaction received
4010488 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-27 | Materials |  |  |  | Materials | Alrowad Construction_OU | -5719.51 | 1 | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 |  | Meter | -61 | 61479284 |  |  |  | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 | 030020100002 | MEP | Received | 2023-04-30 | Accounted transaction received
4010489 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-27 | Materials |  |  |  | Materials | Alrowad Construction_OU | -12839.93 | 1 | ماسورة صلب مجلفن EMT المقاس 1 " طول الماسورة 3.05 |  | Meter | -95.45 | 61479285 |  |  |  | ماسورة صلب مجلفن EMT المقاس 1 " طول الماسورة 3.05 | 030020100003 | MEP | Received | 2023-04-30 | Accounted transaction received
4010490 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-27 | Materials |  |  |  | Materials | Alrowad Construction_OU | -26972.97 | 1 | ماسورة صلب مجلفن EMT المقاس 2 " طول الماسورة 3.05 |  | Meter | -59.9 | 61479286 |  |  |  | ماسورة صلب مجلفن EMT المقاس 2 " طول الماسورة 3.05 | 030020100005 | MEP | Received | 2023-04-30 | Accounted transaction received
4010491 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-04-27 | Materials |  |  |  | Materials | Alrowad Construction_OU | -6855.39 | 1 | EMT coupling/Flexible 2" inch ( Connector + IMC Coupling + Squeeze ) |  | Each | -30 | 61479287 |  |  |  | EMT coupling/Flexible 2" inch ( Connector + IMC Coupling + Squeeze ) | 030020100193 | MEP | Received | 2023-04-30 | Accounted transaction received
4010492 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.13 | Maintenance | 17 | Indirect Cost |  | 2023-04-27 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 114 | 1 | هواية GX 160 |  | Each | 2 | 61479909 |  |  |  | هواية GX 160 | 330040004126 | Equipment | Received | 2023-04-30 | Accounted transaction received
4010494 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-27 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 100.8 | 1 | Hardware Accessories for Wooden Doors Floor Bolt Sleeve TESA Dust excluding socket. Satin Stainless-Steel Finish. 25x38x13.5mm Dia. TESA GUARDAPOLIS S.S.S |  | Each | 1 | 61481320 |  |  |  | Hardware Accessories for Wooden Doors Floor Bolt Sleeve TESA Dust excluding socket. Satin Stainless-Steel Finish. 25x38x13.5mm Dia. TESA GUARDAPOLIS S.S.S | 250010001517 | Procurement | Received | 2023-04-30 | Accounted transaction received
4010495 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-27 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 198 | 1 | Hardware Accessories for Wooden Doors Double Cylinder TESA Security TE-5 Double Cylinder 35x35mm. 5 Spring Loaded Anti pick Pins. Made to EN-1303 Regulation. |  | Each | 1 | 61481321 |  |  |  | Hardware Accessories for Wooden Doors Double Cylinder TESA Security TE-5 Double Cylinder 35x35mm. 5 Spring Loaded Anti pick Pins. Made to EN-1303 Regulation. | 250010001519 | Procurement | Received | 2023-04-30 | Accounted transaction received
4010496 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-27 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 198 | 1 | Hardware Accessories for Wooden Doors Double Cylinder TESA Security TE-5 Double Cylinder 35x35mm. 5 Spring Loaded Anti pick Pins. Made to EN-1303 Regulation. |  | Each | 1 | 61481322 |  |  |  | Hardware Accessories for Wooden Doors Double Cylinder TESA Security TE-5 Double Cylinder 35x35mm. 5 Spring Loaded Anti pick Pins. Made to EN-1303 Regulation. | 250010001519 | Procurement | Received | 2023-04-30 | Accounted transaction received
4010497 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-27 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 103968 | 1 | Hardware accessories for doors HW-126 Bespoke Door Pull as per Muza Lab Specification MT-4 |  | Each | 32 | 61481323 |  |  |  | Hardware accessories for doors HW-126 Bespoke Door Pull as per Muza Lab Specification MT-4 | 250010001554 | Procurement | Received | 2023-04-30 | Accounted transaction received
4010498 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-27 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 20793.6 | 1 | Hardware accessories for doors Bespoke cover plates in MT-4 Antique brass finish for Floor Spring MT-4 |  | Each | 16 | 61481324 |  |  |  | Hardware accessories for doors Bespoke cover plates in MT-4 Antique brass finish for Floor Spring MT-4 | 250010001561 | Procurement | Received | 2023-04-30 | Accounted transaction received
4010499 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-27 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1046.52 | 1 | Hardware Accessories for Doors FLUSH BOLT FOR WOODEN DOORS with DUST PROOF STRIKE Rockwood 557 x 570 626 |  | Each | 1 | 61481325 |  |  |  | Hardware Accessories for Doors FLUSH BOLT FOR WOODEN DOORS with DUST PROOF STRIKE Rockwood 557 x 570 626 | 250010001573 | Procurement | Received | 2023-04-30 | Accounted transaction received
4010500 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-27 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 25079.43 | 1 | Supply Concealed Door closer up to 120KG for wooden doors, including any requirements to complete the works as per consultant's approval & submittal approval. LCN 3133 Silver |  | Each | 2 | 61481326 |  |  |  | Supply Concealed Door closer up to 120KG for wooden doors, including any requirements to complete the works as per consultant's approval & submittal approval. LCN 3133 Silver | 250010001609 | Procurement | Received | 2023-04-30 | Accounted transaction received
4010501 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-27 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 103740 | 1 | Action floor spring max 180kg for Glass doors, brand Stanley |  | Each | 14 | 61481327 |  |  |  | Action floor spring max 180kg for Glass doors, brand Stanley | 310010000018 | Fleets | Received | 2023-04-30 | Accounted transaction received
4010502 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-27 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 85.5 | 1 | Spring action Floor Bolt with Automatic mechanism Dust proof XA808B DUST PROOF STRIKE, with Satin Stainless-Steel Finish |  | Each | 1 | 61481328 |  |  |  | Spring action Floor Bolt with Automatic mechanism Dust proof XA808B DUST PROOF STRIKE, with Satin Stainless-Steel Finish | 250010001696 | Procurement | Received | 2023-04-30 | Accounted transaction received
4010503 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-27 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2197.92 | 1 | Bridal Suite Signage |  | Each | 1 | 61481329 |  |  |  | Bridal Suite Signage | 250010001934 | Procurement | Received | 2023-04-30 | Accounted transaction received
4010504 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.09.03 | Electric Networks | 2 | SITE WORK |  | 2023-04-27 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 74692.8 | 1 | Down Light IP 65 DAL 30250*035 AMBIANCE 100 DIRECTIONAL IP65 Recessed directional down lighter with satin silver reflector and white ceiling trim Overall diameter 100mm cut out diameter 90mm with PHILIPS LED Lamp 5.5W MR16 GU5.3, 2700K |  | Each | 21 | 61481333 |  |  |  | Down Light IP 65 DAL 30250*035 AMBIANCE 100 DIRECTIONAL IP65 Recessed directional down lighter with satin silver reflector and white ceiling trim Overall diameter 100mm cut out diameter 90mm with PHILIPS LED Lamp 5.5W MR16 GU5.3, 2700K | 030040700477 | MEP | Received | 2023-04-30 | Accounted transaction received
4010505 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-04-27 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 6222.6 | 1 | Wall covering – WC-3 – Cole & Son- The Ardmore Collection, Narina Linen 109/10049 |  | Roll | 2 | 61481337 |  |  |  | Wall covering – WC-3 – Cole & Son- The Ardmore Collection, Narina Linen 109/10049 | 050020000013 | Purchasing | Received | 2023-04-30 | Accounted transaction received
4010506 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-27 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 32712.3 | 1 | Supply Concealed Door closer to 80KG for wooden doors, including any requirements to complete the works as per consultant's approval & submittal approval. Consort CDCC3 Silver |  | Each | 4 | 61481480 |  |  |  | Supply Concealed Door closer to 80KG for wooden doors, including any requirements to complete the works as per consultant's approval & submittal approval. Consort CDCC3 Silver | 250010001608 | Procurement | Received | 2023-04-30 | Accounted transaction received
4010507 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-27 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2736 | 1 | Recessed Door Pull as per ABD & UWS Specification Finish MT-8 |  | Each | 2 | 61482555 |  |  |  | Recessed Door Pull as per ABD & UWS Specification Finish MT-8 | 250010001669 | Procurement | Received | 2023-04-30 | Accounted transaction received
4017357 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-04-30 | Hirings Payrool |  |  |  | Indirect | Alrowad Construction_OU | 1162756.52 | 1 | قيد مرتبات شهر ابريل 2023 | Salary-April-2023 | Currency | 1162756.52 | 22602003 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر ابريل 2023 |  | Finacial | Received | 2023-05-03 | Accounted transaction received
4017398 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-04-30 | Honouring of terrorism 0.0005 |  |  |  | Indirect | Alrowad Construction_OU | 340.67 | 1 | قيد مرتبات شهر ابريل 2023 | Salary-April-2023 | Currency | 340.67 | 22602003 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر ابريل 2023 |  | Finacial | Received | 2023-05-03 | Accounted transaction received
4017439 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.06 | Telephones | 17 | Indirect Cost |  | 2023-04-30 | Telephones |  |  |  | Indirect | Alrowad Construction_OU | -285.63 | 1 | قيد مرتبات شهر ابريل 2023 | Salary-April-2023 | Currency | -285.63 | 22602003 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر ابريل 2023 |  | Finacial | Received | 2023-05-03 | Accounted transaction received
4017479 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.02 | Health Care | 17 | Indirect Cost |  | 2023-04-30 | Medical Care |  |  |  | Direct Manpower | Alrowad Construction_OU | -3541.55 | 1 | قيد مرتبات شهر ابريل 2023 | Salary-April-2023 | Currency | -3541.55 | 22602003 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر ابريل 2023 |  | Finacial | Received | 2023-05-03 | Accounted transaction received
4017521 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-04-30 | Hirings Payrool |  |  |  | Indirect | Alrowad Construction_OU | -36292.67 | 1 | قيد مرتبات شهر ابريل 2023 | Salary-April-2023 | Currency | -36292.67 | 22602003 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر ابريل 2023 |  | Finacial | Received | 2023-05-03 | Accounted transaction received
4021077 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-04-30 | Computers Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 2501.65 | 1 |  | Adj.Depreciation dep to projects apt-23 | Currency | 2501.65 | 22619243 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-05-07 | Accounted transaction received
4021122 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-04-30 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 6834.87 | 1 |  | Adj.Depreciation dep to projects apt-23 | Currency | 6834.87 | 22619243 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-05-07 | Accounted transaction received
4021167 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-04-30 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 14580.28 | 1 |  | Adj.Depreciation dep to projects apt-23 | Currency | 14580.28 | 22619243 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-05-07 | Accounted transaction received
4021212 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-04-30 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 10644.2 | 1 |  | Adj.Depreciation dep to projects apt-23 | Currency | 10644.2 | 22619243 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-05-07 | Accounted transaction received
4021257 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-04-30 | Furniture Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 930.35 | 1 |  | Adj.Depreciation dep to projects apt-23 | Currency | 930.35 | 22619243 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-05-07 | Accounted transaction received
4021302 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-04-30 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 1427.35 | 1 |  | Adj.Depreciation dep to projects apt-23 | Currency | 1427.35 | 22619243 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-05-07 | Accounted transaction received
4029183 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2023-05-08 | Accomodation |  |  |  | Indirect | Alrowad Construction_OU | 41400 | 1 | تسويه ك /217 ايجارات شهر مايو -استوريا | st-217-5-23 | Currency | 41400 | 22689432 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /217 ايجارات شهر مايو -استوريا |  | Finacial | Received | 2023-05-09 | Accounted transaction received
4108047 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.06 | Telephones | 17 | Indirect Cost |  | 2023-05-18 | Telephones |  |  |  | Indirect | Alrowad Construction_OU | 9353.8 | 1 | استحقاق فاتورة اورنج عن ش يناير23 | استحقاق فاتورة اورنج عن ش يناير23 | Currency | 9353.8 | 22886958 | 2135 | اورنج مصر للاتصالات | Egypt | استحقاق فاتورة اورنج عن ش يناير23 |  | Finacial | Received | 2023-05-23 | Accounted transaction received
4108194 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.03 | Hirings daily wages | 17 | Indirect Cost |  | 2023-05-21 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 3171.66 | 1 | استقالات 7&8&9&10&11&12-2022/1&2&3&4-2023 | استقالات 7&8&9&10&11&12-2022/1&2&3&4-2023 | Currency | 3171.66 | 22886958 | 9909 | ناو باى لاعداد البرمجيات ونظم المرتبات | rowad | استقالات 7&8&9&10&11&12-2022/1&2&3&4-2023 |  | Finacial | Received | 2023-05-23 | Accounted transaction received
4108389 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-23 | Other Equipment |  |  |  | Indirect | Alrowad Construction_OU | 47880 | 1 | استوريا كوالتى كرين ف/ 334501506103 18/4 | 3.345015061e+11 | Currency | 47880 | 22886958 | 4638 | كواليتي كرين | rowad | استوريا كوالتى كرين ف/ 334501506103 18/4 |  | Finacial | Received | 2023-05-23 | Accounted transaction received
4116590 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 484.5 | 1 | ورنيش مط |  | Kilogram | 1 | 61959478 |  |  |  | ورنيش مط | 050010000211 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4029184 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2023-05-08 | Accomodation |  |  |  | Indirect | Alrowad Construction_OU | -41400 | 1 | تسويه ك /217 ايجارات شهر مايو -استوريا | st-217-5-23 | Currency | -41400 | 22689432 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /217 ايجارات شهر مايو -استوريا |  | Finacial | Received | 2023-05-09 | Accounted transaction received
4029185 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2023-05-08 | Accomodation |  |  |  | Indirect | Alrowad Construction_OU | 35200 | 1 | تسويه ك /217 ايجارات شهر مايو -استوريا | st-217-5-23 | Currency | 35200 | 22689432 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /217 ايجارات شهر مايو -استوريا |  | Finacial | Received | 2023-05-09 | Accounted transaction received
4029225 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-08 | Rented Cars |  |  |  | Indirect | Alrowad Construction_OU | 425 | 1 | تسويه ك / 185-190-191-192-193-متنوعات | st-185-190-191-192-193-5-23 | Currency | 425 | 22689432 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك / 185-190-191-192-193-متنوعات |  | Finacial | Received | 2023-05-09 | Accounted transaction received
4029226 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-08 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 1855 | 1 | تسويه ك / 185-190-191-192-193-متنوعات | st-185-190-191-192-193-5-23 | Currency | 1855 | 22689432 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك / 185-190-191-192-193-متنوعات |  | Finacial | Received | 2023-05-09 | Accounted transaction received
4029227 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-08 | Transportation |  |  |  | Indirect | Alrowad Construction_OU | 235 | 1 | تسويه ك / 185-190-191-192-193-متنوعات | st-185-190-191-192-193-5-23 | Currency | 235 | 22689432 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك / 185-190-191-192-193-متنوعات |  | Finacial | Received | 2023-05-09 | Accounted transaction received
4029228 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-08 | Rented Cars |  |  |  | Indirect | Alrowad Construction_OU | 2500 | 1 | تسويه ك / 185-190-191-192-193-متنوعات | st-185-190-191-192-193-5-23 | Currency | 2500 | 22689432 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك / 185-190-191-192-193-متنوعات |  | Finacial | Received | 2023-05-09 | Accounted transaction received
4029229 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-08 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 1120 | 1 | تسويه ك /196-197-207-208-211-213-214-215-متنوعات | st-196-197-207-208-211-213-214-215-5-23 | Currency | 1120 | 22689432 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /196-197-207-208-211-213-214-215-متنوعات |  | Finacial | Received | 2023-05-09 | Accounted transaction received
4029230 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.08 | Electrical Expenses | 17 | Indirect Cost |  | 2023-05-08 | Electrical Expenses |  |  |  | Indirect | Alrowad Construction_OU | 733 | 1 | تسويه ك /196-197-207-208-211-213-214-215-متنوعات | st-196-197-207-208-211-213-214-215-5-23 | Currency | 733 | 22689432 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /196-197-207-208-211-213-214-215-متنوعات |  | Finacial | Received | 2023-05-09 | Accounted transaction received
4029231 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-08 | Maintenance |  |  |  | Indirect | Alrowad Construction_OU | 850 | 1 | تسويه ك /196-197-207-208-211-213-214-215-متنوعات | st-196-197-207-208-211-213-214-215-5-23 | Currency | 850 | 22689432 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /196-197-207-208-211-213-214-215-متنوعات |  | Finacial | Received | 2023-05-09 | Accounted transaction received
4029265 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.FS.03 | Insurance | 17 | Indirect Cost |  | 2023-05-08 | Insurance |  |  |  | Taxes & Insurance | Alrowad Construction_OU | 15700 | 1 | استوريا جى اى جى و/382-357 | 382-357 | Currency | 15700 | 22689432 | 6025 | جى.اى.جى للتأمين - مصر | rowad | استوريا جى اى جى و/382-357 |  | Finacial | Received | 2023-05-09 | Accounted transaction received
4046162 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-05-01 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | -120440 | 1 | يوميات عماله الفتره 2 ش 4 التقديري | يوميات عماله الفتره 2 ش 4 التقديري | Currency | -120440 | 22725777 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 2 ش 4 التقديري |  | Finacial | Received | 2023-05-17 | Accounted transaction received
4046878 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-11 | Bank Fees |  |  |  | Finance cost | Alrowad Construction_OU | 18415.9 | 1 | LG bM 5/2023 astoria | LG bM 5/2023 astoria | Currency | 18415.9 | 22725777 | 2131 | Miscellaneous supplier | RME | LG bM 5/2023 astoria |  | Finacial | Received | 2023-05-17 | Accounted transaction received
4046889 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-05-11 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 148465 | 1 | يوميات عماله الفتره 2 ش 4 الفعلي | يوميات عماله الفتره 2 ش 4 الفعلي | Currency | 148465 | 22725777 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 2 ش 4 الفعلي |  | Finacial | Received | 2023-05-17 | Accounted transaction received
4047092 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.06 | Material Transportat | 17 | Indirect Cost |  | 2023-05-14 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 27841 | 1 | اعمال نقل ثقيل - 2/ 23 - waldorf astoria | اعمال نقل ثقيل - 2/ 23 - waldorf astoria | Currency | 27841 | 22725777 | 8534 | مكتب الحمد للنقل | rowad | اعمال نقل ثقيل - 2/ 23 - waldorf astoria |  | Finacial | Received | 2023-05-17 | Accounted transaction received
4047183 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.06 | Material Transportat | 17 | Indirect Cost |  | 2023-05-15 | Material Transportation |  |  |  | Indirect | Alrowad Construction_OU | 1710 | 1 | نقل ثقيل 2/ 23waldorf astoria | نقل ثقيل 2/ 23waldorf astoria | Currency | 1710 | 22725777 | 1764 | الوليد للنقل وتجارة العطارة (محمد ماهر | Egypt | نقل ثقيل 2/ 23waldorf astoria |  | Finacial | Received | 2023-05-17 | Accounted transaction received
4047232 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.06 | Material Transportat | 17 | Indirect Cost |  | 2023-05-16 | Material Transportation |  |  |  | Indirect | Alrowad Construction_OU | 10092 | 1 | نقل ثقيل 2/ 23- waldorf astoria | نقل ثقيل 2/ 23- waldorf astoria | Currency | 10092 | 22725777 | 5119 | مكتب الحاتم للنقل | rowad | نقل ثقيل 2/ 23- waldorf astoria |  | Finacial | Received | 2023-05-17 | Accounted transaction received
4058574 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-05-21 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1020 | 1 | 1.1 76627/4 |  | Currency | 5.1 |  | 12356 | محمود يحى احمد محمد-ذاتى |  | 1.1 76627/4 |  | Finacial | Received | 2023-05-21 | Accounted transaction received
4058575 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-05-21 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1530 | 1 | 1.2 76627/4 |  | Currency | 5.1 |  | 12356 | محمود يحى احمد محمد-ذاتى |  | 1.2 76627/4 |  | Finacial | Received | 2023-05-21 | Accounted transaction received
4058576 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-05-21 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2805 | 1 | 1.3 76627/4 |  | Currency | 5.1 |  | 12356 | محمود يحى احمد محمد-ذاتى |  | 1.3 76627/4 |  | Finacial | Received | 2023-05-21 | Accounted transaction received
4116505 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-22 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 8025.6 | 1 | BUDGET LOCK - YALE - Code 30074007 - Art No. 280DN |  | Each | 8 | 62112265 |  |  |  | BUDGET LOCK - YALE - Code 30074007 - Art No. 280DN | 250010000319 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116506 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-22 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 727.32 | 1 | كابل نحاس مجدول شعر مقاس 2 × 1 مم (pvc/pvc) جهد (500/300) |  | Meter | 22 | 62145291 |  |  |  | كابل نحاس مجدول شعر مقاس 2 × 1 مم (pvc/pvc) جهد (500/300) | 030030100151 | MEP | Received | 2023-05-23 | Accounted transaction received
4116507 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-22 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1552.13 | 1 | ماسورة صلب مجلفن EMT المقاس ½ 1 " طول الماسورة 3.05 |  | Meter | 6.1 | 62145292 |  |  |  | ماسورة صلب مجلفن EMT المقاس ½ 1 " طول الماسورة 3.05 | 030020100004 | MEP | Received | 2023-05-23 | Accounted transaction received
4116508 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-22 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1607.85 | 1 | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 |  | Each | 13 | 62145293 |  |  |  | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 | 030060100951 | MEP | Received | 2023-05-23 | Accounted transaction received
4116509 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-22 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 454.53 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 8 | 62145294 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-05-23 | Accounted transaction received
4116510 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-22 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 395.08 | 1 | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 |  | Each | 5 | 62145295 |  |  |  | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 | 030060100956 | MEP | Received | 2023-05-23 | Accounted transaction received
4116511 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-22 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1289.11 | 1 | بواط ثماني فتحات ¾ المقاس ¾ " |  | Each | 20 | 62169118 |  |  |  | بواط ثماني فتحات ¾ المقاس ¾ " | 030020100098 | MEP | Received | 2023-05-23 | Accounted transaction received
4116512 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-22 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 248.1 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 2 | 62169119 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-05-23 | Accounted transaction received
4116513 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-22 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2320.94 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 13 | 62169120 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-05-23 | Accounted transaction received
4116514 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-22 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 17.75 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 1 | 62169121 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-05-23 | Accounted transaction received
4116515 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-22 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 190.17 | 1 | mosaic adapter code 69580 |  | Each | 2 | 62169122 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-05-23 | Accounted transaction received
4116516 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-22 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 160.5 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 2 | 62169123 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-05-23 | Accounted transaction received
4116517 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-22 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 100.39 | 1 | SPLASH PROOF COVER Code : 617636 |  | Each | 1 | 62169124 |  |  |  | SPLASH PROOF COVER Code : 617636 | 030060100927 | MEP | Received | 2023-05-23 | Accounted transaction received
4116518 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-22 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 112.68 | 1 | 1G 20A DP SWT + NEON + E WH - 617671 |  | Each | 1 | 62169125 |  |  |  | 1G 20A DP SWT + NEON + E WH - 617671 | 030060100942 | MEP | Received | 2023-05-23 | Accounted transaction received
4116519 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.13 | Maintenance | 17 | Indirect Cost |  | 2023-05-15 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1322.24 | 1 | سيراميك ارت موديل (جيومتريكا ايبوني وود / جراي) لزوم الأرضيات مقاس 42 سم * 42 سم |  | Square Meter | 12.72 | 61858388 |  |  |  | سيراميك ارت موديل (جيومتريكا ايبوني وود / جراي) لزوم الأرضيات مقاس 42 سم * 42 سم | 170010000273 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116520 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.13 | Maintenance | 17 | Indirect Cost |  | 2023-05-15 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 486.32 | 1 | Nilo Flex 10pz – 4mm |  | Square Meter | 10 | 61858389 |  |  |  | Nilo Flex 10pz – 4mm | 360010000351 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116521 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-15 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 136.8 | 1 | جوان كاوتش 2 بوصة |  | Each | 4 | 61859103 |  |  |  | جوان كاوتش 2 بوصة | 060019000087 | MEP | Received | 2023-05-23 | Accounted transaction received
4116522 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-15 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 729.6 | 1 | جوان كاوتش 3 بوصة |  | Each | 16 | 61859104 |  |  |  | جوان كاوتش 3 بوصة | 060019000088 | MEP | Received | 2023-05-23 | Accounted transaction received
4116523 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-15 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 35032.2 | 1 | Privacy Door Latch Brand Welder part # 43702424 Finish Silver |  | Each | 70 | 61859415 |  |  |  | Privacy Door Latch Brand Welder part # 43702424 Finish Silver | 250010001658 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116524 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 187.97 | 1 | أفيز هانجر EMT المقاس 2 " |  | Each | 11 | 61860838 |  |  |  | أفيز هانجر EMT المقاس 2 " | 030020100080 | MEP | Received | 2023-05-23 | Accounted transaction received
4116525 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 644.56 | 1 | بواط ثماني فتحات ¾ المقاس ¾ " |  | Each | 10 | 61860839 |  |  |  | بواط ثماني فتحات ¾ المقاس ¾ " | 030020100098 | MEP | Received | 2023-05-23 | Accounted transaction received
4116526 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 208.3 | 1 | أدابتور UPVC لماسورة 32مم(اللون أبيض) |  | Each | 16 | 61860840 |  |  |  | أدابتور UPVC لماسورة 32مم(اللون أبيض) | 030010000098 | MEP | Received | 2023-05-23 | Accounted transaction received
4116527 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 14.82 | 1 | أفيز 32مم UPVC(اللون أبيض) |  | Each | 3 | 61860841 |  |  |  | أفيز 32مم UPVC(اللون أبيض) | 030010000108 | MEP | Received | 2023-05-23 | Accounted transaction received
4116528 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1436.4 | 1 | غطاء بواط معدن مقاس 4*4 |  | Each | 210 | 61860842 |  |  |  | غطاء بواط معدن مقاس 4*4 | 030020100129 | MEP | Received | 2023-05-23 | Accounted transaction received
4116529 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 28.5 | 1 | اكستنشن 10*10 مقاس 3/4" |  | Each | 1 | 61860843 |  |  |  | اكستنشن 10*10 مقاس 3/4" | 030020100146 | MEP | Received | 2023-05-23 | Accounted transaction received
4116530 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 80.46 | 1 | أفيز أثنين جناح لماسورة EMT المقاس ½ 1 " |  | Each | 15 | 61860844 |  |  |  | أفيز أثنين جناح لماسورة EMT المقاس ½ 1 " | 030020100036 | MEP | Received | 2023-05-23 | Accounted transaction received
4116531 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4154.68 | 1 | Hot Dip Galvanized cable trunk100x100mm thickness 1.5mm with cover 1.25mm thickness |  | Meter | 9 | 61860845 |  |  |  | Hot Dip Galvanized cable trunk100x100mm thickness 1.5mm with cover 1.25mm thickness | 030100500001 | MEP | Received | 2023-05-23 | Accounted transaction received
4116532 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2400.84 | 1 | لاكور بواط على فليكسبل EMT المقاس 3/4 " |  | Each | 81 | 61860846 |  |  |  | لاكور بواط على فليكسبل EMT المقاس 3/4 " | 030020100214 | MEP | Received | 2023-05-23 | Accounted transaction received
4116533 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3242.16 | 1 | لاكور بواط على فليكسبل EMT المقاس 1" |  | Each | 79 | 61860847 |  |  |  | لاكور بواط على فليكسبل EMT المقاس 1" | 030020100215 | MEP | Received | 2023-05-23 | Accounted transaction received
4116534 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-05-16 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2825.75 | 1 | اسمنت اسود رتبة 12.5 |  | Ton | 1.5 | 61869494 |  |  |  | اسمنت اسود رتبة 12.5 | 140010000089 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116535 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-16 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4003.68 | 1 | Privacy Door Latch Brand Welder part # 43702424 Finish Silver |  | Each | 8 | 61876105 |  |  |  | Privacy Door Latch Brand Welder part # 43702424 Finish Silver | 250010001658 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116536 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-16 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 64.46 | 1 | بواط ثماني فتحات ¾ المقاس ¾ " |  | Each | 1 | 61876217 |  |  |  | بواط ثماني فتحات ¾ المقاس ¾ " | 030020100098 | MEP | Received | 2023-05-23 | Accounted transaction received
4116537 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-16 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 72.62 | 1 | أفيز أثنين جناح لماسورة EMT المقاس ¾ " |  | Each | 29 | 61876218 |  |  |  | أفيز أثنين جناح لماسورة EMT المقاس ¾ " | 030020100033 | MEP | Received | 2023-05-23 | Accounted transaction received
4116538 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-16 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 90 | 1 | Category 6A Field Terminated Plug and Boot with Black Latch Protector Clip |  | Each | 1 | 61876219 |  |  |  | Category 6A Field Terminated Plug and Boot with Black Latch Protector Clip | 031030000447 | MEP | Received | 2023-05-23 | Accounted transaction received
4116539 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-16 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1240.33 | 1 | CEILING MOUNT SPEAKER, Model No. PC-648R |  | Each | 3 | 61876220 |  |  |  | CEILING MOUNT SPEAKER, Model No. PC-648R | 031070000015 | MEP | Received | 2023-05-23 | Accounted transaction received
4116540 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-16 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 36812.88 | 1 | Beige Washed River Pebbles size 4-5 cm |  | Square Meter | 69 | 61877010 |  |  |  | Beige Washed River Pebbles size 4-5 cm | 140010000085 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116541 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-17 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2291.4 | 1 | Concealed Hinges up to 120KG for wooden doors, including any requirements Brand Eurospec – Ceam 3D Code 1131 Finish Black |  | Each | 1 | 61893096 |  |  |  | Concealed Hinges up to 120KG for wooden doors, including any requirements Brand Eurospec – Ceam 3D Code 1131 Finish Black | 250010001651 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116542 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-17 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 369.29 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 25مم وقطر خارجى 31.1مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 1 | 61898786 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 25مم وقطر خارجى 31.1مم طول اللفه 30 متر(اللون رمادى) | 030010000062 | MEP | Received | 2023-05-23 | Accounted transaction received
4116543 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-17 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1653 | 1 | كابل نحاس مجدول شعر مقاس 2 × 1 مم (pvc/pvc) جهد (500/300) |  | Meter | 50 | 61898787 |  |  |  | كابل نحاس مجدول شعر مقاس 2 × 1 مم (pvc/pvc) جهد (500/300) | 030030100151 | MEP | Received | 2023-05-23 | Accounted transaction received
4116544 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-17 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 178.53 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 1 | 61898788 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-05-23 | Accounted transaction received
4116545 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-17 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 163.3 | 1 | 576562 Code وش مربع فضي |  | Each | 3 | 61898789 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-05-23 | Accounted transaction received
4116546 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-17 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 826.89 | 1 | CEILING MOUNT SPEAKER, Model No. PC-648R |  | Each | 2 | 61898790 |  |  |  | CEILING MOUNT SPEAKER, Model No. PC-648R | 031070000015 | MEP | Received | 2023-05-23 | Accounted transaction received
4116547 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3105.12 | 1 | كابل نحاس ترمو ضغط منخفض مقاس 4 × 10 مم (pvc/pvc) |  | Meter | 22 | 61909291 |  |  |  | كابل نحاس ترمو ضغط منخفض مقاس 4 × 10 مم (pvc/pvc) | 030030100005 | MEP | Received | 2023-05-23 | Accounted transaction received
4116548 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 50279.91 | 1 | LAN Cable F/FTB Cat6A, LSZH 4PX23AWG |  | Meter | 1000 | 61909292 |  |  |  | LAN Cable F/FTB Cat6A, LSZH 4PX23AWG | 032030000002 | MEP | Received | 2023-05-23 | Accounted transaction received
4116549 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1710 | 1 | Robe Hook HW-4 |  | Each | 2 | 61940273 |  |  |  | Robe Hook HW-4 | 250010002115 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116550 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1846.8 | 1 | Kick Plate ,, France Metal ,, ST.ST ,, Up to 200 x 1000 mm |  | Each | 3 | 61940347 |  |  |  | Kick Plate ,, France Metal ,, ST.ST ,, Up to 200 x 1000 mm | 250010000569 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116551 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 593.99 | 1 | Hardware Accessories for Wooden Doors Double Cylinder TESA Security TE-5 Double Cylinder 35x35mm. 5 Spring Loaded Anti pick Pins. Made to EN-1303 Regulation. |  | Each | 3 | 61940348 |  |  |  | Hardware Accessories for Wooden Doors Double Cylinder TESA Security TE-5 Double Cylinder 35x35mm. 5 Spring Loaded Anti pick Pins. Made to EN-1303 Regulation. | 250010001519 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116552 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 17111.4 | 1 | Hardware accessories for doors IR-36 Pull Handle as per ABD & UWS Specification MT-4 |  | Each | 2 | 61940349 |  |  |  | Hardware accessories for doors IR-36 Pull Handle as per ABD & UWS Specification MT-4 | 250010001560 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116589 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 769.5 | 1 | اديبوند 65 |  | Kilogram | 5 | 61959477 |  |  |  | اديبوند 65 | 360010000273 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116553 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 51334.2 | 1 | Hardware accessories for doors IR-36 Pull Handle as per ABD & UWS Specification MT-4 |  | Each | 6 | 61940350 |  |  |  | Hardware accessories for doors IR-36 Pull Handle as per ABD & UWS Specification MT-4 | 250010001560 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116554 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 50158.86 | 1 | Supply Concealed Door closer up to 120KG for wooden doors, including any requirements to complete the works as per consultant's approval & submittal approval. LCN 3133 Silver |  | Each | 4 | 61940351 |  |  |  | Supply Concealed Door closer up to 120KG for wooden doors, including any requirements to complete the works as per consultant's approval & submittal approval. LCN 3133 Silver | 250010001609 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116555 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2850 | 1 | Drawer knop for VIP |  | Each | 5 | 61940352 |  |  |  | Drawer knop for VIP | 250010001659 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116556 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 820.8 | 1 | Handle Extension: IR-36 Dimensions: 30mm Materials: Brass Finish: Antique Brass |  | Each | 4 | 61940353 |  |  |  | Handle Extension: IR-36 Dimensions: 30mm Materials: Brass Finish: Antique Brass | 250010002118 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116557 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 5745.6 | 1 | Handle Extension: IR-36 Dimensions: 30mm Materials: Brass Finish: Antique Brass |  | Each | 28 | 61940354 |  |  |  | Handle Extension: IR-36 Dimensions: 30mm Materials: Brass Finish: Antique Brass | 250010002118 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116558 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 306.75 | 1 | سيفتي عمال |  | Each | 1 | 61940572 |  |  |  | سيفتي عمال | 010030000002 | Safety | Received | 2023-05-23 | Accounted transaction received
4116559 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 5198.4 | 1 | Hardware accessories for doors IR-23 Bespoke Metal Kickplate MT-1 |  | Each | 4 | 61940582 |  |  |  | Hardware accessories for doors IR-23 Bespoke Metal Kickplate MT-1 | 250010001563 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116591 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1425 | 1 | اكمون 8 مم |  | Each | 100 | 61959686 |  |  |  | اكمون 8 مم | 200020000098 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116592 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 60 | 1 | جوان 4/3 بوصة |  | Each | 6 | 61959687 |  |  |  | جوان 4/3 بوصة | 240070000170 | MEP | Received | 2023-05-23 | Accounted transaction received
4116593 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 50 | 1 | وصلة مرنة 60 سم |  | Each | 1 | 61959688 |  |  |  | وصلة مرنة 60 سم | 060021000011 | MEP | Received | 2023-05-23 | Accounted transaction received
4116594 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 45 | 1 | جوان مبطط 1.5 |  | Each | 6 | 61959689 |  |  |  | جوان مبطط 1.5 | 060019000080 | MEP | Received | 2023-05-23 | Accounted transaction received
4116595 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2257.2 | 1 | طابق حوض يدوي |  | Each | 12 | 61959690 |  |  |  | طابق حوض يدوي | 060031000015 | MEP | Received | 2023-05-23 | Accounted transaction received
4116596 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 240 | 1 | جلبة تطويل ½*½ |  | Each | 12 | 61959691 |  |  |  | جلبة تطويل ½*½ | 060019000104 | MEP | Received | 2023-05-23 | Accounted transaction received
4116597 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 342 | 1 | فيشر 8 مم |  | Carton | 200 | 61960045 |  |  |  | فيشر 8 مم | 200010000164 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116598 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1254 | 1 | فلكسيبل معدن المقاس ¾ " |  | Meter | 44 | 61960046 |  |  |  | فلكسيبل معدن المقاس ¾ " | 030020100091 | MEP | Received | 2023-05-23 | Accounted transaction received
4116599 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2736 | 1 | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) |  | Meter | 120 | 61960047 |  |  |  | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) | 030010000052 | MEP | Received | 2023-05-23 | Accounted transaction received
4116600 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 798 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 100 | 61960048 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-05-23 | Accounted transaction received
4116601 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 661.2 | 1 | كابل نحاس مجدول شعر مقاس 2 × 1 مم (pvc/pvc) جهد (500/300) |  | Meter | 20 | 61960049 |  |  |  | كابل نحاس مجدول شعر مقاس 2 × 1 مم (pvc/pvc) جهد (500/300) | 030030100151 | MEP | Received | 2023-05-23 | Accounted transaction received
4116602 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 115 | 1 | مسمار 6 مم بالوردة والصامولة |  | Each | 30 | 61960050 |  |  |  | مسمار 6 مم بالوردة والصامولة | 200020000222 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116603 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 171 | 1 | حزام بلاستيك 30 سم × 3.6 مم أبيض |  | Pack | 3 | 61960051 |  |  |  | حزام بلاستيك 30 سم × 3.6 مم أبيض | 030131100015 | MEP | Received | 2023-05-23 | Accounted transaction received
4116604 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 399 | 1 | مسمار مخ طاسة 6* 16 بالوردة والصامولة |  | Each | 200 | 61960052 |  |  |  | مسمار مخ طاسة 6* 16 بالوردة والصامولة | 200020000335 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116605 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 150 | 1 | مسمار 10 مم طول 4 سم بالصامولة والوردة |  | Each | 30 | 61960053 |  |  |  | مسمار 10 مم طول 4 سم بالصامولة والوردة | 200020000414 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116606 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 150 | 1 | Wire Nut 1.5 mm |  | Each | 200 | 61960054 |  |  |  | Wire Nut 1.5 mm | 030130800012 | MEP | Received | 2023-05-23 | Accounted transaction received
4116607 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 182.4 | 1 | Wire Nut 3mm |  | Each | 200 | 61960055 |  |  |  | Wire Nut 3mm | 030130800015 | MEP | Received | 2023-05-23 | Accounted transaction received
4116608 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1425 | 1 | مفتاح فردي 20 امبير |  | Each | 10 | 61960056 |  |  |  | مفتاح فردي 20 امبير | 030110600098 | MEP | Received | 2023-05-23 | Accounted transaction received
4116609 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 285 | 1 | مسمار مخ طاسة 10مم |  | Each | 200 | 61960057 |  |  |  | مسمار مخ طاسة 10مم | 200020000545 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116610 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 79.8 | 1 | ريكم حراري 1 مم |  | Each | 10 | 61960058 |  |  |  | ريكم حراري 1 مم | 030060100824 | MEP | Received | 2023-05-23 | Accounted transaction received
4116611 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 102.6 | 1 | ريكم حراري 2 مم |  | Each | 10 | 61960059 |  |  |  | ريكم حراري 2 مم | 030060100825 | MEP | Received | 2023-05-23 | Accounted transaction received
4116612 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 262.2 | 1 | ريكم سيلكون 3 مم |  | Each | 10 | 61960060 |  |  |  | ريكم سيلكون 3 مم | 030060100826 | MEP | Received | 2023-05-23 | Accounted transaction received
4116613 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2894.11 | 1 | CEILING MOUNT SPEAKER, Model No. PC-648R |  | Each | 7 | 61960061 |  |  |  | CEILING MOUNT SPEAKER, Model No. PC-648R | 031070000015 | MEP | Received | 2023-05-23 | Accounted transaction received
4116614 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 718.2 | 1 | Driver Model RS-15-12. I/P 220VAC Output 12VDC Single Output at 1.3A |  | Each | 2 | 61960062 |  |  |  | Driver Model RS-15-12. I/P 220VAC Output 12VDC Single Output at 1.3A | 030049100070 | MEP | Received | 2023-05-23 | Accounted transaction received
4116615 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1368 | 1 | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) |  | Meter | 60 | 61648782 |  |  |  | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) | 030010000052 | MEP | Received | 2023-05-23 | Accounted transaction received
4116616 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1368 | 1 | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) |  | Meter | 60 | 61648783 |  |  |  | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) | 030010000052 | MEP | Received | 2023-05-23 | Accounted transaction received
4116617 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 351.76 | 1 | بواط 10 * 10 عالى المقاس 1 " |  | Each | 5 | 61648784 |  |  |  | بواط 10 * 10 عالى المقاس 1 " | 030020100104 | MEP | Received | 2023-05-23 | Accounted transaction received
4116618 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 672.51 | 1 | بواط 10 * 10 عالى المقاس ¾ " |  | Each | 10 | 61648785 |  |  |  | بواط 10 * 10 عالى المقاس ¾ " | 030020100105 | MEP | Received | 2023-05-23 | Accounted transaction received
4116619 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 134.5 | 1 | بواط 10 * 10 عالى المقاس ¾ " |  | Each | 2 | 61648786 |  |  |  | بواط 10 * 10 عالى المقاس ¾ " | 030020100105 | MEP | Received | 2023-05-23 | Accounted transaction received
4116620 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 277.76 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 1 | 61648787 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) | 030010000059 | MEP | Received | 2023-05-23 | Accounted transaction received
4116621 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 390.89 | 1 | أدابتور UPVC لماسورة 25مم(اللون أبيض) |  | Each | 50 | 61648788 |  |  |  | أدابتور UPVC لماسورة 25مم(اللون أبيض) | 030010000097 | MEP | Received | 2023-05-23 | Accounted transaction received
4116622 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 742.14 | 1 | سلك نحاس مصمت مقاس 4 مم اللون أصفر (cu/xlpe) جهد (750/450) |  | Meter | 100 | 61648789 |  |  |  | سلك نحاس مصمت مقاس 4 مم اللون أصفر (cu/xlpe) جهد (750/450) | 030030100290 | MEP | Received | 2023-05-23 | Accounted transaction received
4116623 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 165.3 | 1 | جلاند فلكسبل مقاس 16 مم |  | Each | 25 | 61648790 |  |  |  | جلاند فلكسبل مقاس 16 مم | 030010000167 | MEP | Received | 2023-05-23 | Accounted transaction received
4116624 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1143.9 | 1 | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 |  | Meter | 12.2 | 61648791 |  |  |  | ماسورة صلب مجلفن EMT المقاس ¾ " طول الماسورة 3.05 | 030020100002 | MEP | Received | 2023-05-23 | Accounted transaction received
4116625 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1105.8 | 1 | لاكور ماسورة EMT المقاس ¾ " |  | Each | 50 | 61648792 |  |  |  | لاكور ماسورة EMT المقاس ¾ " | 030020100015 | MEP | Received | 2023-05-23 | Accounted transaction received
4116626 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 51.71 | 1 | لاكور ماسورة EMT المقاس 1 " |  | Each | 6 | 61648793 |  |  |  | لاكور ماسورة EMT المقاس 1 " | 030020100016 | MEP | Received | 2023-05-23 | Accounted transaction received
4116627 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 451.08 | 1 | جلبة ماسورة EMT المقاس ¾ " |  | Each | 25 | 61648794 |  |  |  | جلبة ماسورة EMT المقاس ¾ " | 030020100021 | MEP | Received | 2023-05-23 | Accounted transaction received
4116628 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 144.35 | 1 | جلبة ماسورة EMT المقاس ¾ " |  | Each | 8 | 61648795 |  |  |  | جلبة ماسورة EMT المقاس ¾ " | 030020100021 | MEP | Received | 2023-05-23 | Accounted transaction received
4116629 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 125.21 | 1 | أفيز أثنين جناح لماسورة EMT المقاس ¾ " |  | Each | 50 | 61648796 |  |  |  | أفيز أثنين جناح لماسورة EMT المقاس ¾ " | 030020100033 | MEP | Received | 2023-05-23 | Accounted transaction received
4116630 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 20.03 | 1 | أفيز أثنين جناح لماسورة EMT المقاس ¾ " |  | Each | 8 | 61648797 |  |  |  | أفيز أثنين جناح لماسورة EMT المقاس ¾ " | 030020100033 | MEP | Received | 2023-05-23 | Accounted transaction received
4116631 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 72.96 | 1 | أفيز أثنين جناح لماسورة EMT المقاس 1 " |  | Each | 20 | 61648798 |  |  |  | أفيز أثنين جناح لماسورة EMT المقاس 1 " | 030020100034 | MEP | Received | 2023-05-23 | Accounted transaction received
4116632 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 9927.5 | 1 | LCP |  | Each | 1 | 61648799 |  |  |  | LCP | 030050100001 | MEP | Received | 2023-05-23 | Accounted transaction received
4116633 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 811.12 | 1 | سلك نحاس مجدول مقاس 4 مم اللون أصفر × أخضر (cu/pvc) |  | Meter | 100 | 61648800 |  |  |  | سلك نحاس مجدول مقاس 4 مم اللون أصفر × أخضر (cu/pvc) | 030030101027 | MEP | Received | 2023-05-23 | Accounted transaction received
4116634 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 38.02 | 1 | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 |  | Each | 2 | 61648801 |  |  |  | HDG Metal Back Box 75 x 75 mm with Depth 47 mm2 | 150020000178 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116635 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-05-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 613.51 | 1 | سيفتي عمال |  | Each | 2 | 61648901 |  |  |  | سيفتي عمال | 010030000002 | Safety | Received | 2023-05-23 | Accounted transaction received
4116636 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 406.3 | 1 | ماسورة 20مم UPVC سمك ثقيل قطر خارجي 20 قطر داخلي 15.8مم اللفة= 34×3 متر(اللون أبيض) |  | Meter | 54 | 61653007 |  |  |  | ماسورة 20مم UPVC سمك ثقيل قطر خارجي 20 قطر داخلي 15.8مم اللفة= 34×3 متر(اللون أبيض) | 030010000051 | MEP | Received | 2023-05-23 | Accounted transaction received
4116637 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 277.76 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 1 | 61653008 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) | 030010000059 | MEP | Received | 2023-05-23 | Accounted transaction received
4116638 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 231.7 | 1 | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 |  | Each | 2 | 61653009 |  |  |  | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 | 030060100114 | MEP | Received | 2023-05-23 | Accounted transaction received
4116639 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 6267.47 | 1 | 10A INTERMEDIATE SWITCH 1 MOD MAGNESIUM Code 572508 |  | Each | 15 | 61653010 |  |  |  | 10A INTERMEDIATE SWITCH 1 MOD MAGNESIUM Code 572508 | 030060100126 | MEP | Received | 2023-05-23 | Accounted transaction received
4116640 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4570.64 | 1 | TV "F" TYPE 1 MOD Code 572663 |  | Each | 20 | 61653011 |  |  |  | TV "F" TYPE 1 MOD Code 572663 | 030060100134 | MEP | Received | 2023-05-23 | Accounted transaction received
4116641 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 357.07 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 2 | 61653012 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-05-23 | Accounted transaction received
4116642 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 91.21 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 2 | 61653013 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-05-23 | Accounted transaction received
4116643 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 53.26 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 3 | 61653014 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-05-23 | Accounted transaction received
4116644 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 46.04 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 1 | 61653015 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-05-23 | Accounted transaction received
4116645 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 92.07 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 2 | 61653017 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-05-23 | Accounted transaction received
4116742 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 60 | 1 | سلك مواعين |  | Kilogram | 1 | 61816916 |  |  |  | سلك مواعين | 700020000122 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116646 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 216.52 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 1 | 61653018 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-05-23 | Accounted transaction received
4116647 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2932.68 | 1 | UNIVERSAL DIMMER W/O NEUTR 400 Code 572739 |  | Each | 1 | 61653019 |  |  |  | UNIVERSAL DIMMER W/O NEUTR 400 Code 572739 | 030060100176 | MEP | Received | 2023-05-23 | Accounted transaction received
4116648 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2932.68 | 1 | UNIVERSAL DIMMER W/O NEUTR 400 Code 572739 |  | Each | 1 | 61653020 |  |  |  | UNIVERSAL DIMMER W/O NEUTR 400 Code 572739 | 030060100176 | MEP | Received | 2023-05-23 | Accounted transaction received
4116649 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1390.15 | 1 | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 |  | Each | 1 | 61653021 |  |  |  | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 | 030060100182 | MEP | Received | 2023-05-23 | Accounted transaction received
4116650 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 8340.92 | 1 | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 |  | Each | 6 | 61653022 |  |  |  | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 | 030060100182 | MEP | Received | 2023-05-23 | Accounted transaction received
4116651 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 54.43 | 1 | 576562 Code وش مربع فضي |  | Each | 1 | 61653023 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-05-23 | Accounted transaction received
4116652 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 108.87 | 1 | 576562 Code وش مربع فضي |  | Each | 2 | 61653024 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-05-23 | Accounted transaction received
4116653 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 54.43 | 1 | 576562 Code وش مربع فضي |  | Each | 1 | 61653025 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-05-23 | Accounted transaction received
4116654 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 50279.91 | 1 | LAN Cable F/FTB Cat6A, LSZH 4PX23AWG |  | Meter | 1000 | 61653026 |  |  |  | LAN Cable F/FTB Cat6A, LSZH 4PX23AWG | 032030000002 | MEP | Received | 2023-05-23 | Accounted transaction received
4116655 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 176.4 | 1 | Plate British standard Arteor - square - 3 modules - graphite - 575072 |  | Each | 3 | 61653027 |  |  |  | Plate British standard Arteor - square - 3 modules - graphite - 575072 | 030060100898 | MEP | Received | 2023-05-23 | Accounted transaction received
4116656 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2391.63 | 1 | 3.5mm Jack socket Arteor - preterminated - 1 module - magnesium - 572591 |  | Each | 1 | 61653028 |  |  |  | 3.5mm Jack socket Arteor - preterminated - 1 module - magnesium - 572591 | 030060100899 | MEP | Received | 2023-05-23 | Accounted transaction received
4116657 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 9483.13 | 1 | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser |  | Each | 21 | 61653029 |  |  |  | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser | 030040700472 | MEP | Received | 2023-05-23 | Accounted transaction received
4116658 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1158.48 | 1 | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 |  | Each | 10 | 61653302 |  |  |  | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 | 030060100114 | MEP | Received | 2023-05-23 | Accounted transaction received
4116659 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 199.15 | 1 | PLATE 1SQ MOD SCH GRAPHITE Code 576552 |  | Each | 5 | 61653303 |  |  |  | PLATE 1SQ MOD SCH GRAPHITE Code 576552 | 030060100297 | MEP | Received | 2023-05-23 | Accounted transaction received
4116660 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1390.15 | 1 | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 |  | Each | 1 | 61653304 |  |  |  | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 | 030060100182 | MEP | Received | 2023-05-23 | Accounted transaction received
4116661 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 54.43 | 1 | 576562 Code وش مربع فضي |  | Each | 1 | 61653305 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-05-23 | Accounted transaction received
4116662 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 886.01 | 1 | جلاند فلكسبل مقاس 16 مم |  | Each | 134 | 61722619 |  |  |  | جلاند فلكسبل مقاس 16 مم | 030010000167 | MEP | Received | 2023-05-23 | Accounted transaction received
4116663 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 695.09 | 1 | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 |  | Each | 6 | 61722620 |  |  |  | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 | 030060100114 | MEP | Received | 2023-05-23 | Accounted transaction received
4116664 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 6024.09 | 1 | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 |  | Each | 52 | 61722621 |  |  |  | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 | 030060100114 | MEP | Received | 2023-05-23 | Accounted transaction received
4116665 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 75.65 | 1 | 10AX 2 WAY SWITCH 2 MOD Code 572535 |  | Each | 1 | 61722622 |  |  |  | 10AX 2 WAY SWITCH 2 MOD Code 572535 | 030060100125 | MEP | Received | 2023-05-23 | Accounted transaction received
4116666 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 178.53 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 1 | 61722623 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-05-23 | Accounted transaction received
4116667 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1140.1 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 25 | 61722624 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-05-23 | Accounted transaction received
4116668 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 216.52 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 1 | 61722625 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-05-23 | Accounted transaction received
4116669 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 46922.96 | 1 | UNIVERSAL DIMMER W/O NEUTR 400 Code 572739 |  | Each | 16 | 61722626 |  |  |  | UNIVERSAL DIMMER W/O NEUTR 400 Code 572739 | 030060100176 | MEP | Received | 2023-05-23 | Accounted transaction received
4116670 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 13901.54 | 1 | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 |  | Each | 10 | 61722627 |  |  |  | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 | 030060100182 | MEP | Received | 2023-05-23 | Accounted transaction received
4116671 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 63947.08 | 1 | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 |  | Each | 46 | 61722628 |  |  |  | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 | 030060100182 | MEP | Received | 2023-05-23 | Accounted transaction received
4116672 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4783.27 | 1 | 3.5mm Jack socket Arteor - preterminated - 1 module - magnesium - 572591 |  | Each | 2 | 61722629 |  |  |  | 3.5mm Jack socket Arteor - preterminated - 1 module - magnesium - 572591 | 030060100899 | MEP | Received | 2023-05-23 | Accounted transaction received
4116673 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2391.63 | 1 | 3.5mm Jack socket Arteor - preterminated - 1 module - magnesium - 572591 |  | Each | 1 | 61722630 |  |  |  | 3.5mm Jack socket Arteor - preterminated - 1 module - magnesium - 572591 | 030060100899 | MEP | Received | 2023-05-23 | Accounted transaction received
4116674 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 720.02 | 1 | Category 6A Field Terminated Plug and Boot with Black Latch Protector Clip |  | Each | 8 | 61722631 |  |  |  | Category 6A Field Terminated Plug and Boot with Black Latch Protector Clip | 031030000447 | MEP | Received | 2023-05-23 | Accounted transaction received
4116675 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 102.6 | 1 | قلم دوكو |  | Each | 2 | 61725532 |  |  |  | قلم دوكو | 200010000171 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116676 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 102.6 | 1 | بنطة هيلتي 12 مم مكس |  | Each | 2 | 61725533 |  |  |  | بنطة هيلتي 12 مم مكس | 200010000332 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116677 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-08 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 270 | 1 | غراء أبيض |  | Kilogram | 3 | 61725534 |  |  |  | غراء أبيض | 200010001270 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116678 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 225 | 1 | طقم خواشة صغير |  | Each | 1 | 61725535 |  |  |  | طقم خواشة صغير | 200010001601 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116679 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 855 | 1 | زاوية فلسبيكو 5*5 |  | Each | 25 | 61726546 |  |  |  | زاوية فلسبيكو 5*5 | 200010000399 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116680 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-08 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 444.6 | 1 | كيما بوكس 165 |  | Can | 2 | 61727538 |  |  |  | كيما بوكس 165 | 050010000020 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116681 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-05-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1900.8 | 1 | طوب مصمت 6*10*20 |  | Each | 1920 | 61743753 |  |  |  | طوب مصمت 6*10*20 | 140020000045 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116682 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-05-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 5040 | 1 | اسمنت اسود رتبة 42 |  | Ton | 2 | 61743754 |  |  |  | اسمنت اسود رتبة 42 | 140010000015 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116683 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-10 | Materials |  |  |  | Materials | Alrowad Construction_OU | -4136.83 | 1 | Black Lava Washed River Pebbles size 4-5 cm |  | Square Meter | -14 | 61762607 |  |  |  | Black Lava Washed River Pebbles size 4-5 cm | 140010000084 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116684 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-05-10 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 19095 | 1 | Supplying of pendent concealed sprinkler , quick response , standard coverage , 68 C, 1/2", K=5.6 C/W cover plate |  | Each | 25 | 61770657 |  |  |  | Supplying of pendent concealed sprinkler , quick response , standard coverage , 68 C, 1/2", K=5.6 C/W cover plate | 060090100007 | MEP | Received | 2023-05-23 | Accounted transaction received
4116685 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-05-10 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 235.91 | 1 | Rigid Coupling 2'' UL listed, FM approved |  | Each | 1 | 61770658 |  |  |  | Rigid Coupling 2'' UL listed, FM approved | 060011500009 | MEP | Received | 2023-05-23 | Accounted transaction received
4116686 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-05-10 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 907.67 | 1 | flexible coupling 2" UL listed, FM approved |  | Each | 2 | 61770659 |  |  |  | flexible coupling 2" UL listed, FM approved | 060011500033 | MEP | Received | 2023-05-23 | Accounted transaction received
4116687 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-05-10 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 336.3 | 1 | Mechanical anchor (Drop in anchor) size M8 |  | Each | 100 | 61770660 |  |  |  | Mechanical anchor (Drop in anchor) size M8 | 060190100002 | MEP | Received | 2023-05-23 | Accounted transaction received
4116688 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-05-10 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 15002.4 | 1 | Threaded rod size M10 |  | Each | 350 | 61770661 |  |  |  | Threaded rod size M10 | 060190300003 | MEP | Received | 2023-05-23 | Accounted transaction received
4116689 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-05-10 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2250.02 | 1 | وصلات فليكسيبل دكت قطر 8 بوصه معزول |  | Meter | 30 | 61770662 |  |  |  | وصلات فليكسيبل دكت قطر 8 بوصه معزول | 060041200002 | MEP | Received | 2023-05-23 | Accounted transaction received
4116690 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-05-10 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 989.98 | 1 | "Flexible air duct - insulated Diameter 10 |  | Meter | 10 | 61770663 |  |  |  | "Flexible air duct - insulated Diameter 10 | 060041200007 | MEP | Received | 2023-05-23 | Accounted transaction received
4116691 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-05-10 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2999.91 | 1 | Flexible air duct - insulated Diameter 6" |  | Meter | 50 | 61770664 |  |  |  | Flexible air duct - insulated Diameter 6" | 060041200015 | MEP | Received | 2023-05-23 | Accounted transaction received
4116692 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-05-10 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 6384 | 1 | Horizontal Side Wall Sprinkler, Quick Response , Extended Coverage, 68°c Rated Temperature, ½" Orifice, ½" NPT, (K=5.6), Chrome Finished, UL Listed / FM Approved |  | Each | 10 | 61770665 |  |  |  | Horizontal Side Wall Sprinkler, Quick Response , Extended Coverage, 68°c Rated Temperature, ½" Orifice, ½" NPT, (K=5.6), Chrome Finished, UL Listed / FM Approved | 060110100129 | MEP | Received | 2023-05-23 | Accounted transaction received
4116693 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-10 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 322.28 | 1 | بواط ثماني فتحات ¾ المقاس ¾ " |  | Each | 5 | 61771828 |  |  |  | بواط ثماني فتحات ¾ المقاس ¾ " | 030020100098 | MEP | Received | 2023-05-23 | Accounted transaction received
4116694 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-10 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 25.35 | 1 | جلبة ماسورة EMT المقاس 1 " |  | Each | 1 | 61771829 |  |  |  | جلبة ماسورة EMT المقاس 1 " | 030020100022 | MEP | Received | 2023-05-23 | Accounted transaction received
4116695 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-10 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3475.44 | 1 | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 |  | Each | 30 | 61771830 |  |  |  | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 | 030060100114 | MEP | Received | 2023-05-23 | Accounted transaction received
4116696 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-10 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 86.76 | 1 | RECTANGULAR 3 MODULES 2 GANG BOX BS Code 576002 |  | Each | 2 | 61771831 |  |  |  | RECTANGULAR 3 MODULES 2 GANG BOX BS Code 576002 | 030060100306 | MEP | Received | 2023-05-23 | Accounted transaction received
4116697 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-10 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 570.52 | 1 | mosaic adapter code 69580 |  | Each | 6 | 61771832 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-05-23 | Accounted transaction received
4116698 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-10 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 240.74 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 3 | 61771833 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-05-23 | Accounted transaction received
4116699 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-10 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 80.25 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 1 | 61771834 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-05-23 | Accounted transaction received
4116700 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-10 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 95.58 | 1 | Metal Galvanized back box 7x14 cm with deep 47 mm |  | Each | 4 | 61771835 |  |  |  | Metal Galvanized back box 7x14 cm with deep 47 mm | 030069000027 | MEP | Received | 2023-05-23 | Accounted transaction received
4116701 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-10 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 11958.17 | 1 | 3.5mm Jack socket Arteor - preterminated - 1 module - magnesium - 572591 |  | Each | 5 | 61771836 |  |  |  | 3.5mm Jack socket Arteor - preterminated - 1 module - magnesium - 572591 | 030060100899 | MEP | Received | 2023-05-23 | Accounted transaction received
4116702 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-10 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 8766.36 | 1 | Acolyte - ARB95SWBC653.027 - Rapid Ribbon 95+ - LED Strip with 9.8 W/M, 2700K, CRI/97 IP65, 24VDC, with aluminum profile and Opal diffuser |  | Each | 6.25 | 61771837 |  |  |  | Acolyte - ARB95SWBC653.027 - Rapid Ribbon 95+ - LED Strip with 9.8 W/M, 2700K, CRI/97 IP65, 24VDC, with aluminum profile and Opal diffuser | 030040700470 | MEP | Received | 2023-05-23 | Accounted transaction received
4116782 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 148.2 | 1 | مسمار سيلف دريل 6 سم |  | Kilogram | 1 | 61823463 |  |  |  | مسمار سيلف دريل 6 سم | 200020000582 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116703 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-10 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2067.22 | 1 | CEILING MOUNT SPEAKER, Model No. PC-648R |  | Each | 5 | 61771838 |  |  |  | CEILING MOUNT SPEAKER, Model No. PC-648R | 031070000015 | MEP | Received | 2023-05-23 | Accounted transaction received
4116704 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-05-10 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 31113 | 1 | Wall covering – WC-3 – Cole & Son- The Ardmore Collection, Narina Linen 109/10049 |  | Roll | 10 | 61771891 |  |  |  | Wall covering – WC-3 – Cole & Son- The Ardmore Collection, Narina Linen 109/10049 | 050020000013 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116705 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 672.6 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 200 | 61787653 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-05-23 | Accounted transaction received
4116706 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 232.18 | 1 | أفيز 32مم UPVC(اللون أبيض) |  | Each | 47 | 61787654 |  |  |  | أفيز 32مم UPVC(اللون أبيض) | 030010000108 | MEP | Received | 2023-05-23 | Accounted transaction received
4116707 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 454.97 | 1 | PLATE 2SQ MOD F-G WHITE Code 576560 |  | Each | 13 | 61787655 |  |  |  | PLATE 2SQ MOD F-G WHITE Code 576560 | 030060100267 | MEP | Received | 2023-05-23 | Accounted transaction received
4116708 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1016.75 | 1 | سلك نحاس مجدول مقاس4 مم اللون أحمر (cu/pvc) |  | Meter | 100 | 61787656 |  |  |  | سلك نحاس مجدول مقاس4 مم اللون أحمر (cu/pvc) | 030030101023 | MEP | Received | 2023-05-23 | Accounted transaction received
4116709 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 223.58 | 1 | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS |  | Each | 1 | 61787657 |  |  |  | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS | 030060100617 | MEP | Received | 2023-05-23 | Accounted transaction received
4116710 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-11 | MATV system |  |  |  | Materials | Waldorf Astoria-0164 | 98.53 | 1 | Wiring Devices (54000) METAL FLUSH-MOUNTING BOX FOR INSTALLATION IN CONCRETE FLOOR - 3 MODULES |  | Each | 1 | 61787658 |  |  |  | Wiring Devices (54000) METAL FLUSH-MOUNTING BOX FOR INSTALLATION IN CONCRETE FLOOR - 3 MODULES | 030060100618 | MEP | Received | 2023-05-23 | Accounted transaction received
4116711 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.09.04 | Fire Fighting Networ | 2 | SITE WORK |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 7752 | 1 | Cast Iron Gate Valve D151 Crane UK 2" PN 20 |  | Each | 2 | 61814487 |  |  |  | Cast Iron Gate Valve D151 Crane UK 2" PN 20 | 060170100082 | MEP | Received | 2023-05-23 | Accounted transaction received
4116712 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.09.04 | Fire Fighting Networ | 2 | SITE WORK |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 11669.05 | 1 | 2 way control valve Size 2" C/W on/off actuator 3-position ( VVF42.50-31.5 - SAX31.00 )2 way control valve Size 2" C/W on/off actuator 3-position ( VVF42.50-31.5 - SAX31.00 ) |  | Each | 1 | 61814488 |  |  |  | 2 way control valve Size 2" C/W on/off actuator 3-position ( VVF42.50-31.5 - SAX31.00 )2 way control valve Size 2" C/W on/off actuator 3-position ( VVF42.50-31.5 - SAX31.00 ) | 060172800003 | MEP | Received | 2023-05-23 | Accounted transaction received
4116713 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.09.04 | Fire Fighting Networ | 2 | SITE WORK |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 6783 | 1 | Double regulating valve model D931 Size 2" |  | Each | 1 | 61814489 |  |  |  | Double regulating valve model D931 Size 2" | 060170500024 | MEP | Received | 2023-05-23 | Accounted transaction received
4116714 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.09.04 | Fire Fighting Networ | 2 | SITE WORK |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3705 | 1 | Strainer Valve D298 Crane UK 2" PN 16 |  | Each | 1 | 61814490 |  |  |  | Strainer Valve D298 Crane UK 2" PN 16 | 060170500027 | MEP | Received | 2023-05-23 | Accounted transaction received
4116715 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 114 | 1 | اسمنت ابيض |  | Ton | 0.02 | 61816813 |  |  |  | اسمنت ابيض | 140010000001 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116716 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 153.9 | 1 | ماسورة 50مم UPVC سمك خفيف قطر خارجي 50 قطر داخلي 45.1مم اللفة= 5×3 متر(اللون أبيض) |  | Meter | 3 | 61816814 |  |  |  | ماسورة 50مم UPVC سمك خفيف قطر خارجي 50 قطر داخلي 45.1مم اللفة= 5×3 متر(اللون أبيض) | 030010000043 | MEP | Received | 2023-05-23 | Accounted transaction received
4116717 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 205.2 | 1 | ماسورة 63مم UPVC سمك خفيف قطر خارجي 63 قطر داخلي 57مم اللفة= 5×3 متر(اللون أبيض) |  | Meter | 4 | 61816815 |  |  |  | ماسورة 63مم UPVC سمك خفيف قطر خارجي 63 قطر داخلي 57مم اللفة= 5×3 متر(اللون أبيض) | 030010000044 | MEP | Received | 2023-05-23 | Accounted transaction received
4116718 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 102.6 | 1 | جلبة ماسورة 40مم UPVC (اللون أبيض) |  | Each | 2 | 61816816 |  |  |  | جلبة ماسورة 40مم UPVC (اللون أبيض) | 030010000070 | MEP | Received | 2023-05-23 | Accounted transaction received
4116719 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 57 | 1 | جلبة ماسورة50مم UPVC (اللون أبيض) |  | Each | 2 | 61816817 |  |  |  | جلبة ماسورة50مم UPVC (اللون أبيض) | 030010000071 | MEP | Received | 2023-05-23 | Accounted transaction received
4116720 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 193.8 | 1 | جلبة ماسورة 63مم UPVC (اللون أبيض) |  | Each | 2 | 61816818 |  |  |  | جلبة ماسورة 63مم UPVC (اللون أبيض) | 030010000072 | MEP | Received | 2023-05-23 | Accounted transaction received
4116721 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 57 | 1 | كوع صرف ابيض قطر 1.5" ( 48 مم ) |  | Each | 2 | 61816819 |  |  |  | كوع صرف ابيض قطر 1.5" ( 48 مم ) | 060010100207 | MEP | Received | 2023-05-23 | Accounted transaction received
4116722 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 142.5 | 1 | كوع صرف ابيض قطر 2" ( 60 مم ) |  | Each | 5 | 61816820 |  |  |  | كوع صرف ابيض قطر 2" ( 60 مم ) | 060010100208 | MEP | Received | 2023-05-23 | Accounted transaction received
4116723 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 171 | 1 | كوع صرف ابيض 45 درجه قطر 4" ( 110 مم ) |  | Each | 2 | 61816821 |  |  |  | كوع صرف ابيض 45 درجه قطر 4" ( 110 مم ) | 060010100219 | MEP | Received | 2023-05-23 | Accounted transaction received
4116724 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 205.2 | 1 | مشترك صرف ابيض قطر 3" ( 75 مم ) |  | Each | 4 | 61816822 |  |  |  | مشترك صرف ابيض قطر 3" ( 75 مم ) | 060010100231 | MEP | Received | 2023-05-23 | Accounted transaction received
4116725 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 111.72 | 1 | مشترك مسلوب بباب صرف ابيض مقاس 110/"2 مم |  | Each | 1 | 61816823 |  |  |  | مشترك مسلوب بباب صرف ابيض مقاس 110/"2 مم | 060010100291 | MEP | Received | 2023-05-23 | Accounted transaction received
4116726 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2269.74 | 1 | لاكور تجميع ( للمحابس و عدادات المياه ) PPR مقاس 1.1/4"-40 مم |  | Each | 2 | 61816824 |  |  |  | لاكور تجميع ( للمحابس و عدادات المياه ) PPR مقاس 1.1/4"-40 مم | 060010300235 | MEP | Received | 2023-05-23 | Accounted transaction received
4116727 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 189.48 | 1 | مسلوب لحام PPR مقاس 40-25 مم |  | Each | 4 | 61816825 |  |  |  | مسلوب لحام PPR مقاس 40-25 مم | 060010300150 | MEP | Received | 2023-05-23 | Accounted transaction received
4116728 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1073.31 | 1 | جلبه بسن دكر PPR مقاس 1.1/4"-40 مم |  | Each | 2 | 61816826 |  |  |  | جلبه بسن دكر PPR مقاس 1.1/4"-40 مم | 060010300199 | MEP | Received | 2023-05-23 | Accounted transaction received
4116729 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2021.16 | 1 | جلبه بسن دكر PPR مقاس 1.1/2"-50 مم |  | Each | 3 | 61816827 |  |  |  | جلبه بسن دكر PPR مقاس 1.1/2"-50 مم | 060010300200 | MEP | Received | 2023-05-23 | Accounted transaction received
4116730 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 684 | 1 | وصلة مرنة طول 30 سم |  | Each | 20 | 61816828 |  |  |  | وصلة مرنة طول 30 سم | 060010300239 | MEP | Received | 2023-05-23 | Accounted transaction received
4116731 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 547.2 | 1 | وصلة مرنة طول 60 سم |  | Each | 12 | 61816829 |  |  |  | وصلة مرنة طول 60 سم | 060010300242 | MEP | Received | 2023-05-23 | Accounted transaction received
4116732 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 159.6 | 1 | سيفون 1.5 بوصة |  | Each | 2 | 61816830 |  |  |  | سيفون 1.5 بوصة | 240070000181 | MEP | Received | 2023-05-23 | Accounted transaction received
4116733 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 102.6 | 1 | لصق حار ¼ كيلو |  | Each | 1 | 61816831 |  |  |  | لصق حار ¼ كيلو | 060019000011 | MEP | Received | 2023-05-23 | Accounted transaction received
4116734 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 228 | 1 | خرطوم مياة 1/2 بوصة |  | Meter | 4 | 61816832 |  |  |  | خرطوم مياة 1/2 بوصة | 200010001718 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116735 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3575.95 | 1 | "Flexible air duct - insulated Diameter 10 |  | Meter | 30 | 61816833 |  |  |  | "Flexible air duct - insulated Diameter 10 | 060041200007 | MEP | Received | 2023-05-23 | Accounted transaction received
4116736 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1356.6 | 1 | نبل نيكل 1/2" * 3/8" |  | Each | 34 | 61816834 |  |  |  | نبل نيكل 1/2" * 3/8" | 060031000057 | MEP | Received | 2023-05-23 | Accounted transaction received
4116737 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 22.8 | 1 | أفيز كوليه ربط |  | Each | 4 | 61816835 |  |  |  | أفيز كوليه ربط | 330040002184 | Equipment | Received | 2023-05-23 | Accounted transaction received
4116738 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3579.6 | 1 | Flexible air duct - insulated Diameter 12" |  | Meter | 20 | 61816836 |  |  |  | Flexible air duct - insulated Diameter 12" | 060041200013 | MEP | Received | 2023-05-23 | Accounted transaction received
4116739 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 103.95 | 1 | صابون سائل |  | Can | 2 | 61816913 |  |  |  | صابون سائل | 700020000013 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116740 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 100 | 1 | لمبة ليد |  | Each | 4 | 61816914 |  |  |  | لمبة ليد | 030040100001 | MEP | Received | 2023-05-23 | Accounted transaction received
4116741 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 240 | 1 | SOAP DISPENSER |  | Each | 2 | 61816915 |  |  |  | SOAP DISPENSER | 060030800001 | MEP | Received | 2023-05-23 | Accounted transaction received
4116743 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2110.56 | 1 | بواط 10 * 10 عالى المقاس 1 " |  | Each | 30 | 61817637 |  |  |  | بواط 10 * 10 عالى المقاس 1 " | 030020100104 | MEP | Received | 2023-05-23 | Accounted transaction received
4116744 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 833.27 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 3 | 61817638 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 16مم وقطر خارجى 21مم طول اللفه 30 متر(اللون رمادى) | 030010000059 | MEP | Received | 2023-05-23 | Accounted transaction received
4116745 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 13554.6 | 1 | كابل نحاس مجدول شعر مقاس 2 × 1 مم (pvc/pvc) جهد (500/300) |  | Meter | 410 | 61817639 |  |  |  | كابل نحاس مجدول شعر مقاس 2 × 1 مم (pvc/pvc) جهد (500/300) | 030030100151 | MEP | Received | 2023-05-23 | Accounted transaction received
4116746 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 534.33 | 1 | لاكور ماسورة EMT المقاس 1 " |  | Each | 62 | 61817640 |  |  |  | لاكور ماسورة EMT المقاس 1 " | 030020100016 | MEP | Received | 2023-05-23 | Accounted transaction received
4116747 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1495.74 | 1 | جلبة ماسورة EMT المقاس 1 " |  | Each | 59 | 61817641 |  |  |  | جلبة ماسورة EMT المقاس 1 " | 030020100022 | MEP | Received | 2023-05-23 | Accounted transaction received
4116748 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 109.44 | 1 | أفيز أثنين جناح لماسورة EMT المقاس 1 " |  | Each | 30 | 61817642 |  |  |  | أفيز أثنين جناح لماسورة EMT المقاس 1 " | 030020100034 | MEP | Received | 2023-05-23 | Accounted transaction received
4116749 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 463.39 | 1 | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 |  | Each | 4 | 61817643 |  |  |  | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 | 030060100114 | MEP | Received | 2023-05-23 | Accounted transaction received
4116750 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 454.57 | 1 | 10AX SWITCH SP 2 WAY 1 MOD Code 572505 |  | Each | 3 | 61817644 |  |  |  | 10AX SWITCH SP 2 WAY 1 MOD Code 572505 | 030060100123 | MEP | Received | 2023-05-23 | Accounted transaction received
4116751 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 248.1 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 2 | 61817645 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-05-23 | Accounted transaction received
4116752 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 50279.91 | 1 | LAN Cable F/FTB Cat6A, LSZH 4PX23AWG |  | Meter | 1000 | 61817646 |  |  |  | LAN Cable F/FTB Cat6A, LSZH 4PX23AWG | 032030000002 | MEP | Received | 2023-05-23 | Accounted transaction received
4116753 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 58.8 | 1 | Plate British standard Arteor - square - 3 modules - graphite - 575072 |  | Each | 1 | 61817647 |  |  |  | Plate British standard Arteor - square - 3 modules - graphite - 575072 | 030060100898 | MEP | Received | 2023-05-23 | Accounted transaction received
4116754 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 533.52 | 1 | لاكور بواط على فليكسبل EMT المقاس 3/4 " |  | Each | 18 | 61817648 |  |  |  | لاكور بواط على فليكسبل EMT المقاس 3/4 " | 030020100214 | MEP | Received | 2023-05-23 | Accounted transaction received
4116755 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1003.6 | 1 | Duct temperature Sensor -46…104° C - TE-6311M-1 |  | Each | 1 | 61817649 |  |  |  | Duct temperature Sensor -46…104° C - TE-6311M-1 | 030160000176 | MEP | Received | 2023-05-23 | Accounted transaction received
4116756 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 6624.52 | 1 | Differential Pressure Switch, air 140…1000 Pa(P233A-10-PKC) |  | Each | 2 | 61817650 |  |  |  | Differential Pressure Switch, air 140…1000 Pa(P233A-10-PKC) | 030160000251 | MEP | Received | 2023-05-23 | Accounted transaction received
4116757 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 81022.63 | 1 | Wall Paper WC-4 Solid vinyl fabric backed min weight 480/gr /sqm. Textured with geometric pattern in metallic color |  | Meter | 16 | 61822495 |  |  |  | Wall Paper WC-4 Solid vinyl fabric backed min weight 480/gr /sqm. Textured with geometric pattern in metallic color | 050020000014 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116758 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 620.25 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 5 | 61822509 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-05-23 | Accounted transaction received
4116759 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 475.44 | 1 | mosaic adapter code 69580 |  | Each | 5 | 61822510 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-05-23 | Accounted transaction received
4116760 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 401.24 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 5 | 61822511 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-05-23 | Accounted transaction received
4116761 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 444.6 | 1 | لاكور بواط على فليكسبل EMT المقاس 3/4 " |  | Each | 15 | 61822512 |  |  |  | لاكور بواط على فليكسبل EMT المقاس 3/4 " | 030020100214 | MEP | Received | 2023-05-23 | Accounted transaction received
4116762 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 413.44 | 1 | CEILING MOUNT SPEAKER, Model No. PC-648R |  | Each | 1 | 61822513 |  |  |  | CEILING MOUNT SPEAKER, Model No. PC-648R | 031070000015 | MEP | Received | 2023-05-23 | Accounted transaction received
4116763 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 59850 | 1 | بولارد 60 سم يحتوي على 4 بريزة بالغطاء ليجراند مزود بعدد 2 باب كشف لزوم الصيانة للبرايز والترنسات |  | Each | 10 | 61822514 |  |  |  | بولارد 60 سم يحتوي على 4 بريزة بالغطاء ليجراند مزود بعدد 2 باب كشف لزوم الصيانة للبرايز والترنسات | 030040700550 | MEP | Received | 2023-05-23 | Accounted transaction received
4116764 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2066.82 | 1 | سلك نحاس مجدول مقاس 6 مم اللون أصفر × أخضر (cu/pvc) |  | Meter | 100 | 61822922 |  |  |  | سلك نحاس مجدول مقاس 6 مم اللون أصفر × أخضر (cu/pvc) | 030030101032 | MEP | Received | 2023-05-23 | Accounted transaction received
4116765 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 13101.22 | 1 | LV Power cable CU / PVC / PVC 3 X 6 mm2 (0.6/1 KV) |  | Meter | 205 | 61822923 |  |  |  | LV Power cable CU / PVC / PVC 3 X 6 mm2 (0.6/1 KV) | 030030101179 | MEP | Received | 2023-05-23 | Accounted transaction received
4116766 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2679 | 1 | اسمنت اسود رتبة 42 |  | Ton | 1 | 61823447 |  |  |  | اسمنت اسود رتبة 42 | 140010000015 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116767 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 410.4 | 1 | خيط سنارة |  | Kilogram | 12 | 61823448 |  |  |  | خيط سنارة | 200010000394 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116768 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 199.5 | 1 | مكنسة ناعمة |  | Each | 5 | 61823449 |  |  |  | مكنسة ناعمة | 200010000449 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116769 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 150 | 1 | فوطة صفراء |  | Each | 10 | 61823450 |  |  |  | فوطة صفراء | 200010000478 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116770 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 193.8 | 1 | تنر |  | Each | 2 | 61823451 |  |  |  | تنر | 060019000008 | MEP | Received | 2023-05-23 | Accounted transaction received
4116771 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 300 | 1 | شيكارة بلاستيك فارغة |  | Each | 100 | 61823452 |  |  |  | شيكارة بلاستيك فارغة | 200010000115 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116772 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 22.8 | 1 | بنطة رباط |  | Each | 2 | 61823453 |  |  |  | بنطة رباط | 200010001006 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116773 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1368 | 1 | كانة 200*50*30*2 مم |  | Each | 150 | 61823454 |  |  |  | كانة 200*50*30*2 مم | 200010000490 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116774 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 195 | 1 | كوع 4 بوصة 45 درجة |  | Each | 3 | 61823455 |  |  |  | كوع 4 بوصة 45 درجة | 240010000117 | MEP | Received | 2023-05-23 | Accounted transaction received
4116775 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 50 | 1 | لصق حار 1/8 كيلو |  | Each | 1 | 61823456 |  |  |  | لصق حار 1/8 كيلو | 060019000035 | MEP | Received | 2023-05-23 | Accounted transaction received
4116776 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 79.8 | 1 | مسمار خشابى 6 سم |  | Kilogram | 1 | 61823457 |  |  |  | مسمار خشابى 6 سم | 200020000141 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116777 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 307.8 | 1 | مسمار 6مم بفيشر |  | Each | 1 | 61823458 |  |  |  | مسمار 6مم بفيشر | 200020000332 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116778 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 410.4 | 1 | سيلكون فواصل |  | Each | 6 | 61823459 |  |  |  | سيلكون فواصل | 330040000882 | Equipment | Received | 2023-05-23 | Accounted transaction received
4116779 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 15 | 1 | جوان جرنجريت 50 مم ( 4 ثقب * 19.1 مم ) |  | Each | 3 | 61823460 |  |  |  | جوان جرنجريت 50 مم ( 4 ثقب * 19.1 مم ) | 060019000168 | MEP | Received | 2023-05-23 | Accounted transaction received
4116780 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 180 | 1 | مادة لاصق لورق الحائط |  | Kilogram | 2 | 61823461 |  |  |  | مادة لاصق لورق الحائط | 050020000006 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116781 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 570 | 1 | Master Seal NP 472 |  | Kit | 5 | 61823462 |  |  |  | Master Seal NP 472 | 360010000355 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116783 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-05-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1368 | 1 | عجلة براويطة نفخ |  | Each | 4 | 61823467 |  |  |  | عجلة براويطة نفخ | 200010000505 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116784 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-14 | Materials |  |  |  | Materials | Alrowad Construction_OU | -77308.91 | 1 | فوم ابيض سمك 20سم كثافة 35 |  | Cubic Meter | -19.4 | 61832733 |  |  |  | فوم ابيض سمك 20سم كثافة 35 | 040010000184 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116785 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.03 | Pumps | 15 | MECHANICAL WORKS |  | 2023-05-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 9006 | 1 | Flow switch 4" |  | Each | 1 | 61837890 |  |  |  | Flow switch 4" | 060171900005 | MEP | Received | 2023-05-23 | Accounted transaction received
4116786 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 695.09 | 1 | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 |  | Each | 6 | 61842539 |  |  |  | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 | 030060100114 | MEP | Received | 2023-05-23 | Accounted transaction received
4116787 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 124.05 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 1 | 61842540 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-05-23 | Accounted transaction received
4116788 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 106.53 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 6 | 61842541 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-05-23 | Accounted transaction received
4116789 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2066.82 | 1 | سلك نحاس مجدول مقاس 6 مم اللون أصفر × أخضر (cu/pvc) |  | Meter | 100 | 61842542 |  |  |  | سلك نحاس مجدول مقاس 6 مم اللون أصفر × أخضر (cu/pvc) | 030030101032 | MEP | Received | 2023-05-23 | Accounted transaction received
4116790 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 95.09 | 1 | mosaic adapter code 69580 |  | Each | 1 | 61842543 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-05-23 | Accounted transaction received
4116791 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 80.25 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 1 | 61842544 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-05-23 | Accounted transaction received
4116792 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 474.1 | 1 | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 |  | Each | 6 | 61842545 |  |  |  | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 | 030060100956 | MEP | Received | 2023-05-23 | Accounted transaction received
4116793 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 35.51 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 2 | 61843591 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-05-23 | Accounted transaction received
4116794 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5549.66 | 1 | THREADED ROD 8mm,length 2mt |  | Each | 350 | 61843592 |  |  |  | THREADED ROD 8mm,length 2mt | 030120300002 | MEP | Received | 2023-05-23 | Accounted transaction received
4116795 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2066.82 | 1 | سلك نحاس مجدول مقاس 6 مم اللون أصفر × أخضر (cu/pvc) |  | Meter | 100 | 61843593 |  |  |  | سلك نحاس مجدول مقاس 6 مم اللون أصفر × أخضر (cu/pvc) | 030030101032 | MEP | Received | 2023-05-23 | Accounted transaction received
4116796 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 631.22 | 1 | جلبه بسن دكر PPR مقاس 3/4"-25 مم |  | Each | 5 | 61638785 |  |  |  | جلبه بسن دكر PPR مقاس 3/4"-25 مم | 060010300196 | MEP | Received | 2023-05-23 | Accounted transaction received
4116797 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 718.7 | 1 | جلبه بسن دكر PPR مقاس 1"-32 مم |  | Each | 2 | 61638786 |  |  |  | جلبه بسن دكر PPR مقاس 1"-32 مم | 060010300198 | MEP | Received | 2023-05-23 | Accounted transaction received
4116798 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2206.99 | 1 | جلبه بسن دكر PPR مقاس 1.1/2"-50 مم |  | Each | 3 | 61638787 |  |  |  | جلبه بسن دكر PPR مقاس 1.1/2"-50 مم | 060010300200 | MEP | Received | 2023-05-23 | Accounted transaction received
4116799 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 7450.61 | 1 | لاكور تجميع ( للمحابس و عدادات المياه ) PPR مقاس "1/2-20 مم |  | Each | 27 | 61638788 |  |  |  | لاكور تجميع ( للمحابس و عدادات المياه ) PPR مقاس "1/2-20 مم | 060010300228 | MEP | Received | 2023-05-23 | Accounted transaction received
4116800 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 224.86 | 1 | بكرة تيفلون |  | Each | 15 | 61638789 |  |  |  | بكرة تيفلون | 060019000003 | MEP | Received | 2023-05-23 | Accounted transaction received
4116801 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1982.46 | 1 | Aluminium volume DamperSize : 85 x 50 cm |  | Each | 1 | 61638790 |  |  |  | Aluminium volume DamperSize : 85 x 50 cm | 060070700253 | MEP | Received | 2023-05-23 | Accounted transaction received
4116802 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2064.54 | 1 | Aluminium volume DamperSize : 100 x 45 cm |  | Each | 1 | 61638791 |  |  |  | Aluminium volume DamperSize : 100 x 45 cm | 060070700264 | MEP | Received | 2023-05-23 | Accounted transaction received
4116803 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4216.86 | 1 | Curved Slot Diffuser 2 Slot 3/4" spacing Length 3.78 Meter Including 1.38 Meter Dummy |  | Each | 1 | 61638792 |  |  |  | Curved Slot Diffuser 2 Slot 3/4" spacing Length 3.78 Meter Including 1.38 Meter Dummy | 060070300123 | MEP | Received | 2023-05-23 | Accounted transaction received
4116804 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 5306.7 | 1 | Curved Slot Diffuser 2 Slot 3/4" spacing Length 4.7 Meter Including 2.3 Meter Dummy |  | Each | 1 | 61638793 |  |  |  | Curved Slot Diffuser 2 Slot 3/4" spacing Length 4.7 Meter Including 2.3 Meter Dummy | 060070300130 | MEP | Received | 2023-05-23 | Accounted transaction received
4116805 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 36546.12 | 1 | Beige Washed River Pebbles size 4-5 cm |  | Square Meter | 68.5 | 61639188 |  |  |  | Beige Washed River Pebbles size 4-5 cm | 140010000085 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116806 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 124.05 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 1 | 61641020 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-05-23 | Accounted transaction received
4116807 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 496.2 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 4 | 61641021 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-05-23 | Accounted transaction received
4116808 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1240.5 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 10 | 61641022 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-05-23 | Accounted transaction received
4116809 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 45.6 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 1 | 61641023 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-05-23 | Accounted transaction received
4116810 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 6840.61 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 150 | 61641024 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-05-23 | Accounted transaction received
4116811 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 17.75 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 1 | 61641025 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-05-23 | Accounted transaction received
4116812 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1732.16 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 8 | 61641026 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-05-23 | Accounted transaction received
4116813 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1578.72 | 1 | INTERNAL CONTROL UNIT FOR HOTEL BEDROOM Code 572554 |  | Each | 2 | 61641027 |  |  |  | INTERNAL CONTROL UNIT FOR HOTEL BEDROOM Code 572554 | 030060100175 | MEP | Received | 2023-05-23 | Accounted transaction received
4116814 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 326.6 | 1 | 576562 Code وش مربع فضي |  | Each | 6 | 61641028 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-05-23 | Accounted transaction received
4116815 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2549.95 | 1 | Socket outlet Plexo IP55 Code 69733 |  | Each | 10 | 61641029 |  |  |  | Socket outlet Plexo IP55 Code 69733 | 030060100339 | MEP | Received | 2023-05-23 | Accounted transaction received
4116816 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1797.67 | 1 | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 |  | Each | 4 | 61641030 |  |  |  | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 | 030060100572 | MEP | Received | 2023-05-23 | Accounted transaction received
4116817 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 223.58 | 1 | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS |  | Each | 1 | 61641031 |  |  |  | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS | 030060100617 | MEP | Received | 2023-05-23 | Accounted transaction received
4116818 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 665.61 | 1 | mosaic adapter code 69580 |  | Each | 7 | 61641032 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-05-23 | Accounted transaction received
4116819 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 561.73 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 7 | 61641033 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-05-23 | Accounted transaction received
4116820 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 6773.67 | 1 | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser |  | Each | 15 | 61641034 |  |  |  | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser | 030040700472 | MEP | Received | 2023-05-23 | Accounted transaction received
4116821 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 630.02 | 1 | Category 6A Field Terminated Plug and Boot with Black Latch Protector Clip |  | Each | 7 | 61641035 |  |  |  | Category 6A Field Terminated Plug and Boot with Black Latch Protector Clip | 031030000447 | MEP | Received | 2023-05-23 | Accounted transaction received
4116822 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 123.68 | 1 | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 |  | Each | 1 | 61641036 |  |  |  | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 | 030060100951 | MEP | Received | 2023-05-23 | Accounted transaction received
4116823 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 56.82 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 1 | 61641037 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-05-23 | Accounted transaction received
4116824 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 170.45 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 3 | 61641038 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-05-23 | Accounted transaction received
4116825 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 56.82 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 1 | 61641039 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-05-23 | Accounted transaction received
4116826 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 79.02 | 1 | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 |  | Each | 1 | 61641040 |  |  |  | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 | 030060100956 | MEP | Received | 2023-05-23 | Accounted transaction received
4116827 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1215.01 | 1 | ProLink Cate6 UTP Toolless KEYSTONE JACK With Shutter |  | Each | 27 | 61641041 |  |  |  | ProLink Cate6 UTP Toolless KEYSTONE JACK With Shutter | 031030000575 | MEP | Received | 2023-05-23 | Accounted transaction received
4116828 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 20999.94 | 1 | Socket outlet Plexo IP44 - 32 A - 3P+N+E 230 V~ - surface mounting - grey - Legrand 55877 |  | Each | 10 | 61641042 |  |  |  | Socket outlet Plexo IP44 - 32 A - 3P+N+E 230 V~ - surface mounting - grey - Legrand 55877 | 030060100993 | MEP | Received | 2023-05-23 | Accounted transaction received
4158032 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-24 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 16319.97 | 1 | Hardware Accessories for Wooden Doors Concealed hinge system & Bathroom Concealed Hinges Simonswerk completely concealed hinge system with load capacity 80.0 kg two hinges per door leaf (1x2m) |  | Each | 6 | 62404716 |  |  |  | Hardware Accessories for Wooden Doors Concealed hinge system & Bathroom Concealed Hinges Simonswerk completely concealed hinge system with load capacity 80.0 kg two hinges per door leaf (1x2m) | 250010001515 | Procurement | Received | 2023-05-28 | Accounted transaction received
4158033 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-24 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 16356.15 | 1 | Supply Concealed Door closer to 80KG for wooden doors, including any requirements to complete the works as per consultant's approval & submittal approval. Consort CDCC3 Silver |  | Each | 2 | 62404717 |  |  |  | Supply Concealed Door closer to 80KG for wooden doors, including any requirements to complete the works as per consultant's approval & submittal approval. Consort CDCC3 Silver | 250010001608 | Procurement | Received | 2023-05-28 | Accounted transaction received
4158034 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-24 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1368 | 1 | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) |  | Meter | 60 | 62404729 |  |  |  | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) | 030010000052 | MEP | Received | 2023-05-28 | Accounted transaction received
4158035 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-24 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 372.15 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 3 | 62404730 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-05-28 | Accounted transaction received
4158036 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-24 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 53.26 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 3 | 62404731 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-05-28 | Accounted transaction received
4158037 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-24 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 170.45 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 3 | 62404732 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-05-28 | Accounted transaction received
4158038 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-24 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 13560.3 | 1 | Audio, Control & Instrumentation Cable Twisted INDV Shielded (UL),Similar to Belden P/N.8723.Size (2Px22AWG).P.N:C1196 |  | Meter | 305 | 62404733 |  |  |  | Audio, Control & Instrumentation Cable Twisted INDV Shielded (UL),Similar to Belden P/N.8723.Size (2Px22AWG).P.N:C1196 | 032070000047 | MEP | Received | 2023-05-28 | Accounted transaction received
4158039 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-24 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 797 | 1 | فوم ابيض سمك 20سم كثافة 35 |  | Cubic Meter | 0.2 | 62406284 |  |  |  | فوم ابيض سمك 20سم كثافة 35 | 040010000184 | Purchasing | Received | 2023-05-28 | Accounted transaction received
4160476 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 10.06. | Mat | 10 | SPECIALITIES | 64193 | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | 12695.99 | 1 | استوريا ميركل ف/1926 15/3 25 c.m | 1926 c.m | Currency | 12695.99 | 23048444 | 3948 | ميركل للاتصالات-ام سى سى | rowad | استوريا ميركل ف/1926 15/3 25 c.m |  | Mechanical | Received | 2023-05-29 | Accounted transaction received
4160582 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 10.06. | Mat | 10 | SPECIALITIES | 83426 | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -150810.48 | 1 | استوريا ميركل ف/2195 14/5 227 | 2195 USD c.m | Currency | -4872.71 | 23048444 | 3948 | ميركل للاتصالات-ام سى سى | rowad | استوريا ميركل ف/2195 14/5 227 |  | Mechanical | Received | 2023-05-29 | Accounted transaction received
4160584 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 10.06. | Mat | 10 | SPECIALITIES | 83426 | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | 150810.48 | 1 | استوريا ميركل ف/2195 14/5 227 | 2195 | Currency | 150810.48 | 23048444 | 3948 | ميركل للاتصالات-ام سى سى | rowad | استوريا ميركل ف/2195 14/5 227 |  | Mechanical | Received | 2023-05-29 | Accounted transaction received
4160593 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 10.06. | Mat | 10 | SPECIALITIES | 82261 | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -35918.09 | 1 | استوريا الحلول ف/2620 30/4 210 | 2620 USD c.m | Currency | -1160.52 | 23048444 | 11118 | المصرية الهندسية للحلول المتكامله | rowad | استوريا الحلول ف/2620 30/4 210 |  | Mechanical | Received | 2023-05-29 | Accounted transaction received
4160594 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 10.06. | Mat | 10 | SPECIALITIES | 82261 | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | 35918.09 | 1 | استوريا الحلول ف/2620 30/4 210 | 2620 | Currency | 35918.09 | 23048444 | 11118 | المصرية الهندسية للحلول المتكامله | rowad | استوريا الحلول ف/2620 30/4 210 |  | Mechanical | Received | 2023-05-29 | Accounted transaction received
4160595 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 10.06. | Mat | 10 | SPECIALITIES | 63365 | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -13858 | 1 | استوريا الحلول ف/2583 15/2 31 | 2583 USD c.m | Currency | -452.58 | 23048444 | 11118 | المصرية الهندسية للحلول المتكامله | rowad | استوريا الحلول ف/2583 15/2 31 |  | Mechanical | Received | 2023-05-29 | Accounted transaction received
4160604 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 10.06. | Mat | 10 | SPECIALITIES | 63365 | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | 13858 | 1 | استوريا الحلول ف/2583 15/2 31 | 2583 | Currency | 13858 | 23048444 | 11118 | المصرية الهندسية للحلول المتكامله | rowad | استوريا الحلول ف/2583 15/2 31 |  | Mechanical | Received | 2023-05-29 | Accounted transaction received
4160605 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 10.06. | Mat | 10 | SPECIALITIES | 67977 | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -22340.35 | 1 | استوريا الحلول ف/2584 14/2 68 | 2584 USD c.m | Currency | -729.6 | 23048444 | 11118 | المصرية الهندسية للحلول المتكامله | rowad | استوريا الحلول ف/2584 14/2 68 |  | Mechanical | Received | 2023-05-29 | Accounted transaction received
4160606 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 10.06. | Mat | 10 | SPECIALITIES | 67977 | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | 22340.35 | 1 | استوريا الحلول ف/2584 14/2 68 | 2584 | Currency | 22340.35 | 23048444 | 11118 | المصرية الهندسية للحلول المتكامله | rowad | استوريا الحلول ف/2584 14/2 68 |  | Mechanical | Received | 2023-05-29 | Accounted transaction received
4163225 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.02 | Rented Cars | 17 | Indirect Cost |  | 2023-05-29 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 24165 | 1 | نقل افراد 4/23 - astoria 6 | نقل افراد 4/23 - astoria 6 | Currency | 24165 | 23053016 | 9182 | مؤسسة الجينيرال لتأجير السيارات | rowad | نقل افراد 4/23 - astoria 6 |  | Finacial | Received | 2023-05-30 | Accounted transaction received
4014397 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 754.85 | 1 | Aluminium volume DamperSize : 35 x 30 cm |  | Each | 1 | 61528419 |  |  |  | Aluminium volume DamperSize : 35 x 30 cm | 060070700160 | MEP | Received | 2023-05-01 | Accounted transaction received
4014398 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2941.43 | 1 | Aluminium volume DamperSize : 40 x 25 cm |  | Each | 4 | 61528420 |  |  |  | Aluminium volume DamperSize : 40 x 25 cm | 060070700169 | MEP | Received | 2023-05-01 | Accounted transaction received
4014399 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 814.42 | 1 | Aluminium volume DamperSize : 40 x 30 cm |  | Each | 1 | 61528421 |  |  |  | Aluminium volume DamperSize : 40 x 30 cm | 060070700170 | MEP | Received | 2023-05-01 | Accounted transaction received
4014400 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1329.92 | 1 | Aluminium volume DamperSize : 60 x 45 cm |  | Each | 1 | 61528422 |  |  |  | Aluminium volume DamperSize : 60 x 45 cm | 060070700218 | MEP | Received | 2023-05-01 | Accounted transaction received
4014401 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2316.54 | 1 | Aluminium volume DamperSize : 100 x 60 cm |  | Each | 1 | 61528423 |  |  |  | Aluminium volume DamperSize : 100 x 60 cm | 060070700267 | MEP | Received | 2023-05-01 | Accounted transaction received
4014402 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 8351.64 | 1 | Curtain Blade fire damper with sleeve 1.5 mm Size 110 * 60 cm |  | Each | 2 | 61528424 |  |  |  | Curtain Blade fire damper with sleeve 1.5 mm Size 110 * 60 cm | 060070800244 | MEP | Received | 2023-05-01 | Accounted transaction received
4014403 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 976.98 | 1 | Curtain Blade fire damper with sleeve 1.5 mm Size 30 * 20 cm |  | Each | 1 | 61528425 |  |  |  | Curtain Blade fire damper with sleeve 1.5 mm Size 30 * 20 cm | 060070800245 | MEP | Received | 2023-05-01 | Accounted transaction received
4014404 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-04-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 8226.24 | 1 | Curved Plenum Slot Diffuser 3/4" spacing for 2 Slot Length 2.4 Meter C/W Two galvanized round volume damper 6" |  | Each | 2 | 61528426 |  |  |  | Curved Plenum Slot Diffuser 3/4" spacing for 2 Slot Length 2.4 Meter C/W Two galvanized round volume damper 6" | 060070300124 | MEP | Received | 2023-05-01 | Accounted transaction received
4014405 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-04-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 31190.4 | 1 | Hardware accessories for doors HW-108 Back-to-Back Handle for Glazed Door MT-1 |  | Each | 24 | 61529846 |  |  |  | Hardware accessories for doors HW-108 Back-to-Back Handle for Glazed Door MT-1 | 250010001550 | Procurement | Received | 2023-05-01 | Accounted transaction received
4016362 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.03 | Hirings daily wages | 17 | Indirect Cost |  | 2023-04-30 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 64500 | 1 | Eidya astoria | Eidya astoria | Currency | 64500 | 22597839 | 2131 | Miscellaneous supplier | RME | Eidya astoria |  | Finacial | Received | 2023-05-02 | Accounted transaction received
4155376 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.08 | Trafic Permission & | 17 | Indirect Cost |  | 2023-05-23 | Trafic Perm-Station Fees |  |  |  | Indirect | Alrowad Construction_OU | 1495 | 1 | تسوية 62/63-م.سيارات | st-62/63-5-23 | Currency | 1495 | 23043432 | 2162 | Petty Cash | Mohamed Gamal Abdel Moneim Mohamed | تسوية 62/63-م.سيارات |  | Finacial | Received | 2023-05-28 | Accounted transaction received
4155382 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.08 | Trafic Permission & | 17 | Indirect Cost |  | 2023-05-23 | Trafic Perm-Station Fees |  |  |  | Indirect | Alrowad Construction_OU | 385 | 1 | تسوية 62/63-م.سيارات | st-62/63-5-23 | Currency | 385 | 23043432 | 2162 | Petty Cash | Mohamed Gamal Abdel Moneim Mohamed | تسوية 62/63-م.سيارات |  | Finacial | Received | 2023-05-28 | Accounted transaction received
4155418 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2023-05-23 | Accomodation |  |  |  | Indirect | Alrowad Construction_OU | 5800 | 1 | تسويه ك /231 ايجارات شهر مايو - استوريا | st-231-5-23 | Currency | 5800 | 23043432 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /231 ايجارات شهر مايو - استوريا |  | Finacial | Received | 2023-05-28 | Accounted transaction received
4155420 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2023-05-23 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 10425.3 | 1 | تسويه ك /218- رد شيك السويدى-استوريا | st-218-5-23 | Currency | 10425.3 | 23043432 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /218- رد شيك السويدى-استوريا |  | Finacial | Received | 2023-05-28 | Accounted transaction received
4155555 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2023-05-24 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 19857.65 | 1 | تسويه ك /202-203-210-216-219-221-227-228-229-230-232-234-235-متنوعات | st-24-5-23 | Currency | 19857.65 | 23043432 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /202-203-210-216-219-221-227-228-229-230-232-234-235-متنوعات |  | Finacial | Received | 2023-05-28 | Accounted transaction received
4155556 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-24 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 23475 | 1 | تسويه ك /202-203-210-216-219-221-227-228-229-230-232-234-235-متنوعات | st-24-5-23 | Currency | 23475 | 23043432 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /202-203-210-216-219-221-227-228-229-230-232-234-235-متنوعات |  | Finacial | Received | 2023-05-28 | Accounted transaction received
4161384 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3139.56 | 1 | Hardware Accessories for Doors FLUSH BOLT FOR WOODEN DOORS with DUST PROOF STRIKE Rockwood 557 x 570 626 |  | Each | 3 | 62494466 |  |  |  | Hardware Accessories for Doors FLUSH BOLT FOR WOODEN DOORS with DUST PROOF STRIKE Rockwood 557 x 570 626 | 250010001573 | Procurement | Received | 2023-05-29 | Accounted transaction received
4161385 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1243.35 | 1 | خوذة صفراء |  | Each | 31 | 62494842 |  |  |  | خوذة صفراء | 010040000010 | Safety | Received | 2023-05-29 | Accounted transaction received
4161386 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -36480 | 1 | Action floor spring max 300kg for Glass doors, brand Stanley |  | Each | -4 | 62480704 |  |  |  | Action floor spring max 300kg for Glass doors, brand Stanley | 310010000019 | Fleets | Received | 2023-05-29 | Accounted transaction received
4161387 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -5797.24 | 1 | لاكور ماسورة على فلكسبيل EMT المقاس 2 " |  | Each | -67 | 62482069 |  |  |  | لاكور ماسورة على فلكسبيل EMT المقاس 2 " | 030020100055 | MEP | Received | 2023-05-29 | Accounted transaction received
4161388 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -82.08 | 1 | أفيز هانجر EMT المقاس ¾ " |  | Each | -9 | 62482070 |  |  |  | أفيز هانجر EMT المقاس ¾ " | 030020100076 | MEP | Received | 2023-05-29 | Accounted transaction received
4161389 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -393.03 | 1 | أفيز هانجر EMT المقاس 2 " |  | Each | -23 | 62482071 |  |  |  | أفيز هانجر EMT المقاس 2 " | 030020100080 | MEP | Received | 2023-05-29 | Accounted transaction received
4161390 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -2123.82 | 1 | بواط إكستنشن 10 * 10 المقاس 1 " |  | Each | -30 | 62482072 |  |  |  | بواط إكستنشن 10 * 10 المقاس 1 " | 030020100111 | MEP | Received | 2023-05-29 | Accounted transaction received
4161391 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -269.98 | 1 | جلبة ماسورة 20مم UPVC (اللون أبيض) |  | Each | -152 | 62482073 |  |  |  | جلبة ماسورة 20مم UPVC (اللون أبيض) | 030010000067 | MEP | Received | 2023-05-29 | Accounted transaction received
4161392 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -39.9 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | -5 | 62482074 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-05-29 | Accounted transaction received
4161393 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -390.7 | 1 | جلبة ماسورة 32مم UPVC (اللون أبيض) |  | Each | -96 | 62482075 |  |  |  | جلبة ماسورة 32مم UPVC (اللون أبيض) | 030010000069 | MEP | Received | 2023-05-29 | Accounted transaction received
4161394 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -370.5 | 1 | جلبة ماسورة50مم UPVC (اللون أبيض) |  | Each | -13 | 62482076 |  |  |  | جلبة ماسورة50مم UPVC (اللون أبيض) | 030010000071 | MEP | Received | 2023-05-29 | Accounted transaction received
4161395 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -193.8 | 1 | جلبة ماسورة 63مم UPVC (اللون أبيض) |  | Each | -2 | 62482077 |  |  |  | جلبة ماسورة 63مم UPVC (اللون أبيض) | 030010000072 | MEP | Received | 2023-05-29 | Accounted transaction received
4161396 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -168.26 | 1 | بواط نهاية UPVC لماسورة 20مم(اللون أبيض) |  | Each | -24 | 62482078 |  |  |  | بواط نهاية UPVC لماسورة 20مم(اللون أبيض) | 030010000080 | MEP | Received | 2023-05-29 | Accounted transaction received
4161397 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -88.1 | 1 | بواط إمتداد UPVC لماسورة 20مم(اللون أبيض) |  | Each | -13 | 62482079 |  |  |  | بواط إمتداد UPVC لماسورة 20مم(اللون أبيض) | 030010000082 | MEP | Received | 2023-05-29 | Accounted transaction received
4161398 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -50 | 1 | بواط إمتداد UPVC لماسورة 25مم(اللون أبيض) |  | Each | -6 | 62482080 |  |  |  | بواط إمتداد UPVC لماسورة 25مم(اللون أبيض) | 030010000083 | MEP | Received | 2023-05-29 | Accounted transaction received
4161399 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -23.26 | 1 | بواط زاوية UPVC لماسورة 20مم(اللون أبيض) |  | Each | -3 | 62482081 |  |  |  | بواط زاوية UPVC لماسورة 20مم(اللون أبيض) | 030010000084 | MEP | Received | 2023-05-29 | Accounted transaction received
4161400 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -1875.02 | 1 | بواط زاوية UPVC لماسورة 25مم(اللون أبيض) |  | Each | -225 | 62482082 |  |  |  | بواط زاوية UPVC لماسورة 25مم(اللون أبيض) | 030010000085 | MEP | Received | 2023-05-29 | Accounted transaction received
4161401 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -1689.96 | 1 | بواط ثلاثي UPVC لماسورة 25مم(اللون أبيض) |  | Each | -186 | 62482083 |  |  |  | بواط ثلاثي UPVC لماسورة 25مم(اللون أبيض) | 030010000087 | MEP | Received | 2023-05-29 | Accounted transaction received
4161402 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -298.22 | 1 | أدابتور UPVC لماسورة 20مم(اللون أبيض) |  | Each | -92 | 62482084 |  |  |  | أدابتور UPVC لماسورة 20مم(اللون أبيض) | 030010000096 | MEP | Received | 2023-05-29 | Accounted transaction received
4161403 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -304.89 | 1 | أدابتور UPVC لماسورة 25مم(اللون أبيض) |  | Each | -39 | 62482085 |  |  |  | أدابتور UPVC لماسورة 25مم(اللون أبيض) | 030010000097 | MEP | Received | 2023-05-29 | Accounted transaction received
4161404 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -364.53 | 1 | أدابتور UPVC لماسورة 32مم(اللون أبيض) |  | Each | -28 | 62482086 |  |  |  | أدابتور UPVC لماسورة 32مم(اللون أبيض) | 030010000098 | MEP | Received | 2023-05-29 | Accounted transaction received
4161405 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -175.17 | 1 | أدابتور UPVC لماسورة 50مم(اللون أبيض) |  | Each | -6 | 62482087 |  |  |  | أدابتور UPVC لماسورة 50مم(اللون أبيض) | 030010000100 | MEP | Received | 2023-05-29 | Accounted transaction received
4161406 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -8988.9 | 1 | أفيز 20مم UPVC(اللون أبيض) |  | Each | -830 | 62482088 |  |  |  | أفيز 20مم UPVC(اللون أبيض) | 030010000106 | MEP | Received | 2023-05-29 | Accounted transaction received
4161407 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -93.86 | 1 | أفيز 32مم UPVC(اللون أبيض) |  | Each | -19 | 62482089 |  |  |  | أفيز 32مم UPVC(اللون أبيض) | 030010000108 | MEP | Received | 2023-05-29 | Accounted transaction received
4161408 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -753.39 | 1 | ادابتور فلكسبل 25 مم |  | Each | -126 | 62482090 |  |  |  | ادابتور فلكسبل 25 مم | 030010000141 | MEP | Received | 2023-05-29 | Accounted transaction received
4161409 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -5187 | 1 | بواط واتر بروف بفتحات مقاس 30 × 38 × 12 سم |  | Each | -13 | 62482091 |  |  |  | بواط واتر بروف بفتحات مقاس 30 × 38 × 12 سم | 030010000185 | MEP | Received | 2023-05-29 | Accounted transaction received
4161410 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -420.2 | 1 | لاكور ماسورة EMT المقاس ¾ " |  | Each | -19 | 62482092 |  |  |  | لاكور ماسورة EMT المقاس ¾ " | 030020100015 | MEP | Received | 2023-05-29 | Accounted transaction received
4161411 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -189.6 | 1 | لاكور ماسورة EMT المقاس 1 " |  | Each | -22 | 62482093 |  |  |  | لاكور ماسورة EMT المقاس 1 " | 030020100016 | MEP | Received | 2023-05-29 | Accounted transaction received
4161412 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -984.1 | 1 | لاكور ماسورة EMT المقاس ½ 1 " |  | Each | -15 | 62482094 |  |  |  | لاكور ماسورة EMT المقاس ½ 1 " | 030020100018 | MEP | Received | 2023-05-29 | Accounted transaction received
4161413 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -684 | 1 | غطاء بواط معدن مقاس 4*4 |  | Each | -100 | 62482095 |  |  |  | غطاء بواط معدن مقاس 4*4 | 030020100129 | MEP | Received | 2023-05-29 | Accounted transaction received
4161414 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -1015.52 | 1 | لاكور ماسورة EMT المقاس 2 " |  | Each | -17 | 62482096 |  |  |  | لاكور ماسورة EMT المقاس 2 " | 030020100019 | MEP | Received | 2023-05-29 | Accounted transaction received
4161415 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -6667.46 | 1 | جلبة ماسورة EMT المقاس 1 " |  | Each | -263 | 62482097 |  |  |  | جلبة ماسورة EMT المقاس 1 " | 030020100022 | MEP | Received | 2023-05-29 | Accounted transaction received
4161416 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -850.76 | 1 | جلبة ماسورة EMT المقاس ½ 1 " |  | Each | -18 | 62482098 |  |  |  | جلبة ماسورة EMT المقاس ½ 1 " | 030020100024 | MEP | Received | 2023-05-29 | Accounted transaction received
4161417 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -3066.14 | 1 | جلبة ماسورة EMT المقاس 2 " |  | Each | -41 | 62482099 |  |  |  | جلبة ماسورة EMT المقاس 2 " | 030020100025 | MEP | Received | 2023-05-29 | Accounted transaction received
4161418 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -413.2 | 1 | أفيز أثنين جناح لماسورة EMT المقاس ¾ " |  | Each | -165 | 62482100 |  |  |  | أفيز أثنين جناح لماسورة EMT المقاس ¾ " | 030020100033 | MEP | Received | 2023-05-29 | Accounted transaction received
4161419 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -237.12 | 1 | أفيز أثنين جناح لماسورة EMT المقاس 1 " |  | Each | -65 | 62482102 |  |  |  | أفيز أثنين جناح لماسورة EMT المقاس 1 " | 030020100034 | MEP | Received | 2023-05-29 | Accounted transaction received
4161420 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -1206.72 | 1 | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 |  | Each | -41 | 62482103 |  |  |  | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 | 030060100021 | MEP | Received | 2023-05-29 | Accounted transaction received
4161421 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -109.96 | 1 | TV - SINGLE SHIELDED "F" TYPE - 0-2400 HZ - 1 MOD Code 572163 |  | Each | -1 | 62482104 |  |  |  | TV - SINGLE SHIELDED "F" TYPE - 0-2400 HZ - 1 MOD Code 572163 | 030060100029 | MEP | Received | 2023-05-29 | Accounted transaction received
4161422 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -2988.51 | 1 | RJ45 SOCKET - CAT. 6 UTP - 8 CONTACTS - 1 MOD Code 572302 |  | Each | -19 | 62482105 |  |  |  | RJ45 SOCKET - CAT. 6 UTP - 8 CONTACTS - 1 MOD Code 572302 | 030060100031 | MEP | Received | 2023-05-29 | Accounted transaction received
4161423 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -1237.66 | 1 | SWITCH 20AX 1 WAY 1 MOD Code 572509 |  | Each | -9 | 62482106 |  |  |  | SWITCH 20AX 1 WAY 1 MOD Code 572509 | 030060100048 | MEP | Received | 2023-05-29 | Accounted transaction received
4161424 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -744.96 | 1 | TV-FM-SAT SQ WH Code 572172 |  | Each | -1 | 62482107 |  |  |  | TV-FM-SAT SQ WH Code 572172 | 030060100059 | MEP | Received | 2023-05-29 | Accounted transaction received
4161425 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -1621.87 | 1 | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 |  | Each | -14 | 62482108 |  |  |  | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 | 030060100114 | MEP | Received | 2023-05-29 | Accounted transaction received
4161426 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -3885.04 | 1 | TV "F" TYPE 1 MOD Code 572663 |  | Each | -17 | 62482109 |  |  |  | TV "F" TYPE 1 MOD Code 572663 | 030060100134 | MEP | Received | 2023-05-29 | Accounted transaction received
4161427 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -213.05 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | -12 | 62482110 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-05-29 | Accounted transaction received
4161428 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -1329.92 | 1 | PLATE 2SQ MOD F-G WHITE Code 576560 |  | Each | -38 | 62482111 |  |  |  | PLATE 2SQ MOD F-G WHITE Code 576560 | 030060100267 | MEP | Received | 2023-05-29 | Accounted transaction received
4161429 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -358.48 | 1 | PLATE 1SQ MOD SCH GRAPHITE Code 576552 |  | Each | -9 | 62482112 |  |  |  | PLATE 1SQ MOD SCH GRAPHITE Code 576552 | 030060100297 | MEP | Received | 2023-05-29 | Accounted transaction received
4161430 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -130.14 | 1 | RECTANGULAR 3 MODULES 2 GANG BOX BS Code 576002 |  | Each | -3 | 62482113 |  |  |  | RECTANGULAR 3 MODULES 2 GANG BOX BS Code 576002 | 030060100306 | MEP | Received | 2023-05-29 | Accounted transaction received
4161431 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -26631.93 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | -123 | 62482114 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-05-29 | Accounted transaction received
4161432 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -6314.9 | 1 | INTERNAL CONTROL UNIT FOR HOTEL BEDROOM Code 572554 |  | Each | -8 | 62482115 |  |  |  | INTERNAL CONTROL UNIT FOR HOTEL BEDROOM Code 572554 | 030060100175 | MEP | Received | 2023-05-29 | Accounted transaction received
4161433 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -1409.72 | 1 | FUSED 13A SWITCH +NEON SQ ALU Code 572651 |  | Each | -3 | 62482116 |  |  |  | FUSED 13A SWITCH +NEON SQ ALU Code 572651 | 030060100186 | MEP | Received | 2023-05-29 | Accounted transaction received
4161434 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -544.33 | 1 | 576562 Code وش مربع فضي |  | Each | -10 | 62482117 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-05-29 | Accounted transaction received
4161435 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -3919.78 | 1 | COVER 4 M SQUARE 2X2 WHITE F 576000 Code 575080 |  | Each | -56 | 62482118 |  |  |  | COVER 4 M SQUARE 2X2 WHITE F 576000 Code 575080 | 030060100231 | MEP | Received | 2023-05-29 | Accounted transaction received
4161436 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -2549.95 | 1 | Socket outlet Plexo IP55 Code 69733 |  | Each | -10 | 62482119 |  |  |  | Socket outlet Plexo IP55 Code 69733 | 030060100339 | MEP | Received | 2023-05-29 | Accounted transaction received
4161437 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -210 | 1 | B ENC BETON POPUP 4 MOD code 54001 |  | Each | -1 | 62482120 |  |  |  | B ENC BETON POPUP 4 MOD code 54001 | 030060100522 | MEP | Received | 2023-05-29 | Accounted transaction received
4161438 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -6796.71 | 1 | CARRIER PLATE SYNERGY code 730094 |  | Each | -101 | 62482121 |  |  |  | CARRIER PLATE SYNERGY code 730094 | 030060100534 | MEP | Received | 2023-05-29 | Accounted transaction received
4161439 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -1348.26 | 1 | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 |  | Each | -3 | 62482122 |  |  |  | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 | 030060100572 | MEP | Received | 2023-05-29 | Accounted transaction received
4161440 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -406.98 | 1 | 'S/M BOX GREY 2-GANG H Code : 69672 |  | Each | -2 | 62482123 |  |  |  | 'S/M BOX GREY 2-GANG H Code : 69672 | 030060100654 | MEP | Received | 2023-05-29 | Accounted transaction received
4161441 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -793.39 | 1 | DS 2 pole , 63A, ABS Enclsosure IP 65 , PART NUMBER : kem 263u y/r abs |  | Each | -1 | 62482124 |  |  |  | DS 2 pole , 63A, ABS Enclsosure IP 65 , PART NUMBER : kem 263u y/r abs | 030060200023 | MEP | Received | 2023-05-29 | Accounted transaction received
4161442 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -379.98 | 1 | SOCKET ARTEOR - GERMAN - 16 A - 2P+E SHUTTERED - 2 MODULES - ORANGE-code 572460 |  | Each | -4 | 62482125 |  |  |  | SOCKET ARTEOR - GERMAN - 16 A - 2P+E SHUTTERED - 2 MODULES - ORANGE-code 572460 | 030060100673 | MEP | Received | 2023-05-29 | Accounted transaction received
4161443 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -2074.91 | 1 | HDMI Cable 15 M |  | Each | -1 | 62482126 |  |  |  | HDMI Cable 15 M | 800040000129 | IT | Received | 2023-05-29 | Accounted transaction received
4161444 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -240.74 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | -3 | 62482127 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-05-29 | Accounted transaction received
4161445 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -6015.78 | 1 | SCHUKO SKT 2P+E SCREW-TER GY Code ( 69571 ) |  | Each | -30 | 62482128 |  |  |  | SCHUKO SKT 2P+E SCREW-TER GY Code ( 69571 ) | 030060100727 | MEP | Received | 2023-05-29 | Accounted transaction received
4161446 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -4776.41 | 1 | LID & TRIM 3 COMPARTMENTS GREY ( Legrand 689631 ) |  | Each | -6 | 62482129 |  |  |  | LID & TRIM 3 COMPARTMENTS GREY ( Legrand 689631 ) | 030060100738 | MEP | Received | 2023-05-29 | Accounted transaction received
4161447 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -2532.05 | 1 | FRAME 8 MOD MOSAIC ( Legrand 689658 ) |  | Each | -13 | 62482130 |  |  |  | FRAME 8 MOD MOSAIC ( Legrand 689658 ) | 030060100740 | MEP | Received | 2023-05-29 | Accounted transaction received
4163227 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.02 | Rented Cars | 17 | Indirect Cost |  | 2023-05-29 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 36784.2 | 1 | نقل افراد 4/23 - astoria 6 | نقل افراد 4/23 - astoria 6 | Currency | 36784.2 | 23053016 | 5214 | المتحدة لايجار وتوريد السيارات | rowad | نقل افراد 4/23 - astoria 6 |  | Finacial | Received | 2023-05-30 | Accounted transaction received
4163230 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.02 | Rented Cars | 17 | Indirect Cost |  | 2023-05-29 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 19980 | 1 | نقل افراد 4/23 - astoria 6 | نقل افراد 4/23 - astoria 6 | Currency | 19980 | 23053016 | 3084 | محمد احمد محمد محمد | Rowad | نقل افراد 4/23 - astoria 6 |  | Finacial | Received | 2023-05-30 | Accounted transaction received
4163301 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.08 | Trafic Permission & | 17 | Indirect Cost |  | 2023-05-29 | Trafic Perm-Station Fees |  |  |  | Indirect | Alrowad Construction_OU | 3525 | 1 | تسوية 64/65/66-م.سيارات | st-64/65/66-5-23 | Currency | 3525 | 23053016 | 2162 | Petty Cash | Mohamed Gamal Abdel Moneim Mohamed | تسوية 64/65/66-م.سيارات |  | Finacial | Received | 2023-05-30 | Accounted transaction received
4179934 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3599.98 | 1 | Cyber cable network 305 M Cat6 |  | Each | 2 | 62642586 |  |  |  | Cyber cable network 305 M Cat6 | 800060000003 | IT | Received | 2023-05-30 | Accounted transaction received
4116560 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3898.8 | 1 | Hardware accessories for doors IR-23 Bespoke Metal Kickplate MT-4 |  | Each | 3 | 61940583 |  |  |  | Hardware accessories for doors IR-23 Bespoke Metal Kickplate MT-4 | 250010001565 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116561 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 19060.8 | 1 | Hardware accessories for doors IR-33 Bespoke Metal Kickplate MT-5 |  | Each | 8 | 61940584 |  |  |  | Hardware accessories for doors IR-33 Bespoke Metal Kickplate MT-5 | 250010001566 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116562 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 18411 | 1 | Hardware accessories for doors IR-38 Bespoke Oversized Kickplate MT-4 |  | Each | 2 | 61940585 |  |  |  | Hardware accessories for doors IR-38 Bespoke Oversized Kickplate MT-4 | 250010001567 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116563 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 54720 | 1 | Hardware accessories for doors HW-122 Bespoke Door Pull as per Muza Lab Specification MT-4 |  | Each | 4 | 61941747 |  |  |  | Hardware accessories for doors HW-122 Bespoke Door Pull as per Muza Lab Specification MT-4 | 250010001553 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116564 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 446.88 | 1 | Pull Handle-Yale-35-9004-8820-19-31-50-630-305X75 MM |  | Each | 1 | 61942915 |  |  |  | Pull Handle-Yale-35-9004-8820-19-31-50-630-305X75 MM | 250010000295 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116565 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 615.6 | 1 | Kick Plate ,, France Metal ,, ST.ST ,, Up to 200 x 1000 mm |  | Each | 1 | 61942916 |  |  |  | Kick Plate ,, France Metal ,, ST.ST ,, Up to 200 x 1000 mm | 250010000569 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116566 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 11559.6 | 1 | Hinges Mckinney Spring Hinge 1552 4.5" x 4.0" 630 |  | Each | 13 | 61942917 |  |  |  | Hinges Mckinney Spring Hinge 1552 4.5" x 4.0" 630 | 250010000662 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116567 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4377.6 | 1 | Flush Cup Pull France Metal FCP SSS |  | Each | 8 | 61942918 |  |  |  | Flush Cup Pull France Metal FCP SSS | 250010001450 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116568 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1134 | 1 | Hardware Accessories for Wooden Doors TESA TE5 Thumb turn Cylinder 35x35mm. 5 Spring Loaded Anti pick Pins + 1 SENSOR in the key. Certified according to EN1303. |  | Each | 3 | 61942919 |  |  |  | Hardware Accessories for Wooden Doors TESA TE5 Thumb turn Cylinder 35x35mm. 5 Spring Loaded Anti pick Pins + 1 SENSOR in the key. Certified according to EN1303. | 250010001522 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116569 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3648 | 1 | Hardware accessories for doors IR-04 Bespoke Door Pull as per ABD & UWS Specification MT-8 |  | Each | 2 | 61942920 |  |  |  | Hardware accessories for doors IR-04 Bespoke Door Pull as per ABD & UWS Specification MT-8 | 250010001556 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116570 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1284.78 | 1 | Hardware Accessories for Doors Standard Door closer ASSA ABLOY DC110 689 |  | Each | 1 | 61942921 |  |  |  | Hardware Accessories for Doors Standard Door closer ASSA ABLOY DC110 689 | 250010001571 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116571 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3287.76 | 1 | Hardware Accessories for Doors KICK PLATE - Armor Plate France Metal UP TO 1000MM X 1000MM HEIGHT ST.ST |  | Each | 1 | 61942922 |  |  |  | Hardware Accessories for Doors KICK PLATE - Armor Plate France Metal UP TO 1000MM X 1000MM HEIGHT ST.ST | 250010001574 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116572 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 15048 | 1 | T-Bar Handle |  | Each | 12 | 61942923 |  |  |  | T-Bar Handle | 250010001667 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116573 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1710 | 1 | Robe Hook HW-4 |  | Each | 2 | 61942924 |  |  |  | Robe Hook HW-4 | 250010002115 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116574 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 534660 | 1 | A class Engineered oak wood including but not limited to fixing finish and all necessary accessories Code TER plank 7*8 A class parquet flooring Natural wood kiln dried Prefinished 3 layers for maximum stability enabling click system |  | Square Meter | 134 | 61945016 |  |  |  | A class Engineered oak wood including but not limited to fixing finish and all necessary accessories Code TER plank 7*8 A class parquet flooring Natural wood kiln dried Prefinished 3 layers for maximum stability enabling click system | 090040000103 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116575 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3534 | 1 | Master Seal NP 472 |  | Kit | 31 | 61945317 |  |  |  | Master Seal NP 472 | 360010000355 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116576 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 47355.6 | 1 | Supplying of pendent concealed sprinkler , quick response , standard coverage , 68 C, 1/2", K=5.6 C/W cover plate |  | Each | 62 | 61946030 |  |  |  | Supplying of pendent concealed sprinkler , quick response , standard coverage , 68 C, 1/2", K=5.6 C/W cover plate | 060090100007 | MEP | Received | 2023-05-23 | Accounted transaction received
4116577 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 13395 | 1 | Regulating Valve DM931 Crane UK DN 80 |  | Each | 1 | 61946031 |  |  |  | Regulating Valve DM931 Crane UK DN 80 | 060170100089 | MEP | Received | 2023-05-23 | Accounted transaction received
4116578 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 14090.93 | 1 | 2 way control valve Size 3" C/W on/off actuator 3-position ( VVF47.80 - SKB32.50 ) |  | Each | 1 | 61946032 |  |  |  | 2 way control valve Size 3" C/W on/off actuator 3-position ( VVF47.80 - SKB32.50 ) | 060172800005 | MEP | Received | 2023-05-23 | Accounted transaction received
4116579 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 9804 | 1 | Gate Valve D180 Crane UK 3" PN 32 |  | Each | 2 | 61946033 |  |  |  | Gate Valve D180 Crane UK 3" PN 32 | 060170500025 | MEP | Received | 2023-05-23 | Accounted transaction received
4116580 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 6270 | 1 | Strainer Valve FM276 Crane UK 3" PN 16 |  | Each | 1 | 61946034 |  |  |  | Strainer Valve FM276 Crane UK 3" PN 16 | 060170500026 | MEP | Received | 2023-05-23 | Accounted transaction received
4116581 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 6566.4 | 1 | Handle Extension: IR-36 Dimensions: 30mm Materials: Brass Finish: Antique Brass |  | Each | 32 | 61946614 |  |  |  | Handle Extension: IR-36 Dimensions: 30mm Materials: Brass Finish: Antique Brass | 250010002118 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116582 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 96.9 | 1 | Hardware Accessories for Doors Eye Viewer VEKTR 1014/35-60XG-SN SN |  | Each | 1 | 61946736 |  |  |  | Hardware Accessories for Doors Eye Viewer VEKTR 1014/35-60XG-SN SN | 250010001572 | Procurement | Received | 2023-05-23 | Accounted transaction received
4116583 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.13 | Maintenance | 17 | Indirect Cost |  | 2023-05-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 399 | 1 | موبينه صاروخ 5 |  | Each | 1 | 61946921 |  |  |  | موبينه صاروخ 5 | 330040001797 | Equipment | Received | 2023-05-23 | Accounted transaction received
4116584 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 5358 | 1 | اسمنت اسود رتبة 42 |  | Ton | 2 | 61959472 |  |  |  | اسمنت اسود رتبة 42 | 140010000015 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116585 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 28.5 | 1 | كيس قطن |  | Each | 1 | 61959473 |  |  |  | كيس قطن | 200010000712 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116586 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 342 | 1 | الوان سكيب |  | Each | 1 | 61959474 |  |  |  | الوان سكيب | 200010000787 | Purchasing | Received | 2023-05-23 | Accounted transaction received
4116587 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 65 | 1 | سيلكون فواصل |  | Each | 1 | 61959475 |  |  |  | سيلكون فواصل | 330040000882 | Equipment | Received | 2023-05-23 | Accounted transaction received
4116588 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 889.2 | 1 | كرتون مضلع - تغليف |  | Kilogram | 60 | 61959476 |  |  |  | كرتون مضلع - تغليف | 910010000387 | Administration | Received | 2023-05-23 | Accounted transaction received
4164089 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 193.8 | 1 | كوع صرف ابيض قطر 4" ( 110 مم ) |  | Each | 2 | 62495739 |  |  |  | كوع صرف ابيض قطر 4" ( 110 مم ) | 060010100210 | MEP | Received | 2023-05-30 | Accounted transaction received
4164090 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 91.2 | 1 | كوع صرف ابيض 45 درجه قطر 4" ( 110 مم ) |  | Each | 1 | 62495740 |  |  |  | كوع صرف ابيض 45 درجه قطر 4" ( 110 مم ) | 060010100219 | MEP | Received | 2023-05-30 | Accounted transaction received
4164091 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 290.4 | 1 | جلبة تمدد صرف ابيض قطر 4" ( 110 مم ) |  | Each | 5 | 62495741 |  |  |  | جلبة تمدد صرف ابيض قطر 4" ( 110 مم ) | 060010100277 | MEP | Received | 2023-05-30 | Accounted transaction received
4164092 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 17.1 | 1 | مشترك لحام PPR قطر 25 مم |  | Each | 1 | 62495742 |  |  |  | مشترك لحام PPR قطر 25 مم | 060010300070 | MEP | Received | 2023-05-30 | Accounted transaction received
4164093 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 547.2 | 1 | جوان 1 بوصة |  | Each | 48 | 62495743 |  |  |  | جوان 1 بوصة | 240080000142 | MEP | Received | 2023-05-30 | Accounted transaction received
4164094 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 661.2 | 1 | threaded reducing tees size 2"*1/2" UL LISTED,FM APPROVED |  | Each | 2 | 62495744 |  |  |  | threaded reducing tees size 2"*1/2" UL LISTED,FM APPROVED | 060010140168 | MEP | Received | 2023-05-30 | Accounted transaction received
4164095 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 547.2 | 1 | مسامير سيلف دريل 8مم طول 3سم |  | Kilogram | 3 | 62495745 |  |  |  | مسامير سيلف دريل 8مم طول 3سم | 060191210002 | MEP | Received | 2023-05-30 | Accounted transaction received
4164096 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 484.5 | 1 | حنفية بلية إيطالى 1/2 بوصة |  | Each | 5 | 62495746 |  |  |  | حنفية بلية إيطالى 1/2 بوصة | 240070000182 | MEP | Received | 2023-05-30 | Accounted transaction received
4164097 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 108.3 | 1 | لصق حار ¼ كيلو |  | Each | 0.25 | 62495747 |  |  |  | لصق حار ¼ كيلو | 060019000011 | MEP | Received | 2023-05-30 | Accounted transaction received
4164098 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 55 | 1 | لصق حار 1/8 كيلو |  | Each | 1 | 62495748 |  |  |  | لصق حار 1/8 كيلو | 060019000035 | MEP | Received | 2023-05-30 | Accounted transaction received
4179935 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1699.99 | 1 | D Link Rj 45 Cate6 |  | Each | 2 | 62642587 |  |  |  | D Link Rj 45 Cate6 | 800040000256 | IT | Received | 2023-05-30 | Accounted transaction received
4179936 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 129.97 | 1 | لاكور ماسورة EMT المقاس ½ 1 " |  | Each | 2 | 62643008 |  |  |  | لاكور ماسورة EMT المقاس ½ 1 " | 030020100018 | MEP | Received | 2023-05-30 | Accounted transaction received
4179937 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 59.6 | 1 | لاكور ماسورة EMT المقاس 2 " |  | Each | 1 | 62643009 |  |  |  | لاكور ماسورة EMT المقاس 2 " | 030020100019 | MEP | Received | 2023-05-30 | Accounted transaction received
4179938 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5244 | 1 | Connector for Led strip - Acolyte |  | Each | 100 | 62643010 |  |  |  | Connector for Led strip - Acolyte | 030040700476 | MEP | Received | 2023-05-30 | Accounted transaction received
4179939 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-05-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 5040 | 1 | اسمنت اسود رتبة 42 |  | Ton | 2 | 62644053 |  |  |  | اسمنت اسود رتبة 42 | 140010000015 | Purchasing | Received | 2023-05-30 | Accounted transaction received
4186660 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-05-31 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 153450 | 1 | يوميات عماله الفتره 1 ش 5 الفعلي | يوميات عماله الفتره 1 ش 5 الفعلي | Currency | 153450 | 23152412 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 1 ش 5 الفعلي |  | Finacial | Received | 2023-06-01 | Accounted transaction received
4186708 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-05-31 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 153450 | 1 | يوميات عماله الفتره 2 ش 5 التقديري | يوميات عماله الفتره 2 ش 5 التقديري | Currency | 153450 | 23152412 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 2 ش 5 التقديري |  | Finacial | Received | 2023-06-01 | Accounted transaction received
4189485 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 25764 | 1 | Trim around Mirrors |  | Meter | 40 | 62753178 |  |  |  | Trim around Mirrors | 250010001935 | Procurement | Received | 2023-06-04 | Accounted transaction received
4164099 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 199.5 | 1 | لاكور 1" سن داخلي |  | Each | 1 | 62495749 |  |  |  | لاكور 1" سن داخلي | 060010300308 | MEP | Received | 2023-05-30 | Accounted transaction received
4164100 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 150 | 1 | جلبة تطويل تيش 10مم سن داخلي |  | Each | 12 | 62495750 |  |  |  | جلبة تطويل تيش 10مم سن داخلي | 240020000072 | MEP | Received | 2023-05-30 | Accounted transaction received
4164101 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 180 | 1 | فلانشة عمياء PN16 بالجوان والمسامير 3 بوصة |  | Each | 1 | 62495751 |  |  |  | فلانشة عمياء PN16 بالجوان والمسامير 3 بوصة | 060011800193 | MEP | Received | 2023-05-30 | Accounted transaction received
4164102 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2166 | 1 | أدة الومنيوم 3 متر |  | Each | 2 | 62497779 |  |  |  | أدة الومنيوم 3 متر | 200010000016 | Purchasing | Received | 2023-05-30 | Accounted transaction received
4164103 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4998.9 | 1 | سيكا توب سيل SIKA TOP SEAL 107 |  | Bag | 5 | 62497780 |  |  |  | سيكا توب سيل SIKA TOP SEAL 107 | 360010000052 | Purchasing | Received | 2023-05-30 | Accounted transaction received
4164104 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 75 | 1 | اسمنت ابيض |  | Ton | 0.02 | 62497781 |  |  |  | اسمنت ابيض | 140010000001 | Purchasing | Received | 2023-05-30 | Accounted transaction received
4164105 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 8550 | 1 | بولي ايثيلين 200 ميكرون شفاف |  | Kilogram | 100 | 62497782 |  |  |  | بولي ايثيلين 200 ميكرون شفاف | 040010000042 | Purchasing | Received | 2023-05-30 | Accounted transaction received
4164106 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1026 | 1 | سيكا جراوت 214 |  | Bag | 5 | 62497783 |  |  |  | سيكا جراوت 214 | 360010000033 | Purchasing | Received | 2023-05-30 | Accounted transaction received
4164107 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 755.82 | 1 | كرتون مضلع - تغليف |  | Kilogram | 100 | 62497784 |  |  |  | كرتون مضلع - تغليف | 910010000387 | Administration | Received | 2023-05-30 | Accounted transaction received
4164108 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 513 | 1 | تيب دوكو |  | Each | 18 | 62500267 |  |  |  | تيب دوكو | 200010000048 | Purchasing | Received | 2023-05-30 | Accounted transaction received
4164109 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 5358 | 1 | اسمنت اسود رتبة 42 |  | Ton | 2 | 62500268 |  |  |  | اسمنت اسود رتبة 42 | 140010000015 | Purchasing | Received | 2023-05-30 | Accounted transaction received
4164110 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 712.5 | 1 | كوريك باليد |  | Each | 5 | 62500269 |  |  |  | كوريك باليد | 200010000443 | Purchasing | Received | 2023-05-30 | Accounted transaction received
4164111 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 940.5 | 1 | سافيتو جراوت رمادى (مادة سقية سيراميك) |  | Bag | 5 | 62500270 |  |  |  | سافيتو جراوت رمادى (مادة سقية سيراميك) | 170030000003 | Purchasing | Received | 2023-05-30 | Accounted transaction received
4184574 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.10 | Printers / Photo Cop | 17 | Indirect Cost |  | 2023-05-31 | Printers/Photo Copiers |  |  |  | Indirect | Alrowad Construction_OU | 2200 | 1 | تصوير فيديو وصور بالمشاريع. | تصوير فيديو وصور بالمشاريع... | Currency | 2200 | 23151363 | 9821 | محمد عاطف عبدالعزيز موسي | rowad | تصوير فيديو وصور بالمشاريع. |  | Finacial | Received | 2023-06-01 | Accounted transaction received
4184663 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.06 | Telephones | 17 | Indirect Cost |  | 2023-05-31 | Telephones |  |  |  | Indirect | Alrowad Construction_OU | 8526.58 | 1 | استحقاق فاتورة اورنج عن ش فبراير 2023 | استحقاق فاتورة اورنج عن ش فبراير 2023 | Currency | 8526.58 | 23151363 | 2135 | اورنج مصر للاتصالات | Egypt | استحقاق فاتورة اورنج عن ش فبراير 2023 |  | Finacial | Received | 2023-06-01 | Accounted transaction received
4185949 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1600.48 | 1 | كورنشة فيوتك 4 سم |  | Meter | 22 | 62651564 |  |  |  | كورنشة فيوتك 4 سم | 050020000004 | Purchasing | Received | 2023-06-01 | Accounted transaction received
4185950 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1046.52 | 1 | Hardware Accessories for Doors FLUSH BOLT FOR WOODEN DOORS with DUST PROOF STRIKE Rockwood 557 x 570 626 |  | Each | 1 | 62651565 |  |  |  | Hardware Accessories for Doors FLUSH BOLT FOR WOODEN DOORS with DUST PROOF STRIKE Rockwood 557 x 570 626 | 250010001573 | Procurement | Received | 2023-06-01 | Accounted transaction received
4185951 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 85.5 | 1 | Spring action Floor Bolt with Automatic mechanism Dust proof XA808B DUST PROOF STRIKE, with Satin Stainless-Steel Finish |  | Each | 1 | 62651566 |  |  |  | Spring action Floor Bolt with Automatic mechanism Dust proof XA808B DUST PROOF STRIKE, with Satin Stainless-Steel Finish | 250010001696 | Procurement | Received | 2023-06-01 | Accounted transaction received
4185952 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 14206.26 | 1 | 10A INTERMEDIATE SWITCH 1 MOD MAGNESIUM Code 572508 |  | Each | 34 | 62651574 |  |  |  | 10A INTERMEDIATE SWITCH 1 MOD MAGNESIUM Code 572508 | 030060100126 | MEP | Received | 2023-06-01 | Accounted transaction received
4185953 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4217.7 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 34 | 62651575 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-06-01 | Accounted transaction received
4185954 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 27120.6 | 1 | Audio, Control & Instrumentation Cable Twisted INDV Shielded (UL),Similar to Belden P/N.8723.Size (2Px22AWG).P.N:C1196 |  | Meter | 610 | 62651576 |  |  |  | Audio, Control & Instrumentation Cable Twisted INDV Shielded (UL),Similar to Belden P/N.8723.Size (2Px22AWG).P.N:C1196 | 032070000047 | MEP | Received | 2023-06-01 | Accounted transaction received
4185955 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 250 | 1 | مسدس سيلكون ( سيلانت ) |  | Each | 2 | 62651710 |  |  |  | مسدس سيلكون ( سيلانت ) | 200010000224 | Purchasing | Received | 2023-06-01 | Accounted transaction received
4185956 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 142.5 | 1 | مسمار 12 مم طول 6 سم |  | Bag | 1 | 62651711 |  |  |  | مسمار 12 مم طول 6 سم | 200020000016 | Purchasing | Received | 2023-06-01 | Accounted transaction received
4185957 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1140 | 1 | سيكا فبلر Sika fiber |  | Bag | 4 | 62651712 |  |  |  | سيكا فبلر Sika fiber | 360010000062 | Purchasing | Received | 2023-06-01 | Accounted transaction received
4185958 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 8037 | 1 | اسمنت اسود رتبة 42 |  | Ton | 3 | 62651713 |  |  |  | اسمنت اسود رتبة 42 | 140010000015 | Purchasing | Received | 2023-06-01 | Accounted transaction received
4185959 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 513 | 1 | تيب مسلح |  | Each | 10 | 62651714 |  |  |  | تيب مسلح | 200010000382 | Purchasing | Received | 2023-06-01 | Accounted transaction received
4185960 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 188.1 | 1 | برايمر |  | Each | 1 | 62651715 |  |  |  | برايمر | 060019000007 | MEP | Received | 2023-06-01 | Accounted transaction received
4185961 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 655.5 | 1 | معجون ممتاز |  | Bag | 5 | 62651716 |  |  |  | معجون ممتاز | 200010001077 | Purchasing | Received | 2023-06-01 | Accounted transaction received
4185962 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1504.8 | 1 | سيليكون شفاف |  | Each | 12 | 62651717 |  |  |  | سيليكون شفاف | 200010000946 | Purchasing | Received | 2023-06-01 | Accounted transaction received
4185963 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3009.6 | 1 | سيلكون عظم |  | Each | 24 | 62651718 |  |  |  | سيلكون عظم | 330040000420 | Equipment | Received | 2023-06-01 | Accounted transaction received
4185964 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 108.3 | 1 | لاكيه لامع أبيض |  | Kilogram | 1 | 62651719 |  |  |  | لاكيه لامع أبيض | 050010000174 | Purchasing | Received | 2023-06-01 | Accounted transaction received
4185965 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1515.24 | 1 | 10AX SWITCH SP 2 WAY 1 MOD Code 572505 |  | Each | 10 | 62660121 |  |  |  | 10AX SWITCH SP 2 WAY 1 MOD Code 572505 | 030060100123 | MEP | Received | 2023-06-01 | Accounted transaction received
4185966 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 322.26 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 7 | 62660122 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-06-01 | Accounted transaction received
4185967 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 35192.22 | 1 | UNIVERSAL DIMMER W/O NEUTR 400 Code 572739 |  | Each | 12 | 62660123 |  |  |  | UNIVERSAL DIMMER W/O NEUTR 400 Code 572739 | 030060100176 | MEP | Received | 2023-06-01 | Accounted transaction received
4185968 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 98.53 | 1 | Wiring Devices (54000) METAL FLUSH-MOUNTING BOX FOR INSTALLATION IN CONCRETE FLOOR - 3 MODULES |  | Each | 1 | 62660124 |  |  |  | Wiring Devices (54000) METAL FLUSH-MOUNTING BOX FOR INSTALLATION IN CONCRETE FLOOR - 3 MODULES | 030060100618 | MEP | Received | 2023-06-01 | Accounted transaction received
4185969 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1236.81 | 1 | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 |  | Each | 10 | 62660125 |  |  |  | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 | 030060100951 | MEP | Received | 2023-06-01 | Accounted transaction received
4185970 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 68.4 | 1 | فيشر 10 مم |  | Carton | 3 | 62661117 |  |  |  | فيشر 10 مم | 200010000162 | Purchasing | Received | 2023-06-01 | Accounted transaction received
4185971 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 427.5 | 1 | مسمار 13 مم |  | Kilogram | 3 | 62661118 |  |  |  | مسمار 13 مم | 200020000019 | Purchasing | Received | 2023-06-01 | Accounted transaction received
4185972 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 729.6 | 1 | جلاند بلاستيك مقاس 11 PG |  | Each | 80 | 62661119 |  |  |  | جلاند بلاستيك مقاس 11 PG | 030130500036 | MEP | Received | 2023-06-01 | Accounted transaction received
4185973 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 712.5 | 1 | مانيجا ( مادة لزق ) |  | Each | 5 | 62661120 |  |  |  | مانيجا ( مادة لزق ) | 200020000181 | Purchasing | Received | 2023-06-01 | Accounted transaction received
4185974 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1140 | 1 | بكرة شريط لحام |  | Each | 20 | 62661121 |  |  |  | بكرة شريط لحام | 039010000003 | MEP | Received | 2023-06-01 | Accounted transaction received
4189486 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 250.43 | 1 | أفيز أثنين جناح لماسورة EMT المقاس ¾ " |  | Each | 100 | 62753398 |  |  |  | أفيز أثنين جناح لماسورة EMT المقاس ¾ " | 030020100033 | MEP | Received | 2023-06-04 | Accounted transaction received
4189487 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 6498 | 1 | HDMI PRE-CONN 1M Code 572596 |  | Each | 2 | 62753399 |  |  |  | HDMI PRE-CONN 1M Code 572596 | 030060100165 | MEP | Received | 2023-06-04 | Accounted transaction received
4189488 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 151.29 | 1 | 10AX 2 WAY SWITCH 2 MOD Code 572535 |  | Each | 2 | 62753400 |  |  |  | 10AX 2 WAY SWITCH 2 MOD Code 572535 | 030060100125 | MEP | Received | 2023-06-04 | Accounted transaction received
4189489 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-03 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 24640.75 | 1 | Floor box 6 Module with double socket, space for 2 data socket complete with back box , IP66, Part Number GESR2 - OBO Germany |  | Each | 2 | 62753401 |  |  |  | Floor box 6 Module with double socket, space for 2 data socket complete with back box , IP66, Part Number GESR2 - OBO Germany | 030060100992 | MEP | Received | 2023-06-04 | Accounted transaction received
4189490 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 872.99 | 1 | كورنشة فيوتك 4 سم |  | Meter | 12 | 62753454 |  |  |  | كورنشة فيوتك 4 سم | 050020000004 | Purchasing | Received | 2023-06-04 | Accounted transaction received
4189491 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1173.74 | 1 | طوب مصمت 6*10*20 |  | Each | 1040 | 62758373 |  |  |  | طوب مصمت 6*10*20 | 140020000045 | Purchasing | Received | 2023-06-04 | Accounted transaction received
4189492 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-03 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 436.49 | 1 | كورنشة فيوتك 4 سم |  | Meter | 6 | 62758457 |  |  |  | كورنشة فيوتك 4 سم | 050020000004 | Purchasing | Received | 2023-06-04 | Accounted transaction received
4189493 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-04 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 171 | 1 | دفتر Material Request |  | Each | 10 | 62772269 |  |  |  | دفتر Material Request | 910010000269 | Administration | Received | 2023-06-04 | Accounted transaction received
4189494 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-04 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 354.52 | 1 | دفتر تصريح خروج |  | Each | 10 | 62772270 |  |  |  | دفتر تصريح خروج | 910010000386 | Administration | Received | 2023-06-04 | Accounted transaction received
4189495 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 399 | 1 | بواط واتر بروف بفتحات مقاس 30 × 38 × 12 سم |  | Each | 1 | 62772285 |  |  |  | بواط واتر بروف بفتحات مقاس 30 × 38 × 12 سم | 030010000185 | MEP | Received | 2023-06-04 | Accounted transaction received
4189496 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 54.13 | 1 | جلبة ماسورة EMT المقاس ¾ " |  | Each | 3 | 62772286 |  |  |  | جلبة ماسورة EMT المقاس ¾ " | 030020100021 | MEP | Received | 2023-06-04 | Accounted transaction received
4189497 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 765.24 | 1 | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 |  | Each | 26 | 62772287 |  |  |  | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 | 030060100021 | MEP | Received | 2023-06-04 | Accounted transaction received
4189498 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2988.51 | 1 | RJ45 SOCKET - CAT. 6 UTP - 8 CONTACTS - 1 MOD Code 572302 |  | Each | 19 | 62772288 |  |  |  | RJ45 SOCKET - CAT. 6 UTP - 8 CONTACTS - 1 MOD Code 572302 | 030060100031 | MEP | Received | 2023-06-04 | Accounted transaction received
4189499 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 714.13 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 4 | 62772289 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-06-04 | Accounted transaction received
4189500 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3505.92 | 1 | FRAME 8 MOD MOSAIC ( Legrand 689658 ) |  | Each | 18 | 62772290 |  |  |  | FRAME 8 MOD MOSAIC ( Legrand 689658 ) | 030060100740 | MEP | Received | 2023-06-04 | Accounted transaction received
4189738 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.02 | Health Care | 17 | Indirect Cost |  | 2023-05-31 | Hirings Payrool |  |  |  | Indirect | Alrowad Construction_OU | 1082380.38 | 1 | قيد مرتبات شهر مايو 2023 | Salary-MAY-2023 | Currency | 1082380.38 | 23217446 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر مايو 2023 |  | Finacial | Received | 2023-06-04 | Accounted transaction received
4189779 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.02 | Health Care | 17 | Indirect Cost |  | 2023-05-31 | Honouring of terrorism 0.0005 |  |  |  | Indirect | Alrowad Construction_OU | 331.04 | 1 | قيد مرتبات شهر مايو 2023 | Salary-MAY-2023 | Currency | 331.04 | 23217446 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر مايو 2023 |  | Finacial | Received | 2023-06-04 | Accounted transaction received
4197441 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.06 | Material Transportat | 17 | Indirect Cost |  | 2023-05-14 | Material Transportation |  |  |  | Indirect | Alrowad Construction_OU | -27841 | 1 | اعمال نقل ثقيل - 2/ 23 - waldorf astoria | اعمال نقل ثقيل - 2/ 23 - waldorf astoria | Currency | -27841 | 23223931 | 8534 | مكتب الحمد للنقل | rowad | اعمال نقل ثقيل - 2/ 23 - waldorf astoria |  | Finacial | Received | 2023-06-05 | Accounted transaction received
4197442 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.06 | Material Transportat | 17 | Indirect Cost |  | 2023-05-14 | Material Transportation |  |  |  | Indirect | Alrowad Construction_OU | 27841 | 1 | اعمال نقل ثقيل - 2/ 23 - waldorf astoria | اعمال نقل ثقيل - 2/ 23 - waldorf astoria | Currency | 27841 | 23223931 | 8534 | مكتب الحمد للنقل | rowad | اعمال نقل ثقيل - 2/ 23 - waldorf astoria |  | Finacial | Received | 2023-06-05 | Accounted transaction received
4197498 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.08 | Trafic Permission & | 17 | Indirect Cost |  | 2023-06-05 | Trafic Perm-Station Fees |  |  |  | Indirect | Alrowad Construction_OU | 3892 | 1 | تسوية 67/68/69-م.سيارات النقل الثقيل | st-67/68/69-6-23 | Currency | 3892 | 23223931 | 2162 | Petty Cash | Mohamed Gamal Abdel Moneim Mohamed | تسوية 67/68/69-م.سيارات النقل الثقيل |  | Finacial | Received | 2023-06-05 | Accounted transaction received
4197532 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-06-05 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 9850 | 1 | تسويه ك /238-245-254-256-257-261-262-264-265-266- متنوعات | st-238-245-254-256-257-261-262-264-265-266-6-23 | Currency | 9850 | 23223931 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /238-245-254-256-257-261-262-264-265-266- متنوعات |  | Finacial | Received | 2023-06-05 | Accounted transaction received
4197533 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.13 | Maintenance | 17 | Indirect Cost |  | 2023-06-05 | Maintenance |  |  |  | Indirect | Alrowad Construction_OU | 3328.8 | 1 | تسويه ك /238-245-254-256-257-261-262-264-265-266- متنوعات | st-238-245-254-256-257-261-262-264-265-266-6-23 | Currency | 3328.8 | 23223931 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك /238-245-254-256-257-261-262-264-265-266- متنوعات |  | Finacial | Received | 2023-06-05 | Accounted transaction received
4223394 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.06 | Material Transportat | 17 | Indirect Cost |  | 2023-06-14 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1727 | 1 | نقل ثقيل 3 / 23- waldorf astoria | نقل ثقيل 3 / 23- waldorf astoria | Currency | 1727 | 23290543 | 3084 | محمد احمد محمد محمد | Rowad | نقل ثقيل 3 / 23- waldorf astoria |  | Finacial | Received | 2023-06-20 | Accounted transaction received
4185975 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 889.2 | 1 | سيليكون أبيض |  | Each | 12 | 62661122 |  |  |  | سيليكون أبيض | 200010000945 | Purchasing | Received | 2023-06-01 | Accounted transaction received
4185976 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 342 | 1 | مسمار 17 مم بالصامولة والوردتين طول 9 سم مجلفن |  | Each | 100 | 62661123 |  |  |  | مسمار 17 مم بالصامولة والوردتين طول 9 سم مجلفن | 060019000019 | MEP | Received | 2023-06-01 | Accounted transaction received
4185977 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 100.02 | 1 | كوس نحاس 6 م |  | Each | 41 | 62661124 |  |  |  | كوس نحاس 6 م | 030130100122 | MEP | Received | 2023-06-01 | Accounted transaction received
4185978 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 618.41 | 1 | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 |  | Each | 5 | 62661177 |  |  |  | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 | 030060100951 | MEP | Received | 2023-06-01 | Accounted transaction received
4185979 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1533.53 | 1 | Volume Dampers Size : 8" X 10" |  | Each | 3 | 62664014 |  |  |  | Volume Dampers Size : 8" X 10" | 060070700056 | MEP | Received | 2023-06-01 | Accounted transaction received
4185980 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2399.93 | 1 | Flexible air duct - insulated Diameter 6" |  | Meter | 40 | 62664015 |  |  |  | Flexible air duct - insulated Diameter 6" | 060041200015 | MEP | Received | 2023-06-01 | Accounted transaction received
4185981 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 390.89 | 1 | أدابتور UPVC لماسورة 25مم(اللون أبيض) |  | Each | 50 | 62664779 |  |  |  | أدابتور UPVC لماسورة 25مم(اللون أبيض) | 030010000097 | MEP | Received | 2023-06-01 | Accounted transaction received
4185982 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 584.82 | 1 | أفيز 25مم UPVC(اللون أبيض) |  | Each | 75 | 62664780 |  |  |  | أفيز 25مم UPVC(اللون أبيض) | 030010000107 | MEP | Received | 2023-06-01 | Accounted transaction received
4185983 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 478.8 | 1 | بواط واتر بروف بفتحات مقاس 10 × 10 × 5 سم |  | Each | 20 | 62664781 |  |  |  | بواط واتر بروف بفتحات مقاس 10 × 10 × 5 سم | 030010000180 | MEP | Received | 2023-06-01 | Accounted transaction received
4185984 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 198.48 | 1 | جلبة ماسورة EMT المقاس ¾ " |  | Each | 11 | 62664782 |  |  |  | جلبة ماسورة EMT المقاس ¾ " | 030020100021 | MEP | Received | 2023-06-01 | Accounted transaction received
4185985 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 945.29 | 1 | جلبة ماسورة EMT المقاس ½ 1 " |  | Each | 20 | 62664783 |  |  |  | جلبة ماسورة EMT المقاس ½ 1 " | 030020100024 | MEP | Received | 2023-06-01 | Accounted transaction received
4185986 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 328.86 | 1 | ادابتور فلكسبل 25 مم |  | Each | 55 | 62664787 |  |  |  | ادابتور فلكسبل 25 مم | 030010000141 | MEP | Received | 2023-06-01 | Accounted transaction received
4185987 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 620.25 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 5 | 62672460 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-06-01 | Accounted transaction received
4185988 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 620.25 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 5 | 62672461 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-06-01 | Accounted transaction received
4185989 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 892.67 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 5 | 62672462 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-06-01 | Accounted transaction received
4185990 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 88.77 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 5 | 62672463 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-06-01 | Accounted transaction received
4185991 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2066.72 | 1 | SHAVER SOCKET 230V/120-230V WITH EARTH CONNECTOR Code 572653 |  | Each | 3 | 62672464 |  |  |  | SHAVER SOCKET 230V/120-230V WITH EARTH CONNECTOR Code 572653 | 030060100178 | MEP | Received | 2023-06-01 | Accounted transaction received
4185992 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 326.6 | 1 | 576562 Code وش مربع فضي |  | Each | 6 | 62672465 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-06-01 | Accounted transaction received
4185993 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 227635.2 | 1 | Down Light IP 65 DAL 30250*035 AMBIANCE 100 DIRECTIONAL IP65 Recessed directional down lighter with satin silver reflector and white ceiling trim Overall diameter 100mm cut out diameter 90mm with PHILIPS LED Lamp 5.5W MR16 GU5.3, 2700K |  | Each | 64 | 62672466 |  |  |  | Down Light IP 65 DAL 30250*035 AMBIANCE 100 DIRECTIONAL IP65 Recessed directional down lighter with satin silver reflector and white ceiling trim Overall diameter 100mm cut out diameter 90mm with PHILIPS LED Lamp 5.5W MR16 GU5.3, 2700K | 030040700477 | MEP | Received | 2023-06-01 | Accounted transaction received
4185994 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 284.08 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 5 | 62672467 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-06-01 | Accounted transaction received
4185995 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 12320.38 | 1 | Floor box 6 Module with double socket, space for 2 data socket complete with back box , IP66, Part Number GESR2 - OBO Germany |  | Each | 1 | 62672468 |  |  |  | Floor box 6 Module with double socket, space for 2 data socket complete with back box , IP66, Part Number GESR2 - OBO Germany | 030060100992 | MEP | Received | 2023-06-01 | Accounted transaction received
4185996 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 161.42 | 1 | Mechanical anchor (Drop in anchor) size M8 |  | Each | 48 | 62672522 |  |  |  | Mechanical anchor (Drop in anchor) size M8 | 060190100002 | MEP | Received | 2023-06-01 | Accounted transaction received
4185997 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 162.45 | 1 | Mechanical anchor (Drop in anchor) size M10 |  | Each | 30 | 62672523 |  |  |  | Mechanical anchor (Drop in anchor) size M10 | 060190100003 | MEP | Received | 2023-06-01 | Accounted transaction received
4185998 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-05-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4520 | 1 | اسمنت اسود رتبة 42 |  | Ton | 2 | 62672540 |  |  |  | اسمنت اسود رتبة 42 | 140010000015 | Purchasing | Received | 2023-06-01 | Accounted transaction received
4185999 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 70 | 1 | COVER 4 M SQUARE 2X2 WHITE F 576000 Code 575080 |  | Each | 1 | 62672544 |  |  |  | COVER 4 M SQUARE 2X2 WHITE F 576000 Code 575080 | 030060100231 | MEP | Received | 2023-06-01 | Accounted transaction received
4186000 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-31 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2711.4 | 1 | THREADED ROD 8mm,length 2mt |  | Each | 171 | 62672738 |  |  |  | THREADED ROD 8mm,length 2mt | 030120300002 | MEP | Received | 2023-06-01 | Accounted transaction received
4189820 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.06 | Telephones | 17 | Indirect Cost |  | 2023-05-31 | Telephones |  |  |  | Indirect | Alrowad Construction_OU | -263.47 | 1 | قيد مرتبات شهر مايو 2023 | Salary-MAY-2023 | Currency | -263.47 | 23217446 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر مايو 2023 |  | Finacial | Received | 2023-06-04 | Accounted transaction received
4189860 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.02 | Health Care | 17 | Indirect Cost |  | 2023-05-31 | Medical Care |  |  |  | Direct Manpower | Alrowad Construction_OU | -3541.55 | 1 | قيد مرتبات شهر مايو 2023 | Salary-MAY-2023 | Currency | -3541.55 | 23217446 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر مايو 2023 |  | Finacial | Received | 2023-06-04 | Accounted transaction received
4189901 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.02 | Health Care | 17 | Indirect Cost |  | 2023-05-31 | Hirings Payrool |  |  |  | Indirect | Alrowad Construction_OU | -32922.63 | 1 | قيد مرتبات شهر مايو 2023 | Salary-MAY-2023 | Currency | -32922.63 | 23217446 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر مايو 2023 |  | Finacial | Received | 2023-06-04 | Accounted transaction received
4192657 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-31 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 900 | 1 |  | Adj.FA Depreciations May-23 | Currency | 900 | 23219586 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-06-04 | Accounted transaction received
4192658 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-31 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 2764.5 | 1 |  | Adj.FA Depreciations May-23 | Currency | 2764.5 | 23219586 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-06-04 | Accounted transaction received
4192659 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-31 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 4644.75 | 1 |  | Adj.FA Depreciations May-23 | Currency | 4644.75 | 23219586 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-06-04 | Accounted transaction received
4192660 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-31 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 995.14 | 1 |  | Adj.FA Depreciations May-23 | Currency | 995.14 | 23219586 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-06-04 | Accounted transaction received
4192661 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-31 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 14.98 | 1 |  | Adj.FA Depreciations May-23 | Currency | 14.98 | 23219586 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-06-04 | Accounted transaction received
4192662 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-31 | Electrical appliance Deprectia |  |  |  | Depreciation | Alrowad Construction_OU | 1316.5 | 1 |  | Adj.FA Depreciations May-23 | Currency | 1316.5 | 23219586 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-06-04 | Accounted transaction received
4192663 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-31 | Furniture Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 8324.58 | 1 |  | Adj.FA Depreciations May-23 | Currency | 8324.58 | 23219586 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-06-04 | Accounted transaction received
4192664 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-31 | Electrical appliance Deprectia |  |  |  | Depreciation | Alrowad Construction_OU | 3076.19 | 1 |  | Adj.FA Depreciations May-23 | Currency | 3076.19 | 23219586 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-06-04 | Accounted transaction received
4192665 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-31 | Computers Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 4832 | 1 |  | Adj.FA Depreciations May-23 | Currency | 4832 | 23219586 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-06-04 | Accounted transaction received
4192666 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-31 | Electrical appliance Deprectia |  |  |  | Depreciation | Alrowad Construction_OU | 2583.29 | 1 |  | Adj.FA Depreciations May-23 | Currency | 2583.29 | 23219586 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-06-04 | Accounted transaction received
4192937 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-31 | Consultancy |  |  |  | Indirect | Alrowad Construction_OU | 23056.83 | 1 |  | adj consultant fees to projects | Currency | 23056.83 | 23219586 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-06-04 | Accounted transaction received
4161448 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -501.78 | 1 | Metal Galvanized back box 7x14 cm with deep 47 mm |  | Each | -21 | 62482131 |  |  |  | Metal Galvanized back box 7x14 cm with deep 47 mm | 030069000027 | MEP | Received | 2023-05-29 | Accounted transaction received
4161449 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -2352.05 | 1 | Plate British standard Arteor - square - 3 modules - graphite - 575072 |  | Each | -40 | 62482132 |  |  |  | Plate British standard Arteor - square - 3 modules - graphite - 575072 | 030060100898 | MEP | Received | 2023-05-29 | Accounted transaction received
4161450 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -11958.17 | 1 | 3.5mm Jack socket Arteor - preterminated - 1 module - magnesium - 572591 |  | Each | -5 | 62482133 |  |  |  | 3.5mm Jack socket Arteor - preterminated - 1 module - magnesium - 572591 | 030060100899 | MEP | Received | 2023-05-29 | Accounted transaction received
4161451 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -417.55 | 1 | Plate Arteor -British standard - square - 1 module – graphite - 575122 |  | Each | -5 | 62482134 |  |  |  | Plate Arteor -British standard - square - 1 module – graphite - 575122 | 030060100901 | MEP | Received | 2023-05-29 | Accounted transaction received
4161452 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -715.35 | 1 | HD15 PRE-CONNEC.1M MG.ARTEOR S - 572597 (INDIA) |  | Each | -1 | 62482135 |  |  |  | HD15 PRE-CONNEC.1M MG.ARTEOR S - 572597 (INDIA) | 030060100909 | MEP | Received | 2023-05-29 | Accounted transaction received
4161453 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -1094.4 | 1 | Honeywell thermostat model (WS8B4WB/U) |  | Each | -2 | 62482136 |  |  |  | Honeywell thermostat model (WS8B4WB/U) | 060081900004 | MEP | Received | 2023-05-29 | Accounted transaction received
4161454 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -5400.18 | 1 | Category 6A Field Terminated Plug and Boot with Black Latch Protector Clip |  | Each | -60 | 62482137 |  |  |  | Category 6A Field Terminated Plug and Boot with Black Latch Protector Clip | 031030000447 | MEP | Received | 2023-05-29 | Accounted transaction received
4161455 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -1204.66 | 1 | SPLASH PROOF COVER Code : 617636 |  | Each | -12 | 62482138 |  |  |  | SPLASH PROOF COVER Code : 617636 | 030060100927 | MEP | Received | 2023-05-29 | Accounted transaction received
4161456 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -515.09 | 1 | DS , 4 pole , 40A , 400V , abs enclosure IP 65 Code : KEM 440U Y/R ABS |  | Each | -1 | 62482139 |  |  |  | DS , 4 pole , 40A , 400V , abs enclosure IP 65 Code : KEM 440U Y/R ABS | 030060200073 | MEP | Received | 2023-05-29 | Accounted transaction received
4161457 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -350 | 1 | High Definition 4K HDMI Audio Video Cable Length 3 meter |  | Each | -1 | 62482140 |  |  |  | High Definition 4K HDMI Audio Video Cable Length 3 meter | 031060000032 | MEP | Received | 2023-05-29 | Accounted transaction received
4161458 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -275 | 1 | High Definition 4K HDMI Audio Video Cable Length 5 meter |  | Each | -1 | 62482141 |  |  |  | High Definition 4K HDMI Audio Video Cable Length 5 meter | 031060000033 | MEP | Received | 2023-05-29 | Accounted transaction received
4161459 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -23884.91 | 1 | Attenuator 30W, Model No. AT-4030B-EB |  | Each | -16 | 62482142 |  |  |  | Attenuator 30W, Model No. AT-4030B-EB | 031070000016 | MEP | Received | 2023-05-29 | Accounted transaction received
4161460 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -450.71 | 1 | 1G 20A DP SWT + NEON + E WH - 617671 |  | Each | -4 | 62482143 |  |  |  | 1G 20A DP SWT + NEON + E WH - 617671 | 030060100942 | MEP | Received | 2023-05-29 | Accounted transaction received
4161461 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -130.01 | 1 | Double pole switches 32 A – 250V~ 1 gang 1?way switch + led power indicator - 617629 |  | Each | -1 | 62482144 |  |  |  | Double pole switches 32 A – 250V~ 1 gang 1?way switch + led power indicator - 617629 | 030060100943 | MEP | Received | 2023-05-29 | Accounted transaction received
4161462 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -909.06 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | -16 | 62482145 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-05-29 | Accounted transaction received
4161463 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -632.14 | 1 | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 |  | Each | -8 | 62482146 |  |  |  | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 | 030060100956 | MEP | Received | 2023-05-29 | Accounted transaction received
4161464 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -7545.66 | 1 | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 |  | Each | -10 | 62482147 |  |  |  | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 | 030060100957 | MEP | Received | 2023-05-29 | Accounted transaction received
4161465 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -175 | 1 | High Definition 4K HDMI Audio Video Cable Length 10 meter |  | Each | -1 | 62482148 |  |  |  | High Definition 4K HDMI Audio Video Cable Length 10 meter | 031060000057 | MEP | Received | 2023-05-29 | Accounted transaction received
4161466 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-05-28 | Materials |  |  |  | Materials | Alrowad Construction_OU | -20999.94 | 1 | Socket outlet Plexo IP44 - 32 A - 3P+N+E 230 V~ - surface mounting - grey - Legrand 55877 |  | Each | -10 | 62482149 |  |  |  | Socket outlet Plexo IP44 - 32 A - 3P+N+E 230 V~ - surface mounting - grey - Legrand 55877 | 030060100993 | MEP | Received | 2023-05-29 | Accounted transaction received
4161467 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-28 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 627 | 1 | Threaded Flange 2'' UL listed, FM approved |  | Each | 2 | 62485880 |  |  |  | Threaded Flange 2'' UL listed, FM approved | 060011500329 | MEP | Received | 2023-05-29 | Accounted transaction received
4161468 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-05-28 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 5937.12 | 1 | فلانشة حديد3'' - PN 16 |  | Each | 14 | 62485881 |  |  |  | فلانشة حديد3'' - PN 16 | 060011800045 | MEP | Received | 2023-05-29 | Accounted transaction received
4161469 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-28 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 446.88 | 1 | Pull Handle-Yale-35-9004-8820-19-31-50-630-305X75 MM |  | Each | 1 | 62485934 |  |  |  | Pull Handle-Yale-35-9004-8820-19-31-50-630-305X75 MM | 250010000295 | Procurement | Received | 2023-05-29 | Accounted transaction received
4161470 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-05-28 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 615.6 | 1 | Kick Plate ,, France Metal ,, ST.ST ,, Up to 200 x 1000 mm |  | Each | 1 | 62485935 |  |  |  | Kick Plate ,, France Metal ,, ST.ST ,, Up to 200 x 1000 mm | 250010000569 | Procurement | Received | 2023-05-29 | Accounted transaction received
4161471 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1368 | 1 | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) |  | Meter | 60 | 62485952 |  |  |  | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) | 030010000052 | MEP | Received | 2023-05-29 | Accounted transaction received
4161472 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 95.09 | 1 | mosaic adapter code 69580 |  | Each | 1 | 62485953 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-05-29 | Accounted transaction received
4161473 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 80.25 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 1 | 62485954 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-05-29 | Accounted transaction received
4161474 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 90 | 1 | Category 6A Field Terminated Plug and Boot with Black Latch Protector Clip |  | Each | 1 | 62485955 |  |  |  | Category 6A Field Terminated Plug and Boot with Black Latch Protector Clip | 031030000447 | MEP | Received | 2023-05-29 | Accounted transaction received
4161475 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2864.18 | 1 | P17 TEMPRA COMBINED UNITS 2P+E Code : 56634 |  | Each | 1 | 62485956 |  |  |  | P17 TEMPRA COMBINED UNITS 2P+E Code : 56634 | 030060100937 | MEP | Received | 2023-05-29 | Accounted transaction received
4161476 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-05-28 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 413.44 | 1 | CEILING MOUNT SPEAKER, Model No. PC-648R |  | Each | 1 | 62485957 |  |  |  | CEILING MOUNT SPEAKER, Model No. PC-648R | 031070000015 | MEP | Received | 2023-05-29 | Accounted transaction received
4197895 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-06-06 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 810 | 1 | 1.3 80895/2 |  | Currency | 1.35 |  | 12635 | خالد محمد نصر الدين احمد-ذاتى |  | 1.3 80895/2 |  | Finacial | Received | 2023-06-06 | Accounted transaction received
4198755 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.03 | Hirings daily wages | 17 | Indirect Cost |  | 2023-06-07 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 34492.48 | 1 | يوميات عماله م10-astoria cairo | يوميات عماله م10-astoria cairo | Currency | 34492.48 | 23233623 | 12252 | حامد حسين احمد خالد – ذاتى | rowad | يوميات عماله م10-astoria cairo |  | Finacial | Received | 2023-06-07 | Accounted transaction received
4201382 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.13 | Maintenance | 17 | Indirect Cost |  | 2023-06-07 | Car Maintenance |  |  |  | Transportation | Alrowad Construction_OU | 9852.71 | 1 | استوريا السبع ف/9450 18/5 | 9450 | Currency | 9852.71 | 23238163 | 929 | السبع اوتو سيرفيس | Egypt | استوريا السبع ف/9450 18/5 |  | Finacial | Received | 2023-06-08 | Accounted transaction received
4220921 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 275.04 | 1 | SWITCH 20AX 1 WAY 1 MOD Code 572509 |  | Each | 2 | 63098058 |  |  |  | SWITCH 20AX 1 WAY 1 MOD Code 572509 | 030060100048 | MEP | Received | 2023-06-20 | Accounted transaction received
4220922 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 91.21 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 2 | 63098059 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-06-20 | Accounted transaction received
4220923 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 715.73 | 1 | mosaic adapter code 69580 |  | Each | 2 | 63098060 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-06-20 | Accounted transaction received
4220924 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-20 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 127.86 | 1 | S/M BOX 1-GANG GREY Code (69651 ) |  | Each | 2 | 63098061 |  |  |  | S/M BOX 1-GANG GREY Code (69651 ) | 030060100728 | MEP | Received | 2023-06-20 | Accounted transaction received
4220925 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-06-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 14820 | 1 | Action floor spring max 180kg for Glass doors, brand Stanley |  | Each | 2 | 63098157 |  |  |  | Action floor spring max 180kg for Glass doors, brand Stanley | 310010000018 | Fleets | Received | 2023-06-20 | Accounted transaction received
4220926 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-06-20 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 22543.5 | 1 | Trim around Mirrors |  | Meter | 35 | 63098158 |  |  |  | Trim around Mirrors | 250010001935 | Procurement | Received | 2023-06-20 | Accounted transaction received
4220927 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 6498 | 1 | HDMI PRE-CONN 1M Code 572596 |  | Each | 2 | 62923496 |  |  |  | HDMI PRE-CONN 1M Code 572596 | 030060100165 | MEP | Received | 2023-06-20 | Accounted transaction received
4220928 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 151.29 | 1 | 10AX 2 WAY SWITCH 2 MOD Code 572535 |  | Each | 2 | 62923497 |  |  |  | 10AX 2 WAY SWITCH 2 MOD Code 572535 | 030060100125 | MEP | Received | 2023-06-20 | Accounted transaction received
4220929 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1390.15 | 1 | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 |  | Each | 1 | 62923498 |  |  |  | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 | 030060100182 | MEP | Received | 2023-06-20 | Accounted transaction received
4220930 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1009.41 | 1 | CARRIER PLATE SYNERGY code 730094 |  | Each | 15 | 62923499 |  |  |  | CARRIER PLATE SYNERGY code 730094 | 030060100534 | MEP | Received | 2023-06-20 | Accounted transaction received
4220931 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 490.85 | 1 | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 |  | Each | 1 | 62923500 |  |  |  | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 | 030060100572 | MEP | Received | 2023-06-20 | Accounted transaction received
4220932 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 223.58 | 1 | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS |  | Each | 1 | 62923501 |  |  |  | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS | 030060100617 | MEP | Received | 2023-06-20 | Accounted transaction received
4220933 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 15104.36 | 1 | Wallbox with 1 Chassis Space ( 3-CAB7B ) |  | Each | 1 | 62923502 |  |  |  | Wallbox with 1 Chassis Space ( 3-CAB7B ) | 031010000133 | MEP | Received | 2023-06-20 | Accounted transaction received
4220934 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 6153.63 | 1 | Battery Cabinet 14" x 18.25"x 7.25" - 40AH max ( BC-1 ) |  | Each | 1 | 62923503 |  |  |  | Battery Cabinet 14" x 18.25"x 7.25" - 40AH max ( BC-1 ) | 031010000137 | MEP | Received | 2023-06-20 | Accounted transaction received
4220935 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 58.8 | 1 | Plate British standard Arteor - square - 3 modules - graphite - 575072 |  | Each | 1 | 62923504 |  |  |  | Plate British standard Arteor - square - 3 modules - graphite - 575072 | 030060100898 | MEP | Received | 2023-06-20 | Accounted transaction received
4220936 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-12 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 11155 | 1 | 10 Amp Booster Power Supply, 220V ( BPS10A/230 ) |  | Each | 1 | 62923505 |  |  |  | 10 Amp Booster Power Supply, 220V ( BPS10A/230 ) | 031010000261 | MEP | Received | 2023-06-20 | Accounted transaction received
4220937 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-12 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 22230 | 1 | Action floor spring max 180kg for Glass doors, brand Stanley |  | Each | 3 | 62923515 |  |  |  | Action floor spring max 180kg for Glass doors, brand Stanley | 310010000018 | Fleets | Received | 2023-06-20 | Accounted transaction received
4220938 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1000.93 | 1 | نهاية بياض 10 مم |  | Each | 35 | 62944631 |  |  |  | نهاية بياض 10 مم | 200010000462 | Purchasing | Received | 2023-06-20 | Accounted transaction received
4220939 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2694.96 | 1 | سلك نحاس مصمت مقاس 16 مم اللون أصفر × أخضر (cu/pvc) جهد (750/450) |  | Meter | 50 | 62959312 |  |  |  | سلك نحاس مصمت مقاس 16 مم اللون أصفر × أخضر (cu/pvc) جهد (750/450) | 030030100325 | MEP | Received | 2023-06-20 | Accounted transaction received
4220940 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 364.74 | 1 | ماسورة صلب مجلفن EMT المقاس 2 " طول الماسورة 3.05 |  | Meter | 0.81 | 62959313 |  |  |  | ماسورة صلب مجلفن EMT المقاس 2 " طول الماسورة 3.05 | 030020100005 | MEP | Received | 2023-06-20 | Accounted transaction received
4220941 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 7316.1 | 1 | كابل نحاس ترمو ضغط منخفض مقاس 4 × 16 مم (xlpe/pvc) |  | Meter | 31 | 62959314 |  |  |  | كابل نحاس ترمو ضغط منخفض مقاس 4 × 16 مم (xlpe/pvc) | 030030100008 | MEP | Received | 2023-06-20 | Accounted transaction received
4220942 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 378.23 | 1 | 10AX 2 WAY SWITCH 2 MOD Code 572535 |  | Each | 5 | 62959315 |  |  |  | 10AX 2 WAY SWITCH 2 MOD Code 572535 | 030060100125 | MEP | Received | 2023-06-20 | Accounted transaction received
4220943 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 456.04 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 10 | 62959316 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-06-20 | Accounted transaction received
4220944 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5539.58 | 1 | Hot Dip Galvanized cable trunk100x100mm thickness 1.5mm with cover 1.25mm thickness |  | Meter | 12 | 62959317 |  |  |  | Hot Dip Galvanized cable trunk100x100mm thickness 1.5mm with cover 1.25mm thickness | 030100500001 | MEP | Received | 2023-06-20 | Accounted transaction received
4220945 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 156.75 | 1 | STEEL ANCHOR 10MM |  | Each | 50 | 62959318 |  |  |  | STEEL ANCHOR 10MM | 030120100009 | MEP | Received | 2023-06-20 | Accounted transaction received
4220946 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 168.15 | 1 | Mechanical anchor (Drop in anchor) size M8 |  | Each | 50 | 62959319 |  |  |  | Mechanical anchor (Drop in anchor) size M8 | 060190100002 | MEP | Received | 2023-06-20 | Accounted transaction received
4220947 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 294.12 | 1 | Threaded rod size M8 |  | Each | 10 | 62959320 |  |  |  | Threaded rod size M8 | 060190300002 | MEP | Received | 2023-06-20 | Accounted transaction received
4220948 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 490.85 | 1 | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 |  | Each | 1 | 62959321 |  |  |  | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 | 030060100572 | MEP | Received | 2023-06-20 | Accounted transaction received
4220949 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 670.74 | 1 | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS |  | Each | 3 | 62959322 |  |  |  | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS | 030060100617 | MEP | Received | 2023-06-20 | Accounted transaction received
4220950 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1592.14 | 1 | LID & TRIM 3 COMPARTMENTS GREY ( Legrand 689631 ) |  | Each | 2 | 62959324 |  |  |  | LID & TRIM 3 COMPARTMENTS GREY ( Legrand 689631 ) | 030060100738 | MEP | Received | 2023-06-20 | Accounted transaction received
4220951 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5600 | 1 | Copper Cable UTP Cat6A, 4Pair, LSZH, Roll= 305Mt. |  | Each | 1 | 62959326 |  |  |  | Copper Cable UTP Cat6A, 4Pair, LSZH, Roll= 305Mt. | 031030000359 | MEP | Received | 2023-06-20 | Accounted transaction received
4220952 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 13873.64 | 1 | 15/75 cd Speaker/Strobe, 70V - 4" Cone, Round - WHITE - 965-7A-4RW |  | Each | 8 | 62959327 |  |  |  | 15/75 cd Speaker/Strobe, 70V - 4" Cone, Round - WHITE - 965-7A-4RW | 031010000241 | MEP | Received | 2023-06-20 | Accounted transaction received
4220953 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 889.2 | 1 | لاكور بواط على فليكسبل EMT المقاس 3/4 " |  | Each | 30 | 62959328 |  |  |  | لاكور بواط على فليكسبل EMT المقاس 3/4 " | 030020100214 | MEP | Received | 2023-06-20 | Accounted transaction received
4220954 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 585 | 1 | ProLink Cate6 UTP Toolless KEYSTONE JACK With Shutter |  | Each | 13 | 62959329 |  |  |  | ProLink Cate6 UTP Toolless KEYSTONE JACK With Shutter | 031030000575 | MEP | Received | 2023-06-20 | Accounted transaction received
4220955 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-06-14 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 11010.12 | 1 | Privacy Door Latch Brand Welder part # 43702424 Finish Silver |  | Each | 22 | 62962378 |  |  |  | Privacy Door Latch Brand Welder part # 43702424 Finish Silver | 250010001658 | Procurement | Received | 2023-06-20 | Accounted transaction received
4220956 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 417.19 | 1 | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) |  | Meter | 24 | 62976604 |  |  |  | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) | 030010000052 | MEP | Received | 2023-06-20 | Accounted transaction received
4220957 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 738.58 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 25مم وقطر خارجى 31.1مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 2 | 62976605 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 25مم وقطر خارجى 31.1مم طول اللفه 30 متر(اللون رمادى) | 030010000062 | MEP | Received | 2023-06-20 | Accounted transaction received
4220958 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1158.48 | 1 | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 |  | Each | 10 | 62976606 |  |  |  | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 | 030060100114 | MEP | Received | 2023-06-20 | Accounted transaction received
4220959 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 14663.42 | 1 | UNIVERSAL DIMMER W/O NEUTR 400 Code 572739 |  | Each | 5 | 62976607 |  |  |  | UNIVERSAL DIMMER W/O NEUTR 400 Code 572739 | 030060100176 | MEP | Received | 2023-06-20 | Accounted transaction received
4220960 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 8340.92 | 1 | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 |  | Each | 6 | 62976608 |  |  |  | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 | 030060100182 | MEP | Received | 2023-06-20 | Accounted transaction received
4220961 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 10712.91 | 1 | Central Processor Unit Module ( 3-CPU3 ) |  | Each | 1 | 62976609 |  |  |  | Central Processor Unit Module ( 3-CPU3 ) | 031010000126 | MEP | Received | 2023-06-20 | Accounted transaction received
4220962 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5762.03 | 1 | Liquid Crystal Display Module ( 3-LCD ) |  | Each | 1 | 62976610 |  |  |  | Liquid Crystal Display Module ( 3-LCD ) | 031010000127 | MEP | Received | 2023-06-20 | Accounted transaction received
4220963 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 20922.34 | 1 | Primary Power Supply with Local Rail Module, 230V ( 3-PPS/M-230 ) |  | Each | 1 | 62976611 |  |  |  | Primary Power Supply with Local Rail Module, 230V ( 3-PPS/M-230 ) | 031010000128 | MEP | Received | 2023-06-20 | Accounted transaction received
4220964 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 30880.03 | 1 | Signature Dual Driver Controller ( 3-SDDC1 ) |  | Each | 1 | 62976612 |  |  |  | Signature Dual Driver Controller ( 3-SDDC1 ) | 031010000129 | MEP | Received | 2023-06-20 | Accounted transaction received
4220965 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 7440.3 | 1 | Chassis Assembly ( 3-CHAS7 ) |  | Each | 1 | 62976613 |  |  |  | Chassis Assembly ( 3-CHAS7 ) | 031010000132 | MEP | Received | 2023-06-20 | Accounted transaction received
4220966 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 15663.78 | 1 | Door for CAB7B Series Wallbox ( 3-CAB7D ) |  | Each | 1 | 62976614 |  |  |  | Door for CAB7B Series Wallbox ( 3-CAB7D ) | 031010000134 | MEP | Received | 2023-06-20 | Accounted transaction received
4220967 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1734.2 | 1 | 15/75 cd Speaker/Strobe, 70V - 4" Cone, Round - WHITE - 965-7A-4RW |  | Each | 1 | 62976615 |  |  |  | 15/75 cd Speaker/Strobe, 70V - 4" Cone, Round - WHITE - 965-7A-4RW | 031010000241 | MEP | Received | 2023-06-20 | Accounted transaction received
4220968 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 8841.04 | 1 | Network Communications Card, Class A ( 3-RS485A ) |  | Each | 1 | 62976616 |  |  |  | Network Communications Card, Class A ( 3-RS485A ) | 031010000259 | MEP | Received | 2023-06-20 | Accounted transaction received
4220969 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 28698.29 | 1 | Zoned Amplifier, 40 Watt, Class A/B ( 3-ZA40A ) |  | Each | 2 | 62976617 |  |  |  | Zoned Amplifier, 40 Watt, Class A/B ( 3-ZA40A ) | 031010000260 | MEP | Received | 2023-06-20 | Accounted transaction received
4220970 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-15 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 675.01 | 1 | ProLink Cate6 UTP Toolless KEYSTONE JACK With Shutter |  | Each | 15 | 62976618 |  |  |  | ProLink Cate6 UTP Toolless KEYSTONE JACK With Shutter | 031030000575 | MEP | Received | 2023-06-20 | Accounted transaction received
4220971 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 807.53 | 1 | CARRIER PLATE SYNERGY code 730094 |  | Each | 12 | 63038631 |  |  |  | CARRIER PLATE SYNERGY code 730094 | 030060100534 | MEP | Received | 2023-06-20 | Accounted transaction received
4220972 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1391.42 | 1 | Signature Detector Base ( SIGA-SB ) |  | Each | 10 | 63038632 |  |  |  | Signature Detector Base ( SIGA-SB ) | 031010000145 | MEP | Received | 2023-06-20 | Accounted transaction received
4220973 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 401.79 | 1 | Detector Base with Isolator ( SIGA-IB ) |  | Each | 1 | 63038633 |  |  |  | Detector Base with Isolator ( SIGA-IB ) | 031010000146 | MEP | Received | 2023-06-20 | Accounted transaction received
4220974 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 9135.5 | 1 | Intelligent multi-criteria optical smoke and Heat detector - SIGA-OSHD |  | Each | 12 | 63038634 |  |  |  | Intelligent multi-criteria optical smoke and Heat detector - SIGA-OSHD | 031010000240 | MEP | Received | 2023-06-20 | Accounted transaction received
4220975 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 5202.61 | 1 | 15/75 cd Speaker/Strobe, 70V - 4" Cone, Round - WHITE - 965-7A-4RW |  | Each | 3 | 63038635 |  |  |  | 15/75 cd Speaker/Strobe, 70V - 4" Cone, Round - WHITE - 965-7A-4RW | 031010000241 | MEP | Received | 2023-06-20 | Accounted transaction received
4220976 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-06-18 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 39.4 | 1 | فيست برتقالي |  | Each | 1 | 63047279 |  |  |  | فيست برتقالي | 010020000008 | Safety | Received | 2023-06-20 | Accounted transaction received
4220977 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1693.7 | 1 | كابل نحاس ترمو ضغط منخفض مقاس 4 × 10 مم (pvc/pvc) |  | Meter | 12 | 63047404 |  |  |  | كابل نحاس ترمو ضغط منخفض مقاس 4 × 10 مم (pvc/pvc) | 030030100005 | MEP | Received | 2023-06-20 | Accounted transaction received
4220978 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1736.7 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 14 | 63047405 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-06-20 | Accounted transaction received
4220979 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1299.12 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 6 | 63047406 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-06-20 | Accounted transaction received
4220980 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 170 | 1 | عود دكت 1.5 *1.5 سم |  | Each | 10 | 63047407 |  |  |  | عود دكت 1.5 *1.5 سم | 060010100816 | MEP | Received | 2023-06-20 | Accounted transaction received
4220981 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 741 | 1 | سيلكون فواصل |  | Each | 10 | 63047408 |  |  |  | سيلكون فواصل | 330040000882 | Equipment | Received | 2023-06-20 | Accounted transaction received
4220982 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5010.13 | 1 | mosaic adapter code 69580 |  | Each | 14 | 63047409 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-06-20 | Accounted transaction received
4220983 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 17108.55 | 1 | Hot dip Galvanized after fabrication, Cable Tray Trunk Type, 200mm Width, 100mm height of Side,1.5mm thickness,10mmReturnFlange ,3000mm Length. |  | Meter | 87 | 63047410 |  |  |  | Hot dip Galvanized after fabrication, Cable Tray Trunk Type, 200mm Width, 100mm height of Side,1.5mm thickness,10mmReturnFlange ,3000mm Length. | 030101400048 | MEP | Received | 2023-06-20 | Accounted transaction received
4220984 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1123.47 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 14 | 63047411 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-06-20 | Accounted transaction received
4220985 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 7476.61 | 1 | Single Input (Riser) Module (for siren) (SIGA-CC1 ) |  | Each | 4 | 63047412 |  |  |  | Single Input (Riser) Module (for siren) (SIGA-CC1 ) | 031010000147 | MEP | Received | 2023-06-20 | Accounted transaction received
4220986 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 14349.14 | 1 | Zoned Amplifier, 40 Watt, Class A/B ( 3-ZA40A ) |  | Each | 1 | 63047413 |  |  |  | Zoned Amplifier, 40 Watt, Class A/B ( 3-ZA40A ) | 031010000260 | MEP | Received | 2023-06-20 | Accounted transaction received
4220987 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 395.08 | 1 | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 |  | Each | 5 | 63047414 |  |  |  | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 | 030060100956 | MEP | Received | 2023-06-20 | Accounted transaction received
4220988 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 360 | 1 | ProLink Cate6 UTP Toolless KEYSTONE JACK With Shutter |  | Each | 8 | 63047415 |  |  |  | ProLink Cate6 UTP Toolless KEYSTONE JACK With Shutter | 031030000575 | MEP | Received | 2023-06-20 | Accounted transaction received
4220989 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 675.01 | 1 | ProLink Cate6 UTP Toolless KEYSTONE JACK With Shutter |  | Each | 15 | 63047416 |  |  |  | ProLink Cate6 UTP Toolless KEYSTONE JACK With Shutter | 031030000575 | MEP | Received | 2023-06-20 | Accounted transaction received
4220990 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 13612.4 | 1 | Dual Input Signal Module With Class A Operation ( Siga-CC2A ) |  | Each | 4 | 63047417 |  |  |  | Dual Input Signal Module With Class A Operation ( Siga-CC2A ) | 031010000280 | MEP | Received | 2023-06-20 | Accounted transaction received
4220991 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1082.6 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 5 | 63048203 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-06-20 | Accounted transaction received
4220992 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 272.17 | 1 | 576562 Code وش مربع فضي |  | Each | 5 | 63048204 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-06-20 | Accounted transaction received
4220993 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 294.01 | 1 | Plate British standard Arteor - square - 3 modules - graphite - 575072 |  | Each | 5 | 63048205 |  |  |  | Plate British standard Arteor - square - 3 modules - graphite - 575072 | 030060100898 | MEP | Received | 2023-06-20 | Accounted transaction received
4220994 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2391.63 | 1 | 3.5mm Jack socket Arteor - preterminated - 1 module - magnesium - 572591 |  | Each | 1 | 63048206 |  |  |  | 3.5mm Jack socket Arteor - preterminated - 1 module - magnesium - 572591 | 030060100899 | MEP | Received | 2023-06-20 | Accounted transaction received
4220995 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-18 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4234.78 | 1 | V-Plex Hold-Up switch with stainless steel cover (polling loop only)( 269SN) |  | Each | 1 | 63048207 |  |  |  | V-Plex Hold-Up switch with stainless steel cover (polling loop only)( 269SN) | 031010000301 | MEP | Received | 2023-06-20 | Accounted transaction received
4220996 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1240.5 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 10 | 62827890 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-06-20 | Accounted transaction received
4220997 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 230.18 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 5 | 62827891 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-06-20 | Accounted transaction received
4220998 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1082.6 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 5 | 62827892 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-06-20 | Accounted transaction received
4220999 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 215.05 | 1 | Metal Galvanized back box 7x14 cm with deep 47 mm |  | Each | 9 | 62827893 |  |  |  | Metal Galvanized back box 7x14 cm with deep 47 mm | 030069000027 | MEP | Received | 2023-06-20 | Accounted transaction received
4221000 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 540.02 | 1 | Category 6A Field Terminated Plug and Boot with Black Latch Protector Clip |  | Each | 6 | 62827894 |  |  |  | Category 6A Field Terminated Plug and Boot with Black Latch Protector Clip | 031030000447 | MEP | Received | 2023-06-20 | Accounted transaction received
4221001 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 27803.08 | 1 | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 |  | Each | 20 | 62828145 |  |  |  | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 | 030060100182 | MEP | Received | 2023-06-20 | Accounted transaction received
4221002 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 496.2 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 4 | 62835737 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-06-20 | Accounted transaction received
4221003 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2280.2 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 50 | 62835738 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-06-20 | Accounted transaction received
4221004 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 184.15 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 4 | 62835739 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-06-20 | Accounted transaction received
4221005 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1390.15 | 1 | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 |  | Each | 1 | 62835740 |  |  |  | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 | 030060100182 | MEP | Received | 2023-06-20 | Accounted transaction received
4221006 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 163.3 | 1 | 576562 Code وش مربع فضي |  | Each | 3 | 62835741 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-06-20 | Accounted transaction received
4221007 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 108.87 | 1 | 576562 Code وش مربع فضي |  | Each | 2 | 62835742 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-06-20 | Accounted transaction received
4221008 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1094.4 | 1 | Honeywell thermostat model (WS8B4WB/U) |  | Each | 2 | 62835743 |  |  |  | Honeywell thermostat model (WS8B4WB/U) | 060081900004 | MEP | Received | 2023-06-20 | Accounted transaction received
4221009 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 494.72 | 1 | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 |  | Each | 4 | 62835744 |  |  |  | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 | 030060100951 | MEP | Received | 2023-06-20 | Accounted transaction received
4221010 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3018.26 | 1 | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 |  | Each | 4 | 62835745 |  |  |  | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 | 030060100957 | MEP | Received | 2023-06-20 | Accounted transaction received
4221011 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 49052.88 | 1 | Vista Turbo partitioned commercial burglary alarm panel (VISTA-250BPT) |  | Each | 1 | 62835746 |  |  |  | Vista Turbo partitioned commercial burglary alarm panel (VISTA-250BPT) | 031010000300 | MEP | Received | 2023-06-20 | Accounted transaction received
4221012 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4234.78 | 1 | V-Plex Hold-Up switch with stainless steel cover (polling loop only)( 269SN) |  | Each | 1 | 62835747 |  |  |  | V-Plex Hold-Up switch with stainless steel cover (polling loop only)( 269SN) | 031010000301 | MEP | Received | 2023-06-20 | Accounted transaction received
4221013 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4587.68 | 1 | Siren with strobe (Texecom) |  | Each | 1 | 62835748 |  |  |  | Siren with strobe (Texecom) | 031010000302 | MEP | Received | 2023-06-20 | Accounted transaction received
4221014 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-06-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 16319.97 | 1 | Hardware Accessories for Wooden Doors Concealed hinge system & Bathroom Concealed Hinges Simonswerk completely concealed hinge system with load capacity 80.0 kg two hinges per door leaf (1x2m) |  | Each | 6 | 62863911 |  |  |  | Hardware Accessories for Wooden Doors Concealed hinge system & Bathroom Concealed Hinges Simonswerk completely concealed hinge system with load capacity 80.0 kg two hinges per door leaf (1x2m) | 250010001515 | Procurement | Received | 2023-06-20 | Accounted transaction received
4221015 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 50.09 | 1 | أفيز أثنين جناح لماسورة EMT المقاس ¾ " |  | Each | 20 | 62863970 |  |  |  | أفيز أثنين جناح لماسورة EMT المقاس ¾ " | 030020100033 | MEP | Received | 2023-06-20 | Accounted transaction received
4221016 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 248.1 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 2 | 62863971 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-06-20 | Accounted transaction received
4221017 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 535.6 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 3 | 62863972 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-06-20 | Accounted transaction received
4221018 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 46.04 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 1 | 62863973 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-06-20 | Accounted transaction received
4221019 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 618.41 | 1 | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 |  | Each | 5 | 62863974 |  |  |  | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 | 030060100951 | MEP | Received | 2023-06-20 | Accounted transaction received
4221020 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-06-10 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3072.3 | 1 | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² |  | Kilogram | 55 | 62878196 |  |  |  | تصنيع مجاري هواء مستطليلة من الصاج المجلفن تصنيع و تجمييع جلفنة 275 كجم/ م² | 060040200001 | MEP | Received | 2023-06-20 | Accounted transaction received
4221021 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.02.00 | HVAC Works(G) | 15 | MECHANICAL WORKS |  | 2023-06-10 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 228 | 1 | HVAC DUCT Square to Round , 10" ? 8" * 14 |  | Each | 2 | 62878197 |  |  |  | HVAC DUCT Square to Round , 10" ? 8" * 14 | 060040800043 | MEP | Received | 2023-06-20 | Accounted transaction received
4221022 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-06-10 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 5439.99 | 1 | Hardware Accessories for Wooden Doors Concealed hinge system & Bathroom Concealed Hinges Simonswerk completely concealed hinge system with load capacity 80.0 kg two hinges per door leaf (1x2m) |  | Each | 2 | 62878290 |  |  |  | Hardware Accessories for Wooden Doors Concealed hinge system & Bathroom Concealed Hinges Simonswerk completely concealed hinge system with load capacity 80.0 kg two hinges per door leaf (1x2m) | 250010001515 | Procurement | Received | 2023-06-20 | Accounted transaction received
4221023 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-06-10 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 32639.93 | 1 | Hardware Accessories for Wooden Doors Concealed hinge system & Bathroom Concealed Hinges Simonswerk completely concealed hinge system with load capacity 80.0 kg two hinges per door leaf (1x2m) |  | Each | 12 | 62878314 |  |  |  | Hardware Accessories for Wooden Doors Concealed hinge system & Bathroom Concealed Hinges Simonswerk completely concealed hinge system with load capacity 80.0 kg two hinges per door leaf (1x2m) | 250010001515 | Procurement | Received | 2023-06-20 | Accounted transaction received
4221024 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-06-10 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 16356.15 | 1 | Supply Concealed Door closer to 80KG for wooden doors, including any requirements to complete the works as per consultant's approval & submittal approval. Consort CDCC3 Silver |  | Each | 2 | 62878315 |  |  |  | Supply Concealed Door closer to 80KG for wooden doors, including any requirements to complete the works as per consultant's approval & submittal approval. Consort CDCC3 Silver | 250010001608 | Procurement | Received | 2023-06-20 | Accounted transaction received
4221025 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-06-10 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 198 | 1 | Hardware Accessories for Wooden Doors Double Cylinder TESA Security TE-5 Double Cylinder 35x35mm. 5 Spring Loaded Anti pick Pins. Made to EN-1303 Regulation. |  | Each | 1 | 62878474 |  |  |  | Hardware Accessories for Wooden Doors Double Cylinder TESA Security TE-5 Double Cylinder 35x35mm. 5 Spring Loaded Anti pick Pins. Made to EN-1303 Regulation. | 250010001519 | Procurement | Received | 2023-06-20 | Accounted transaction received
4221026 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-06-10 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 378 | 1 | Hardware Accessories for Wooden Doors TESA TE5 Thumb turn Cylinder 35x35mm. 5 Spring Loaded Anti pick Pins + 1 SENSOR in the key. Certified according to EN1303. |  | Each | 1 | 62878475 |  |  |  | Hardware Accessories for Wooden Doors TESA TE5 Thumb turn Cylinder 35x35mm. 5 Spring Loaded Anti pick Pins + 1 SENSOR in the key. Certified according to EN1303. | 250010001522 | Procurement | Received | 2023-06-20 | Accounted transaction received
4221027 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-10 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 380.35 | 1 | mosaic adapter code 69580 |  | Each | 4 | 62878597 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-06-20 | Accounted transaction received
4221028 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-10 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 320.99 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 4 | 62878598 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-06-20 | Accounted transaction received
4221029 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-10 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 903.16 | 1 | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser |  | Each | 2 | 62878599 |  |  |  | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser | 030040700472 | MEP | Received | 2023-06-20 | Accounted transaction received
4221030 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-10 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 88.92 | 1 | لاكور بواط على فليكسبل EMT المقاس 3/4 " |  | Each | 3 | 62878600 |  |  |  | لاكور بواط على فليكسبل EMT المقاس 3/4 " | 030020100214 | MEP | Received | 2023-06-20 | Accounted transaction received
4221031 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-10 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 82.08 | 1 | لاكور بواط على فليكسبل EMT المقاس 1" |  | Each | 2 | 62878601 |  |  |  | لاكور بواط على فليكسبل EMT المقاس 1" | 030020100215 | MEP | Received | 2023-06-20 | Accounted transaction received
4221032 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-10 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 35 | 1 | 576540 Code وش 1 فتحة |  | Each | 1 | 62880440 |  |  |  | 576540 Code وش 1 فتحة | 030060100266 | MEP | Received | 2023-06-20 | Accounted transaction received
4221033 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-10 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 255.72 | 1 | S/M BOX 1-GANG GREY Code (69651 ) |  | Each | 4 | 62880441 |  |  |  | S/M BOX 1-GANG GREY Code (69651 ) | 030060100728 | MEP | Received | 2023-06-20 | Accounted transaction received
4221034 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-10 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3980.34 | 1 | LID & TRIM 3 COMPARTMENTS GREY ( Legrand 689631 ) |  | Each | 5 | 62880442 |  |  |  | LID & TRIM 3 COMPARTMENTS GREY ( Legrand 689631 ) | 030060100738 | MEP | Received | 2023-06-20 | Accounted transaction received
4221035 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-10 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 451.58 | 1 | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser |  | Each | 1 | 62880443 |  |  |  | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser | 030040700472 | MEP | Received | 2023-06-20 | Accounted transaction received
4221036 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-10 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1240.5 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 10 | 62886818 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-06-20 | Accounted transaction received
4221037 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-10 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 230.18 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 5 | 62886819 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-06-20 | Accounted transaction received
4221038 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-10 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 119.47 | 1 | Metal Galvanized back box 7x14 cm with deep 47 mm |  | Each | 5 | 62886820 |  |  |  | Metal Galvanized back box 7x14 cm with deep 47 mm | 030069000027 | MEP | Received | 2023-06-20 | Accounted transaction received
4221039 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-06-10 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 7410 | 1 | Action floor spring max 180kg for Glass doors, brand Stanley |  | Each | 1 | 62886827 |  |  |  | Action floor spring max 180kg for Glass doors, brand Stanley | 310010000018 | Fleets | Received | 2023-06-20 | Accounted transaction received
4194414 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-31 | Computers Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 1320.95 | 1 |  | Adj.Depreciation To projects may-23 | Currency | 1320.95 | 23221112 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-06-04 | Accounted transaction received
4194451 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-31 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 3685.52 | 1 |  | Adj.Depreciation To projects may-23 | Currency | 3685.52 | 23221112 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-06-04 | Accounted transaction received
4194488 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-31 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 9321.02 | 1 |  | Adj.Depreciation To projects may-23 | Currency | 9321.02 | 23221112 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-06-04 | Accounted transaction received
4194525 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-31 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 5422.65 | 1 |  | Adj.Depreciation To projects may-23 | Currency | 5422.65 | 23221112 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-06-04 | Accounted transaction received
4194562 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-31 | Furniture Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 505.02 | 1 |  | Adj.Depreciation To projects may-23 | Currency | 505.02 | 23221112 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-06-04 | Accounted transaction received
4194599 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-05-31 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 745.56 | 1 |  | Adj.Depreciation To projects may-23 | Currency | 745.56 | 23221112 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-06-04 | Accounted transaction received
4223071 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-06-01 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | -153450 | 1 | يوميات عماله الفتره 2 ش 5 التقديري | يوميات عماله الفتره 2 ش 5 التقديري | Currency | -153450 | 23290543 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 2 ش 5 التقديري |  | Finacial | Received | 2023-06-20 | Accounted transaction received
4223525 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.06 | Material Transportat | 17 | Indirect Cost |  | 2023-06-14 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 6867 | 1 | نقل ثقيل 4/23- waldorf astoria | نقل ثقيل 4/23- waldorf astoria | Currency | 6867 | 23290543 | 4551 | الزمزم للنقل بالسيارات وتجارة وتوريدات مواد البناء | rowad | نقل ثقيل 4/23- waldorf astoria |  | Finacial | Received | 2023-06-20 | Accounted transaction received
4223740 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-06-14 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 160005 | 1 | يوميات عماله الفتره 2 ش 5 الفعلي | يوميات عماله الفتره 2 ش 5 الفعلي | Currency | 160005 | 23290543 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 2 ش 5 الفعلي |  | Finacial | Received | 2023-06-20 | Accounted transaction received
4223848 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.08 | Trafic Permission & | 17 | Indirect Cost |  | 2023-06-15 | Trafic Perm-Station Fees |  |  |  | Indirect | Alrowad Construction_OU | 3460 | 1 | تسوية70-م.سيارات النقل الثقيل | st-70-6-23 | Currency | 3460 | 23290543 | 2162 | Petty Cash | Mohamed Gamal Abdel Moneim Mohamed | تسوية70-م.سيارات النقل الثقيل |  | Finacial | Received | 2023-06-20 | Accounted transaction received
4223896 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.06 | Material Transportat | 17 | Indirect Cost |  | 2023-06-15 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4387.6 | 1 | نقل ثقيل شهر 3/23- waldorf astoria | نقل ثقيل شهر 3/23- waldorf astoria | Currency | 4387.6 | 23290543 | 5119 | مكتب الحاتم للنقل | rowad | نقل ثقيل شهر 3/23- waldorf astoria |  | Finacial | Received | 2023-06-20 | Accounted transaction received
4223949 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.06 | Material Transportat | 17 | Indirect Cost |  | 2023-06-18 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5047 | 1 | نقل ثقيل 3/ 23 - waldorf astoria | نقل ثقيل 3/ 23 - waldorf astoria | Currency | 5047 | 23290543 | 710 | المصطفي للنقل (مصطفي سعد محمد ) | Egypt | نقل ثقيل 3/ 23 - waldorf astoria |  | Finacial | Received | 2023-06-20 | Accounted transaction received
4224063 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.08 | Trafic Permission & | 17 | Indirect Cost |  | 2023-06-20 | Trafic Perm-Station Fees |  |  |  | Indirect | Alrowad Construction_OU | 4030 | 1 | تسوية71/72-م.سيارات الثقيل | st-71/72-6-23 | Currency | 4030 | 23290543 | 2162 | Petty Cash | Mohamed Gamal Abdel Moneim Mohamed | تسوية71/72-م.سيارات الثقيل |  | Finacial | Received | 2023-06-20 | Accounted transaction received
4233221 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 19380 | 1 | 1.5 61155/8 |  | Currency | 0.2 |  | 10847 | برونكس لتشغيل المعادن |  | 1.5 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233222 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 115200 | 1 | 1.12 61155/8 |  | Currency | 7.2 |  | 10847 | برونكس لتشغيل المعادن |  | 1.12 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233223 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 58000 | 1 | 1.18 61155/8 |  | Currency | 0.2 |  | 10847 | برونكس لتشغيل المعادن |  | 1.18 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233224 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 39922.8 | 1 | 1.20 61155/8 |  | Currency | 34 |  | 10847 | برونكس لتشغيل المعادن |  | 1.20 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233225 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 592.8 | 1 | 1.50 61155/8 |  | Currency | 1 |  | 10847 | برونكس لتشغيل المعادن |  | 1.50 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233226 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2964 | 1 | 1.52 61155/8 |  | Currency | 5 |  | 10847 | برونكس لتشغيل المعادن |  | 1.52 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233227 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1778.4 | 1 | 1.54 61155/8 |  | Currency | 3 |  | 10847 | برونكس لتشغيل المعادن |  | 1.54 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233228 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1778.4 | 1 | 1.56 61155/8 |  | Currency | 3 |  | 10847 | برونكس لتشغيل المعادن |  | 1.56 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233229 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4959 | 1 | 1.57 61155/8 |  | Currency | 15 |  | 10847 | برونكس لتشغيل المعادن |  | 1.57 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233230 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1778.4 | 1 | 1.58 61155/8 |  | Currency | 3 |  | 10847 | برونكس لتشغيل المعادن |  | 1.58 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233231 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4959 | 1 | 1.61 61155/8 |  | Currency | 15 |  | 10847 | برونكس لتشغيل المعادن |  | 1.61 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233232 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3306 | 1 | 1.62 61155/8 |  | Currency | 10 |  | 10847 | برونكس لتشغيل المعادن |  | 1.62 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233233 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3306 | 1 | 1.63 61155/8 |  | Currency | 10 |  | 10847 | برونكس لتشغيل المعادن |  | 1.63 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233234 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3306 | 1 | 1.64 61155/8 |  | Currency | 10 |  | 10847 | برونكس لتشغيل المعادن |  | 1.64 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233235 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1185.6 | 1 | 1.65 61155/8 |  | Currency | 2 |  | 10847 | برونكس لتشغيل المعادن |  | 1.65 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233236 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1185.6 | 1 | 1.66 61155/8 |  | Currency | 2 |  | 10847 | برونكس لتشغيل المعادن |  | 1.66 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233237 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1185.6 | 1 | 1.67 61155/8 |  | Currency | 2 |  | 10847 | برونكس لتشغيل المعادن |  | 1.67 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233238 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 8664 | 1 | 1.68 61155/8 |  | Currency | 8 |  | 10847 | برونكس لتشغيل المعادن |  | 1.68 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233239 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 25992 | 1 | 1.69 61155/8 |  | Currency | 6 |  | 10847 | برونكس لتشغيل المعادن |  | 1.69 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233241 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 12996 | 1 | 1.71 61155/8 |  | Currency | 3 |  | 10847 | برونكس لتشغيل المعادن |  | 1.71 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233242 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3249 | 1 | 1.72 61155/8 |  | Currency | 3 |  | 10847 | برونكس لتشغيل المعادن |  | 1.72 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233243 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 12996 | 1 | 1.74 61155/8 |  | Currency | 3 |  | 10847 | برونكس لتشغيل المعادن |  | 1.74 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233244 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 25992 | 1 | 1.75 61155/8 |  | Currency | 6 |  | 10847 | برونكس لتشغيل المعادن |  | 1.75 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233245 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3249 | 1 | 1.76 61155/8 |  | Currency | 0.75 |  | 10847 | برونكس لتشغيل المعادن |  | 1.76 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233246 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3556.8 | 1 | 1.79 61155/8 |  | Currency | 6 |  | 10847 | برونكس لتشغيل المعادن |  | 1.79 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233247 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 14227.2 | 1 | 1.80 61155/8 |  | Currency | 24 |  | 10847 | برونكس لتشغيل المعادن |  | 1.80 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233248 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 24375 | 1 | 2.3 61155/8 |  | Currency | 75 |  | 10847 | برونكس لتشغيل المعادن |  | 2.3 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233249 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4742.4 | 1 | 2.4 61155/8 |  | Currency | 8 |  | 10847 | برونكس لتشغيل المعادن |  | 2.4 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233250 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4959 | 1 | 2.5 61155/8 |  | Currency | 15 |  | 10847 | برونكس لتشغيل المعادن |  | 2.5 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233251 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1778.4 | 1 | 2.8 61155/8 |  | Currency | 3 |  | 10847 | برونكس لتشغيل المعادن |  | 2.8 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233317 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.08.00 | Gypsum Board(G) | 9 | FINISHES WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -8370 | 1 | 3.1 80045/6 |  | Currency | -6.2 |  | 12187 | اركاد للترميم |  | 3.1 80045/6 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233252 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1778.4 | 1 | 2.9 61155/8 |  | Currency | 3 |  | 10847 | برونكس لتشغيل المعادن |  | 2.9 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233253 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1778.4 | 1 | 2.10 61155/8 |  | Currency | 3 |  | 10847 | برونكس لتشغيل المعادن |  | 2.10 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233254 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1185.6 | 1 | 2.12 61155/8 |  | Currency | 2 |  | 10847 | برونكس لتشغيل المعادن |  | 2.12 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233255 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 12996 | 1 | 2.13 61155/8 |  | Currency | 3 |  | 10847 | برونكس لتشغيل المعادن |  | 2.13 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233256 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1931.86 | 1 | LABOUR_OFFICE 61155/8 |  | Currency | -1931.86 |  | 10847 | برونكس لتشغيل المعادن |  | LABOUR_OFFICE 61155/8 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233297 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.03.02 | Repair | 2 | SITE WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 21936 | 1 | 3.1 64209/7 |  | Currency | 100 |  | 8108 | سامى عياد فهيم حليم |  | 3.1 64209/7 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233300 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.03.02 | Repair | 2 | SITE WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 360 | 1 | 1.4 64209/7 |  | Currency | 0 |  | 8108 | سامى عياد فهيم حليم |  | 1.4 64209/7 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233302 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.03.02 | Repair | 2 | SITE WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5107.64 | 1 | 1.6 64209/7 |  | Currency | 0 |  | 8108 | سامى عياد فهيم حليم |  | 1.6 64209/7 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233303 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.03.02 | Repair | 2 | SITE WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7200 | 1 | 2.1 64209/7 |  | Currency | 0 |  | 8108 | سامى عياد فهيم حليم |  | 2.1 64209/7 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233304 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.03.02 | Repair | 2 | SITE WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -155.72 | 1 | LABOUR_OFFICE 64209/7 |  | Currency | -155.72 |  | 8108 | سامى عياد فهيم حليم |  | LABOUR_OFFICE 64209/7 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233305 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.03.02 | Repair | 2 | SITE WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3071.04 | 1 | 3.1 64209/7 |  | Currency | 0 |  | 8108 | سامى عياد فهيم حليم |  | 3.1 64209/7 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233308 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.03.02 | Repair | 2 | SITE WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 50.4 | 1 | 1.4 64209/7 |  | Currency | 0 |  | 8108 | سامى عياد فهيم حليم |  | 1.4 64209/7 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233310 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.03.02 | Repair | 2 | SITE WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 715.07 | 1 | 1.6 64209/7 |  | Currency | 0 |  | 8108 | سامى عياد فهيم حليم |  | 1.6 64209/7 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233311 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.03.02 | Repair | 2 | SITE WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1008 | 1 | 2.1 64209/7 |  | Currency | 0 |  | 8108 | سامى عياد فهيم حليم |  | 2.1 64209/7 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233316 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.08.00 | Gypsum Board(G) | 9 | FINISHES WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 60900 | 1 | 1.1 80045/6 |  | Currency | 84 |  | 12187 | اركاد للترميم |  | 1.1 80045/6 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233318 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.08.00 | Gypsum Board(G) | 9 | FINISHES WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -2415 | 1 | 4.1 80045/6 |  | Currency | -2.3 |  | 12187 | اركاد للترميم |  | 4.1 80045/6 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233319 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.08.00 | Gypsum Board(G) | 9 | FINISHES WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 6000 | 1 | 5.1 80045/6 |  | Currency | 0 |  | 12187 | اركاد للترميم |  | 5.1 80045/6 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233320 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.08.00 | Gypsum Board(G) | 9 | FINISHES WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 23100 | 1 | 6.1 80045/6 |  | Currency | 84 |  | 12187 | اركاد للترميم |  | 6.1 80045/6 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4233321 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.08.00 | Gypsum Board(G) | 9 | FINISHES WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -356.47 | 1 | LABOUR_OFFICE 80045/6 |  | Currency | -356.47 |  | 12187 | اركاد للترميم |  | LABOUR_OFFICE 80045/6 |  | Finacial | Received | 2023-06-22 | Accounted transaction received
4234206 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1158.48 | 1 | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 |  | Each | 10 | 63126866 |  |  |  | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 | 030060100114 | MEP | Received | 2023-06-22 | Accounted transaction received
4234207 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 992.4 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 8 | 63126867 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-06-22 | Accounted transaction received
4234208 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5865.37 | 1 | UNIVERSAL DIMMER W/O NEUTR 400 Code 572739 |  | Each | 2 | 63126868 |  |  |  | UNIVERSAL DIMMER W/O NEUTR 400 Code 572739 | 030060100176 | MEP | Received | 2023-06-22 | Accounted transaction received
4234209 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2862.93 | 1 | mosaic adapter code 69580 |  | Each | 8 | 63126869 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-06-22 | Accounted transaction received
4234210 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 895.07 | 1 | Single Input Module ( SIGA-CT1 ) |  | Each | 1 | 63126870 |  |  |  | Single Input Module ( SIGA-CT1 ) | 031010000262 | MEP | Received | 2023-06-22 | Accounted transaction received
4234211 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1509.13 | 1 | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 |  | Each | 2 | 63126871 |  |  |  | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 | 030060100957 | MEP | Received | 2023-06-22 | Accounted transaction received
4234212 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 912.08 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 20 | 63127145 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-06-22 | Accounted transaction received
4234213 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 35 | 1 | PLATE 2SQ MOD F-G WHITE Code 576560 |  | Each | 1 | 63127146 |  |  |  | PLATE 2SQ MOD F-G WHITE Code 576560 | 030060100267 | MEP | Received | 2023-06-22 | Accounted transaction received
4234214 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2165.2 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 10 | 63127147 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-06-22 | Accounted transaction received
4234215 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 544.33 | 1 | 576562 Code وش مربع فضي |  | Each | 10 | 63127148 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-06-22 | Accounted transaction received
4234216 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 70 | 1 | COVER 4 M SQUARE 2X2 WHITE F 576000 Code 575080 |  | Each | 1 | 63127149 |  |  |  | COVER 4 M SQUARE 2X2 WHITE F 576000 Code 575080 | 030060100231 | MEP | Received | 2023-06-22 | Accounted transaction received
4234217 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 588.01 | 1 | Plate British standard Arteor - square - 3 modules - graphite - 575072 |  | Each | 10 | 63127150 |  |  |  | Plate British standard Arteor - square - 3 modules - graphite - 575072 | 030060100898 | MEP | Received | 2023-06-22 | Accounted transaction received
4234218 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 23916.34 | 1 | 3.5mm Jack socket Arteor - preterminated - 1 module - magnesium - 572591 |  | Each | 10 | 63127151 |  |  |  | 3.5mm Jack socket Arteor - preterminated - 1 module - magnesium - 572591 | 030060100899 | MEP | Received | 2023-06-22 | Accounted transaction received
4239093 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | 54150 | 1 | 67059/11 |  | Currency | 54150 |  | 4820 | سيجاب للهندسه والتجاره |  | 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239095 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 54 | 1 | 2.2.001 67059/11 |  | Currency | 6 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.001 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239096 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 54 | 1 | 2.2.002 67059/11 |  | Currency | 6 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.002 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239097 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 270 | 1 | 2.2.003 67059/11 |  | Currency | 30 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.003 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239098 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 60 | 1 | 2.2.004 67059/11 |  | Currency | 6 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.004 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239099 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 70 | 1 | 2.2.005 67059/11 |  | Currency | 7 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.005 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239100 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 25 | 1 | 2.2.006 67059/11 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.006 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239101 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 37.5 | 1 | 2.2.007 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.007 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239102 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 60 | 1 | 2.2.008 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.008 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239103 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 525 | 1 | 2.2.009 67059/11 |  | Currency | 7 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.009 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239104 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 800 | 1 | 2.2.01 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.01 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239105 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9.5 | 1 | 2.2.013 67059/11 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.013 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239106 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9.5 | 1 | 2.2.014 67059/11 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.014 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239107 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 33.25 | 1 | 2.2.015 67059/11 |  | Currency | 7 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.015 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239108 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 19 | 1 | 2.2.016 67059/11 |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.016 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239109 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 114 | 1 | 2.2.017 67059/11 |  | Currency | 24 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.017 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239110 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 33.25 | 1 | 2.2.018 67059/11 |  | Currency | 7 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.018 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239111 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2736 | 1 | 2.2.02 67059/11 |  | Currency | 40 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.02 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239112 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2052 | 1 | 4.4.01 67059/11 |  | Currency | 30 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.01 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239113 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 900 | 1 | 4.4.014 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.014 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239114 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2120.4 | 1 | 4.4.011 67059/11 |  | Currency | 31 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.011 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239115 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 18 | 1 | 4.4.022 67059/11 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.022 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239116 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 40 | 1 | 4.4.023 67059/11 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.023 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239117 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 972 | 1 | 5.5.022 67059/11 |  | Currency | 9 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.022 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239118 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -875 | 1 | 5.5.024 67059/11 |  | Currency | -10 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.024 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239119 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3477 | 1 | 5.5.05 67059/11 |  | Currency | 5 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.05 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239120 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1710 | 1 | 6.6.003 67059/11 |  | Currency | 10 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.003 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239121 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 115.3 | 1 | 6.6.018 67059/11 |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.018 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239122 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5130 | 1 | 6.6.019 67059/11 |  | Currency | 12 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.019 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239123 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1895.25 | 1 | 6.6.032 67059/11 |  | Currency | 21 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.032 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239124 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9.5 | 1 | 6.6.035 67059/11 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.035 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239125 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 339.15 | 1 | 6.6.038 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.038 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239126 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 40.57 | 1 | 6.6.039 67059/11 |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.039 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239127 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 37.94 | 1 | 6.6.04 67059/11 |  | Currency | 12 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.04 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239128 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7.63 | 1 | 6.6.041 67059/11 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.041 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239129 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 15.75 | 1 | 6.6.043 67059/11 |  | Currency | 3 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.043 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239130 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 27.79 | 1 | 6.6.044 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.044 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239131 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1130.5 | 1 | 6.6.051 67059/11 |  | Currency | 10 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.051 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239132 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2185 | 1 | 6.6.055 67059/11 |  | Currency | 46 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.055 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239133 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 71.25 | 1 | 6.6.061 67059/11 |  | Currency | 15 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.061 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239134 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 52.25 | 1 | 6.6.063 67059/11 |  | Currency | 11 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.063 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239135 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 19 | 1 | 6.6.064 67059/11 |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.064 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239136 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -2052 | 1 | 7.7.001 67059/11 |  | Currency | -9 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.001 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239137 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1710 | 1 | 7.7.009 67059/11 |  | Currency | 10 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.009 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239138 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 315.88 | 1 | 7.7.039 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.039 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239139 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 60.07 | 1 | 7.7.041 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.041 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239140 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 199.45 | 1 | 7.7.045 67059/11 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.045 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239141 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 361 | 1 | 7.7.056 67059/11 |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.056 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239142 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1522.5 | 1 | 7.7.057 67059/11 |  | Currency | 31 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.057 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239143 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 361 | 1 | 7.7.066 67059/11 |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.066 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239144 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9636.71 | 1 | 8.8.036 67059/11 |  | Currency | 30 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.036 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239145 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4500 | 1 | 8.8.087 67059/11 |  | Currency | 100 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.087 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239146 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9609.82 | 1 | 8.8.098 67059/11 |  | Currency | 44 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.098 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239147 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 36008.5 | 1 | 11.6 67059/11 |  | Currency | 530 |  | 4820 | سيجاب للهندسه والتجاره |  | 11.6 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239148 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3828 | 1 | 12.6 67059/11 |  | Currency | 29 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.6 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239149 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2464 | 1 | 12.7 67059/11 |  | Currency | 14 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.7 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239150 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 960 | 1 | 12.10 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.10 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239151 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 30000 | 1 | 12.11 67059/11 |  | Currency | 750 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.11 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239152 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 132000 | 1 | 12.12 67059/11 |  | Currency | 11000 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.12 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239153 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1872 | 1 | 12.16 67059/11 |  | Currency | 78 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.16 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239154 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2496 | 1 | 12.17 67059/11 |  | Currency | 78 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.17 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239155 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4056 | 1 | 12.18 67059/11 |  | Currency | 78 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.18 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239156 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 13728 | 1 | 12.19 67059/11 |  | Currency | 78 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.19 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239157 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 800 | 1 | 12.25 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.25 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239158 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 800 | 1 | 12.26 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.26 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239159 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 800 | 1 | 12.27 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.27 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239160 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 800 | 1 | 12.28 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.28 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239161 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 800 | 1 | 12.29 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.29 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239162 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 800 | 1 | 12.30 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.30 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239163 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2400 | 1 | 12.32 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.32 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239164 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 960 | 1 | 12.33 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.33 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239165 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 960 | 1 | 12.34 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.34 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239166 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 840 | 1 | 5.5.023 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.023 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239167 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 12408 | 1 | 12.1 67059/11 |  | Currency | 282 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.1 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239168 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1324.8 | 1 | 12.2 67059/11 |  | Currency | 24 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.2 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239169 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2656 | 1 | 12.3 67059/11 |  | Currency | 40 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.3 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239170 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2992 | 1 | 12.4 67059/11 |  | Currency | 34 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.4 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239171 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5740.8 | 1 | 12.5 67059/11 |  | Currency | 52 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.5 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239172 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | -17000 | 1 | 67059/11 |  | Currency | -17000 |  | 4820 | سيجاب للهندسه والتجاره |  | 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239173 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1418.04 | 1 | LABOUR_OFFICE 67059/11 |  | Currency | -1418.04 |  | 4820 | سيجاب للهندسه والتجاره |  | LABOUR_OFFICE 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239255 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | 28400 | 1 | 62820/14 |  | Currency | 28400 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 62820/14 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239256 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 24268.64 | 1 | 1.1 62820/14 |  | Currency | 2.59 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 1.1 62820/14 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239257 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2951.59 | 1 | 1.2 62820/14 |  | Currency | 0.21 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 1.2 62820/14 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239259 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 263.24 | 1 | 2.19 62820/14 |  | Currency | 21 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.19 62820/14 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239260 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2440.16 | 1 | 2.24 62820/14 |  | Currency | 8 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.24 62820/14 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239261 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 167.13 | 1 | 2.25 62820/14 |  | Currency | 10 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.25 62820/14 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239262 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 25.07 | 1 | 2.26 62820/14 |  | Currency | 1 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.26 62820/14 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239263 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 350.98 | 1 | 2.27 62820/14 |  | Currency | 21 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.27 62820/14 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239264 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 200.56 | 1 | 2.29 62820/14 |  | Currency | 16 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.29 62820/14 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239265 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 162.96 | 1 | 2.31 62820/14 |  | Currency | 13 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.31 62820/14 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239266 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 116.99 | 1 | 2.36 62820/14 |  | Currency | 7 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.36 62820/14 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239267 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 31.34 | 1 | 2.47 62820/14 |  | Currency | 5 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.47 62820/14 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239268 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -263.24 | 1 | 2.63 62820/14 |  | Currency | -28 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.63 62820/14 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239269 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -950.57 | 1 | 2.64 62820/14 |  | Currency | -70 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.64 62820/14 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239270 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -83.57 | 1 | 2.65 62820/14 |  | Currency | -4 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.65 62820/14 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239271 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 39485.39 | 1 | 2.1 62820/14 |  | Currency | 54 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 2.1 62820/14 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239272 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | -3647 | 1 | 62820/14 |  | Currency | -3647 |  | 11007 | الاسراء للمقاولات والتوريدات |  | 62820/14 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239273 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -311.25 | 1 | LABOUR_OFFICE 62820/14 |  | Currency | -311.25 |  | 11007 | الاسراء للمقاولات والتوريدات |  | LABOUR_OFFICE 62820/14 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239290 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | 54150 | 1 | 67059/11 |  | Currency | 54150 |  | 4820 | سيجاب للهندسه والتجاره |  | 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239292 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 54 | 1 | 2.2.001 67059/11 |  | Currency | 6 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.001 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239293 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 54 | 1 | 2.2.002 67059/11 |  | Currency | 6 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.002 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239294 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 270 | 1 | 2.2.003 67059/11 |  | Currency | 30 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.003 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239295 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 60 | 1 | 2.2.004 67059/11 |  | Currency | 6 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.004 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239296 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 70 | 1 | 2.2.005 67059/11 |  | Currency | 7 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.005 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239297 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 25 | 1 | 2.2.006 67059/11 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.006 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239298 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 37.5 | 1 | 2.2.007 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.007 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239299 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 60 | 1 | 2.2.008 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.008 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239300 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 525 | 1 | 2.2.009 67059/11 |  | Currency | 7 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.009 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239301 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 800 | 1 | 2.2.01 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.01 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239302 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9.5 | 1 | 2.2.013 67059/11 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.013 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239303 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9.5 | 1 | 2.2.014 67059/11 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.014 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239304 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 33.25 | 1 | 2.2.015 67059/11 |  | Currency | 7 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.015 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239305 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 19 | 1 | 2.2.016 67059/11 |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.016 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239306 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 114 | 1 | 2.2.017 67059/11 |  | Currency | 24 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.017 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239307 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 33.25 | 1 | 2.2.018 67059/11 |  | Currency | 7 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.018 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239308 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2736 | 1 | 2.2.02 67059/11 |  | Currency | 40 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.02 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239309 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2052 | 1 | 4.4.01 67059/11 |  | Currency | 30 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.01 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239310 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 900 | 1 | 4.4.014 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.014 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239311 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2120.4 | 1 | 4.4.011 67059/11 |  | Currency | 31 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.011 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239312 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 18 | 1 | 4.4.022 67059/11 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.022 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239313 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 40 | 1 | 4.4.023 67059/11 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.023 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239314 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 972 | 1 | 5.5.022 67059/11 |  | Currency | 9 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.022 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239315 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -875 | 1 | 5.5.024 67059/11 |  | Currency | -10 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.024 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239316 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3477 | 1 | 5.5.05 67059/11 |  | Currency | 5 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.05 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239317 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1710 | 1 | 6.6.003 67059/11 |  | Currency | 10 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.003 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239318 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 115.3 | 1 | 6.6.018 67059/11 |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.018 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239319 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5130 | 1 | 6.6.019 67059/11 |  | Currency | 12 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.019 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239320 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1895.25 | 1 | 6.6.032 67059/11 |  | Currency | 21 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.032 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239321 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9.5 | 1 | 6.6.035 67059/11 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.035 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239322 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 339.15 | 1 | 6.6.038 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.038 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239323 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 40.57 | 1 | 6.6.039 67059/11 |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.039 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239324 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 37.94 | 1 | 6.6.04 67059/11 |  | Currency | 12 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.04 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239325 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 7.63 | 1 | 6.6.041 67059/11 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.041 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239326 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 15.75 | 1 | 6.6.043 67059/11 |  | Currency | 3 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.043 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239327 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 27.79 | 1 | 6.6.044 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.044 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4221040 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5580.19 | 1 | Category 6A Field Terminated Plug and Boot with Black Latch Protector Clip |  | Each | 62 | 62898352 |  |  |  | Category 6A Field Terminated Plug and Boot with Black Latch Protector Clip | 031030000447 | MEP | Received | 2023-06-20 | Accounted transaction received
4221041 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 315 | 1 | ProLink Cate6 UTP Toolless KEYSTONE JACK With Shutter |  | Each | 7 | 62898353 |  |  |  | ProLink Cate6 UTP Toolless KEYSTONE JACK With Shutter | 031030000575 | MEP | Received | 2023-06-20 | Accounted transaction received
4221042 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 10543.8 | 1 | CD/MP3 Player with AM/FM Tuner, with USB/SD, 1U height, Model No. T-2221 |  | Each | 1 | 62898510 |  |  |  | CD/MP3 Player with AM/FM Tuner, with USB/SD, 1U height, Model No. T-2221 | 031070000021 | MEP | Received | 2023-06-20 | Accounted transaction received
4221043 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 23415.21 | 1 | 4 input - 1 x 120W DriveCore Mixer-Amp, Fanless, 4ohm/8ohm/70V/100V, 1U Half-Rack, Mounting kit (EU Version) , Model No. NCSMA1120-U-EU - JBL |  | Each | 1 | 62898511 |  |  |  | 4 input - 1 x 120W DriveCore Mixer-Amp, Fanless, 4ohm/8ohm/70V/100V, 1U Half-Rack, Mounting kit (EU Version) , Model No. NCSMA1120-U-EU - JBL | 031060000081 | MEP | Received | 2023-06-20 | Accounted transaction received
4221044 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1429.81 | 1 | Threaded Mechanical Tee 2.5''*1.25'' UL listed, FM approved |  | Each | 2 | 62902998 |  |  |  | Threaded Mechanical Tee 2.5''*1.25'' UL listed, FM approved | 060011500214 | MEP | Received | 2023-06-20 | Accounted transaction received
4221045 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 482.11 | 1 | flexible coupling 2.50'' UL listed, FM approved |  | Each | 1 | 62902999 |  |  |  | flexible coupling 2.50'' UL listed, FM approved | 060011500034 | MEP | Received | 2023-06-20 | Accounted transaction received
4221046 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 820.39 | 1 | Grooved Reducer 4''*2.5'' UL listed, FM approved |  | Each | 1 | 62903000 |  |  |  | Grooved Reducer 4''*2.5'' UL listed, FM approved | 060011500372 | MEP | Received | 2023-06-20 | Accounted transaction received
4221047 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2561.71 | 1 | Grooved Mechanical Tee 3''*1.5'' UL listed, FM approved |  | Each | 2 | 62903001 |  |  |  | Grooved Mechanical Tee 3''*1.5'' UL listed, FM approved | 060011500256 | MEP | Received | 2023-06-20 | Accounted transaction received
4221048 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 196.01 | 1 | threaded couplings size 2" UL LISTED,FM APPROVED |  | Each | 3 | 62903002 |  |  |  | threaded couplings size 2" UL LISTED,FM APPROVED | 060010140483 | MEP | Received | 2023-06-20 | Accounted transaction received
4221049 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 69.54 | 1 | threaded bushings size 1.25"*1" UL LISTED,FM APPROVED |  | Each | 1 | 62903003 |  |  |  | threaded bushings size 1.25"*1" UL LISTED,FM APPROVED | 060010140400 | MEP | Received | 2023-06-20 | Accounted transaction received
4221050 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 248.1 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 2 | 62903032 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-06-20 | Accounted transaction received
4221051 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1984.8 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 16 | 62903033 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-06-20 | Accounted transaction received
4221052 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 568.14 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 32 | 62903034 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-06-20 | Accounted transaction received
4221053 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1363.6 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 24 | 62903035 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-06-20 | Accounted transaction received
4221054 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 12073.06 | 1 | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 |  | Each | 16 | 62903036 |  |  |  | 2USB CHARG 2M A+C 3A 15 WMG - Legrand 572577 | 030060100957 | MEP | Received | 2023-06-20 | Accounted transaction received
4221055 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1745.98 | 1 | كورنشة فيوتك 4 سم |  | Meter | 24 | 62906442 |  |  |  | كورنشة فيوتك 4 سم | 050020000004 | Purchasing | Received | 2023-06-20 | Accounted transaction received
4221056 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 570 | 1 | تيب دوكو |  | Each | 20 | 62906454 |  |  |  | تيب دوكو | 200010000048 | Purchasing | Received | 2023-06-20 | Accounted transaction received
4221057 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 205.2 | 1 | جلبة لحام 3/4بوصة |  | Each | 15 | 62906455 |  |  |  | جلبة لحام 3/4بوصة | 240020000041 | MEP | Received | 2023-06-20 | Accounted transaction received
4221058 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 518.7 | 1 | كوع لحام PPR قطر 20 مم |  | Each | 35 | 62906456 |  |  |  | كوع لحام PPR قطر 20 مم | 060010300036 | MEP | Received | 2023-06-20 | Accounted transaction received
4221059 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 85 | 1 | Supply of 0.5" Escutcheon Recessed Two Pieces , RELIABLE , Model G/F1 ,Chrome Finished. |  | Each | 1 | 62906457 |  |  |  | Supply of 0.5" Escutcheon Recessed Two Pieces , RELIABLE , Model G/F1 ,Chrome Finished. | 060090300002 | MEP | Received | 2023-06-20 | Accounted transaction received
4221060 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1852.5 | 1 | سيلكون فواصل |  | Each | 25 | 62906458 |  |  |  | سيلكون فواصل | 330040000882 | Equipment | Received | 2023-06-20 | Accounted transaction received
4221061 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 193.8 | 1 | شريط قياس 5م |  | Each | 2 | 62906511 |  |  |  | شريط قياس 5م | 200010000105 | Purchasing | Received | 2023-06-20 | Accounted transaction received
4221062 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 570 | 1 | تيب دوكو |  | Each | 20 | 62906512 |  |  |  | تيب دوكو | 200010000048 | Purchasing | Received | 2023-06-20 | Accounted transaction received
4221063 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 119.7 | 1 | مهزة |  | Each | 3 | 62906513 |  |  |  | مهزة | 200010000305 | Purchasing | Received | 2023-06-20 | Accounted transaction received
4221064 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1026 | 1 | تيب مسلح |  | Each | 20 | 62906514 |  |  |  | تيب مسلح | 200010000382 | Purchasing | Received | 2023-06-20 | Accounted transaction received
4221065 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 57 | 1 | سلاح كتر |  | Each | 1 | 62906515 |  |  |  | سلاح كتر | 200010000411 | Purchasing | Received | 2023-06-20 | Accounted transaction received
4221066 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 199.5 | 1 | مكنسة ناعمة |  | Each | 5 | 62906516 |  |  |  | مكنسة ناعمة | 200010000449 | Purchasing | Received | 2023-06-20 | Accounted transaction received
4221067 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 108.3 | 1 | منجفرة كبيرة (لزوم المحارة) |  | Each | 1 | 62906517 |  |  |  | منجفرة كبيرة (لزوم المحارة) | 200010000899 | Purchasing | Received | 2023-06-20 | Accounted transaction received
4221068 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 273.6 | 1 | مسمار سن صاج 2.50 سم |  | Each | 2 | 62906518 |  |  |  | مسمار سن صاج 2.50 سم | 200020000238 | Purchasing | Received | 2023-06-20 | Accounted transaction received
4221069 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 684 | 1 | تنر |  | Each | 3 | 62906519 |  |  |  | تنر | 060019000008 | MEP | Received | 2023-06-20 | Accounted transaction received
4221070 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 136.8 | 1 | مسمار سن صاج 3 سم |  | Kilogram | 1 | 62906520 |  |  |  | مسمار سن صاج 3 سم | 200020000239 | Purchasing | Received | 2023-06-20 | Accounted transaction received
4221071 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 513 | 1 | بنطة (مسمار) تكسير لهيلتي 70 |  | Each | 2 | 62906521 |  |  |  | بنطة (مسمار) تكسير لهيلتي 70 | 200010000997 | Purchasing | Received | 2023-06-20 | Accounted transaction received
4221072 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 91.2 | 1 | مسمار خشابى 6 سم |  | Kilogram | 1 | 62906522 |  |  |  | مسمار خشابى 6 سم | 200020000141 | Purchasing | Received | 2023-06-20 | Accounted transaction received
4221073 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 148.2 | 1 | غراء أبيض |  | Kilogram | 2 | 62906523 |  |  |  | غراء أبيض | 200010001270 | Purchasing | Received | 2023-06-20 | Accounted transaction received
4221074 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 91.2 | 1 | مسمار خشابى 10 سم |  | Kilogram | 1 | 62906524 |  |  |  | مسمار خشابى 10 سم | 200020000307 | Purchasing | Received | 2023-06-20 | Accounted transaction received
4221075 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1254 | 1 | سيلكون عظم |  | Each | 10 | 62906525 |  |  |  | سيلكون عظم | 330040000420 | Equipment | Received | 2023-06-20 | Accounted transaction received
4221076 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1026 | 1 | سلك مواعين |  | Kilogram | 15 | 62906526 |  |  |  | سلك مواعين | 700020000122 | Purchasing | Received | 2023-06-20 | Accounted transaction received
4221077 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 632.81 | 1 | كرتون مضلع - تغليف |  | Kilogram | 42.7 | 62906527 |  |  |  | كرتون مضلع - تغليف | 910010000387 | Administration | Received | 2023-06-20 | Accounted transaction received
4221078 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 769.5 | 1 | اديبوند 65 |  | Kilogram | 5 | 62906528 |  |  |  | اديبوند 65 | 360010000273 | Purchasing | Received | 2023-06-20 | Accounted transaction received
4221079 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 193.8 | 1 | مادة لاصق لورق الحائط |  | Kilogram | 2 | 62906529 |  |  |  | مادة لاصق لورق الحائط | 050020000006 | Purchasing | Received | 2023-06-20 | Accounted transaction received
4221080 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 135 | 1 | ميتال جبس بورد |  | Roll | 1 | 62906530 |  |  |  | ميتال جبس بورد | 050020000029 | Purchasing | Received | 2023-06-20 | Accounted transaction received
4221081 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 788.88 | 1 | سلك نحاس مصمت مقاس 1 مم اللون أسود (cu/xlpe) جهد (750/450) |  | Meter | 100 | 62906621 |  |  |  | سلك نحاس مصمت مقاس 1 مم اللون أسود (cu/xlpe) جهد (750/450) | 030030100244 | MEP | Received | 2023-06-20 | Accounted transaction received
4221082 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4389 | 1 | كابل نحاس مجدول مصمت مقاس 3 × 3 مم (xlpe/pvc) جهد (500/300) |  | Meter | 50 | 62906622 |  |  |  | كابل نحاس مجدول مصمت مقاس 3 × 3 مم (xlpe/pvc) جهد (500/300) | 030030100118 | MEP | Received | 2023-06-20 | Accounted transaction received
4221083 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 57 | 1 | كوس نحاس 16 مم |  | Each | 5 | 62906623 |  |  |  | كوس نحاس 16 مم | 030130100106 | MEP | Received | 2023-06-20 | Accounted transaction received
4221084 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 85 | 1 | عود دكت 1.5 *1.5 سم |  | Each | 5 | 62906624 |  |  |  | عود دكت 1.5 *1.5 سم | 060010100816 | MEP | Received | 2023-06-20 | Accounted transaction received
4221085 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2245.8 | 1 | مفتاح ثلااثي 32 A |  | Each | 2 | 62906625 |  |  |  | مفتاح ثلااثي 32 A | 330040000502 | Equipment | Received | 2023-06-20 | Accounted transaction received
4221086 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 598.5 | 1 | ريكم فاي 4 مم |  | Meter | 50 | 62906626 |  |  |  | ريكم فاي 4 مم | 030060100619 | MEP | Received | 2023-06-20 | Accounted transaction received
4221087 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 50 | 1 | فيشة ذكر كاوتش 16أمبير 220 فولت |  | Each | 10 | 62906627 |  |  |  | فيشة ذكر كاوتش 16أمبير 220 فولت | 039010000049 | MEP | Received | 2023-06-20 | Accounted transaction received
4221088 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 50 | 1 | فيشة نتاية كاوتش 16أمبير 220 فولت |  | Each | 10 | 62906628 |  |  |  | فيشة نتاية كاوتش 16أمبير 220 فولت | 039010000050 | MEP | Received | 2023-06-20 | Accounted transaction received
4221089 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 114 | 1 | Wire Nut 1.5 mm |  | Each | 200 | 62906629 |  |  |  | Wire Nut 1.5 mm | 030130800012 | MEP | Received | 2023-06-20 | Accounted transaction received
4221090 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 148.2 | 1 | Wire Nut 3mm |  | Each | 200 | 62906630 |  |  |  | Wire Nut 3mm | 030130800015 | MEP | Received | 2023-06-20 | Accounted transaction received
4221091 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 738.58 | 1 | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 25مم وقطر خارجى 31.1مم طول اللفه 30 متر(اللون رمادى) |  | Roll | 2 | 62906648 |  |  |  | لفة فلكسبلUPVC (مقاوم للحريق)قطرداخلى 25مم وقطر خارجى 31.1مم طول اللفه 30 متر(اللون رمادى) | 030010000062 | MEP | Received | 2023-06-20 | Accounted transaction received
4221092 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 496.2 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 4 | 62906649 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-06-20 | Accounted transaction received
4221093 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1071.2 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 6 | 62906650 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-06-20 | Accounted transaction received
4221094 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 184.15 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 4 | 62906651 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-06-20 | Accounted transaction received
4221095 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 7960.68 | 1 | LID & TRIM 3 COMPARTMENTS GREY ( Legrand 689631 ) |  | Each | 10 | 62906652 |  |  |  | LID & TRIM 3 COMPARTMENTS GREY ( Legrand 689631 ) | 030060100738 | MEP | Received | 2023-06-20 | Accounted transaction received
4221096 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 695.71 | 1 | Signature Detector Base ( SIGA-SB ) |  | Each | 5 | 62906653 |  |  |  | Signature Detector Base ( SIGA-SB ) | 031010000145 | MEP | Received | 2023-06-20 | Accounted transaction received
4221097 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 401.79 | 1 | Detector Base with Isolator ( SIGA-IB ) |  | Each | 1 | 62906654 |  |  |  | Detector Base with Isolator ( SIGA-IB ) | 031010000146 | MEP | Received | 2023-06-20 | Accounted transaction received
4221098 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 494.72 | 1 | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 |  | Each | 4 | 62906655 |  |  |  | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 | 030060100951 | MEP | Received | 2023-06-20 | Accounted transaction received
4221099 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-04 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 18525 | 1 | Rubber flooring; including all necessary accessories; preparations; to Floors; SP-16 & as per submittal approval |  | Square Meter | 25 | 62774453 |  |  |  | Rubber flooring; including all necessary accessories; preparations; to Floors; SP-16 & as per submittal approval | 140030000124 | Purchasing | Received | 2023-06-20 | Accounted transaction received
4221100 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 17.09 | 1 | أفيز هانجر EMT المقاس 2 " |  | Each | 1 | 62774855 |  |  |  | أفيز هانجر EMT المقاس 2 " | 030020100080 | MEP | Received | 2023-06-20 | Accounted transaction received
4221101 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 7.98 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 1 | 62774856 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-06-20 | Accounted transaction received
4221102 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 193.8 | 1 | جلبة ماسورة 63مم UPVC (اللون أبيض) |  | Each | 2 | 62774857 |  |  |  | جلبة ماسورة 63مم UPVC (اللون أبيض) | 030010000072 | MEP | Received | 2023-06-20 | Accounted transaction received
4221103 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 142.91 | 1 | بواط نهاية UPVC لماسورة 20مم(اللون أبيض) |  | Each | 23 | 62774858 |  |  |  | بواط نهاية UPVC لماسورة 20مم(اللون أبيض) | 030010000080 | MEP | Received | 2023-06-20 | Accounted transaction received
4221104 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 7.3 | 1 | أفيز أثنين جناح لماسورة EMT المقاس 1 " |  | Each | 2 | 62774859 |  |  |  | أفيز أثنين جناح لماسورة EMT المقاس 1 " | 030020100034 | MEP | Received | 2023-06-20 | Accounted transaction received
4221105 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 638.46 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 14 | 62778578 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-06-20 | Accounted transaction received
4221106 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 35.51 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 2 | 62778579 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-06-20 | Accounted transaction received
4221107 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 134.59 | 1 | CARRIER PLATE SYNERGY code 730094 |  | Each | 2 | 62778580 |  |  |  | CARRIER PLATE SYNERGY code 730094 | 030060100534 | MEP | Received | 2023-06-20 | Accounted transaction received
4221108 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-04 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 113.63 | 1 | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 |  | Each | 2 | 62778581 |  |  |  | 2 MOD 1G PLATE SQ DARK BRONZE - Legrand 571592 | 030060100955 | MEP | Received | 2023-06-20 | Accounted transaction received
4221109 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-04 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 12882 | 1 | Trim around Mirrors |  | Meter | 20 | 62778585 |  |  |  | Trim around Mirrors | 250010001935 | Procurement | Received | 2023-06-20 | Accounted transaction received
4239341 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9636.71 | 1 | 8.8.036 67059/11 |  | Currency | 30 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.036 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239342 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4500 | 1 | 8.8.087 67059/11 |  | Currency | 100 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.087 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239343 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9609.82 | 1 | 8.8.098 67059/11 |  | Currency | 44 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.098 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239344 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 36008.5 | 1 | 11.6 67059/11 |  | Currency | 530 |  | 4820 | سيجاب للهندسه والتجاره |  | 11.6 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239345 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3828 | 1 | 12.6 67059/11 |  | Currency | 29 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.6 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239346 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2464 | 1 | 12.7 67059/11 |  | Currency | 14 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.7 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239347 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 960 | 1 | 12.10 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.10 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239348 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 30000 | 1 | 12.11 67059/11 |  | Currency | 750 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.11 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239349 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 132000 | 1 | 12.12 67059/11 |  | Currency | 11000 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.12 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239350 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1872 | 1 | 12.16 67059/11 |  | Currency | 78 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.16 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239351 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2496 | 1 | 12.17 67059/11 |  | Currency | 78 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.17 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239352 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4056 | 1 | 12.18 67059/11 |  | Currency | 78 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.18 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239353 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 13728 | 1 | 12.19 67059/11 |  | Currency | 78 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.19 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239354 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 800 | 1 | 12.25 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.25 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239355 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 800 | 1 | 12.26 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.26 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4223402 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.06 | Material Transportat | 17 | Indirect Cost |  | 2023-06-14 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5130 | 1 | نقل ثقيل 3/23- astoria | نقل ثقيل 3/23- astoria | Currency | 5130 | 23290543 | 8534 | مكتب الحمد للنقل | rowad | نقل ثقيل 3/23- astoria |  | Finacial | Received | 2023-06-20 | Accounted transaction received
4257625 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-06-30 | Hirings Payrool |  |  |  | Indirect | Alrowad Construction_OU | 807514.51 | 1 | قيد مرتبات شهر يونيو 2023 | Salary-JUNE-2023 | Currency | 807514.51 | 23349819 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر يونيو 2023 |  | Finacial | Received | 2023-07-05 | Accounted transaction received
4239356 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 800 | 1 | 12.27 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.27 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239357 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 800 | 1 | 12.28 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.28 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239358 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 800 | 1 | 12.29 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.29 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239359 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 800 | 1 | 12.30 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.30 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239360 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2400 | 1 | 12.32 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.32 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239361 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 960 | 1 | 12.33 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.33 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239362 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 960 | 1 | 12.34 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.34 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239363 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 840 | 1 | 5.5.023 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.023 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239364 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 12408 | 1 | 12.1 67059/11 |  | Currency | 282 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.1 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239365 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1324.8 | 1 | 12.2 67059/11 |  | Currency | 24 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.2 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239366 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2656 | 1 | 12.3 67059/11 |  | Currency | 40 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.3 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239367 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2992 | 1 | 12.4 67059/11 |  | Currency | 34 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.4 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239368 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5740.8 | 1 | 12.5 67059/11 |  | Currency | 52 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.5 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239369 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | -17000 | 1 | 67059/11 |  | Currency | -17000 |  | 4820 | سيجاب للهندسه والتجاره |  | 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239370 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1418.04 | 1 | LABOUR_OFFICE 67059/11 |  | Currency | -1418.04 |  | 4820 | سيجاب للهندسه والتجاره |  | LABOUR_OFFICE 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4251382 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 909.15 | 1 | 10AX SWITCH SP 2 WAY 1 MOD Code 572505 |  | Each | 6 | 63355419 |  |  |  | 10AX SWITCH SP 2 WAY 1 MOD Code 572505 | 030060100123 | MEP | Received | 2023-07-01 | Accounted transaction received
4251383 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 248.1 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 2 | 63355420 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-07-01 | Accounted transaction received
4251384 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 3.00. | Concrete Works | 3 | CONCRETE WORK |  | 2023-06-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 9815.4 | 1 | خرسانة مسلحة بالالياف جهد 200 كجم/سم2 محتوي اسمنتى 325 |  | Cubic Meter | 7 | 63355757 |  |  |  | خرسانة مسلحة بالالياف جهد 200 كجم/سم2 محتوي اسمنتى 325 | 100100000192 | Procurement | Received | 2023-07-01 | Accounted transaction received
4251385 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 6384 | 1 | Spot ring: Main scope: Supply only Dimensions: OD 100 - ID 82 Materials: Brass 1.25mm Finish: Brushed Stainless Steel |  | Each | 70 | 63355928 |  |  |  | Spot ring: Main scope: Supply only Dimensions: OD 100 - ID 82 Materials: Brass 1.25mm Finish: Brushed Stainless Steel | 250010002117 | Procurement | Received | 2023-07-01 | Accounted transaction received
4251386 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-06-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 230.01 | 1 | متر خرطوم هواء |  | Each | 2 | 63130532 |  |  |  | متر خرطوم هواء | 330040000290 | Equipment | Received | 2023-07-01 | Accounted transaction received
4251387 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-06-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 5643 | 1 | Vertical Roof Drain 3'' ( Wilson ) |  | Each | 3 | 63130533 |  |  |  | Vertical Roof Drain 3'' ( Wilson ) | 060020500002 | MEP | Received | 2023-07-01 | Accounted transaction received
4251388 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-06-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4617 | 1 | Cast Iron planter drain Size 3" |  | Each | 3 | 63130534 |  |  |  | Cast Iron planter drain Size 3" | 060010901089 | MEP | Received | 2023-07-01 | Accounted transaction received
4251389 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.08.00 | Gypsum Board(G) | 9 | FINISHES WORK |  | 2023-06-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 125 | 1 | مسمار بورمة 2سم |  | Bag | 1 | 63130566 |  |  |  | مسمار بورمة 2سم | 200020000056 | Purchasing | Received | 2023-07-01 | Accounted transaction received
4251390 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.08.00 | Gypsum Board(G) | 9 | FINISHES WORK |  | 2023-06-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2508 | 1 | باب كاشف 120*60 |  | Each | 2 | 63130567 |  |  |  | باب كاشف 120*60 | 300020000024 | Purchasing | Received | 2023-07-01 | Accounted transaction received
4251391 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.08.00 | Gypsum Board(G) | 9 | FINISHES WORK |  | 2023-06-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4788 | 1 | باب كشف جبس 60 * 60 سم |  | Each | 6 | 63130568 |  |  |  | باب كشف جبس 60 * 60 سم | 250010000533 | Procurement | Received | 2023-07-01 | Accounted transaction received
4251392 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.08.00 | Gypsum Board(G) | 9 | FINISHES WORK |  | 2023-06-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2308.5 | 1 | باب كشف جبس 40 * 40 سم |  | Each | 3 | 63130569 |  |  |  | باب كشف جبس 40 * 40 سم | 250010000809 | Procurement | Received | 2023-07-01 | Accounted transaction received
4251393 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 655.5 | 1 | جبس |  | Ton | 0.25 | 63130728 |  |  |  | جبس | 140010000004 | Purchasing | Received | 2023-07-01 | Accounted transaction received
4251394 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 8037 | 1 | اسمنت اسود رتبة 42 |  | Ton | 3 | 63130729 |  |  |  | اسمنت اسود رتبة 42 | 140010000015 | Purchasing | Received | 2023-07-01 | Accounted transaction received
4251395 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 957.6 | 1 | لباد موكيت 1000 جم مجهز |  | Square Meter | 120 | 63130730 |  |  |  | لباد موكيت 1000 جم مجهز | 700020000178 | Purchasing | Received | 2023-07-01 | Accounted transaction received
4251396 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-06-21 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 125 | 1 | سلك شبك فايبر 15 سم |  | Roll | 1 | 63130731 |  |  |  | سلك شبك فايبر 15 سم | 200010002171 | Purchasing | Received | 2023-07-01 | Accounted transaction received
4251397 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5894.31 | 1 | HN-VC120 Volume Controller |  | Each | 1 | 63131365 |  |  |  | HN-VC120 Volume Controller | 031070000069 | MEP | Received | 2023-07-01 | Accounted transaction received
4251398 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 62.7 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 10 | 63141022 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-07-01 | Accounted transaction received
4251399 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 91.67 | 1 | بواط إمتداد UPVC لماسورة 25مم(اللون أبيض) |  | Each | 11 | 63141023 |  |  |  | بواط إمتداد UPVC لماسورة 25مم(اللون أبيض) | 030010000083 | MEP | Received | 2023-07-01 | Accounted transaction received
4251400 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 16.67 | 1 | بواط زاوية UPVC لماسورة 25مم(اللون أبيض) |  | Each | 2 | 63141024 |  |  |  | بواط زاوية UPVC لماسورة 25مم(اللون أبيض) | 030010000085 | MEP | Received | 2023-07-01 | Accounted transaction received
4251401 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 470.92 | 1 | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 |  | Each | 16 | 63141025 |  |  |  | SOCKET - GERMAN - 16 A - 2P+E SHUTTERED - 2 MOD Code 572118 | 030060100021 | MEP | Received | 2023-07-01 | Accounted transaction received
4251402 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1737.72 | 1 | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 |  | Each | 15 | 63141026 |  |  |  | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 | 030060100114 | MEP | Received | 2023-07-01 | Accounted transaction received
4251403 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 53.26 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 3 | 63141027 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-07-01 | Accounted transaction received
4251404 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 14663.42 | 1 | UNIVERSAL DIMMER W/O NEUTR 400 Code 572739 |  | Each | 5 | 63141028 |  |  |  | UNIVERSAL DIMMER W/O NEUTR 400 Code 572739 | 030060100176 | MEP | Received | 2023-07-01 | Accounted transaction received
4251405 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2066.72 | 1 | SHAVER SOCKET 230V/120-230V WITH EARTH CONNECTOR Code 572653 |  | Each | 3 | 63141029 |  |  |  | SHAVER SOCKET 230V/120-230V WITH EARTH CONNECTOR Code 572653 | 030060100178 | MEP | Received | 2023-07-01 | Accounted transaction received
4251406 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 13901.54 | 1 | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 |  | Each | 10 | 63141030 |  |  |  | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 | 030060100182 | MEP | Received | 2023-07-01 | Accounted transaction received
4251407 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 490.85 | 1 | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 |  | Each | 1 | 63141031 |  |  |  | POP-UP BOX TO BE EQUIPPED - 2 X 4 MODULES - MATT ALUMINIUM FINISH code 54013 | 030060100572 | MEP | Received | 2023-07-01 | Accounted transaction received
4251408 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 176.4 | 1 | Plate British standard Arteor - square - 3 modules - graphite - 575072 |  | Each | 3 | 63141032 |  |  |  | Plate British standard Arteor - square - 3 modules - graphite - 575072 | 030060100898 | MEP | Received | 2023-07-01 | Accounted transaction received
4251409 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 24640.75 | 1 | Floor box 6 Module with double socket, space for 2 data socket complete with back box , IP66, Part Number GESR2 - OBO Germany |  | Each | 2 | 63141033 |  |  |  | Floor box 6 Module with double socket, space for 2 data socket complete with back box , IP66, Part Number GESR2 - OBO Germany | 030060100992 | MEP | Received | 2023-07-01 | Accounted transaction received
4251410 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 22144.5 | 1 | MCC- Pump |  | Each | 1 | 63141735 |  |  |  | MCC- Pump | 030050303285 | MEP | Received | 2023-07-01 | Accounted transaction received
4251411 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-21 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2684.7 | 1 | سلك ترمو بلاستيك 2*1 |  | Meter | 100 | 63142389 |  |  |  | سلك ترمو بلاستيك 2*1 | 030030101017 | MEP | Received | 2023-07-01 | Accounted transaction received
4251412 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1737.72 | 1 | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 |  | Each | 15 | 63329553 |  |  |  | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 | 030060100114 | MEP | Received | 2023-07-01 | Accounted transaction received
4251413 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 378.23 | 1 | 10AX 2 WAY SWITCH 2 MOD Code 572535 |  | Each | 5 | 63329554 |  |  |  | 10AX 2 WAY SWITCH 2 MOD Code 572535 | 030060100125 | MEP | Received | 2023-07-01 | Accounted transaction received
4251414 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 14663.42 | 1 | UNIVERSAL DIMMER W/O NEUTR 400 Code 572739 |  | Each | 5 | 63329555 |  |  |  | UNIVERSAL DIMMER W/O NEUTR 400 Code 572739 | 030060100176 | MEP | Received | 2023-07-01 | Accounted transaction received
4251415 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 357.87 | 1 | mosaic adapter code 69580 |  | Each | 1 | 63329556 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-07-01 | Accounted transaction received
4251416 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 80.25 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 1 | 63329557 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-07-01 | Accounted transaction received
4251417 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-06-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1140 | 1 | Robe Hook Plate 70*70*10 |  | Each | 10 | 63329578 |  |  |  | Robe Hook Plate 70*70*10 | 250010001933 | Procurement | Received | 2023-07-01 | Accounted transaction received
4251418 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-06-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 22543.5 | 1 | Trim around Mirrors |  | Meter | 35 | 63329579 |  |  |  | Trim around Mirrors | 250010001935 | Procurement | Received | 2023-07-01 | Accounted transaction received
4251419 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-06-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 8550 | 1 | Robe Hook HW-4 |  | Each | 10 | 63329580 |  |  |  | Robe Hook HW-4 | 250010002115 | Procurement | Received | 2023-07-01 | Accounted transaction received
4251420 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1612.65 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 13 | 63339812 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-07-01 | Accounted transaction received
4251421 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 456.04 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 10 | 63339813 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-07-01 | Accounted transaction received
4251422 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 159.79 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 9 | 63339814 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-07-01 | Accounted transaction received
4251423 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 230.18 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 5 | 63339815 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-07-01 | Accounted transaction received
4251424 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 381.03 | 1 | 576562 Code وش مربع فضي |  | Each | 7 | 63339816 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-07-01 | Accounted transaction received
4251425 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-06-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3220.5 | 1 | Trim around Mirrors |  | Meter | 5 | 63341678 |  |  |  | Trim around Mirrors | 250010001935 | Procurement | Received | 2023-07-01 | Accounted transaction received
4254504 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 156 | 1 | 12.17 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.17 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254460 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | 60440 | 1 | 67059/12 |  | Currency | 60440 |  | 4820 | سيجاب للهندسه والتجاره |  | 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254461 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 631.75 | 1 | 2.2.019 67059/12 |  | Currency | 7 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.019 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254462 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 270.75 | 1 | 2.2.022 67059/12 |  | Currency | 3 |  | 4820 | سيجاب للهندسه والتجاره |  | 2.2.022 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254463 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 315 | 1 | 6.6.057 67059/12 |  | Currency | 7 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.057 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254464 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1350 | 1 | 6.6.058 67059/12 |  | Currency | 30 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.058 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254465 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 405 | 1 | 7.7.058 67059/12 |  | Currency | 9 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.058 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254466 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 252 | 1 | 7.7.059 67059/12 |  | Currency | 5.6 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.059 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254467 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3706.43 | 1 | 8.8.047 67059/12 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.047 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254468 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 375.25 | 1 | 8.8.058 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.058 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254469 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 361 | 1 | 8.8.061 67059/12 |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.061 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254470 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 152 | 1 | 8.8.064 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.064 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254471 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3158.75 | 1 | 8.8.065 67059/12 |  | Currency | 35 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.065 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254472 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 631.75 | 1 | 8.8.067 67059/12 |  | Currency | 7 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.067 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254473 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 541.5 | 1 | 8.8.069 67059/12 |  | Currency | 6 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.069 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254474 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 180.5 | 1 | 8.8.071 67059/12 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.071 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254475 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 180.5 | 1 | 8.8.072 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.072 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254476 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 14.25 | 1 | 8.8.074 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.074 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254477 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 256.5 | 1 | 8.8.075 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.075 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254478 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 655.5 | 1 | 8.8.076 67059/12 |  | Currency | 6 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.076 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254479 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 128.25 | 1 | 8.8.077 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.077 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254480 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 52.25 | 1 | 8.8.079 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.079 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254481 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 9.5 | 1 | 8.8.08 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.08 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254482 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 47.5 | 1 | 8.8.081 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.081 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254483 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 61.75 | 1 | 8.8.083 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.083 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254484 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 293.4 | 1 | 8.8.09 67059/12 |  | Currency | 6.52 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.09 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254485 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1980 | 1 | 8.8.094 67059/12 |  | Currency | 44 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.094 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254486 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 88.2 | 1 | 8.8.095 67059/12 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.095 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254487 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5320 | 1 | 5.5.023 67059/12 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.023 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254488 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5795 | 1 | 5.5.05 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.05 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254489 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4590 | 1 | 8.8.087 67059/12 |  | Currency | 102 |  | 4820 | سيجاب للهندسه والتجاره |  | 8.8.087 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254490 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3672 | 1 | 12.8 67059/12 |  | Currency | 54 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.8 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254491 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 775.5 | 1 | 12.1 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.1 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254492 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 82.8 | 1 | 12.2 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.2 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254493 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 166 | 1 | 12.3 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.3 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254494 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 187 | 1 | 12.4 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.4 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254495 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 358.8 | 1 | 12.5 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.5 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254496 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 239.25 | 1 | 12.6 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.6 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254497 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 154 | 1 | 12.7 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.7 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254498 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 60 | 1 | 12.10 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.10 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254499 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1875 | 1 | 12.11 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.11 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254500 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 8250 | 1 | 12.12 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.12 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254501 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 765 | 1 | 12.14 67059/12 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.14 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254502 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 255 | 1 | 12.15 67059/12 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.15 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254503 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 117 | 1 | 12.16 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.16 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254505 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 253.5 | 1 | 12.18 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.18 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254506 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 858 | 1 | 12.19 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.19 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254507 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 50 | 1 | 12.26 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.26 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254508 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 50 | 1 | 12.27 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.27 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254509 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 50 | 1 | 12.28 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.28 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254510 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 50 | 1 | 12.29 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.29 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254511 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 50 | 1 | 12.30 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.30 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254512 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 5600 | 1 | 12.31 67059/12 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.31 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254513 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 150 | 1 | 12.32 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.32 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254514 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 60 | 1 | 12.33 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.33 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254515 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 60 | 1 | 12.34 67059/12 |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.34 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254516 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 13594.5 | 1 | 11.5 67059/12 |  | Currency | 318 |  | 4820 | سيجاب للهندسه والتجاره |  | 11.5 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254517 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4347.2 | 1 | 11.10 67059/12 |  | Currency | 16 |  | 4820 | سيجاب للهندسه والتجاره |  | 11.10 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254518 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3556.8 | 1 | 3.3.005 67059/12 |  | Currency | 52 |  | 4820 | سيجاب للهندسه والتجاره |  | 3.3.005 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254519 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 612 | 1 | 5.5.055 67059/12 |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 5.5.055 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254520 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2291.4 | 1 | 4.4.01 67059/12 |  | Currency | 33.5 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.01 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254521 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 3693.6 | 1 | 4.4.011 67059/12 |  | Currency | 54 |  | 4820 | سيجاب للهندسه والتجاره |  | 4.4.011 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254522 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 900 | 1 | 12.25 67059/12 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 12.25 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254523 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1361.35 | 1 | 3.3.002 67059/12 |  | Currency | 14.33 |  | 4820 | سيجاب للهندسه والتجاره |  | 3.3.002 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4254524 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -389.28 | 1 | LABOUR_OFFICE 67059/12 |  | Currency | -389.28 |  | 4820 | سيجاب للهندسه والتجاره |  | LABOUR_OFFICE 67059/12 |  | Finacial | Received | 2023-07-04 | Accounted transaction received
4257342 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2023-06-30 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 4543.5 | 1 | تسويه ك -286 - بوفيه | st-286/ 06-23 | Currency | 4543.5 | 23349819 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك -286 - بوفيه |  | Finacial | Received | 2023-07-05 | Accounted transaction received
4257343 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2023-06-30 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 114 | 1 | تسويه ك - 289 - انتقالات | st-289/ 06-23 | Currency | 114 | 23349819 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك - 289 - انتقالات |  | Finacial | Received | 2023-07-05 | Accounted transaction received
4257750 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.02 | Health Care | 17 | Indirect Cost |  | 2023-06-30 | Medical Care |  |  |  | Direct Manpower | Alrowad Construction_OU | -1474.7 | 1 | قيد مرتبات شهر يونيو 2023 | Salary-JUNE-2023 | Currency | -1474.7 | 23349819 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر يونيو 2023 |  | Finacial | Received | 2023-07-05 | Accounted transaction received
4257794 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.02 | Health Care | 17 | Indirect Cost |  | 2023-06-30 | Hirings Payrool |  |  |  | Indirect | Alrowad Construction_OU | -29151.67 | 1 | قيد مرتبات شهر يونيو 2023 | Salary-JUNE-2023 | Currency | -29151.67 | 23349819 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر يونيو 2023 |  | Finacial | Received | 2023-07-05 | Accounted transaction received
4257889 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.04 | Fuel,Oil & Gas | 17 | Indirect Cost |  | 2023-06-30 | Fuel,Oil & Gas |  |  |  | Indirect | Alrowad Construction_OU | 3940.3 | 1 | 558068-8146-8815-8960-9131 astoria | 558068-8146-8815-8960-9131 astoria | Currency | 3940.3 | 23349819 | 3903 | توتال ايجيبت | rowad | 558068-8146-8815-8960-9131 astoria |  | Finacial | Received | 2023-07-05 | Accounted transaction received
4258019 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-06-30 | Networks and programs |  |  |  | Depreciation | Alrowad Construction_OU | 48825.29 | 1 | 4775-4776-4777 astorialfa | 4775-4776-4777 astoria | Currency | 48825.29 | 23349819 | 1675 | هيومان اي تي سوليوشنز | Egypt | 4775-4776-4777 astorialfa |  | Finacial | Received | 2023-07-05 | Accounted transaction received
4258033 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.04 | Fuel,Oil & Gas | 17 | Indirect Cost |  | 2023-06-30 | Fuel,Oil & Gas |  |  |  | Indirect | Alrowad Construction_OU | 3674 | 1 | 559831-9914-560409-560711-560771 astoria | 559831-9914-560409-560711-560771 astoria | Currency | 3674 | 23349819 | 3903 | توتال ايجيبت | rowad | 559831-9914-560409-560711-560771 astoria |  | Finacial | Received | 2023-07-05 | Accounted transaction received
4258645 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1.01 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -1.01 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258646 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -21.04 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -21.04 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258647 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -4.21 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -4.21 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258648 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -3.61 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -3.61 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258649 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1.2 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -1.2 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258650 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1.2 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -1.2 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258651 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -0.09 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -0.09 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258652 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1.71 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -1.71 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258653 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -4.37 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -4.37 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258654 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -0.85 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -0.85 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258655 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -0.35 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -0.35 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258656 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -0.06 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -0.06 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258657 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -0.32 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -0.32 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258658 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -0.41 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -0.41 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258659 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1.95 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -1.95 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258660 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -13.19 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -13.19 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258661 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -0.59 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -0.59 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258662 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -35.43 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -35.43 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258663 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -38.6 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -38.6 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258664 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -30.57 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -30.57 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258665 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -24.46 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -24.46 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258666 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -5.17 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -5.17 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258667 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -0.55 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -0.55 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258668 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1.11 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -1.11 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258669 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1.25 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -1.25 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258670 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -2.39 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -2.39 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258671 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1.59 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -1.59 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258672 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1.03 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -1.03 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258673 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -0.4 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -0.4 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258674 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -12.49 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -12.49 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258675 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -54.95 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -54.95 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258676 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -5.1 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -5.1 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258677 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1.7 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -1.7 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258678 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -0.78 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -0.78 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258679 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1.04 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -1.04 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258680 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1.69 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -1.69 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258681 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -5.71 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -5.71 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258682 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -0.33 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -0.33 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258683 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -0.33 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -0.33 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258684 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -0.33 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -0.33 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258685 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -0.33 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -0.33 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258686 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -0.33 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -0.33 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258687 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -37.3 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -37.3 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258688 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -1 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258689 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -0.4 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -0.4 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258690 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -0.4 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -0.4 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258691 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -90.55 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -90.55 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258692 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -28.95 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -28.95 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258693 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -23.69 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -23.69 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258694 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -4.08 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -4.08 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258695 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -15.26 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -15.26 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258696 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -24.6 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -24.6 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258697 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -5.99 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -5.99 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258698 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -9.07 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -9.07 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258699 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2.59 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | 2.59 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258700 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -402.56 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -402.56 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258701 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -4.21 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -4.21 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258702 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1.8 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -1.8 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258703 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -2.1 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -2.1 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258704 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -8.99 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -8.99 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258705 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -2.7 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -2.7 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258706 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1.68 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -1.68 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4257668 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-06-30 | Honouring of terrorism 0.0005 |  |  |  | Indirect | Alrowad Construction_OU | 226.62 | 1 | قيد مرتبات شهر يونيو 2023 | Salary-JUNE-2023 | Currency | 226.62 | 23349819 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر يونيو 2023 |  | Finacial | Received | 2023-07-05 | Accounted transaction received
4257708 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.06 | Telephones | 17 | Indirect Cost |  | 2023-06-30 | Telephones |  |  |  | Indirect | Alrowad Construction_OU | -233.44 | 1 | قيد مرتبات شهر يونيو 2023 | Salary-JUNE-2023 | Currency | -233.44 | 23349819 | 2161 | Staff Loan | SALARY & WAGES | قيد مرتبات شهر يونيو 2023 |  | Finacial | Received | 2023-07-05 | Accounted transaction received
4261152 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-06-30 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 55045 | 1 | يوميات عماله الفتره 2 ش 6 التقديري | يوميات عماله الفتره 2 ش 6 التقديري | Currency | 55045 | 23352102 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 2 ش 6 التقديري |  | Finacial | Received | 2023-07-07 | Accounted transaction received
4261239 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-06-30 | Computers Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 1396.3 | 1 |  | FA depreciation to projects june-23 | Currency | 1396.3 | 23352268 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-07-07 | Accounted transaction received
4261285 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-06-30 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 3601.37 | 1 |  | FA depreciation to projects june-23 | Currency | 3601.37 | 23352268 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-07-07 | Accounted transaction received
4261331 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-06-30 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 8360.18 | 1 |  | FA depreciation to projects june-23 | Currency | 8360.18 | 23352268 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-07-07 | Accounted transaction received
4261377 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-06-30 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 5578.34 | 1 |  | FA depreciation to projects june-23 | Currency | 5578.34 | 23352268 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-07-07 | Accounted transaction received
4261423 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-06-30 | Furniture Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 483.84 | 1 |  | FA depreciation to projects june-23 | Currency | 483.84 | 23352268 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-07-07 | Accounted transaction received
4263235 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.02 | Rented Cars | 17 | Indirect Cost |  | 2023-07-09 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 18647.33 | 1 | نقل افراد5/23 - waldorf astoria 7 | نقل افراد5/23 - waldorf astoria 7 | Currency | 18647.33 | 23355559 | 3084 | محمد احمد محمد محمد | Rowad | نقل افراد5/23 - waldorf astoria 7 |  | Finacial | Received | 2023-07-09 | Accounted transaction received
4239328 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1130.5 | 1 | 6.6.051 67059/11 |  | Currency | 10 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.051 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239329 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2185 | 1 | 6.6.055 67059/11 |  | Currency | 46 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.055 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239330 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 71.25 | 1 | 6.6.061 67059/11 |  | Currency | 15 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.061 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239331 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 52.25 | 1 | 6.6.063 67059/11 |  | Currency | 11 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.063 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239332 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 19 | 1 | 6.6.064 67059/11 |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 6.6.064 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239333 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -2052 | 1 | 7.7.001 67059/11 |  | Currency | -9 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.001 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239334 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1710 | 1 | 7.7.009 67059/11 |  | Currency | 10 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.009 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239335 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 315.88 | 1 | 7.7.039 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.039 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239336 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 60.07 | 1 | 7.7.041 67059/11 |  | Currency | 1 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.041 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239337 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 199.45 | 1 | 7.7.045 67059/11 |  | Currency | 2 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.045 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239338 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 361 | 1 | 7.7.056 67059/11 |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.056 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239339 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1522.5 | 1 | 7.7.057 67059/11 |  | Currency | 31 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.057 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4239340 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 361 | 1 | 7.7.066 67059/11 |  | Currency | 4 |  | 4820 | سيجاب للهندسه والتجاره |  | 7.7.066 67059/11 |  | Finacial | Received | 2023-06-25 | Accounted transaction received
4259107 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-06-30 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 900 | 1 |  | FA DEPRECIATION - jun -23 | Currency | 900 | 23350938 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-07-06 | Accounted transaction received
4259108 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-06-30 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 2764.5 | 1 |  | FA DEPRECIATION - jun -23 | Currency | 2764.5 | 23350938 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-07-06 | Accounted transaction received
4259109 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-06-30 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 4644.74 | 1 |  | FA DEPRECIATION - jun -23 | Currency | 4644.74 | 23350938 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-07-06 | Accounted transaction received
4259110 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-06-30 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 995.14 | 1 |  | FA DEPRECIATION - jun -23 | Currency | 995.14 | 23350938 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-07-06 | Accounted transaction received
4259111 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-06-30 | Machines Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 14.98 | 1 |  | FA DEPRECIATION - jun -23 | Currency | 14.98 | 23350938 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-07-06 | Accounted transaction received
4259112 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-06-30 | Furniture Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 7042.1 | 1 |  | FA DEPRECIATION - jun -23 | Currency | 7042.1 | 23350938 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-07-06 | Accounted transaction received
4259113 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-06-30 | Electrical appliance Deprectia |  |  |  | Depreciation | Alrowad Construction_OU | 1316.5 | 1 |  | FA DEPRECIATION - jun -23 | Currency | 1316.5 | 23350938 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-07-06 | Accounted transaction received
4259114 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-06-30 | Electrical appliance Deprectia |  |  |  | Depreciation | Alrowad Construction_OU | 3076.19 | 1 |  | FA DEPRECIATION - jun -23 | Currency | 3076.19 | 23350938 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-07-06 | Accounted transaction received
4259115 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-06-30 | Computers Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 4832 | 1 |  | FA DEPRECIATION - jun -23 | Currency | 4832 | 23350938 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-07-06 | Accounted transaction received
4259116 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-06-30 | Electrical appliance Deprectia |  |  |  | Depreciation | Alrowad Construction_OU | 2583.29 | 1 |  | FA DEPRECIATION - jun -23 | Currency | 2583.29 | 23350938 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-07-06 | Accounted transaction received
4259287 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-06-30 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 6060 | 1 | استوريا الماسه ف/65305-65306 6/6 | 65305-65306 | Currency | 6060 | 23350938 | 12416 | الماسه للتاجير ومعالجه المياه | rowad | استوريا الماسه ف/65305-65306 6/6 |  | Finacial | Received | 2023-07-06 | Accounted transaction received
4261101 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-06-30 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 165135 | 1 | يوميات عماله الفتره 1 ش 6 الفعلي | يوميات عماله الفتره 1 ش 6 الفعلي | Currency | 165135 | 23352102 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 1 ش 6 الفعلي |  | Finacial | Received | 2023-07-07 | Accounted transaction received
4261469 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-06-30 | Tools Depreciation |  |  |  | Depreciation | Alrowad Construction_OU | 763.17 | 1 |  | FA depreciation to projects june-23 | Currency | 763.17 | 23352268 | 2131 | Miscellaneous supplier | RME |  |  | Finacial | Received | 2023-07-07 | Accounted transaction received
4262075 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.02 | Rented Cars | 17 | Indirect Cost |  | 2023-06-30 | Transportation |  |  |  | Indirect | Alrowad Construction_OU | 1569.8 | 1 | اوبر | اوبر ترانسبورت00 | Currency | 1569.8 | 23354114 | 12487 | اوبر تكنولوجيز ايجيبت | rowad | اوبر |  | Finacial | Received | 2023-07-09 | Accounted transaction received
4262971 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-07-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 306.75 | 1 | سيفتي عمال |  | Each | 1 | 63521206 |  |  |  | سيفتي عمال | 010030000002 | Safety | Received | 2023-07-09 | Accounted transaction received
4262972 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-07-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 63.64 | 1 | جوانتي جلد ثقيل ( خرسانة ) |  | Each | 2 | 63521207 |  |  |  | جوانتي جلد ثقيل ( خرسانة ) | 010010000003 | Safety | Received | 2023-07-09 | Accounted transaction received
4262973 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-07-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 39.4 | 1 | فيست برتقالي |  | Each | 1 | 63521208 |  |  |  | فيست برتقالي | 010020000008 | Safety | Received | 2023-07-09 | Accounted transaction received
4262974 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-07-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 82.08 | 1 | فيست ليموني |  | Each | 2 | 63521209 |  |  |  | فيست ليموني | 010020000009 | Safety | Received | 2023-07-09 | Accounted transaction received
4262975 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-07-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 90 | 1 | اكرة محبس 3/4 بوصة |  | Each | 2 | 63521210 |  |  |  | اكرة محبس 3/4 بوصة | 240080000190 | MEP | Received | 2023-07-09 | Accounted transaction received
4262976 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 570 | 1 | تيب دوكو |  | Each | 20 | 63521224 |  |  |  | تيب دوكو | 200010000048 | Purchasing | Received | 2023-07-09 | Accounted transaction received
4262977 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4961.28 | 1 | بولي ايثيلين 200 ميكرون شفاف |  | Kilogram | 54.4 | 63521225 |  |  |  | بولي ايثيلين 200 ميكرون شفاف | 040010000042 | Purchasing | Received | 2023-07-09 | Accounted transaction received
4262978 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 10716 | 1 | اسمنت اسود رتبة 42 |  | Ton | 4 | 63521226 |  |  |  | اسمنت اسود رتبة 42 | 140010000015 | Purchasing | Received | 2023-07-09 | Accounted transaction received
4262979 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 712.5 | 1 | كولة رخام |  | Each | 5 | 63521227 |  |  |  | كولة رخام | 200010000710 | Purchasing | Received | 2023-07-09 | Accounted transaction received
4262980 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 684 | 1 | شيكارة بلاستيك فارغة |  | Each | 200 | 63521228 |  |  |  | شيكارة بلاستيك فارغة | 200010000115 | Purchasing | Received | 2023-07-09 | Accounted transaction received
4262981 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 692.55 | 1 | كرتون مضلع - تغليف |  | Kilogram | 45 | 63521229 |  |  |  | كرتون مضلع - تغليف | 910010000387 | Administration | Received | 2023-07-09 | Accounted transaction received
4262982 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2194.5 | 1 | كابل نحاس مجدول مصمت مقاس 3 × 3 مم (xlpe/pvc) جهد (500/300) |  | Meter | 25 | 63521452 |  |  |  | كابل نحاس مجدول مصمت مقاس 3 × 3 مم (xlpe/pvc) جهد (500/300) | 030030100118 | MEP | Received | 2023-07-09 | Accounted transaction received
4262983 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 684 | 1 | بكرة شريط لحام |  | Each | 30 | 63521453 |  |  |  | بكرة شريط لحام | 039010000003 | MEP | Received | 2023-07-09 | Accounted transaction received
4262984 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 342 | 1 | حزام بلاستيك 30 سم × 3.6 مم أبيض |  | Pack | 6 | 63521454 |  |  |  | حزام بلاستيك 30 سم × 3.6 مم أبيض | 030131100015 | MEP | Received | 2023-07-09 | Accounted transaction received
4262985 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 357.87 | 1 | mosaic adapter code 69580 |  | Each | 1 | 63521455 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-07-09 | Accounted transaction received
4262986 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 205.2 | 1 | 'wire nut 6 mm Water prove |  | Each | 2 | 63521456 |  |  |  | 'wire nut 6 mm Water prove | 030130800014 | MEP | Received | 2023-07-09 | Accounted transaction received
4274750 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-10 | Materials |  |  |  | Materials | Alrowad Construction_OU | -48245.61 | 1 | كنسة موقع Scrap |  | Lot | -1 | 63619087 |  |  |  | كنسة موقع Scrap | 150070000036 | Purchasing | Received | 2023-07-11 | Accounted transaction received
4274751 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-07-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 8159.98 | 1 | Hardware Accessories for Wooden Doors Concealed hinge system & Bathroom Concealed Hinges Simonswerk completely concealed hinge system with load capacity 80.0 kg two hinges per door leaf (1x2m) |  | Each | 3 | 63680164 |  |  |  | Hardware Accessories for Wooden Doors Concealed hinge system & Bathroom Concealed Hinges Simonswerk completely concealed hinge system with load capacity 80.0 kg two hinges per door leaf (1x2m) | 250010001515 | Procurement | Received | 2023-07-11 | Accounted transaction received
4274752 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 124.05 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 1 | 63680260 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-07-11 | Accounted transaction received
4274753 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 714.13 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 4 | 63680261 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-07-11 | Accounted transaction received
4274754 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4330.39 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 20 | 63680262 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-07-11 | Accounted transaction received
4274755 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 29326.85 | 1 | UNIVERSAL DIMMER W/O NEUTR 400 Code 572739 |  | Each | 10 | 63680263 |  |  |  | UNIVERSAL DIMMER W/O NEUTR 400 Code 572739 | 030060100176 | MEP | Received | 2023-07-11 | Accounted transaction received
4274756 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 18072 | 1 | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 |  | Each | 13 | 63680264 |  |  |  | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 | 030060100182 | MEP | Received | 2023-07-11 | Accounted transaction received
4274757 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1088.66 | 1 | 576562 Code وش مربع فضي |  | Each | 20 | 63680265 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-07-11 | Accounted transaction received
4274758 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1431.47 | 1 | mosaic adapter code 69580 |  | Each | 4 | 63680266 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-07-11 | Accounted transaction received
4274759 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 357.87 | 1 | mosaic adapter code 69580 |  | Each | 1 | 63680267 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-07-11 | Accounted transaction received
4274760 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 320.99 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 4 | 63680268 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-07-11 | Accounted transaction received
4274761 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 80.25 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 1 | 63680269 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-07-11 | Accounted transaction received
4274762 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 136.87 | 1 | UPVC BACK BOX 10X10 |  | Each | 6 | 63680270 |  |  |  | UPVC BACK BOX 10X10 | 030069000025 | MEP | Received | 2023-07-11 | Accounted transaction received
4274763 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 940.82 | 1 | Plate British standard Arteor - square - 3 modules - graphite - 575072 |  | Each | 16 | 63680271 |  |  |  | Plate British standard Arteor - square - 3 modules - graphite - 575072 | 030060100898 | MEP | Received | 2023-07-11 | Accounted transaction received
4274764 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 48735 | 1 | HDMI PRE-CONN 1M Code 572596 |  | Each | 15 | 63562791 |  |  |  | HDMI PRE-CONN 1M Code 572596 | 030060100165 | MEP | Received | 2023-07-11 | Accounted transaction received
4274765 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 32490 | 1 | HDMI PRE-CONN 1M Code 572596 |  | Each | 10 | 63562792 |  |  |  | HDMI PRE-CONN 1M Code 572596 | 030060100165 | MEP | Received | 2023-07-11 | Accounted transaction received
4274766 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 695.09 | 1 | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 |  | Each | 6 | 63562793 |  |  |  | 10AX SWITCH SP 1 WAY 1 MOD Code 572504 | 030060100114 | MEP | Received | 2023-07-11 | Accounted transaction received
4274767 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2272.86 | 1 | 10AX SWITCH SP 2 WAY 1 MOD Code 572505 |  | Each | 15 | 63562794 |  |  |  | 10AX SWITCH SP 2 WAY 1 MOD Code 572505 | 030060100123 | MEP | Received | 2023-07-11 | Accounted transaction received
4274768 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 992.4 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 8 | 63562795 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-07-11 | Accounted transaction received
4274769 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 714.13 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 4 | 63562796 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-07-11 | Accounted transaction received
4274770 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 456.04 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 10 | 63562797 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-07-11 | Accounted transaction received
4274771 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 88.77 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 5 | 63562798 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-07-11 | Accounted transaction received
4274772 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2165.2 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 10 | 63562799 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-07-11 | Accounted transaction received
4274773 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 20852.31 | 1 | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 |  | Each | 15 | 63562800 |  |  |  | USB CHARG.SINGLE MAG.ARTEOR S Code 572571 | 030060100182 | MEP | Received | 2023-07-11 | Accounted transaction received
4274774 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1415.26 | 1 | 576562 Code وش مربع فضي |  | Each | 26 | 63562801 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-07-11 | Accounted transaction received
4262987 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 80.25 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 1 | 63521457 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-07-09 | Accounted transaction received
4262988 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 63.93 | 1 | S/M BOX 1-GANG GREY Code (69651 ) |  | Each | 1 | 63521458 |  |  |  | S/M BOX 1-GANG GREY Code (69651 ) | 030060100728 | MEP | Received | 2023-07-09 | Accounted transaction received
4262989 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-07 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 790.17 | 1 | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 |  | Each | 10 | 63521459 |  |  |  | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 | 030060100956 | MEP | Received | 2023-07-09 | Accounted transaction received
4262990 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-07-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1440 | 1 | رزمة ورق تصوير باور A4 |  | Each | 10 | 63521516 |  |  |  | رزمة ورق تصوير باور A4 | 910020000002 | Administration | Received | 2023-07-09 | Accounted transaction received
4262991 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 44430.36 | 1 | Galvanized Motorized Smoke Damper complete with Actuator Size 44" * 24" |  | Each | 2 | 63522161 |  |  |  | Galvanized Motorized Smoke Damper complete with Actuator Size 44" * 24" | 060070800260 | MEP | Received | 2023-07-09 | Accounted transaction received
4262992 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SP.02 | Stationary | 17 | Indirect Cost |  | 2023-07-07 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1254 | 1 | Canon MF3010 Cartridge |  | Each | 2 | 63522429 |  |  |  | Canon MF3010 Cartridge | 800030000086 | IT | Received | 2023-07-09 | Accounted transaction received
4262993 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -135.66 | 1 | Threaded Reducer 2''*1'' UL listed, FM approved |  | Each | -1 | 63556061 |  |  |  | Threaded Reducer 2''*1'' UL listed, FM approved | 060011500384 | MEP | Received | 2023-07-09 | Accounted transaction received
4262994 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -135.66 | 1 | Threaded Reducer 2''*1.25'' UL listed, FM approved |  | Each | -1 | 63556062 |  |  |  | Threaded Reducer 2''*1.25'' UL listed, FM approved | 060011500385 | MEP | Received | 2023-07-09 | Accounted transaction received
4262995 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -1179.9 | 1 | threaded elbows f 90° size 1" UL LISTED,FM APPROVED |  | Each | -15 | 63556063 |  |  |  | threaded elbows f 90° size 1" UL LISTED,FM APPROVED | 060010140056 | MEP | Received | 2023-07-09 | Accounted transaction received
4262996 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -383.04 | 1 | threaded elbows f 90° size 1.25" UL LISTED,FM APPROVED |  | Each | -4 | 63556064 |  |  |  | threaded elbows f 90° size 1.25" UL LISTED,FM APPROVED | 060010140057 | MEP | Received | 2023-07-09 | Accounted transaction received
4262997 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -372.78 | 1 | threaded elbows f 90° size 1.5" UL LISTED,FM APPROVED |  | Each | -3 | 63556065 |  |  |  | threaded elbows f 90° size 1.5" UL LISTED,FM APPROVED | 060010140058 | MEP | Received | 2023-07-09 | Accounted transaction received
4262998 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -2593.5 | 1 | threaded elbows f 90° size 2" UL LISTED,FM APPROVED |  | Each | -13 | 63556066 |  |  |  | threaded elbows f 90° size 2" UL LISTED,FM APPROVED | 060010140059 | MEP | Received | 2023-07-09 | Accounted transaction received
4262999 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -513 | 1 | threaded reducing tees size 1.5"*1.25"*1.5" UL LISTED,FM APPROVED |  | Each | -3 | 63556067 |  |  |  | threaded reducing tees size 1.5"*1.25"*1.5" UL LISTED,FM APPROVED | 060010140237 | MEP | Received | 2023-07-09 | Accounted transaction received
4263000 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -1333.8 | 1 | threaded tees size 1" UL LISTED,FM APPROVED |  | Each | -15 | 63556068 |  |  |  | threaded tees size 1" UL LISTED,FM APPROVED | 060010140276 | MEP | Received | 2023-07-09 | Accounted transaction received
4263001 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -114 | 1 | threaded tees size 1.25" UL LISTED,FM APPROVED |  | Each | -1 | 63556069 |  |  |  | threaded tees size 1.25" UL LISTED,FM APPROVED | 060010140277 | MEP | Received | 2023-07-09 | Accounted transaction received
4263002 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -221.16 | 1 | threaded tees size 2" UL LISTED,FM APPROVED |  | Each | -1 | 63556070 |  |  |  | threaded tees size 2" UL LISTED,FM APPROVED | 060010140278 | MEP | Received | 2023-07-09 | Accounted transaction received
4263003 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -285 | 1 | threaded hexagon nipples size 1.25" UL LISTED,FM APPROVED |  | Each | -5 | 63556071 |  |  |  | threaded hexagon nipples size 1.25" UL LISTED,FM APPROVED | 060010140494 | MEP | Received | 2023-07-09 | Accounted transaction received
4263004 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -159.6 | 1 | threaded hexagon nipples size 1.5" UL LISTED,FM APPROVED |  | Each | -2 | 63556072 |  |  |  | threaded hexagon nipples size 1.5" UL LISTED,FM APPROVED | 060010140495 | MEP | Received | 2023-07-09 | Accounted transaction received
4263005 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -752.4 | 1 | threaded street tees size 1.5" UL LISTED,FM APPROVED |  | Each | -5 | 63556073 |  |  |  | threaded street tees size 1.5" UL LISTED,FM APPROVED | 060010140288 | MEP | Received | 2023-07-09 | Accounted transaction received
4263006 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -2599.2 | 1 | threaded reducing coupling size 1"*1/2" UL LISTED,FM APPROVED |  | Each | -40 | 63556074 |  |  |  | threaded reducing coupling size 1"*1/2" UL LISTED,FM APPROVED | 060010140334 | MEP | Received | 2023-07-09 | Accounted transaction received
4263007 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -101.13 | 1 | threaded reducing coupling size 1.5"*1" UL LISTED,FM APPROVED |  | Each | -1 | 63556075 |  |  |  | threaded reducing coupling size 1.5"*1" UL LISTED,FM APPROVED | 060010140343 | MEP | Received | 2023-07-09 | Accounted transaction received
4263008 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -933.66 | 1 | threaded reducing coupling size 1.5"*1.25" UL LISTED,FM APPROVED |  | Each | -9 | 63556076 |  |  |  | threaded reducing coupling size 1.5"*1.25" UL LISTED,FM APPROVED | 060010140344 | MEP | Received | 2023-07-09 | Accounted transaction received
4263009 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -103.74 | 1 | threaded reducing coupling size 1.5"*1.25" UL LISTED,FM APPROVED |  | Each | -1 | 63556077 |  |  |  | threaded reducing coupling size 1.5"*1.25" UL LISTED,FM APPROVED | 060010140344 | MEP | Received | 2023-07-09 | Accounted transaction received
4263010 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -323.76 | 1 | threaded reducing coupling size 2"*1.5" UL LISTED,FM APPROVED |  | Each | -2 | 63556078 |  |  |  | threaded reducing coupling size 2"*1.5" UL LISTED,FM APPROVED | 060010140351 | MEP | Received | 2023-07-09 | Accounted transaction received
4263011 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -542.64 | 1 | threaded reducing tees size 1.25"*1" UL LISTED,FM APPROVED |  | Each | -4 | 63556079 |  |  |  | threaded reducing tees size 1.25"*1" UL LISTED,FM APPROVED | 060010140163 | MEP | Received | 2023-07-09 | Accounted transaction received
4263012 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -462.58 | 1 | threaded reducing tees size 1.5"*1" UL LISTED,FM APPROVED |  | Each | -3 | 63556080 |  |  |  | threaded reducing tees size 1.5"*1" UL LISTED,FM APPROVED | 060010140167 | MEP | Received | 2023-07-09 | Accounted transaction received
4263013 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -725.04 | 1 | threaded reducing tees size 2"*1.25" UL LISTED,FM APPROVED |  | Each | -3 | 63556081 |  |  |  | threaded reducing tees size 2"*1.25" UL LISTED,FM APPROVED | 060010140171 | MEP | Received | 2023-07-09 | Accounted transaction received
4263014 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -711.36 | 1 | threaded bushings size 1.5"*1" UL LISTED,FM APPROVED |  | Each | -8 | 63556082 |  |  |  | threaded bushings size 1.5"*1" UL LISTED,FM APPROVED | 060010140405 | MEP | Received | 2023-07-09 | Accounted transaction received
4263015 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -1244.88 | 1 | threaded bushings size 1.5"*1.25" UL LISTED,FM APPROVED |  | Each | -14 | 63556083 |  |  |  | threaded bushings size 1.5"*1.25" UL LISTED,FM APPROVED | 060010140406 | MEP | Received | 2023-07-09 | Accounted transaction received
4263016 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -1799.95 | 1 | seamless steel pipe size 1.25" SCH.40 |  | Meter | -6 | 63556084 |  |  |  | seamless steel pipe size 1.25" SCH.40 | 060010500016 | MEP | Received | 2023-07-09 | Accounted transaction received
4263017 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -19104.12 | 1 | seamless steel pipe size 2.5" SCH.40 |  | Meter | -30 | 63556085 |  |  |  | seamless steel pipe size 2.5" SCH.40 | 060010500025 | MEP | Received | 2023-07-09 | Accounted transaction received
4263018 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -8724.5 | 1 | seamless steel pipe size 3" SCH.40 |  | Meter | -24 | 63556086 |  |  |  | seamless steel pipe size 3" SCH.40 | 060010500028 | MEP | Received | 2023-07-09 | Accounted transaction received
4263019 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-09 | Materials |  |  |  | Materials | Alrowad Construction_OU | -8122.5 | 1 | seamless steel pipe size 4" SCH.40 |  | Meter | -6 | 63556087 |  |  |  | seamless steel pipe size 4" SCH.40 | 060010500033 | MEP | Received | 2023-07-09 | Accounted transaction received
4266305 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.02.00 | Painting(G) | 9 | FINISHES WORK |  | 2023-06-20 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 11061.6 | 1 | 1.1 80894/3 |  | Currency | 553.08 |  | 12636 | مصطفي شعبان عطية بيومي-ذاتى |  | 1.1 80894/3 |  | Finacial | Received | 2023-07-10 | Accounted transaction received
4266432 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 2.10. | Cement | 2 | SITE WORK |  | 2023-06-20 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 4138.4 | 1 | 1.1 80733/2 |  | Currency | 206.92 |  | 6238 | محمد بسطاوي حامد سعيد-ذاتى |  | 1.1 80733/2 |  | Finacial | Received | 2023-07-10 | Accounted transaction received
4271062 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 6.04. | Wood Flooring | 6 | WOOD & PLASTIC WORK |  | 2023-07-11 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 195932.4 | 1 | 1.1 86003/1 |  | Currency | 526.7 |  | 11717 | مكتب النصر لاعمال الباركيه |  | 1.1 86003/1 |  | Finacial | Received | 2023-07-11 | Accounted transaction received
4271063 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 6.04. | Wood Flooring | 6 | WOOD & PLASTIC WORK |  | 2023-07-11 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -881.7 | 1 | LABOUR_OFFICE 86003/1 |  | Currency | -881.7 |  | 11717 | مكتب النصر لاعمال الباركيه |  | LABOUR_OFFICE 86003/1 |  | Finacial | Received | 2023-07-11 | Accounted transaction received
4277078 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -900 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277079 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -54150 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277080 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -54 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277081 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -54 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277082 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -270 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277083 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -60 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277084 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -70 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277085 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -25 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277086 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -37.5 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277087 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -60 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277088 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -525 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277089 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -800 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277090 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -9.5 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277091 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -9.5 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277092 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -33.25 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277093 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -19 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277094 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -114 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277095 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -33.25 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277096 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -2736 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277097 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -2052 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277098 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -2120.4 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277099 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -18 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277100 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -40 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277101 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -972 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277102 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 875 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277103 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -3477 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277104 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1895.25 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277105 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1710 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277106 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -115.3 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277107 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -5130 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277108 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -9.5 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277109 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -339.15 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277110 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -40.57 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277111 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -37.94 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277112 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -7.63 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277113 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -15.75 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277114 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -27.79 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277115 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1130.5 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277116 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -2185 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277117 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -71.25 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277118 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -52.25 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277119 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -19 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277120 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2052 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277121 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1710 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277122 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -4500 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277123 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -315.88 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277124 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -60.07 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277125 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -199.45 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277126 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -361 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277127 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1522.5 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277128 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -361 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277129 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -9636.71 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4274775 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2906.52 | 1 | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS |  | Each | 13 | 63562802 |  |  |  | Wiring Devices (54010) POP-UP BOX TO BE EQUIPPED - 3 MODULES - MATT ALUMINIUM FINIS | 030060100617 | MEP | Received | 2023-07-11 | Accounted transaction received
4274776 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 294.01 | 1 | Plate British standard Arteor - square - 3 modules - graphite - 575072 |  | Each | 5 | 63562803 |  |  |  | Plate British standard Arteor - square - 3 modules - graphite - 575072 | 030060100898 | MEP | Received | 2023-07-11 | Accounted transaction received
4274777 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2257.89 | 1 | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser |  | Each | 5 | 63562804 |  |  |  | Acolyte - ARB95SWBC201. 527 - Rapid Ribbon 95+ - LED Strip with 4.8 W/M, 2700K, CRI/97 IP20, 24VDC, with aluminum profile and Opal diffuser | 030040700472 | MEP | Received | 2023-07-11 | Accounted transaction received
4274778 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 521.48 | 1 | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) |  | Meter | 30 | 63563265 |  |  |  | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) | 030010000052 | MEP | Received | 2023-07-11 | Accounted transaction received
4274779 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 62.7 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 10 | 63563266 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-07-11 | Accounted transaction received
4274780 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 221.16 | 1 | لاكور ماسورة EMT المقاس ¾ " |  | Each | 10 | 63563267 |  |  |  | لاكور ماسورة EMT المقاس ¾ " | 030020100015 | MEP | Received | 2023-07-11 | Accounted transaction received
4274781 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 180.43 | 1 | جلبة ماسورة EMT المقاس ¾ " |  | Each | 10 | 63563268 |  |  |  | جلبة ماسورة EMT المقاس ¾ " | 030020100021 | MEP | Received | 2023-07-11 | Accounted transaction received
4274782 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 20.03 | 1 | أفيز أثنين جناح لماسورة EMT المقاس ¾ " |  | Each | 8 | 63563269 |  |  |  | أفيز أثنين جناح لماسورة EMT المقاس ¾ " | 030020100033 | MEP | Received | 2023-07-11 | Accounted transaction received
4274783 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 22.81 | 1 | UPVC BACK BOX 10X10 |  | Each | 1 | 63563270 |  |  |  | UPVC BACK BOX 10X10 | 030069000025 | MEP | Received | 2023-07-11 | Accounted transaction received
4274784 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-09 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1329.39 | 1 | Micro Switch Hafele/ Marckophon - 820.22.110/4321 - Switches 230 VDoor contact switches - Built-in switch |  | Each | 1 | 63563271 |  |  |  | Micro Switch Hafele/ Marckophon - 820.22.110/4321 - Switches 230 VDoor contact switches - Built-in switch | 030060200070 | MEP | Received | 2023-07-11 | Accounted transaction received
4274785 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 8.04.00 | Special Doors(G) | 8 | DOORS & WINDOWS WOR |  | 2023-07-09 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 68400 | 1 | Antique brass (MT-4) frame; WAH_PA_GL_PT_70 DT; to Existing vanity mirrors |  | Meter | 120 | 63563737 |  |  |  | Antique brass (MT-4) frame; WAH_PA_GL_PT_70 DT; to Existing vanity mirrors | 250010001673 | Procurement | Received | 2023-07-11 | Accounted transaction received
4300834 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 8682.99 | 1 | INTERNAL CONTROL UNIT FOR HOTEL BEDROOM Code 572554 |  | Each | 11 | 63932787 |  |  |  | INTERNAL CONTROL UNIT FOR HOTEL BEDROOM Code 572554 | 030060100175 | MEP | Received | 2023-07-26 | Accounted transaction received
4277130 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -9609.82 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277131 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -36008.5 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277132 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -840 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277133 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 17000 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277134 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 1418.04 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277135 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -3828 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277136 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -2464 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277137 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -960 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277138 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -30000 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277139 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -132000 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277140 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1872 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277141 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -2496 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277142 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -4056 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277143 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -13728 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277144 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -800 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277145 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -800 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277146 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -800 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277147 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -800 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277148 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -800 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277149 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -800 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277150 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -2400 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277151 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -12408 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277152 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -960 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277153 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -960 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277154 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -1324.8 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277155 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -2656 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277156 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -2992 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4277157 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 5.02.00 | METAL FABRICATION (G | 5 | METAL WORK |  | 2023-06-22 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -5740.8 | 1 |  |  | Currency | 0 |  | 4820 | سيجاب للهندسه والتجاره |  |  |  | Finacial | Received | 2023-07-12 | Accounted transaction received
4279087 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.02 | Rented Cars | 17 | Indirect Cost |  | 2023-07-12 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 39000 | 1 | نقل افراد 5/23- WALDORF6 | نقل افراد 5/23- WALDORF6 | Currency | 39000 | 23405701 | 5214 | المتحدة لايجار وتوريد السيارات | rowad | نقل افراد 5/23- WALDORF6 |  | Finacial | Received | 2023-07-13 | Accounted transaction received
4279092 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.10 | Printers / Photo Cop | 17 | Indirect Cost |  | 2023-07-12 | Printers/Photo Copiers |  |  |  | Indirect | Alrowad Construction_OU | 2508 | 1 | تصوير فيديو وصور بالمشاريع-07-23 | تصوير فيديو وصور بالمشاريع-07-23 | Currency | 2508 | 23405701 | 9821 | محمد عاطف عبدالعزيز موسي | rowad | تصوير فيديو وصور بالمشاريع-07-23 |  | Finacial | Received | 2023-07-13 | Accounted transaction received
4292351 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.02 | Rented Cars | 17 | Indirect Cost |  | 2023-07-14 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 27330.5 | 1 | نقل افراد 5/23- Waldorf Astorya | نقل افراد 5/23- Waldorf Astorya | Currency | 27330.5 | 23423888 | 9182 | مؤسسة الجينيرال لتأجير السيارات | rowad | نقل افراد 5/23- Waldorf Astorya |  | Finacial | Received | 2023-07-25 | Accounted transaction received
4292380 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.03 | Accomodation | 17 | Indirect Cost |  | 2023-07-15 | Accomodation |  |  |  | Indirect | Alrowad Construction_OU | 39000 | 1 | تسويه ك 268/304 ايجارات سكن | st-268/304 07-23 | Currency | 39000 | 23423888 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك 268/304 ايجارات سكن |  | Finacial | Received | 2023-07-25 | Accounted transaction received
4292382 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.08 | Electrical Expenses | 17 | Indirect Cost |  | 2023-07-15 | Electrical Expenses |  |  |  | Indirect | Alrowad Construction_OU | 4249 | 1 | تسويه ك 246/250/269/271/282/290/291/298/305 -متنوعات | st-246/250/269/271/282/290/291/298/305 07-23 | Currency | 4249 | 23423888 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك 246/250/269/271/282/290/291/298/305 -متنوعات |  | Finacial | Received | 2023-07-25 | Accounted transaction received
4292383 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.08 | Trafic Permission & | 17 | Indirect Cost |  | 2023-07-15 | Trafic Perm-Station Fees |  |  |  | Indirect | Alrowad Construction_OU | 150 | 1 | تسويه ك 246/250/269/271/282/290/291/298/305 -متنوعات | st-246/250/269/271/282/290/291/298/305 07-23 | Currency | 150 | 23423888 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك 246/250/269/271/282/290/291/298/305 -متنوعات |  | Finacial | Received | 2023-07-25 | Accounted transaction received
4292384 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SE.06 | Surveying Equipment | 17 | Indirect Cost |  | 2023-07-15 | Surveying Equipment |  |  |  | Indirect | Alrowad Construction_OU | 478.8 | 1 | تسويه ك 246/250/269/271/282/290/291/298/305 -متنوعات | st-246/250/269/271/282/290/291/298/305 07-23 | Currency | 478.8 | 23423888 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك 246/250/269/271/282/290/291/298/305 -متنوعات |  | Finacial | Received | 2023-07-25 | Accounted transaction received
4292388 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-07-15 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 8075 | 1 | تسويه ك st-252/270/277/281/293/301/306/307 -متنوعات | st-252/270/277/281/293/301/306/307 07-23 | Currency | 8075 | 23423888 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك st-252/270/277/281/293/301/306/307 -متنوعات |  | Finacial | Received | 2023-07-25 | Accounted transaction received
4292391 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.13 | Sunderies | 17 | Indirect Cost |  | 2023-07-15 | Sunderies |  |  |  | Indirect | Alrowad Construction_OU | 7394.25 | 1 | تسويه ك st-248/249/274/297/299/308 -متنوعات | st-248/249/274/297/299/308 07-23 | Currency | 7394.25 | 23423888 | 2162 | Petty Cash | Hassan Mohamed Hassan Salim | تسويه ك st-248/249/274/297/299/308 -متنوعات |  | Finacial | Received | 2023-07-25 | Accounted transaction received
4292833 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.06 | Material Transportat | 17 | Indirect Cost |  | 2023-07-17 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 26601.5 | 1 | اعمال نقل ثقيل 4/23-waldorf astoria | اعمال نقل ثقيل 4/23-waldorf astoria | Currency | 26601.5 | 23423888 | 2740 | حمدى محمود دياب غطاس | CAIRO | اعمال نقل ثقيل 4/23-waldorf astoria |  | Finacial | Received | 2023-07-25 | Accounted transaction received
4292856 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.06 | Material Transportat | 17 | Indirect Cost |  | 2023-07-19 | Material Transportation |  |  |  | Indirect | Alrowad Construction_OU | 36700.4 | 1 | اعمال نقل ثقيل 4/23- استوريا | اعمال نقل ثقيل 4/23- استوريا | Currency | 36700.4 | 23423888 | 8534 | مكتب الحمد للنقل | rowad | اعمال نقل ثقيل 4/23- استوريا |  | Finacial | Received | 2023-07-25 | Accounted transaction received
4293169 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-07-25 | Subcontracts |  |  |  | Contingencies | Alrowad Construction_OU | 14000 | 1 | 1.1 85759/1 |  | Currency | 200 |  | 12357 | عماد عبدالناصر ابراهيم حسين-ذاتى |  | 1.1 85759/1 |  | Finacial | Received | 2023-07-25 | Accounted transaction received
4293170 | WORK_CONFRIMATION | 164 | Waldorf Astoria Cairo |  | 9.11. | Wall Paper | 9 | FINISHES WORK |  | 2023-07-25 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 2800 | 1 | 2.1 85759/1 |  | Currency | 40 |  | 12357 | عماد عبدالناصر ابراهيم حسين-ذاتى |  | 2.1 85759/1 |  | Finacial | Received | 2023-07-25 | Accounted transaction received
4300854 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-07-17 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 19104.12 | 1 | seamless steel pipe size 2.5" SCH.40 |  | Meter | 30 | 63784031 |  |  |  | seamless steel pipe size 2.5" SCH.40 | 060010500025 | MEP | Received | 2023-07-26 | Accounted transaction received
4300855 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-17 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3059.76 | 1 | Square ceiling Diffuser nick 6" * 6" face 24" * 24" |  | Each | 2 | 63790826 |  |  |  | Square ceiling Diffuser nick 6" * 6" face 24" * 24" | 060070100181 | MEP | Received | 2023-07-26 | Accounted transaction received
4300856 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-17 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2496.6 | 1 | Dummy linear grill length 1.2m, width 200mm |  | Each | 2 | 63790827 |  |  |  | Dummy linear grill length 1.2m, width 200mm | 060070100312 | MEP | Received | 2023-07-26 | Accounted transaction received
4300857 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 10.01. | Bridge Bearing | 10 | SPECIALITIES |  | 2023-07-17 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 47025 | 1 | Robe Hook HW-4 |  | Each | 55 | 63794073 |  |  |  | Robe Hook HW-4 | 250010002115 | Procurement | Received | 2023-07-26 | Accounted transaction received
4300858 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 521.48 | 1 | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) |  | Meter | 30 | 63683691 |  |  |  | ماسورة 25مم UPVC سمك ثقيل قطر خارجي 25 قطر داخلي 21.1مم اللفة= 20×3 متر(اللون أبيض) | 030010000052 | MEP | Received | 2023-07-26 | Accounted transaction received
4300859 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 124.05 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 1 | 63683692 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-07-26 | Accounted transaction received
4300860 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4154.68 | 1 | Hot Dip Galvanized cable trunk100x100mm thickness 1.5mm with cover 1.25mm thickness |  | Meter | 9 | 63683693 |  |  |  | Hot Dip Galvanized cable trunk100x100mm thickness 1.5mm with cover 1.25mm thickness | 030100500001 | MEP | Received | 2023-07-26 | Accounted transaction received
4300861 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2276.42 | 1 | Galvanized cable tray cover 150mm (snap on type) thickness 1mm |  | Meter | 33 | 63683694 |  |  |  | Galvanized cable tray cover 150mm (snap on type) thickness 1mm | 030101500002 | MEP | Received | 2023-07-26 | Accounted transaction received
4300862 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 357.87 | 1 | mosaic adapter code 69580 |  | Each | 1 | 63683695 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-07-26 | Accounted transaction received
4300863 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 63.93 | 1 | S/M BOX 1-GANG GREY Code (69651 ) |  | Each | 1 | 63683696 |  |  |  | S/M BOX 1-GANG GREY Code (69651 ) | 030060100728 | MEP | Received | 2023-07-26 | Accounted transaction received
4300864 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-11 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4783.27 | 1 | 3.5mm Jack socket Arteor - preterminated - 1 module - magnesium - 572591 |  | Each | 2 | 63683697 |  |  |  | 3.5mm Jack socket Arteor - preterminated - 1 module - magnesium - 572591 | 030060100899 | MEP | Received | 2023-07-26 | Accounted transaction received
4300865 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2322.04 | 1 | أنبوبة سليكون |  | Each | 54 | 63684195 |  |  |  | أنبوبة سليكون | 060019000001 | MEP | Received | 2023-07-26 | Accounted transaction received
4300866 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 8122.5 | 1 | seamless steel pipe size 4" SCH.40 |  | Meter | 6 | 63684196 |  |  |  | seamless steel pipe size 4" SCH.40 | 060010500033 | MEP | Received | 2023-07-26 | Accounted transaction received
4300867 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-11 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 7496 | 1 | Linear floor drain with bottom outlet length 1050mm, Model: BECO D40 Part Number : CH 1050/S40 H |  | Each | 2 | 63684197 |  |  |  | Linear floor drain with bottom outlet length 1050mm, Model: BECO D40 Part Number : CH 1050/S40 H | 060004000012 | MEP | Received | 2023-07-26 | Accounted transaction received
4300868 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.03.00 | FireFighting Works(G | 15 | MECHANICAL WORKS |  | 2023-07-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 19104.12 | 1 | seamless steel pipe size 2.5" SCH.40 |  | Meter | 30 | 63712678 |  |  |  | seamless steel pipe size 2.5" SCH.40 | 060010500025 | MEP | Received | 2023-07-26 | Accounted transaction received
4300869 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 22.12 | 1 | لاكور ماسورة EMT المقاس ¾ " |  | Each | 1 | 63716473 |  |  |  | لاكور ماسورة EMT المقاس ¾ " | 030020100015 | MEP | Received | 2023-07-26 | Accounted transaction received
4300870 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 18.04 | 1 | جلبة ماسورة EMT المقاس ¾ " |  | Each | 1 | 63716474 |  |  |  | جلبة ماسورة EMT المقاس ¾ " | 030020100021 | MEP | Received | 2023-07-26 | Accounted transaction received
4300871 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3030.48 | 1 | 10AX SWITCH SP 2 WAY 1 MOD Code 572505 |  | Each | 20 | 63716475 |  |  |  | 10AX SWITCH SP 2 WAY 1 MOD Code 572505 | 030060100123 | MEP | Received | 2023-07-26 | Accounted transaction received
4300872 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 124.05 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 1 | 63716476 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-07-26 | Accounted transaction received
4300873 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 744.3 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 6 | 63716477 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-07-26 | Accounted transaction received
4300874 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1428.27 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 8 | 63716478 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-07-26 | Accounted transaction received
4300875 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 456.04 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 10 | 63716479 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-07-26 | Accounted transaction received
4300876 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 142.03 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 8 | 63716480 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-07-26 | Accounted transaction received
4300877 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 142.03 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 8 | 63716481 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-07-26 | Accounted transaction received
4300878 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3247.8 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 15 | 63716482 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-07-26 | Accounted transaction received
4300879 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 326.6 | 1 | 576562 Code وش مربع فضي |  | Each | 6 | 63716483 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-07-26 | Accounted transaction received
4300880 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1088.66 | 1 | 576562 Code وش مربع فضي |  | Each | 20 | 63716484 |  |  |  | 576562 Code وش مربع فضي | 030060100194 | MEP | Received | 2023-07-26 | Accounted transaction received
4300881 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1197 | 1 | بواط واتر بروف بفتحات مقاس 30 × 38 × 12 سم |  | Each | 3 | 63717804 |  |  |  | بواط واتر بروف بفتحات مقاس 30 × 38 × 12 سم | 030010000185 | MEP | Received | 2023-07-26 | Accounted transaction received
4300882 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 16245 | 1 | HDMI PRE-CONN 1M Code 572596 |  | Each | 5 | 63717805 |  |  |  | HDMI PRE-CONN 1M Code 572596 | 030060100165 | MEP | Received | 2023-07-26 | Accounted transaction received
4300883 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 2272.86 | 1 | 10AX SWITCH SP 2 WAY 1 MOD Code 572505 |  | Each | 15 | 63717806 |  |  |  | 10AX SWITCH SP 2 WAY 1 MOD Code 572505 | 030060100123 | MEP | Received | 2023-07-26 | Accounted transaction received
4300884 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-13 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 11958.17 | 1 | 3.5mm Jack socket Arteor - preterminated - 1 module - magnesium - 572591 |  | Each | 5 | 63717807 |  |  |  | 3.5mm Jack socket Arteor - preterminated - 1 module - magnesium - 572591 | 030060100899 | MEP | Received | 2023-07-26 | Accounted transaction received
4300885 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 456 | 1 | Robe Hook Plate 70*70*10 |  | Each | 4 | 63717866 |  |  |  | Robe Hook Plate 70*70*10 | 250010001933 | Procurement | Received | 2023-07-26 | Accounted transaction received
4300886 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-13 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 20520 | 1 | Robe Hook HW-4 |  | Each | 24 | 63717867 |  |  |  | Robe Hook HW-4 | 250010002115 | Procurement | Received | 2023-07-26 | Accounted transaction received
4300887 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-13 | Materials |  |  |  | Materials | Alrowad Construction_OU | -19104.12 | 1 | seamless steel pipe size 2.5" SCH.40 |  | Meter | -30 | 63719245 |  |  |  | seamless steel pipe size 2.5" SCH.40 | 060010500025 | MEP | Received | 2023-07-26 | Accounted transaction received
4300888 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 32490 | 1 | HDMI PRE-CONN 1M Code 572596 |  | Each | 10 | 63733052 |  |  |  | HDMI PRE-CONN 1M Code 572596 | 030060100165 | MEP | Received | 2023-07-26 | Accounted transaction received
4300889 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4545.73 | 1 | 10AX SWITCH SP 2 WAY 1 MOD Code 572505 |  | Each | 30 | 63733053 |  |  |  | 10AX SWITCH SP 2 WAY 1 MOD Code 572505 | 030060100123 | MEP | Received | 2023-07-26 | Accounted transaction received
4300890 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 248.1 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 2 | 63733054 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-07-26 | Accounted transaction received
4300891 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 178.53 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 1 | 63733055 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-07-26 | Accounted transaction received
4300892 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1368.12 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 30 | 63733056 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-07-26 | Accounted transaction received
4300893 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 124.28 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 7 | 63733057 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-07-26 | Accounted transaction received
4300894 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-14 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4330.39 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 20 | 63733058 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-07-26 | Accounted transaction received
4300823 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 11765.17 | 1 | اسمنت اسود رتبة 42 |  | Ton | 5.25 | 63931127 |  |  |  | اسمنت اسود رتبة 42 | 140010000015 | Purchasing | Received | 2023-07-26 | Accounted transaction received
4300824 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-25 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 3699.95 | 1 | جيوتكستايل 400 جرام / م2 |  | Square Meter | 200 | 63931128 |  |  |  | جيوتكستايل 400 جرام / م2 | 050010000035 | Purchasing | Received | 2023-07-26 | Accounted transaction received
4300825 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 125.4 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 20 | 63932778 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-07-26 | Accounted transaction received
4300826 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 399 | 1 | بواط واتر بروف بفتحات مقاس 30 × 38 × 12 سم |  | Each | 1 | 63932779 |  |  |  | بواط واتر بروف بفتحات مقاس 30 × 38 × 12 سم | 030010000185 | MEP | Received | 2023-07-26 | Accounted transaction received
4300827 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 110.58 | 1 | لاكور ماسورة EMT المقاس ¾ " |  | Each | 5 | 63932780 |  |  |  | لاكور ماسورة EMT المقاس ¾ " | 030020100015 | MEP | Received | 2023-07-26 | Accounted transaction received
4300828 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3249 | 1 | HDMI PRE-CONN 1M Code 572596 |  | Each | 1 | 63932781 |  |  |  | HDMI PRE-CONN 1M Code 572596 | 030060100165 | MEP | Received | 2023-07-26 | Accounted transaction received
4300829 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 868.35 | 1 | 2P + T SHUTTERED 16A Code 572618 |  | Each | 7 | 63932782 |  |  |  | 2P + T SHUTTERED 16A Code 572618 | 030060100128 | MEP | Received | 2023-07-26 | Accounted transaction received
4300830 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1428.27 | 1 | 572802 Code بريزة داتا UTP CAT 6 |  | Each | 8 | 63932783 |  |  |  | 572802 Code بريزة داتا UTP CAT 6 | 030060100137 | MEP | Received | 2023-07-26 | Accounted transaction received
4300831 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 136.81 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 3 | 63932784 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-07-26 | Accounted transaction received
4300832 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 322.26 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 7 | 63932785 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-07-26 | Accounted transaction received
4300833 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 159.32 | 1 | PLATE 1SQ MOD SCH GRAPHITE Code 576552 |  | Each | 4 | 63932786 |  |  |  | PLATE 1SQ MOD SCH GRAPHITE Code 576552 | 030060100297 | MEP | Received | 2023-07-26 | Accounted transaction received
4300835 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 357.87 | 1 | mosaic adapter code 69580 |  | Each | 1 | 63932788 |  |  |  | mosaic adapter code 69580 | 030060100628 | MEP | Received | 2023-07-26 | Accounted transaction received
4300836 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 641.98 | 1 | PLATE 1 GANG & SUPPORT GREY Code 69681 |  | Each | 8 | 63932789 |  |  |  | PLATE 1 GANG & SUPPORT GREY Code 69681 | 030060100676 | MEP | Received | 2023-07-26 | Accounted transaction received
4300837 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 796.07 | 1 | LID & TRIM 3 COMPARTMENTS GREY ( Legrand 689631 ) |  | Each | 1 | 63932790 |  |  |  | LID & TRIM 3 COMPARTMENTS GREY ( Legrand 689631 ) | 030060100738 | MEP | Received | 2023-07-26 | Accounted transaction received
4300838 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3420 | 1 | Indication Lamps |  | Each | 15 | 63932791 |  |  |  | Indication Lamps | 039019000047 | MEP | Received | 2023-07-26 | Accounted transaction received
4300839 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 114.06 | 1 | UPVC BACK BOX 10X10 |  | Each | 5 | 63932792 |  |  |  | UPVC BACK BOX 10X10 | 030069000025 | MEP | Received | 2023-07-26 | Accounted transaction received
4300840 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 5600 | 1 | Copper Cable UTP Cat6A, 4Pair, LSZH, Roll= 305Mt. |  | Each | 1 | 63932793 |  |  |  | Copper Cable UTP Cat6A, 4Pair, LSZH, Roll= 305Mt. | 031030000359 | MEP | Received | 2023-07-26 | Accounted transaction received
4300841 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 83.51 | 1 | Plate Arteor -British standard - square - 1 module – graphite - 575122 |  | Each | 1 | 63932794 |  |  |  | Plate Arteor -British standard - square - 1 module – graphite - 575122 | 030060100901 | MEP | Received | 2023-07-26 | Accounted transaction received
4300842 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 9975 | 1 | Driver Tridonic - 87500855 - Essence series - Driver LC 180W 24V SC 24 V – not dimmable (IP20) |  | Each | 5 | 63932795 |  |  |  | Driver Tridonic - 87500855 - Essence series - Driver LC 180W 24V SC 24 V – not dimmable (IP20) | 030040700474 | MEP | Received | 2023-07-26 | Accounted transaction received
4300843 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 681.72 | 1 | لاكور بواط على فليكسبل EMT المقاس 3/4 " |  | Each | 23 | 63932796 |  |  |  | لاكور بواط على فليكسبل EMT المقاس 3/4 " | 030020100214 | MEP | Received | 2023-07-26 | Accounted transaction received
4300844 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 903.5 | 1 | SPLASH PROOF COVER Code : 617636 |  | Each | 9 | 63932797 |  |  |  | SPLASH PROOF COVER Code : 617636 | 030060100927 | MEP | Received | 2023-07-26 | Accounted transaction received
4300845 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 371.04 | 1 | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 |  | Each | 3 | 63932798 |  |  |  | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 | 030060100951 | MEP | Received | 2023-07-26 | Accounted transaction received
4300846 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 371.04 | 1 | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 |  | Each | 3 | 63932799 |  |  |  | 2X2M 2G PLATE SQ DARK BRONZE - Legrand 571334 | 030060100951 | MEP | Received | 2023-07-26 | Accounted transaction received
4300847 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 237.05 | 1 | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 |  | Each | 3 | 63932800 |  |  |  | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 | 030060100956 | MEP | Received | 2023-07-26 | Accounted transaction received
4300848 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 16865.01 | 1 | BLX14R LAV SYSTEM WITH CVL, Model No.: BLX14RE/CVL-H8E |  | Each | 1 | 63933274 |  |  |  | BLX14R LAV SYSTEM WITH CVL, Model No.: BLX14RE/CVL-H8E | 031060000048 | MEP | Received | 2023-07-26 | Accounted transaction received
4300849 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 19999.99 | 1 | 42 U Data Rack 800 x 800 including Fan Power strip and all accessories |  | Each | 1 | 63933463 |  |  |  | 42 U Data Rack 800 x 800 including Fan Power strip and all accessories | 031030000319 | MEP | Received | 2023-07-26 | Accounted transaction received
4300850 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 573.42 | 1 | سلك نحاس مصمت مقاس 3 مم اللون أصفر × أخضر (cu/xlpe) جهد (750/450) |  | Meter | 100 | 63934281 |  |  |  | سلك نحاس مصمت مقاس 3 مم اللون أصفر × أخضر (cu/xlpe) جهد (750/450) | 030030100286 | MEP | Received | 2023-07-26 | Accounted transaction received
4300851 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-25 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 553.58 | 1 | سلك نحاس مجدول مقاس 3 مم اللون أسود (cu/pvc) |  | Meter | 100 | 63934282 |  |  |  | سلك نحاس مجدول مقاس 3 مم اللون أسود (cu/pvc) | 030030101021 | MEP | Received | 2023-07-26 | Accounted transaction received
4300852 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-25 | Materials |  |  |  | Materials | Alrowad Construction_OU | -16865.01 | 1 | BLX14R LAV SYSTEM WITH CVL, Model No.: BLX14RE/CVL-H8E |  | Each | -1 | 63939122 |  |  |  | BLX14R LAV SYSTEM WITH CVL, Model No.: BLX14RE/CVL-H8E | 031060000048 | MEP | Received | 2023-07-26 | Accounted transaction received
4300853 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1596 | 1 | pipe clamp size 1.5" |  | Each | 25 | 63950958 |  |  |  | pipe clamp size 1.5" | 060191100006 | MEP | Received | 2023-07-26 | Accounted transaction received
4308119 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.03 | Hirings daily wages | 17 | Indirect Cost |  | 2023-07-26 | Bank Fees |  |  |  | Finance cost | Alrowad Construction_OU | 35596.57 | 1 | lg Bm astoria 7/2023 | lg Bm astoria 7/2023 | Currency | 35596.57 | 23432398 | 2131 | Miscellaneous supplier | RME | lg Bm astoria 7/2023 |  | Finacial | Received | 2023-07-30 | Accounted transaction received
4308120 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.06 | Material Transportat | 17 | Indirect Cost |  | 2023-07-26 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | 14136 | 1 | نقل ثقيل شهر ابريل - waldorf astoria | نقل ثقيل شهر ابريل - waldorf astoria | Currency | 14136 | 23432398 | 710 | المصطفي للنقل (مصطفي سعد محمد ) | Egypt | نقل ثقيل شهر ابريل - waldorf astoria |  | Finacial | Received | 2023-07-30 | Accounted transaction received
4308159 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.03 | Maintenance | 17 | Indirect Cost |  | 2023-07-27 | Maintenance |  |  |  | Indirect | Alrowad Construction_OU | 40 | 1 | تسوية89/90/91-م.سيارات | st-89/90/91-7-23 | Currency | 40 | 23432398 | 2162 | Petty Cash | Mustafa Ahmed El Badawi Mohamed | تسوية89/90/91-م.سيارات |  | Finacial | Received | 2023-07-30 | Accounted transaction received
4311761 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-07-30 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 89670 | 1 | يوميات عماله الفتره 1 ش 7 الفعلي | يوميات عماله الفتره 1 ش 7 الفعلي | Currency | 89670 | 23437310 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 1 ش 7 الفعلي |  | Finacial | Received | 2023-08-01 | Accounted transaction received
4311812 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-07-30 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 89670 | 1 | يوميات عماله الفتره 2 ش 7 التقديري | يوميات عماله الفتره 2 ش 7 التقديري | Currency | 89670 | 23437310 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 2 ش 7 التقديري |  | Finacial | Received | 2023-08-01 | Accounted transaction received
4312037 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.02 | Health Care | 17 | Indirect Cost |  | 2023-07-31 | Medical Care |  |  |  | Direct Manpower | Alrowad Construction_OU | 95563.86 | 1 | استحقاق فاتورة التامين التكافلي الربع الرابع1/3/2023الي 31/5/2023 | استحقاق فاتورة التامين التكافلي الربع الرابع2023 | Currency | 95563.86 | 23437310 | 3671 | المصرية للتأمين التكافلى | Rowad | استحقاق فاتورة التامين التكافلي الربع الرابع1/3/2023الي 31/5/2023 |  | Finacial | Received | 2023-08-01 | Accounted transaction received
4312135 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.06 | Telephones | 17 | Indirect Cost |  | 2023-07-31 | Telephones |  |  |  | Indirect | Alrowad Construction_OU | 16424.28 | 1 | استحقاق فاتورة أورنج مارس&ابريل&مايو2023 | استحقاق فاتورة أورنج مارس&ابريل&مايو2023 | Currency | 16424.28 | 23437310 | 2135 | اورنج مصر للاتصالات | Egypt | استحقاق فاتورة أورنج مارس&ابريل&مايو2023 |  | Finacial | Received | 2023-08-01 | Accounted transaction received
4315829 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 456 | 1 | اسبراي فضي |  | Each | 5 | 64005893 |  |  |  | اسبراي فضي | 200010001257 | Purchasing | Received | 2023-08-01 | Accounted transaction received
4315788 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 62.7 | 1 | جلبة ماسورة 25مم UPVC (اللون أبيض) |  | Each | 10 | 64055838 |  |  |  | جلبة ماسورة 25مم UPVC (اللون أبيض) | 030010000068 | MEP | Received | 2023-08-01 | Accounted transaction received
4315789 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 78.18 | 1 | أدابتور UPVC لماسورة 25مم(اللون أبيض) |  | Each | 10 | 64055839 |  |  |  | أدابتور UPVC لماسورة 25مم(اللون أبيض) | 030010000097 | MEP | Received | 2023-08-01 | Accounted transaction received
4315790 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1368.12 | 1 | 1 MODULE BLANK Code 572841 |  | Each | 30 | 64055840 |  |  |  | 1 MODULE BLANK Code 572841 | 030060100245 | MEP | Received | 2023-08-01 | Accounted transaction received
4315791 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 68.43 | 1 | UPVC BACK BOX 10X10 |  | Each | 3 | 64055841 |  |  |  | UPVC BACK BOX 10X10 | 030069000025 | MEP | Received | 2023-08-01 | Accounted transaction received
4300895 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-07-16 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 103.74 | 1 | threaded reducing coupling size 1.5"*1.25" UL LISTED,FM APPROVED |  | Each | 1 | 63768087 |  |  |  | threaded reducing coupling size 1.5"*1.25" UL LISTED,FM APPROVED | 060010140344 | MEP | Received | 2023-07-26 | Accounted transaction received
4300896 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-07-16 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 208.62 | 1 | threaded bushings size 1.25"*1" UL LISTED,FM APPROVED |  | Each | 3 | 63768088 |  |  |  | threaded bushings size 1.25"*1" UL LISTED,FM APPROVED | 060010140400 | MEP | Received | 2023-07-26 | Accounted transaction received
4300897 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-07-16 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 5300 | 1 | Flush Plate For flush actuation with Geberit Alpha concealed cisterns - Jet black RAL9005 Code : 115.060.DW.1 |  | Each | 2 | 63768089 |  |  |  | Flush Plate For flush actuation with Geberit Alpha concealed cisterns - Jet black RAL9005 Code : 115.060.DW.1 | 060030200051 | MEP | Received | 2023-07-26 | Accounted transaction received
4300898 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-16 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 962.63 | 1 | SWITCH 20AX 1 WAY 1 MOD Code 572509 |  | Each | 7 | 63768400 |  |  |  | SWITCH 20AX 1 WAY 1 MOD Code 572509 | 030060100048 | MEP | Received | 2023-07-26 | Accounted transaction received
4300899 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-16 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 3485.06 | 1 | 10AX SWITCH SP 2 WAY 1 MOD Code 572505 |  | Each | 23 | 63768401 |  |  |  | 10AX SWITCH SP 2 WAY 1 MOD Code 572505 | 030060100123 | MEP | Received | 2023-07-26 | Accounted transaction received
4300900 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-16 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 228.53 | 1 | TV "F" TYPE 1 MOD Code 572663 |  | Each | 1 | 63768402 |  |  |  | TV "F" TYPE 1 MOD Code 572663 | 030060100134 | MEP | Received | 2023-07-26 | Accounted transaction received
4300901 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-16 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 177.54 | 1 | SUPPORT FRAME 2 M SQAURE Code 576021 |  | Each | 10 | 63768403 |  |  |  | SUPPORT FRAME 2 M SQAURE Code 576021 | 030060100248 | MEP | Received | 2023-07-26 | Accounted transaction received
4300902 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-16 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 46.04 | 1 | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 |  | Each | 1 | 63768404 |  |  |  | SUPPORT FRAM 4 M ENGLISH TYPE Code 576000 | 030060100249 | MEP | Received | 2023-07-26 | Accounted transaction received
4300903 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-16 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 6495.59 | 1 | PLATE 2X2M BS 2G SQ DARK Code 575082 |  | Each | 30 | 63768405 |  |  |  | PLATE 2X2M BS 2G SQ DARK Code 575082 | 030060100338 | MEP | Received | 2023-07-26 | Accounted transaction received
4300904 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-16 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 301.17 | 1 | SPLASH PROOF COVER Code : 617636 |  | Each | 3 | 63768406 |  |  |  | SPLASH PROOF COVER Code : 617636 | 030060100927 | MEP | Received | 2023-07-26 | Accounted transaction received
4300905 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-16 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 792.79 | 1 | LID & TRIM 4 COMPARTMENTS GRE - 689641 |  | Each | 1 | 63768407 |  |  |  | LID & TRIM 4 COMPARTMENTS GRE - 689641 | 030060100945 | MEP | Received | 2023-07-26 | Accounted transaction received
4300906 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-16 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 123120 | 1 | Trim around screens: Main scope: Supply and install brass trim Materials: FB 20x10mm Polyurethane glue Finish: Antique brass |  | Meter | 80 | 63769682 |  |  |  | Trim around screens: Main scope: Supply and install brass trim Materials: FB 20x10mm Polyurethane glue Finish: Antique brass | 250010002116 | Procurement | Received | 2023-07-26 | Accounted transaction received
4300907 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-16 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 51300 | 1 | Brass Decorative Trim at Elevators |  | Each | 36 | 63769683 |  |  |  | Brass Decorative Trim at Elevators | 250010002119 | Procurement | Received | 2023-07-26 | Accounted transaction received
4300908 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-16 | Materials |  |  |  | Materials | Alrowad Construction_OU | -15048 | 1 | seamless steel pipe size 2" SCH.40 |  | Meter | -30 | 63772608 |  |  |  | seamless steel pipe size 2" SCH.40 | 060010500022 | MEP | Received | 2023-07-26 | Accounted transaction received
4300909 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-16 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 1621.08 | 1 | Bathroom Lock Yale -Sss 20-H372-007S-60-31-11 |  | Each | 2 | 63773350 |  |  |  | Bathroom Lock Yale -Sss 20-H372-007S-60-31-11 | 250010000426 | Procurement | Received | 2023-07-26 | Accounted transaction received
4300910 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-16 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 198 | 1 | Hardware Accessories for Wooden Doors Double Cylinder TESA Security TE-5 Double Cylinder 35x35mm. 5 Spring Loaded Anti pick Pins. Made to EN-1303 Regulation. |  | Each | 1 | 63773351 |  |  |  | Hardware Accessories for Wooden Doors Double Cylinder TESA Security TE-5 Double Cylinder 35x35mm. 5 Spring Loaded Anti pick Pins. Made to EN-1303 Regulation. | 250010001519 | Procurement | Received | 2023-07-26 | Accounted transaction received
4308069 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-07-01 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | -55045 | 1 | يوميات عماله الفتره 2 ش 6 التقديري | يوميات عماله الفتره 2 ش 6 التقديري | Currency | -55045 | 23432398 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 2 ش 6 التقديري |  | Finacial | Received | 2023-07-30 | Accounted transaction received
4311873 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SC.01 | Hirings payrool | 17 | Indirect Cost |  | 2023-07-30 | Hirings daily wages |  |  |  | Direct Manpower | Alrowad Construction_OU | 67600 | 1 | يوميات عماله الفتره 2 ش 6 الفعلي | يوميات عماله الفتره 2 ش 6 الفعلي | Currency | 67600 | 23437310 | 2161 | Staff Loan | SALARY & WAGES | يوميات عماله الفتره 2 ش 6 الفعلي |  | Finacial | Received | 2023-08-01 | Accounted transaction received
4315808 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2679 | 1 | اسمنت اسود رتبة 42 |  | Ton | 1 | 63961845 |  |  |  | اسمنت اسود رتبة 42 | 140010000015 | Purchasing | Received | 2023-08-01 | Accounted transaction received
4315809 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 199.5 | 1 | اسطوانة قطعية 5 بوصة |  | Each | 5 | 63961846 |  |  |  | اسطوانة قطعية 5 بوصة | 200010000391 | Purchasing | Received | 2023-08-01 | Accounted transaction received
4315810 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 193.8 | 1 | كولة رخام |  | Each | 2 | 63961847 |  |  |  | كولة رخام | 200010000710 | Purchasing | Received | 2023-08-01 | Accounted transaction received
4315811 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 7695 | 1 | سيلكون ضد البكتريا |  | Each | 30 | 63961848 |  |  |  | سيلكون ضد البكتريا | 060019000017 | MEP | Received | 2023-08-01 | Accounted transaction received
4315812 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 171 | 1 | غراء أبيض |  | Kilogram | 2 | 63961849 |  |  |  | غراء أبيض | 200010001270 | Purchasing | Received | 2023-08-01 | Accounted transaction received
4315813 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 570 | 1 | اسطوانة رخام 5 بوصة |  | Each | 5 | 63961850 |  |  |  | اسطوانة رخام 5 بوصة | 200010001327 | Purchasing | Received | 2023-08-01 | Accounted transaction received
4315814 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 877.8 | 1 | سيلكون عظم |  | Each | 7 | 63961851 |  |  |  | سيلكون عظم | 330040000420 | Equipment | Received | 2023-08-01 | Accounted transaction received
4315815 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 285 | 1 | مادة لاصق لورق الحائط |  | Kilogram | 2 | 63961852 |  |  |  | مادة لاصق لورق الحائط | 050020000006 | Purchasing | Received | 2023-08-01 | Accounted transaction received
4315816 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.01 | Plumbing Networks | 15 | MECHANICAL WORKS |  | 2023-07-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 16 | 1 | جلبة بولي بروبلين 32مم |  | Each | 2 | 63961860 |  |  |  | جلبة بولي بروبلين 32مم | 240020000020 | MEP | Received | 2023-08-01 | Accounted transaction received
4315817 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.11 | Safety tools | 17 | Indirect Cost |  | 2023-07-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 82.08 | 1 | فيست ليموني |  | Each | 2 | 63961861 |  |  |  | فيست ليموني | 010020000009 | Safety | Received | 2023-08-01 | Accounted transaction received
4315818 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-27 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 75 | 1 | بواط إمتداد UPVC لماسورة 25مم(اللون أبيض) |  | Each | 9 | 63976257 |  |  |  | بواط إمتداد UPVC لماسورة 25مم(اللون أبيض) | 030010000083 | MEP | Received | 2023-08-01 | Accounted transaction received
4315819 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-27 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 694.83 | 1 | جلاند فلكسبل مقاس 25 مم |  | Each | 50 | 63976258 |  |  |  | جلاند فلكسبل مقاس 25 مم | 030010000170 | MEP | Received | 2023-08-01 | Accounted transaction received
4315820 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-27 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 265.68 | 1 | Mechanical anchor (Drop in anchor) size M8 |  | Each | 79 | 63976259 |  |  |  | Mechanical anchor (Drop in anchor) size M8 | 060190100002 | MEP | Received | 2023-08-01 | Accounted transaction received
4315821 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-27 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 557.23 | 1 | Threaded rod size M10 |  | Each | 13 | 63976260 |  |  |  | Threaded rod size M10 | 060190300003 | MEP | Received | 2023-08-01 | Accounted transaction received
4315822 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-27 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 228 | 1 | ASB-CBL-12 (sleeves) |  | Each | 5 | 63976261 |  |  |  | ASB-CBL-12 (sleeves) | 060170200059 | MEP | Received | 2023-08-01 | Accounted transaction received
4315823 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-27 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 119.47 | 1 | Metal Galvanized back box 7x14 cm with deep 47 mm |  | Each | 5 | 63976262 |  |  |  | Metal Galvanized back box 7x14 cm with deep 47 mm | 030069000027 | MEP | Received | 2023-08-01 | Accounted transaction received
4315824 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-27 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 246.24 | 1 | لاكور بواط على فليكسبل EMT المقاس 1" |  | Each | 6 | 63976263 |  |  |  | لاكور بواط على فليكسبل EMT المقاس 1" | 030020100215 | MEP | Received | 2023-08-01 | Accounted transaction received
4315825 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-27 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2307.36 | 1 | AH-ORXS-30 |  | Each | 4 | 63976264 |  |  |  | AH-ORXS-30 | 060170200131 | MEP | Received | 2023-08-01 | Accounted transaction received
4315826 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 2679 | 1 | أسمنت أسود |  | Ton | 1 | 64005890 |  |  |  | أسمنت أسود | 140010000003 | Purchasing | Received | 2023-08-01 | Accounted transaction received
4315827 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 142.5 | 1 | كولة الشعلة |  | Kilogram | 1 | 64005891 |  |  |  | كولة الشعلة | 200010000711 | Purchasing | Received | 2023-08-01 | Accounted transaction received
4315828 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-29 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 684 | 1 | شيكارة بلاستيك فارغة |  | Each | 200 | 64005892 |  |  |  | شيكارة بلاستيك فارغة | 200010000115 | Purchasing | Received | 2023-08-01 | Accounted transaction received
4315830 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-29 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 159.32 | 1 | PLATE 1SQ MOD SCH GRAPHITE Code 576552 |  | Each | 4 | 64011941 |  |  |  | PLATE 1SQ MOD SCH GRAPHITE Code 576552 | 030060100297 | MEP | Received | 2023-08-01 | Accounted transaction received
4315831 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-29 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 23.89 | 1 | Metal Galvanized back box 7x14 cm with deep 47 mm |  | Each | 1 | 64011942 |  |  |  | Metal Galvanized back box 7x14 cm with deep 47 mm | 030069000027 | MEP | Received | 2023-08-01 | Accounted transaction received
4315792 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-31 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 6218.18 | 1 | HN-VC60 Volume Controller |  | Each | 3 | 64055842 |  |  |  | HN-VC60 Volume Controller | 031070000068 | MEP | Received | 2023-08-01 | Accounted transaction received
4315793 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 4250.72 | 1 | Wall Paper WC-8 Trapezium 26560 Arte International Vinyl wall /industriezone de waerde |  | Roll | 1 | 63956003 |  |  |  | Wall Paper WC-8 Trapezium 26560 Arte International Vinyl wall /industriezone de waerde | 050020000018 | Purchasing | Received | 2023-08-01 | Accounted transaction received
4315794 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 15.01.00 | Plumbing Works(G) | 15 | MECHANICAL WORKS |  | 2023-07-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 530.01 | 1 | محبس زاوية 1/2" * 1/2" / Code G4303 / IDEAL STANDARD |  | Each | 4 | 63956008 |  |  |  | محبس زاوية 1/2" * 1/2" / Code G4303 / IDEAL STANDARD | 060031000053 | MEP | Received | 2023-08-01 | Accounted transaction received
4315795 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 866.4 | 1 | Set of Capital Letters Alphabet A-B-C-D-E-F-G-H-L-M-N-R-S-Y |  | Pack | 8 | 63956021 |  |  |  | Set of Capital Letters Alphabet A-B-C-D-E-F-G-H-L-M-N-R-S-Y | 030131200007 | MEP | Received | 2023-08-01 | Accounted transaction received
4315796 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 9900.39 | 1 | Hot Dip Galvanized cable tray 200x100mm thickness 1.5mm with cover 1.25mm thickness |  | Meter | 21 | 63959308 |  |  |  | Hot Dip Galvanized cable tray 200x100mm thickness 1.5mm with cover 1.25mm thickness | 030100100003 | MEP | Received | 2023-08-01 | Accounted transaction received
4315797 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 49428.14 | 1 | Field Equipment Controller with (6UI, 2BI, 3BO, 2AO, 4CO) and mounting base,integral real time clock |  | Each | 1 | 63959309 |  |  |  | Field Equipment Controller with (6UI, 2BI, 3BO, 2AO, 4CO) and mounting base,integral real time clock | 030160000022 | MEP | Received | 2023-08-01 | Accounted transaction received
4315798 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4408.11 | 1 | 'HotDip Galvanized Cable Trunk 20*20 cm Thickness 1.5 mm |  | Meter | 18 | 63959310 |  |  |  | 'HotDip Galvanized Cable Trunk 20*20 cm Thickness 1.5 mm | 030101400050 | MEP | Received | 2023-08-01 | Accounted transaction received
4315799 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 1442.1 | 1 | Hot Dip Galvanized c-channel 40x20x2.5mm |  | Meter | 23 | 63959311 |  |  |  | Hot Dip Galvanized c-channel 40x20x2.5mm | 030100200219 | MEP | Received | 2023-08-01 | Accounted transaction received
4315800 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 949.98 | 1 | Lamp (24 volt) |  | Each | 4 | 63959312 |  |  |  | Lamp (24 volt) | 030160000190 | MEP | Received | 2023-08-01 | Accounted transaction received
4315801 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 159.6 | 1 | بكرة شريط لحام |  | Each | 7 | 63961728 |  |  |  | بكرة شريط لحام | 039010000003 | MEP | Received | 2023-08-01 | Accounted transaction received
4315802 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 39.9 | 1 | حزام بلاستيك 20 سم × 2.5 مم أبيض |  | Pack | 1 | 63961729 |  |  |  | حزام بلاستيك 20 سم × 2.5 مم أبيض | 030131100007 | MEP | Received | 2023-08-01 | Accounted transaction received
4315803 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 131.1 | 1 | كوس نحاس 16 مم |  | Each | 5 | 63961730 |  |  |  | كوس نحاس 16 مم | 030130100106 | MEP | Received | 2023-08-01 | Accounted transaction received
4315804 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 205.2 | 1 | عود دكت 1.5 *1.5 سم |  | Each | 9 | 63961731 |  |  |  | عود دكت 1.5 *1.5 سم | 060010100816 | MEP | Received | 2023-08-01 | Accounted transaction received
4315805 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-26 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 207.48 | 1 | كوس نحاس 10م |  | Each | 14 | 63961732 |  |  |  | كوس نحاس 10م | 030130100112 | MEP | Received | 2023-08-01 | Accounted transaction received
4315806 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 712.5 | 1 | تيب دوكو |  | Each | 25 | 63961843 |  |  |  | تيب دوكو | 200010000048 | Purchasing | Received | 2023-08-01 | Accounted transaction received
4315807 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-26 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 256.5 | 1 | جبس |  | Ton | 0.2 | 63961844 |  |  |  | جبس | 140010000004 | Purchasing | Received | 2023-08-01 | Accounted transaction received
4315832 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-29 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 316.07 | 1 | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 |  | Each | 4 | 64011943 |  |  |  | 1 MOD 1G PLATE SQ DARK BRONZE - Legrand 571591 | 030060100956 | MEP | Received | 2023-08-01 | Accounted transaction received
4315833 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-29 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 24640.75 | 1 | Floor box 6 Module with double socket, space for 2 data socket complete with back box , IP66, Part Number GESR2 - OBO Germany |  | Each | 2 | 64011944 |  |  |  | Floor box 6 Module with double socket, space for 2 data socket complete with back box , IP66, Part Number GESR2 - OBO Germany | 030060100992 | MEP | Received | 2023-08-01 | Accounted transaction received
4315834 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 945.08 | 1 | pipe clamp size 3" |  | Each | 25 | 64025062 |  |  |  | pipe clamp size 3" | 060191100009 | MEP | Received | 2023-08-01 | Accounted transaction received
4315835 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-30 | Materials |  |  |  | Materials | Waldorf Astoria-0164 | 511.18 | 1 | Volume Dampers Size : 8" X 10" |  | Each | 1 | 64025063 |  |  |  | Volume Dampers Size : 8" X 10" | 060070700056 | MEP | Received | 2023-08-01 | Accounted transaction received
4315836 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -14.82 | 1 | جلبة بولي بروبلين 25 مم |  | Each | -1 | 64027561 |  |  |  | جلبة بولي بروبلين 25 مم | 240020000019 | MEP | Received | 2023-08-01 | Accounted transaction received
4315837 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -777.57 | 1 | طبة 1/2 بولي |  | Each | -48 | 64027562 |  |  |  | طبة 1/2 بولي | 240070000081 | MEP | Received | 2023-08-01 | Accounted transaction received
4315838 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -96.9 | 1 | كوع صرف ابيض قطر 4" ( 110 مم ) |  | Each | -1 | 64027563 |  |  |  | كوع صرف ابيض قطر 4" ( 110 مم ) | 060010100210 | MEP | Received | 2023-08-01 | Accounted transaction received
4315839 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -324.9 | 1 | مشترك صرف ابيض قطر 4" ( 110 مم ) |  | Each | -3 | 64027564 |  |  |  | مشترك صرف ابيض قطر 4" ( 110 مم ) | 060010100232 | MEP | Received | 2023-08-01 | Accounted transaction received
4315840 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -91.2 | 1 | جلبه لصق صرف ابيض قطر 4" ( 110 مم ) |  | Each | -2 | 64027565 |  |  |  | جلبه لصق صرف ابيض قطر 4" ( 110 مم ) | 060010100251 | MEP | Received | 2023-08-01 | Accounted transaction received
4315841 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -22.92 | 1 | كوع لحام PPR قطر 25 مم |  | Each | -3 | 64027566 |  |  |  | كوع لحام PPR قطر 25 مم | 060010300037 | MEP | Received | 2023-08-01 | Accounted transaction received
4315842 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -19.38 | 1 | كوع لحام 45 درجه PPR قطر 25 مم |  | Each | -2 | 64027567 |  |  |  | كوع لحام 45 درجه PPR قطر 25 مم | 060010300048 | MEP | Received | 2023-08-01 | Accounted transaction received
4315843 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -51.3 | 1 | مشترك لحام PPR قطر 25 مم |  | Each | -3 | 64027568 |  |  |  | مشترك لحام PPR قطر 25 مم | 060010300070 | MEP | Received | 2023-08-01 | Accounted transaction received
4315844 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -615.6 | 1 | وصلة مرنة طول 30 سم |  | Each | -18 | 64027569 |  |  |  | وصلة مرنة طول 30 سم | 060010300239 | MEP | Received | 2023-08-01 | Accounted transaction received
4315845 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -1192 | 1 | كمرة حديد UPN 120 |  | Kilogram | -100 | 64027570 |  |  |  | كمرة حديد UPN 120 | 060190800007 | MEP | Received | 2023-08-01 | Accounted transaction received
4315846 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -228 | 1 | جلبة بسن خارجى 3/4 بوصة * 1/2 بوصة |  | Each | -5 | 64027571 |  |  |  | جلبة بسن خارجى 3/4 بوصة * 1/2 بوصة | 240020000056 | MEP | Received | 2023-08-01 | Accounted transaction received
4315847 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 17.SE.19 | Other Equipment | 17 | Indirect Cost |  | 2023-07-30 | Materials |  |  |  | Materials | Alrowad Construction_OU | -598.5 | 1 | Pressure Gauge 0.5" |  | Each | -2 | 64027572 |  |  |  | Pressure Gauge 0.5" | 060179000007 | MEP | Received | 2023-08-01 | Accounted transaction received
4315848 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 8156.7 | 1 | Hot dip Galvanized after fabrication, Cover 1mm thickness ,3000mm Length ،for Cable Tray Trunk Type, 200mm Width, 100mm height of Side,1.5mm thickness,10mmReturnFlange ,3000mm Length. |  | Meter | 90 | 64034563 |  |  |  | Hot dip Galvanized after fabrication, Cover 1mm thickness ,3000mm Length ،for Cable Tray Trunk Type, 200mm Width, 100mm height of Side,1.5mm thickness,10mmReturnFlange ,3000mm Length. | 030101600036 | MEP | Received | 2023-08-01 | Accounted transaction received
4315849 | Inventory Misc | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS |  | 2023-07-30 | Electric Utilities |  |  |  | Materials | Waldorf Astoria-0164 | 4333.9 | 1 | Reading lamp - Recessed down light LED 12W, IP 65, 2700K, CRI 90, Optics 30°, Aluminum with textured powder coat finish body |  | Each | 2 | 64034564 |  |  |  | Reading lamp - Recessed down light LED 12W, IP 65, 2700K, CRI 90, Optics 30°, Aluminum with textured powder coat finish body | 030040700461 | MEP | Received | 2023-08-01 | Accounted transaction received
4258707 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -24.69 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -24.69 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258708 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -2.5 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -2.5 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258709 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 16.00. | Electrical Works (G) | 16 | ELECTRICAL WORKS | 67059 | 2023-06-30 | Subcontractor |  |  |  | Subcontracts | Alrowad Construction_OU | -2.4 | 1 | 12 Waldorf Astoria Cairo 67059/12 | 12 Waldorf Astoria Cairo 67059/12 | Currency | -2.4 | 23350938 | 4820 | سيجاب للهندسه والتجاره | rowad | 12 Waldorf Astoria Cairo 67059/12 |  | Mechanical | Received | 2023-07-06 | Accounted transaction received
4258746 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.04 | Fuel,Oil & Gas | 17 | Indirect Cost |  | 2023-06-30 | Fuel,Oil & Gas |  |  |  | Indirect | Alrowad Construction_OU | 2082 | 1 | 561625-1716-1866-2509-2511-2708 astoria | 561625-1716-1866-2509-2511-2708 astoria | Currency | 2082 | 23350938 | 3903 | توتال ايجيبت | rowad | 561625-1716-1866-2509-2511-2708 astoria |  | Finacial | Received | 2023-07-06 | Accounted transaction received
4258829 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.SP.01 | Mobilization | 17 | Indirect Cost |  | 2023-06-30 | Networks and programs |  |  |  | Depreciation | Alrowad Construction_OU | 8516.39 | 1 | 4833-4796-4814 astoria | 4833-4796-4814 astoria | Currency | 8516.39 | 23350938 | 1675 | هيومان اي تي سوليوشنز | Egypt | 4833-4796-4814 astoria |  | Finacial | Received | 2023-07-06 | Accounted transaction received
4258859 | Oracle Payables Supplier Invoices | 164 | Waldorf Astoria Cairo |  | 17.TR.01 | Private Cars | 17 | Indirect Cost |  | 2023-06-30 | Transportation |  |  |  | Indirect | Alrowad Construction_OU | 1900 | 1 | تسويه ك 39 - م.انتقالات | st 39/ 06-23 | Currency | 1900 | 23350938 | 2162 | Petty Cash | Mohamed Ahmed Matok Ali | تسويه ك 39 - م.انتقالات |  | Finacial | Received | 2023-07-06 | Accounted transaction received